## Task Properties
Task Name | Activity Type | Planned Start | Planned Finish | Actual Start | Actual Finish | L2 Description | L2 Supply Data Identifier | Parent WBS Level | TASK_ID
EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW) |  | 2022-09-27 08:00 | 2026-09-25 17:00 | 2022-08-24 17:07 |  |  |  |  | 206812274
Zero Date of Project | MIL | 2022-09-27 08:00 | 2022-09-27 08:00 | 2022-09-27 14:51 | 2022-09-27 14:51 |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812275
Milestones/ as per Work Schedule | MIL | 2022-10-27 08:00 | 2026-09-25 17:00 |  |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812276
Milestones: Basic Engineering | MIL | 2022-10-27 08:00 | 2023-02-23 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812277
Milestones: Detailed Engineering | MIL | 2022-12-26 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812278
Milestone: Commencement of Manufacturing | MIL | 2023-03-25 17:00 | 2023-03-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812279
Ordering of Major BOIs | MIL | 2023-03-26 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812280
Milestone: COMPLETION of Ordering of Balance BOIs | MIL | 2025-01-21 17:00 | 2025-01-21 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812281
Milestone: Establishment of Storage & pre-assembly yard | MIL | 2023-01-30 08:00 | 2023-05-29 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812282
Milestones: Supply of foundation materials for Boiler and Bunker Structures | MIL | 2023-03-29 08:00 | 2023-03-29 08:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812283
Milestones: Commencement of supplies of Structures & Main Equipment | MIL | 2023-06-28 08:00 | 2023-06-28 08:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812284
Milestones: Boiler Erection Start | MIL | 2023-09-26 08:00 | 2023-09-26 08:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812285
Milestones: Ceiling Girder Lifting | MIL | 2024-07-25 17:00 | 2024-07-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812286
Milestones: Drainable Hydro Test | MIL | 2025-07-26 17:00 | 2025-07-26 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812287
Milestones: Non Drainable Hydro test Readiness | MIL | 2025-11-29 17:00 | 2025-11-29 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812288
Milestones: Supply of Critical piping | MIL | 2025-05-30 | 2025-05-30 23:59 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812289
Milestones: Pre-Assembly/Erection of Critical piping | MIL | 2024-03-25 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812290
Milestones: C&I readiness for Boiler Light up | MIL | 2026-01-19 17:00 | 2026-01-19 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812291
Milestones: Boiler Light up & Chemical Cleaning | MIL | 2026-01-24 17:00 | 2026-01-24 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812292
Milestones: Supply of Coal Mills | MIL | 2023-10-27 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812293
Milestones: Steam Blowing start with Coal | MIL | 2026-02-27 17:00 | 2026-02-27 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812294
Milestones: Steam Blowing COMPLETION with Coal | MIL | 2026-03-26 17:00 | 2026-03-26 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812295
Milestones: Condenser Erection start | MIL | 2024-07-31 17:00 | 2024-07-31 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812296
Milestones: Turbine Erection start | MIL | 2024-08-07 08:00 | 2024-08-07 08:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812297
Milestones: Generator Stator lifting | MIL | 2025-04-07 17:00 | 2025-04-07 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812298
Milestone: Supply of CW Puddle flange | MIL | 2024-03-19 08:00 | 2024-03-19 08:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812299
Milestone: Supply of TG Embedment | MIL | 2023-12-25 17:00 | 2023-12-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812300
Milestone: Supply of EOT Crane | MIL | 2024-02-11 17:00 | 2024-02-11 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812301
Milestones: Turbine Box up | MIL | 2025-09-25 17:00 | 2025-09-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812302
Milestone: Turbine Oil flushing COMPLETION | MIL | 2025-11-25 17:00 | 2025-11-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812303
Milestones: Turbine on Barring gear | MIL | 2026-01-26 17:00 | 2026-01-26 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812304
Milestones: Synchronization on Coal | MIL | 2026-05-26 17:00 | 2026-05-26 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812305
Milestones: Full Load operation | MIL | 2026-06-25 17:00 | 2026-06-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812306
Milestones: COMPLETION of Trial Operation & PG test | MIL | 2026-06-25 08:00 | 2026-07-24 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812307
Milestones: COMPLETION of Major supplies | MIL | 2026-01-11 17:00 | 2026-01-11 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812308
Milestones: COMPLETION of all Supplies | MIL | 2026-02-09 17:00 | 2026-02-09 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812309
Milestones: COMPLETION of site delivery of all mandatory spares | MIL | 2025-12-09 17:00 | 2025-12-09 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812310
Milestones: COMPLETION of Facilities | MIL | 2026-09-25 17:00 | 2026-09-25 17:00 |  |  |  |  | 1.2(Milestones/ as per Work Schedule) | 206812311
Readiness of Major Civil Foundation | CIV | 2023-06-27 08:00 | 2025-07-27 17:00 |  |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812312
Readiness of Major Civil Foundation: Boiler Foundation | CIV | 2023-09-25 17:00 | 2023-09-25 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812313
Readiness of Major Civil Foundation: ESP Foundation | CIV | 2023-12-22 17:00 | 2023-12-22 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812314
Readiness of Major Civil Foundation: Commencement of Excavation for TG Building | CIV | 2023-06-27 08:00 | 2023-06-27 08:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812315
Readiness of Major Civil Foundation: Casting of TG Raft | CIV | 2023-08-31 17:00 | 2023-08-31 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812316
Readiness of Major Civil Foundation: Casting of TG Deck | CIV | 2024-04-07 17:00 | 2024-04-07 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812317
Readiness of Major Civil Foundation: Readiness of TG Deck with EOT crane and approach | CIV | 2024-08-06 17:00 | 2024-08-06 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812318
Readiness of Major Civil Foundation: Condenser Foundation | CIV | 2024-02-23 17:00 | 2024-02-23 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812319
Readiness of Major Civil Foundation: ID Fan Foundation | CIV | 2024-06-27 17:00 | 2024-06-27 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812320
Readiness of Major Civil Foundation: FD Fan Foundation | CIV | 2025-07-09 17:00 | 2025-07-09 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812321
Readiness of Major Civil Foundation: PA Fan Foundation | CIV | 2025-07-27 17:00 | 2025-07-27 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812322
Readiness of Major Civil Foundation: SA Fan Foundation | CIV | 2025-07-09 17:00 | 2025-07-09 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812323
Readiness of Major Civil Foundation: Mill Foundation | CIV | 2024-09-15 17:00 | 2024-09-15 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812324
Readiness of Major Civil Foundation: Bunker Bay Foundation | CIV | 2023-09-27 08:00 | 2025-01-04 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812325
Readiness of Major Civil Foundation: MDBFP Foundation | CIV | 2025-01-07 17:00 | 2025-01-07 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812326
Readiness of Major Civil Foundation: TDBFP Foundation | CIV | 2025-02-07 17:00 | 2025-02-07 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812327
Readiness of Major Civil Foundation: CEP Foundation | CIV | 2024-08-05 17:00 | 2024-08-05 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812328
Readiness of Major Civil Foundation: BOF-ESP Duct Foundation | CIV | 2025-04-20 17:00 | 2025-04-20 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812329
Readiness of Major Civil Foundation: ESP-ID Duct Foundation | CIV | 2024-09-26 17:00 | 2024-09-26 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812330
Readiness of Major Civil Foundation: ID-Chimney Duct Foundation | CIV | 2024-11-27 17:00 | 2024-11-27 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812331
Readiness of Major Civil Foundation: GT Foundation | CIV | 2024-09-09 17:00 | 2024-09-09 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812332
Readiness of Major Civil Foundation: ST Foundation | CIV | 2025-02-20 17:00 | 2025-02-20 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812333
Readiness of Major Civil Foundation: UAT Foundation | CIV | 2025-01-01 17:00 | 2025-01-01 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812334
Readiness of Major Civil Foundation: SAT Foundation | CIV | 2025-01-03 17:00 | 2025-01-03 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812335
Readiness of Major Civil Foundation: SPBD Foundation | CIV | 2025-04-22 17:00 | 2025-04-22 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812336
Readiness of Major Civil Foundation: IPBD Foundation | CIV | 2025-02-22 17:00 | 2025-02-22 17:00 |  |  |  |  | 1.3(Readiness of Major Civil Foundation) | 206812337
Readiness of Major Equipment and system | OTH | 2025-02-20 17:00 | 2026-06-20 17:00 |  |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812338
Readiness of Major Equipment and system: DMCW System | OTH | 2025-08-19 17:00 | 2025-08-19 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812339
Readiness of Major Equipment and system: First ID Fan | OTH | 2025-12-31 17:00 | 2025-12-31 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812340
Readiness of Major Equipment and system: Second ID Fan | OTH | 2026-03-31 17:00 | 2026-03-31 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812341
Readiness of Major Equipment and system: First FD Fan | OTH | 2025-12-09 17:00 | 2025-12-09 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812342
Readiness of Major Equipment and system: Second FD Fan | OTH | 2026-02-03 17:00 | 2026-02-03 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812343
Readiness of Major Equipment and system: First APH | OTH | 2025-11-29 17:00 | 2025-11-29 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812344
Readiness of Major Equipment and system: Second APH | OTH | 2026-02-01 17:00 | 2026-02-01 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812345
Readiness of Major Equipment and system: Second PA Fan | OTH | 2026-03-06 17:00 | 2026-03-06 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812346
Readiness of Major Equipment and system: First PA Fan | OTH | 2026-02-19 17:00 | 2026-02-19 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812347
Readiness of Major Equipment and system: SA Fan | OTH | 2026-05-01 17:00 | 2026-05-01 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812348
Readiness of Major Equipment and system: MDBFP | OTH | 2025-09-17 17:00 | 2025-09-17 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812349
Readiness of Major Equipment and system: CEP | OTH | 2025-11-18 17:00 | 2025-11-18 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812350
Readiness of Major Equipment and system: TDBFP | OTH | 2026-04-18 17:00 | 2026-04-18 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812351
Readiness of Major Equipment and system: Service transformer, Aux transformer Charging | OTH | 2025-05-24 17:00 | 2025-05-24 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812352
Readiness of Major Equipment and system: DCS Panel Charging | OTH | 2025-10-27 17:00 | 2025-10-27 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812353
Readiness of Major Equipment and system: C&I for BLU (Gun Trial of AB Elevation) | OTH | 2025-12-19 17:00 | 2025-12-19 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812354
Readiness of Major Equipment and system: C&I for Chemical Cleaning (Gun Trial CD elevation) | OTH | 2025-11-25 17:00 | 2025-11-25 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812355
Readiness of Major Equipment and system: C&I for SB | OTH | 2025-12-25 17:00 | 2025-12-25 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812356
Readiness of Major Equipment and system: C&I for Sync | OTH | 2026-04-27 17:00 | 2026-04-27 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812357
Readiness of Major Equipment and system: C&I for Full Loading | OTH | 2025-06-03 17:00 | 2025-06-03 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812358
Readiness of Major Equipment and system: Mills | OTH | 2025-11-15 17:00 | 2025-11-15 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812359
Readiness of Major Equipment and system: Feeders | OTH | 2025-11-20 17:00 | 2025-11-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812360
Readiness of Major Equipment and system: Scanner FAN | OTH | 2025-11-02 17:00 | 2025-11-02 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812361
Readiness of Major Equipment and system: Soot Blowing System | OTH | 2025-08-18 17:00 | 2025-08-18 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812362
Readiness of Major Equipment and system: ESP Charging | OTH | 2025-12-20 17:00 | 2025-12-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812363
Readiness of Major Equipment and system: COMPLETION of Main Boiler Structure work | OTH | 2025-02-20 17:00 | 2025-02-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812364
Readiness of Major Equipment and system: DM Plant for HT | OTH | 2025-02-20 17:00 | 2025-02-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812365
Readiness of Major Equipment and system: Complete DM Plant | OTH | 2025-07-20 17:00 | 2025-07-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812366
Readiness of Major Equipment and system: Compressed air system | OTH | 2025-10-24 17:00 | 2025-10-24 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812367
Readiness of Major Equipment and system: Air conditioning system | OTH | 2026-01-19 17:00 | 2026-01-19 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812368
Readiness of Major Equipment and system: Cooling Tower | OTH | 2025-11-25 17:00 | 2025-11-25 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812369
Readiness of Major Equipment and system: Chimney for BLU | OTH | 2025-09-01 17:00 | 2025-09-01 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812370
Readiness of Major Equipment and system: Complete Chimney | OTH | 2025-11-30 17:00 | 2025-11-30 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812371
Readiness of Major Equipment and system: Ventilation system | OTH | 2026-03-26 17:00 | 2026-03-26 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812372
Readiness of Major Equipment and system: FPS for BLU | OTH | 2026-01-05 17:00 | 2026-01-05 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812373
Readiness of Major Equipment and system: Completed FPS | OTH | 2026-04-15 17:00 | 2026-04-15 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812374
Readiness of Major Equipment and system: DG set | OTH | 2025-08-27 17:00 | 2025-08-27 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812375
Readiness of Major Equipment and system: CPU | OTH | 2026-02-24 17:00 | 2026-02-24 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812376
Readiness of Major Equipment and system: ACW | OTH | 2025-11-04 17:00 | 2025-11-04 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812377
Readiness of Major Equipment and system: CW | OTH | 2025-07-13 17:00 | 2025-07-13 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812378
Readiness of Major Equipment and system: Fuel Oil system | OTH | 2025-11-17 17:00 | 2025-11-17 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812379
Readiness of Major Equipment and system: Bunker | OTH | 2025-06-23 17:00 | 2025-06-23 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812380
Readiness of Major Equipment and system: WTP | OTH | 2025-02-20 17:00 | 2025-02-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812381
Readiness of Major Equipment and system: STP | OTH | 2026-06-14 17:00 | 2026-06-14 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812382
Readiness of Major Equipment and system: MRS | OTH | 2026-06-20 17:00 | 2026-06-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812383
Readiness of Major Equipment and system: CHP | OTH | 2026-01-26 17:00 | 2026-01-26 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812384
Readiness of Major Equipment and system: AHP | OTH | 2025-02-20 17:00 | 2025-02-20 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812385
Readiness of Major Equipment and system: FGD | OTH | 2026-05-18 17:00 | 2026-05-18 17:00 |  |  |  |  | 1.4(Readiness of Major Equipment and system) | 206812386
CUSTOMER Inputs | CUST | 2022-09-27 08:00 | 2025-11-25 17:00 | 2022-09-27 14:54 |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812387
CUSTOMER INPUTS: LAND (FREE FROM ALL ENCUMBRANCES) | CUST | 2022-09-27 08:00 | 2022-11-25 17:00 | 2022-09-27 14:54 |  |  |  | 1.5(CUSTOMER Inputs) | 206812388
APPROACH ROAD UPTO THE MAIN PLANT | CUST | 2022-09-27 08:00 | 2022-09-27 08:00 | 2022-09-27 14:59 |  |  |  | 1.5(CUSTOMER Inputs) | 206812389
CUSTOMER INPUTS: CONSTRUCTION WATER | CUST | 2022-10-11 17:00 | 2022-10-11 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812390
CUSTOMER INPUTS: CONSTRUCTION POWER SOURCE | CUST | 2022-10-11 17:00 | 2022-10-11 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812391
CUSTOMER INPUTS: AVAILABILITY OF START-UP POWER | CUST | 2025-01-25 17:00 | 2025-01-25 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812392
CUSTOMER INPUTS: RAW WATER AVAILABILITY UPTO THE TERMINAL POINT OF PLANT | CUST | 2024-12-26 17:00 | 2024-12-26 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812393
CUSTOMER INPUTS: FUEL OIL AVAILABILITY | CUST | 2025-08-27 17:00 | 2025-08-27 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812394
CUSTOMER INPUTS: LIMESTONE AVAILABILITY | CUST | 2025-09-27 17:00 | 2025-09-27 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812395
CUSTOMER INPUTS: COAL AVAILABILITY | CUST | 2025-11-25 17:00 | 2025-11-25 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812396
CUSTOMER INPUTS: AVAILABILITY OF POWER EVACUATION | CUST | 2025-08-17 17:00 | 2025-08-17 17:00 |  |  |  |  | 1.5(CUSTOMER Inputs) | 206812397
Award of Sub-Contracts by PS-Region | PRC | 2022-09-27 08:00 | 2024-11-15 17:00 | 2022-08-24 17:07 |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812398
Construction power package including construction lighting in plant, construction water, steel yard | PRC | 2022-09-27 08:00 | 2022-11-10 17:00 | 2022-08-24 17:07 | 2022-12-20 15:01 |  |  | 1.6(Award of Sub-Contracts by PS-Region) | 206812399
NIT | ENQ | 2022-09-27 08:00 | 2022-09-27 08:00 | 2022-08-24 17:07 | 2022-08-24 17:07 |  |  | 1.6.1(Construction power package including construction lighting in plant, construction water, steel yard) | 206812400
LOI | ORD | 2022-09-27 08:00 | 2022-10-26 17:00 | 2022-09-19 17:07 | 2022-12-08 17:07 |  |  | 1.6.1(Construction power package including construction lighting in plant, construction water, steel yard) | 206812401
MOBILIZATION BY AGENCY AT SITE | ORD | 2022-10-27 08:00 | 2022-11-10 17:00 | 2022-12-14 15:01 | 2022-12-20 15:01 |  |  | 1.6.1(Construction power package including construction lighting in plant, construction water, steel yard) | 206812402
Enabling work | PRC | 2022-11-25 17:00 | 2023-02-08 17:00 | 2022-08-24 17:07 | 2022-12-20 15:01 |  |  | 1.6(Award of Sub-Contracts by PS-Region) | 206812403
NIT | ENQ | 2022-11-25 17:00 | 2022-11-25 17:00 | 2022-08-24 17:07 | 2022-08-24 17:07 |  |  | 1.6.2(Enabling work) | 206812404
LOI | ORD | 2022-11-26 08:00 | 2023-01-24 17:00 | 2022-09-19 17:07 | 2022-12-08 17:07 |  |  | 1.6.2(Enabling work) | 206812405
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-01-25 08:00 | 2023-02-08 17:00 | 2022-12-14 15:01 | 2022-12-20 15:01 |  |  | 1.6.2(Enabling work) | 206812406
Civil | PRC | 2022-10-06 17:00 | 2023-09-06 17:00 | 2022-11-03 15:49 |  |  |  | 1.6(Award of Sub-Contracts by PS-Region) | 206812407
Dismantling work of above ground facility | PRC | 2022-10-06 17:00 | 2022-12-20 17:00 | 2022-11-24 15:49 |  |  |  | 1.6.3(Civil) | 206812408
NIT | ENQ | 2022-10-06 17:00 | 2022-10-06 17:00 | 2022-11-24 15:49 | 2022-11-24 15:49 |  |  | 1.6.3.1(Dismantling work of above ground facility) | 206812409
LOI | ORD | 2022-10-07 08:00 | 2022-12-05 17:00 | 2022-12-08 15:49 | 2022-12-18 15:49 |  |  | 1.6.3.1(Dismantling work of above ground facility) | 206812410
MOBILIZATION BY AGENCY AT SITE | ORD | 2022-12-06 08:00 | 2022-12-20 17:00 |  |  |  |  | 1.6.3.1(Dismantling work of above ground facility) | 206812411
Civil- SG-1+ ESP-1+FGD-1 (Absorber+Fan+ Duct up to Chimney etc)+ BAH-1+ SCR-1 + Levelling & Grading+ Below ground dismantling work and excluding Paving work of this package | PRC | 2022-10-26 17:00 | 2023-01-14 17:00 | 2022-12-20 10:11 |  |  |  | 1.6.3(Civil) | 206812412
NIT | ENQ | 2022-10-26 17:00 | 2022-10-26 17:00 | 2022-12-20 10:11 | 2022-12-20 10:11 |  |  | 1.6.3.2(Civil- SG-1+ ESP-1+FGD-1 (Absorber+Fan+ Duct up to Chimney etc)+ BAH-1+ SCR-1 + Levelling & Grading+ Below ground dismantling work and excluding Paving work of this package) | 206812413
LOI | ORD | 2022-10-27 08:00 | 2022-12-25 17:00 |  |  |  |  | 1.6.3.2(Civil- SG-1+ ESP-1+FGD-1 (Absorber+Fan+ Duct up to Chimney etc)+ BAH-1+ SCR-1 + Levelling & Grading+ Below ground dismantling work and excluding Paving work of this package) | 206812414
MOBILIZATION BY AGENCY AT SITE | ORD | 2022-12-26 08:00 | 2023-01-14 17:00 |  |  |  |  | 1.6.3.2(Civil- SG-1+ ESP-1+FGD-1 (Absorber+Fan+ Duct up to Chimney etc)+ BAH-1+ SCR-1 + Levelling & Grading+ Below ground dismantling work and excluding Paving work of this package) | 206812415
Civil -PH-1+X-mer Yard-1+ESP/FGD Control Room+ DG building + Levelling & Grading+ Below ground dismantling work | PRC | 2022-10-26 17:00 | 2023-02-28 17:00 |  |  |  |  | 1.6.3(Civil) | 206812416
NIT | ENQ | 2022-10-26 17:00 | 2022-10-26 17:00 |  |  |  |  | 1.6.3.3(Civil -PH-1+X-mer Yard-1+ESP/FGD Control Room+ DG building + Levelling & Grading+ Below ground dismantling work) | 206812417
LOI | ORD | 2022-10-27 08:00 | 2022-12-25 17:00 |  |  |  |  | 1.6.3.3(Civil -PH-1+X-mer Yard-1+ESP/FGD Control Room+ DG building + Levelling & Grading+ Below ground dismantling work) | 206812418
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-02-09 08:00 | 2023-02-28 17:00 |  |  |  |  | 1.6.3.3(Civil -PH-1+X-mer Yard-1+ESP/FGD Control Room+ DG building + Levelling & Grading+ Below ground dismantling work) | 206812419
Switch Yard+ 33 Kv SWGR + Levelling & Grading+ Below ground dismantling work | OTH | 2022-11-25 17:00 | 2023-03-30 17:00 | 2022-11-22 10:11 |  |  |  | 1.6.3(Civil) | 206812420
NIT | ENQ | 2022-11-25 17:00 | 2022-11-25 17:00 | 2022-11-22 10:11 | 2022-11-22 10:11 |  |  | 1.6.3.4(Switch Yard+ 33 Kv SWGR + Levelling & Grading+ Below ground dismantling work) | 206812421
LOI | ORD | 2022-11-26 08:00 | 2023-01-24 17:00 |  |  |  |  | 1.6.3.4(Switch Yard+ 33 Kv SWGR + Levelling & Grading+ Below ground dismantling work) | 206812422
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-03-11 08:00 | 2023-03-30 17:00 |  |  |  |  | 1.6.3.4(Switch Yard+ 33 Kv SWGR + Levelling & Grading+ Below ground dismantling work) | 206812423
Civil for Coal Handling Plant (CHP) | OTH | 2022-11-25 17:00 | 2023-03-30 17:00 | 2022-11-09 10:11 |  |  |  | 1.6.3(Civil) | 206812424
NIT | ENQ | 2022-11-25 17:00 | 2022-11-25 17:00 | 2022-11-09 10:11 | 2022-11-09 10:11 |  |  | 1.6.3.5(Civil for Coal Handling Plant (CHP)) | 206812425
LOI | ORD | 2022-11-26 08:00 | 2023-01-24 17:00 |  |  |  |  | 1.6.3.5(Civil for Coal Handling Plant (CHP)) | 206812426
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-03-11 08:00 | 2023-03-30 17:00 |  |  |  |  | 1.6.3.5(Civil for Coal Handling Plant (CHP)) | 206812427
Civil for Ash Handling Plant (AHP) | PRC | 2023-04-24 17:00 | 2023-08-27 17:00 | 2023-01-03 15:49 |  |  |  | 1.6.3(Civil) | 206812428
NIT | ENQ | 2023-04-24 17:00 | 2023-04-24 17:00 | 2023-01-03 15:49 | 2023-01-03 15:49 |  |  | 1.6.3.6(Civil for Ash Handling Plant (AHP)) | 206812429
LOI | ORD | 2023-04-25 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.6.3.6(Civil for Ash Handling Plant (AHP)) | 206812430
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-08-08 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.6.3.6(Civil for Ash Handling Plant (AHP)) | 206812431
NDCT cooling Tower | PRC | 2022-11-25 17:00 | 2023-03-30 17:00 | 2022-11-26 15:49 |  |  |  | 1.6.3(Civil) | 206812432
NIT | ENQ | 2022-11-25 17:00 | 2022-11-25 17:00 | 2022-11-26 15:49 | 2022-11-26 15:49 |  |  | 1.6.3.7(NDCT cooling Tower) | 206812433
LOI | ORD | 2022-11-26 08:00 | 2023-01-24 17:00 |  |  |  |  | 1.6.3.7(NDCT cooling Tower) | 206812434
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-03-11 08:00 | 2023-03-30 17:00 |  |  |  |  | 1.6.3.7(NDCT cooling Tower) | 206812435
Balance BOPs civil | PRC | 2023-04-24 17:00 | 2023-07-13 17:00 |  |  |  |  | 1.6.3(Civil) | 206812436
NIT | ENQ | 2023-04-24 17:00 | 2023-04-24 17:00 |  |  |  |  | 1.6.3.8(Balance BOPs civil) | 206812437
LOI | ORD | 2023-04-25 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.6.3.8(Balance BOPs civil) | 206812438
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-06-24 08:00 | 2023-07-13 17:00 |  |  |  |  | 1.6.3.8(Balance BOPs civil) | 206812439
Civil agency for Chimney | PRC | 2022-11-25 17:00 | 2023-04-09 17:00 | 2022-11-03 15:49 |  |  |  | 1.6.3(Civil) | 206812440
NIT | ENQ | 2022-11-25 17:00 | 2022-11-25 17:00 | 2022-11-03 15:49 | 2022-11-03 15:49 |  |  | 1.6.3.9(Civil agency for Chimney) | 206812441
LOI | ORD | 2022-11-26 08:00 | 2023-02-03 17:00 | 2022-11-28 15:49 | 2022-12-26 10:11 |  |  | 1.6.3.9(Civil agency for Chimney) | 206812442
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-03-21 08:00 | 2023-04-09 17:00 |  |  |  |  | 1.6.3.9(Civil agency for Chimney) | 206812443
Civil- FGD buildings (LHP+GHP etc) + Levelling & Grading+ Below ground dismantling work | PRC | 2023-04-24 17:00 | 2023-09-06 17:00 |  |  |  |  | 1.6.3(Civil) | 206812444
NIT | ENQ | 2023-04-24 17:00 | 2023-04-24 17:00 |  |  |  |  | 1.6.3.10(Civil- FGD buildings (LHP+GHP etc) + Levelling & Grading+ Below ground dismantling work) | 206812445
LOI | ORD | 2023-04-25 08:00 | 2023-07-03 17:00 |  |  |  |  | 1.6.3.10(Civil- FGD buildings (LHP+GHP etc) + Levelling & Grading+ Below ground dismantling work) | 206812446
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-08-18 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.6.3.10(Civil- FGD buildings (LHP+GHP etc) + Levelling & Grading+ Below ground dismantling work) | 206812447
Mechanical | PRC | 2023-03-25 17:00 | 2024-07-27 17:00 |  |  |  |  | 1.6(Award of Sub-Contracts by PS-Region) | 206812448
Mechanical – Boiler, Aux Boiler & Bunker | PRC | 2023-06-03 17:00 | 2023-09-21 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812449
NIT | ENQ | 2023-06-03 17:00 | 2023-06-03 17:00 |  |  |  |  | 1.6.4.1(Mechanical – Boiler, Aux Boiler & Bunker) | 206812450
LOI | ORD | 2023-06-04 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.6.4.1(Mechanical – Boiler, Aux Boiler & Bunker) | 206812451
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-09-02 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.6.4.1(Mechanical – Boiler, Aux Boiler & Bunker) | 206812452
Mechanical – ESP & FGD | PRC | 2023-07-08 17:00 | 2023-10-26 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812453
NIT | ENQ | 2023-07-08 17:00 | 2023-07-08 17:00 |  |  |  |  | 1.6.4.2(Mechanical – ESP & FGD) | 206812454
LOI | ORD | 2023-07-09 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.6.4.2(Mechanical – ESP & FGD) | 206812455
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-10-07 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.6.4.2(Mechanical – ESP & FGD) | 206812456
Power Cycle Piping | PRC | 2024-02-08 17:00 | 2024-07-27 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812457
NIT | ENQ | 2024-02-08 17:00 | 2024-02-08 17:00 |  |  |  |  | 1.6.4.3( Power Cycle Piping ) | 206812458
LOI | ORD | 2024-02-09 08:00 | 2024-07-07 17:00 |  |  |  |  | 1.6.4.3( Power Cycle Piping ) | 206812459
MOBILIZATION BY AGENCY AT SITE | ORD | 2024-07-08 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.6.4.3( Power Cycle Piping ) | 206812460
Steam Turbine & Generator | PRC | 2024-02-09 17:00 | 2024-05-29 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812461
NIT | ENQ | 2024-02-09 17:00 | 2024-02-09 17:00 |  |  |  |  | 1.6.4.4(Steam Turbine & Generator) | 206812462
LOI | ORD | 2024-02-10 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.6.4.4(Steam Turbine & Generator) | 206812463
MOBILIZATION BY AGENCY AT SITE | ORD | 2024-05-10 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.6.4.4(Steam Turbine & Generator) | 206812464
Structure:- Power House | PRC | 2023-03-25 17:00 | 2023-06-13 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812465
NIT | ENQ | 2023-03-25 17:00 | 2023-03-25 17:00 |  |  |  |  | 1.6.4.5(Structure:- Power House) | 206812466
LOI | ORD | 2023-03-26 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.6.4.5(Structure:- Power House) | 206812467
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-05-25 08:00 | 2023-06-13 17:00 |  |  |  |  | 1.6.4.5(Structure:- Power House) | 206812468
Structure:- CHP | PRC | 2023-08-22 17:00 | 2023-11-10 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812469
NIT | ENQ | 2023-08-22 17:00 | 2023-08-22 17:00 |  |  |  |  | 1.6.4.6(Structure:- CHP) | 206812470
LOI | ORD | 2023-08-23 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.6.4.6(Structure:- CHP) | 206812471
MOBILIZATION BY AGENCY AT SITE | ORD | 2023-10-22 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.6.4.6(Structure:- CHP) | 206812472
Structure:- FGD+AHP+Pipe Rack | PRC | 2023-11-30 17:00 | 2024-02-18 17:00 |  |  |  |  | 1.6.4(Mechanical) | 206812473
NIT | ENQ | 2023-11-30 17:00 | 2023-11-30 17:00 |  |  |  |  | 1.6.4.7(Structure:- FGD+AHP+Pipe Rack) | 206812474
LOI | ORD | 2023-12-01 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.6.4.7(Structure:- FGD+AHP+Pipe Rack) | 206812475
MOBILIZATION BY AGENCY AT SITE | ORD | 2024-01-30 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.6.4.7(Structure:- FGD+AHP+Pipe Rack) | 206812476
Electrical & Cabling Pkg | PRC | 2024-06-28 17:00 | 2024-10-16 17:00 |  |  |  |  | 1.6(Award of Sub-Contracts by PS-Region) | 206812477
NIT | ENQ | 2024-06-28 17:00 | 2024-06-28 17:00 |  |  |  |  | 1.6.5(Electrical & Cabling Pkg ) | 206812478
LOI | ORD | 2024-06-29 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.6.5(Electrical & Cabling Pkg ) | 206812479
MOBILIZATION BY AGENCY AT SITE | ORD | 2024-09-27 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.6.5(Electrical & Cabling Pkg ) | 206812480
C&I Pkg | PRC | 2024-07-28 17:00 | 2024-11-15 17:00 |  |  |  |  | 1.6(Award of Sub-Contracts by PS-Region) | 206812481
NIT | ENQ | 2024-07-28 17:00 | 2024-07-28 17:00 |  |  |  |  | 1.6.6(C&I Pkg ) | 206812482
LOI | ORD | 2024-07-29 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.6.6(C&I Pkg ) | 206812483
MOBILIZATION BY AGENCY AT SITE | ORD | 2024-10-27 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.6.6(C&I Pkg ) | 206812484
Topographical Survey and Soil Investigation | ENG | 2022-09-27 08:00 | 2022-10-26 17:00 | 2022-09-27 16:35 | 2022-11-26 16:36 |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812485
Topographical Survey and Soil Investigation: Work COMPLETION and Report Submission | ENG | 2022-09-27 08:00 | 2022-10-26 17:00 | 2022-09-27 16:35 | 2022-11-26 16:36 |  |  | 1.7(Topographical Survey and Soil Investigation) | 206812486
Development of Site Infrastructure | OTH | 2022-09-27 08:00 | 2024-05-18 17:00 | 2022-09-27 16:57 |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812487
Mobilization of site levelling agency at site and commencement of site levelling works including dismantling activities |  | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812488
Completion of Site Levelling | CIV | 2023-04-25 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812489
Readiness of Priority Roads including Drains | CIV | 2023-05-25 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812490
Readiness of External Drain for evacuation of plant area drainage | CIV | 2023-03-26 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812491
Readiness of area lighting in Plant | OTH | 2023-03-26 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812492
Readiness of Temporary office of BHEL | CIV | 2022-09-27 08:00 | 2022-11-25 17:00 | 2022-09-27 16:57 | 2022-11-30 16:57 |  |  | 1.8(Development of Site Infrastructure) | 206812493
Readiness of BHEL office | CIV | 2022-09-27 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812494
Readiness of Safety Control Room & Site office of NTPC | CIV | 2023-06-23 17:00 | 2023-06-23 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812495
Readiness of Storage and Preassembly yard with Hard crusting, Roads & Drains etc. as per priority requirement of project | CIV | 2023-03-26 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812496
Establishment of workers habitat in phased manner | CIV | 2022-12-26 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812497
Dismantling | CIV | 2022-12-21 08:00 | 2024-01-30 17:00 |  |  |  |  | 1.8(Development of Site Infrastructure) | 206812498
Dismantling of existing raw material reservoirs | CIV | 2023-07-15 08:00 | 2024-01-30 17:00 |  |  |  |  | 1.8.11(Dismantling) | 206812499
Dismantling of super structure | CIV | 2022-12-21 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.8.11(Dismantling) | 206812500
Boiler & Auxiliaries | OTH | 2022-09-27 08:00 | 2026-05-28 17:00 | 2022-11-21 |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206812501
Boiler Structure | OTH | 2022-09-27 08:00 | 2026-04-30 17:00 | 2022-12-15 |  |  |  | 1.9(Boiler & Auxiliaries) | 206812502
Basic engineering | ENG | 2022-10-27 08:00 | 2023-02-23 17:00 |  |  |  |  | 1.9.1(Boiler Structure) | 206812503
Supply (BHEL TRY) | SUP | 2022-09-27 08:00 | 2025-11-10 17:00 | 2022-12-15 |  |  |  | 1.9.1(Boiler Structure) | 206812504
Main Boiler supporting structure (PG-35) | OTH | 2022-09-27 08:00 | 2024-03-11 17:00 | 2022-12-15 |  |  | PG35 | 1.9.1.2(Supply (BHEL TRY)) | 206812505
FOUNDATION MATERIALS- (PGMA-35011) | SUP | 2022-10-27 08:00 | 2023-05-27 17:00 | 2022-12-15 |  |  | 35010 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812506
Engineering | ENG | 2022-10-27 08:00 | 2023-01-19 17:00 | 2022-12-15 |  |  | 35011 | 1.9.1.2.1.1(FOUNDATION MATERIALS- (PGMA-35011)) | 206812507
Manufacturing | MFG | 2023-01-20 08:00 | 2023-04-27 17:00 |  |  |  | 35011 | 1.9.1.2.1.1(FOUNDATION MATERIALS- (PGMA-35011)) | 206812508
Dispatch | DIS | 2023-03-29 08:00 | 2023-05-27 17:00 |  |  |  | 35011 | 1.9.1.2.1.1(FOUNDATION MATERIALS- (PGMA-35011)) | 206812509
MAIN COLUMNS LEFT 1ST PASS (PGMA-35111) | SUP | 2022-10-27 08:00 | 2023-09-10 17:00 |  |  |  | 35111 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812510
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35111 | 1.9.1.2.1.2(MAIN COLUMNS LEFT 1ST PASS (PGMA-35111)) | 206812511
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35111 | 1.9.1.2.1.2(MAIN COLUMNS LEFT 1ST PASS (PGMA-35111)) | 206812512
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-10 17:00 |  |  |  | 35111 | 1.9.1.2.1.2(MAIN COLUMNS LEFT 1ST PASS (PGMA-35111)) | 206812513
MAIN COLUMNS LEFT 2ND PASS (PGMA-35112) | SUP | 2022-10-27 08:00 | 2023-09-10 17:00 |  |  |  | 35112 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812514
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35112 | 1.9.1.2.1.3(MAIN COLUMNS LEFT 2ND PASS (PGMA-35112)) | 206812515
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35112 | 1.9.1.2.1.3(MAIN COLUMNS LEFT 2ND PASS (PGMA-35112)) | 206812516
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-10 17:00 |  |  |  | 35112 | 1.9.1.2.1.3(MAIN COLUMNS LEFT 2ND PASS (PGMA-35112)) | 206812517
MAIN COLUMNS RIGHT 1ST PASS (PGMA-35121) | SUP | 2022-10-27 08:00 | 2023-09-25 17:00 |  |  |  | 35121 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812518
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35121 | 1.9.1.2.1.4(MAIN COLUMNS RIGHT 1ST PASS (PGMA-35121)) | 206812519
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35121 | 1.9.1.2.1.4(MAIN COLUMNS RIGHT 1ST PASS (PGMA-35121)) | 206812520
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-25 17:00 |  |  |  | 35121 | 1.9.1.2.1.4(MAIN COLUMNS RIGHT 1ST PASS (PGMA-35121)) | 206812521
MAIN COLUMNS RIGHT 2ND PASS (PGMA-35122) | SUP | 2022-10-27 08:00 | 2023-09-25 17:00 |  |  |  | 35122 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812522
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35122 | 1.9.1.2.1.5(MAIN COLUMNS RIGHT 2ND PASS (PGMA-35122)) | 206812523
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35122 | 1.9.1.2.1.5(MAIN COLUMNS RIGHT 2ND PASS (PGMA-35122)) | 206812524
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-25 17:00 |  |  |  | 35122 | 1.9.1.2.1.5(MAIN COLUMNS RIGHT 2ND PASS (PGMA-35122)) | 206812525
MAIN COLUMNS MIDDLE (PGMA-35130) | SUP | 2022-10-27 08:00 | 2023-09-25 17:00 |  |  |  | 35130 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812526
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35130 | 1.9.1.2.1.6(MAIN COLUMNS MIDDLE (PGMA-35130)) | 206812527
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35130 | 1.9.1.2.1.6(MAIN COLUMNS MIDDLE (PGMA-35130)) | 206812528
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-25 17:00 |  |  |  | 35130 | 1.9.1.2.1.6(MAIN COLUMNS MIDDLE (PGMA-35130)) | 206812529
AUXILIARY COLUMNS-LEFT SIDE (PGMA-35140) | SUP | 2022-10-27 08:00 | 2023-09-25 17:00 |  |  |  | 35140 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812530
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35140 | 1.9.1.2.1.7(AUXILIARY COLUMNS-LEFT SIDE (PGMA-35140)) | 206812531
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35140 | 1.9.1.2.1.7(AUXILIARY COLUMNS-LEFT SIDE (PGMA-35140)) | 206812532
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-25 17:00 |  |  |  | 35140 | 1.9.1.2.1.7(AUXILIARY COLUMNS-LEFT SIDE (PGMA-35140)) | 206812533
AUXILIARY COLUMNS-RIGHT SIDE (PGMA-35150) | SUP | 2022-10-27 08:00 | 2023-09-25 17:00 |  |  |  | 35150 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812534
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35150 | 1.9.1.2.1.8(AUXILIARY COLUMNS-RIGHT SIDE (PGMA-35150)) | 206812535
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35150 | 1.9.1.2.1.8(AUXILIARY COLUMNS-RIGHT SIDE (PGMA-35150)) | 206812536
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-25 17:00 |  |  |  | 35150 | 1.9.1.2.1.8(AUXILIARY COLUMNS-RIGHT SIDE (PGMA-35150)) | 206812537
GIRDER PIN CONNECTIONS (PGMA-35190) | SUP | 2022-10-27 08:00 | 2023-10-26 17:00 |  |  |  | 35190 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812538
Engineering | ENG | 2022-10-27 08:00 | 2023-05-23 17:00 |  |  |  | 35190 | 1.9.1.2.1.9(GIRDER PIN CONNECTIONS (PGMA-35190)) | 206812539
Manufacturing | MFG | 2023-03-05 08:00 | 2023-08-27 17:00 |  |  |  | 35190 | 1.9.1.2.1.9(GIRDER PIN CONNECTIONS (PGMA-35190)) | 206812540
Dispatch | DIS | 2023-08-28 08:00 | 2023-10-26 17:00 |  |  |  | 35190 | 1.9.1.2.1.9(GIRDER PIN CONNECTIONS (PGMA-35190)) | 206812541
CEILING STRUCTURE-MAIN GIRDERS 1ST PASS (PGMA-35211) | SUP | 2022-10-27 08:00 | 2023-12-19 17:00 |  |  |  | 35211 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812542
Engineering | ENG | 2022-10-27 08:00 | 2023-05-23 17:00 |  |  |  | 35211 | 1.9.1.2.1.10(CEILING STRUCTURE-MAIN GIRDERS 1ST PASS (PGMA-35211)) | 206812543
Manufacturing | MFG | 2023-03-05 08:00 | 2023-09-20 17:00 |  |  |  | 35211 | 1.9.1.2.1.10(CEILING STRUCTURE-MAIN GIRDERS 1ST PASS (PGMA-35211)) | 206812544
Dispatch | DIS | 2023-09-21 08:00 | 2023-12-19 17:00 |  |  |  | 35211 | 1.9.1.2.1.10(CEILING STRUCTURE-MAIN GIRDERS 1ST PASS (PGMA-35211)) | 206812545
CEILING STRUCTURE-MAIN GIRDERS 2ND PASS (PGMA-35212) | SUP | 2022-10-27 08:00 | 2023-12-19 17:00 |  |  |  | 35212 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812546
Engineering | ENG | 2022-10-27 08:00 | 2023-05-23 17:00 |  |  |  | 35212 | 1.9.1.2.1.11(CEILING STRUCTURE-MAIN GIRDERS 2ND PASS (PGMA-35212)) | 206812547
Manufacturing | MFG | 2023-03-05 08:00 | 2023-09-20 17:00 |  |  |  | 35212 | 1.9.1.2.1.11(CEILING STRUCTURE-MAIN GIRDERS 2ND PASS (PGMA-35212)) | 206812548
Dispatch | DIS | 2023-09-21 08:00 | 2023-12-19 17:00 |  |  |  | 35212 | 1.9.1.2.1.11(CEILING STRUCTURE-MAIN GIRDERS 2ND PASS (PGMA-35212)) | 206812549
CEIL STRUCT-CROSS WELDED BEAMS 1ST PASS (PGMA-35213) | SUP | 2022-10-27 08:00 | 2023-12-21 17:00 |  |  |  | 35213 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812550
Engineering | ENG | 2022-10-27 08:00 | 2023-05-23 17:00 |  |  |  | 35213 | 1.9.1.2.1.12(CEIL STRUCT-CROSS WELDED BEAMS 1ST PASS (PGMA-35213)) | 206812551
Manufacturing | MFG | 2023-03-07 08:00 | 2023-09-22 17:00 |  |  |  | 35213 | 1.9.1.2.1.12(CEIL STRUCT-CROSS WELDED BEAMS 1ST PASS (PGMA-35213)) | 206812552
Dispatch | DIS | 2023-09-23 08:00 | 2023-12-21 17:00 |  |  |  | 35213 | 1.9.1.2.1.12(CEIL STRUCT-CROSS WELDED BEAMS 1ST PASS (PGMA-35213)) | 206812553
CEIL STRUCT-CROSS WELDED BEAMS 2ND PASS (PGMA-35214) | SUP | 2022-10-27 08:00 | 2023-12-21 17:00 |  |  |  | 35214 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812554
Engineering | ENG | 2022-10-27 08:00 | 2023-05-23 17:00 |  |  |  | 35214 | 1.9.1.2.1.13(CEIL STRUCT-CROSS WELDED BEAMS 2ND PASS (PGMA-35214)) | 206812555
Manufacturing | MFG | 2023-03-07 08:00 | 2023-09-22 17:00 |  |  |  | 35214 | 1.9.1.2.1.13(CEIL STRUCT-CROSS WELDED BEAMS 2ND PASS (PGMA-35214)) | 206812556
Dispatch | DIS | 2023-09-23 08:00 | 2023-12-21 17:00 |  |  |  | 35214 | 1.9.1.2.1.13(CEIL STRUCT-CROSS WELDED BEAMS 2ND PASS (PGMA-35214)) | 206812557
CEILING STRUCTURE ROLLED BEAM 1ST PASS (PGMA-35221) | SUP | 2022-09-27 08:00 | 2024-01-03 17:00 |  |  |  | 35221 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812558
Engineering | ENG | 2022-09-27 08:00 | 2023-06-05 17:00 |  |  |  | 35221 | 1.9.1.2.1.14(CEILING STRUCTURE ROLLED BEAM 1ST PASS (PGMA-35221)) | 206812559
Manufacturing | MFG | 2023-03-20 08:00 | 2023-10-05 17:00 |  |  |  | 35221 | 1.9.1.2.1.14(CEILING STRUCTURE ROLLED BEAM 1ST PASS (PGMA-35221)) | 206812560
Dispatch | DIS | 2023-10-06 08:00 | 2024-01-03 17:00 |  |  |  | 35221 | 1.9.1.2.1.14(CEILING STRUCTURE ROLLED BEAM 1ST PASS (PGMA-35221)) | 206812561
CEILING STRUCTURE ROLLED BEAM 2ND PASS (PGMA-35222) | SUP | 2022-09-27 08:00 | 2024-01-03 17:00 |  |  |  | 35222 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812562
Engineering | ENG | 2022-09-27 08:00 | 2023-06-05 17:00 |  |  |  | 35222 | 1.9.1.2.1.15(CEILING STRUCTURE ROLLED BEAM 2ND PASS (PGMA-35222)) | 206812563
Manufacturing | MFG | 2023-03-20 08:00 | 2023-10-05 17:00 |  |  |  | 35222 | 1.9.1.2.1.15(CEILING STRUCTURE ROLLED BEAM 2ND PASS (PGMA-35222)) | 206812564
Dispatch | DIS | 2023-10-06 08:00 | 2024-01-03 17:00 |  |  |  | 35222 | 1.9.1.2.1.15(CEILING STRUCTURE ROLLED BEAM 2ND PASS (PGMA-35222)) | 206812565
CEILING STRUCTURE HORBRACING 1ST PASS (PGMA-35231) | SUP | 2022-10-27 08:00 | 2024-02-02 17:00 |  |  |  | 35231 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812566
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35231 | 1.9.1.2.1.16(CEILING STRUCTURE HORBRACING 1ST PASS (PGMA-35231)) | 206812567
Manufacturing | MFG | 2023-04-19 08:00 | 2023-11-04 17:00 |  |  |  | 35231 | 1.9.1.2.1.16(CEILING STRUCTURE HORBRACING 1ST PASS (PGMA-35231)) | 206812568
Dispatch | DIS | 2023-11-05 08:00 | 2024-02-02 17:00 |  |  |  | 35231 | 1.9.1.2.1.16(CEILING STRUCTURE HORBRACING 1ST PASS (PGMA-35231)) | 206812569
CEILING STRUCTURE HORBRACING 2ND PASS (PGMA-35232) | SUP | 2022-10-27 08:00 | 2024-02-02 17:00 |  |  |  | 35232 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812570
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35232 | 1.9.1.2.1.17(CEILING STRUCTURE HORBRACING 2ND PASS (PGMA-35232)) | 206812571
Manufacturing | MFG | 2023-04-19 08:00 | 2023-11-04 17:00 |  |  |  | 35232 | 1.9.1.2.1.17(CEILING STRUCTURE HORBRACING 2ND PASS (PGMA-35232)) | 206812572
Dispatch | DIS | 2023-11-05 08:00 | 2024-02-02 17:00 |  |  |  | 35232 | 1.9.1.2.1.17(CEILING STRUCTURE HORBRACING 2ND PASS (PGMA-35232)) | 206812573
HORIZONTAL BRACING I PASS IMBL (PGMA-35311) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35311 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812574
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35311 | 1.9.1.2.1.18(HORIZONTAL BRACING I PASS IMBL (PGMA-35311)) | 206812575
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35311 | 1.9.1.2.1.18(HORIZONTAL BRACING I PASS IMBL (PGMA-35311)) | 206812576
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35311 | 1.9.1.2.1.18(HORIZONTAL BRACING I PASS IMBL (PGMA-35311)) | 206812577
HORIZ BRACING II PASS I MBL (PGMA-35312) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35312 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812578
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35312 | 1.9.1.2.1.19(HORIZ BRACING II PASS I MBL (PGMA-35312)) | 206812579
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35312 | 1.9.1.2.1.19(HORIZ BRACING II PASS I MBL (PGMA-35312)) | 206812580
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35312 | 1.9.1.2.1.19(HORIZ BRACING II PASS I MBL (PGMA-35312)) | 206812581
HORIZ BRACING I PASS II MBL (PGMA-35321) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35321 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812582
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35321 | 1.9.1.2.1.20(HORIZ BRACING I PASS II MBL (PGMA-35321)) | 206812583
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35321 | 1.9.1.2.1.20(HORIZ BRACING I PASS II MBL (PGMA-35321)) | 206812584
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35321 | 1.9.1.2.1.20(HORIZ BRACING I PASS II MBL (PGMA-35321)) | 206812585
HORIZ BRACING II PASS II MBL (PGMA-35322) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35322 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812586
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35322 | 1.9.1.2.1.21(HORIZ BRACING II PASS II MBL (PGMA-35322)) | 206812587
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35322 | 1.9.1.2.1.21(HORIZ BRACING II PASS II MBL (PGMA-35322)) | 206812588
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35322 | 1.9.1.2.1.21(HORIZ BRACING II PASS II MBL (PGMA-35322)) | 206812589
HORIZ BRACING I PASS III MBL (PGMA-35331) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35331 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812590
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35331 | 1.9.1.2.1.22(HORIZ BRACING I PASS III MBL (PGMA-35331)) | 206812591
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35331 | 1.9.1.2.1.22(HORIZ BRACING I PASS III MBL (PGMA-35331)) | 206812592
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35331 | 1.9.1.2.1.22(HORIZ BRACING I PASS III MBL (PGMA-35331)) | 206812593
HORIZ BRACING II PASS III MBL (PGMA-35332) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35332 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812594
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35332 | 1.9.1.2.1.23(HORIZ BRACING II PASS III MBL (PGMA-35332)) | 206812595
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35332 | 1.9.1.2.1.23(HORIZ BRACING II PASS III MBL (PGMA-35332)) | 206812596
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35332 | 1.9.1.2.1.23(HORIZ BRACING II PASS III MBL (PGMA-35332)) | 206812597
HORIZ BRACING I PASS IV MBL (PGMA-35341) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35341 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812598
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35341 | 1.9.1.2.1.24(HORIZ BRACING I PASS IV MBL (PGMA-35341)) | 206812599
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35341 | 1.9.1.2.1.24(HORIZ BRACING I PASS IV MBL (PGMA-35341)) | 206812600
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35341 | 1.9.1.2.1.24(HORIZ BRACING I PASS IV MBL (PGMA-35341)) | 206812601
HORIZ BRACING II PASS IV MBL (PGMA-35342) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35342 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812602
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35342 | 1.9.1.2.1.25(HORIZ BRACING II PASS IV MBL (PGMA-35342)) | 206812603
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35342 | 1.9.1.2.1.25(HORIZ BRACING II PASS IV MBL (PGMA-35342)) | 206812604
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35342 | 1.9.1.2.1.25(HORIZ BRACING II PASS IV MBL (PGMA-35342)) | 206812605
HORIZ BRACING I PASS V MBL (PGMA-35351) | SUP | 2022-10-27 08:00 | 2024-02-02 17:00 |  |  |  | 35351 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812606
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35351 | 1.9.1.2.1.26(HORIZ BRACING I PASS V MBL (PGMA-35351)) | 206812607
Manufacturing | MFG | 2023-04-19 08:00 | 2023-11-04 17:00 |  |  |  | 35351 | 1.9.1.2.1.26(HORIZ BRACING I PASS V MBL (PGMA-35351)) | 206812608
Dispatch | DIS | 2023-11-05 08:00 | 2024-02-02 17:00 |  |  |  | 35351 | 1.9.1.2.1.26(HORIZ BRACING I PASS V MBL (PGMA-35351)) | 206812609
HORIZ BRACING II PASS V MBL (PGMA-35352) | SUP | 2022-10-27 08:00 | 2024-02-02 17:00 |  |  |  | 35352 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812610
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35352 | 1.9.1.2.1.27(HORIZ BRACING II PASS V MBL (PGMA-35352)) | 206812611
Manufacturing | MFG | 2023-04-19 08:00 | 2023-11-04 17:00 |  |  |  | 35352 | 1.9.1.2.1.27(HORIZ BRACING II PASS V MBL (PGMA-35352)) | 206812612
Dispatch | DIS | 2023-11-05 08:00 | 2024-02-02 17:00 |  |  |  | 35352 | 1.9.1.2.1.27(HORIZ BRACING II PASS V MBL (PGMA-35352)) | 206812613
HORIZ BRACING I PASS VI MBL (PGMA-35361) | SUP | 2022-10-27 08:00 | 2024-02-02 17:00 |  |  |  | 35361 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812614
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35361 | 1.9.1.2.1.28(HORIZ BRACING I PASS VI MBL (PGMA-35361)) | 206812615
Manufacturing | MFG | 2023-04-19 08:00 | 2023-11-04 17:00 |  |  |  | 35361 | 1.9.1.2.1.28(HORIZ BRACING I PASS VI MBL (PGMA-35361)) | 206812616
Dispatch | DIS | 2023-11-05 08:00 | 2024-02-02 17:00 |  |  |  | 35361 | 1.9.1.2.1.28(HORIZ BRACING I PASS VI MBL (PGMA-35361)) | 206812617
HORIZ BRACING II PASS VI MBL (PGMA-35362) | SUP | 2022-10-27 08:00 | 2024-02-02 17:00 |  |  |  | 35362 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812618
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35362 | 1.9.1.2.1.29(HORIZ BRACING II PASS VI MBL (PGMA-35362)) | 206812619
Manufacturing | MFG | 2023-04-19 08:00 | 2023-11-04 17:00 |  |  |  | 35362 | 1.9.1.2.1.29(HORIZ BRACING II PASS VI MBL (PGMA-35362)) | 206812620
Dispatch | DIS | 2023-11-05 08:00 | 2024-02-02 17:00 |  |  |  | 35362 | 1.9.1.2.1.29(HORIZ BRACING II PASS VI MBL (PGMA-35362)) | 206812621
LAND & CONN PLAT TIER-1 (PGMA-35381) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35381 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812622
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35381 | 1.9.1.2.1.30(LAND & CONN PLAT TIER-1 (PGMA-35381)) | 206812623
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35381 | 1.9.1.2.1.30(LAND & CONN PLAT TIER-1 (PGMA-35381)) | 206812624
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35381 | 1.9.1.2.1.30(LAND & CONN PLAT TIER-1 (PGMA-35381)) | 206812625
LAND & CONN PLAT TIER-2 (PGMA-35382) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35382 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812626
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35382 | 1.9.1.2.1.31(LAND & CONN PLAT TIER-2 (PGMA-35382)) | 206812627
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35382 | 1.9.1.2.1.31(LAND & CONN PLAT TIER-2 (PGMA-35382)) | 206812628
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35382 | 1.9.1.2.1.31(LAND & CONN PLAT TIER-2 (PGMA-35382)) | 206812629
LAND & CONN PLAT TIER-3 (PGMA-35383) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35383 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812630
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35383 | 1.9.1.2.1.32(LAND & CONN PLAT TIER-3 (PGMA-35383)) | 206812631
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35383 | 1.9.1.2.1.32(LAND & CONN PLAT TIER-3 (PGMA-35383)) | 206812632
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35383 | 1.9.1.2.1.32(LAND & CONN PLAT TIER-3 (PGMA-35383)) | 206812633
HORIL BEAMS FIRST PASS-TIER-1 (PGMA-35441) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35441 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812634
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35441 | 1.9.1.2.1.33(HORIL BEAMS FIRST PASS-TIER-1 (PGMA-35441)) | 206812635
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35441 | 1.9.1.2.1.33(HORIL BEAMS FIRST PASS-TIER-1 (PGMA-35441)) | 206812636
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35441 | 1.9.1.2.1.33(HORIL BEAMS FIRST PASS-TIER-1 (PGMA-35441)) | 206812637
HORIL BEAMS FIRST PASS-TIER-2 (PGMA-35442) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35442 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812638
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35442 | 1.9.1.2.1.34(HORIL BEAMS FIRST PASS-TIER-2 (PGMA-35442)) | 206812639
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35442 | 1.9.1.2.1.34(HORIL BEAMS FIRST PASS-TIER-2 (PGMA-35442)) | 206812640
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35442 | 1.9.1.2.1.34(HORIL BEAMS FIRST PASS-TIER-2 (PGMA-35442)) | 206812641
HORIL BEAMS FIRST PASS-TIER-3 (PGMA-35443) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35443 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812642
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35443 | 1.9.1.2.1.35(HORIL BEAMS FIRST PASS-TIER-3 (PGMA-35443)) | 206812643
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35443 | 1.9.1.2.1.35(HORIL BEAMS FIRST PASS-TIER-3 (PGMA-35443)) | 206812644
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35443 | 1.9.1.2.1.35(HORIL BEAMS FIRST PASS-TIER-3 (PGMA-35443)) | 206812645
HOR BEAM-SECOND PASS- TIER-1 (PGMA-35451) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35451 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812646
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35451 | 1.9.1.2.1.36(HOR BEAM-SECOND PASS- TIER-1 (PGMA-35451)) | 206812647
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35451 | 1.9.1.2.1.36(HOR BEAM-SECOND PASS- TIER-1 (PGMA-35451)) | 206812648
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35451 | 1.9.1.2.1.36(HOR BEAM-SECOND PASS- TIER-1 (PGMA-35451)) | 206812649
HOR BEAM-SECOND PASS- TIER-2 (PGMA-35452) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35452 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812650
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35452 | 1.9.1.2.1.37(HOR BEAM-SECOND PASS- TIER-2 (PGMA-35452)) | 206812651
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35452 | 1.9.1.2.1.37(HOR BEAM-SECOND PASS- TIER-2 (PGMA-35452)) | 206812652
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35452 | 1.9.1.2.1.37(HOR BEAM-SECOND PASS- TIER-2 (PGMA-35452)) | 206812653
HOR BEAM-SECOND PASS- TIER-3 (PGMA-35453) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35453 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812654
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35453 | 1.9.1.2.1.38(HOR BEAM-SECOND PASS- TIER-3 (PGMA-35453)) | 206812655
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35453 | 1.9.1.2.1.38(HOR BEAM-SECOND PASS- TIER-3 (PGMA-35453)) | 206812656
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35453 | 1.9.1.2.1.38(HOR BEAM-SECOND PASS- TIER-3 (PGMA-35453)) | 206812657
FRONT BRACING-TIER-1 (PGMA-35511) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35511 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812658
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35511 | 1.9.1.2.1.39(FRONT BRACING-TIER-1 (PGMA-35511)) | 206812659
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35511 | 1.9.1.2.1.39(FRONT BRACING-TIER-1 (PGMA-35511)) | 206812660
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35511 | 1.9.1.2.1.39(FRONT BRACING-TIER-1 (PGMA-35511)) | 206812661
FRONT BRACING-TIER-2 (PGMA-35512) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35512 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812662
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35512 | 1.9.1.2.1.40(FRONT BRACING-TIER-2 (PGMA-35512)) | 206812663
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35512 | 1.9.1.2.1.40(FRONT BRACING-TIER-2 (PGMA-35512)) | 206812664
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35512 | 1.9.1.2.1.40(FRONT BRACING-TIER-2 (PGMA-35512)) | 206812665
FRONT BRACING-TIER-3 (PGMA-35513) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35513 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812666
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35513 | 1.9.1.2.1.41(FRONT BRACING-TIER-3 (PGMA-35513)) | 206812667
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35513 | 1.9.1.2.1.41(FRONT BRACING-TIER-3 (PGMA-35513)) | 206812668
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35513 | 1.9.1.2.1.41(FRONT BRACING-TIER-3 (PGMA-35513)) | 206812669
SIDE BRACING-TIER-1 (PGMA-35521) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35521 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812670
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35521 | 1.9.1.2.1.42(SIDE BRACING-TIER-1 (PGMA-35521)) | 206812671
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35521 | 1.9.1.2.1.42(SIDE BRACING-TIER-1 (PGMA-35521)) | 206812672
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35521 | 1.9.1.2.1.42(SIDE BRACING-TIER-1 (PGMA-35521)) | 206812673
SIDE BRACING-TIER-2 (PGMA-35522) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35522 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812674
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35522 | 1.9.1.2.1.43(SIDE BRACING-TIER-2 (PGMA-35522)) | 206812675
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35522 | 1.9.1.2.1.43(SIDE BRACING-TIER-2 (PGMA-35522)) | 206812676
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35522 | 1.9.1.2.1.43(SIDE BRACING-TIER-2 (PGMA-35522)) | 206812677
SIDE BRACING-TIER-3 (PGMA-35523) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35523 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812678
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35523 | 1.9.1.2.1.44(SIDE BRACING-TIER-3 (PGMA-35523)) | 206812679
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35523 | 1.9.1.2.1.44(SIDE BRACING-TIER-3 (PGMA-35523)) | 206812680
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35523 | 1.9.1.2.1.44(SIDE BRACING-TIER-3 (PGMA-35523)) | 206812681
REAR BRACING-TIER-1 (PGMA-35531) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35531 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812682
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35531 | 1.9.1.2.1.45(REAR BRACING-TIER-1 (PGMA-35531)) | 206812683
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35531 | 1.9.1.2.1.45(REAR BRACING-TIER-1 (PGMA-35531)) | 206812684
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35531 | 1.9.1.2.1.45(REAR BRACING-TIER-1 (PGMA-35531)) | 206812685
REAR BRACING-TIER-2 (PGMA-35532) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35532 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812686
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35532 | 1.9.1.2.1.46(REAR BRACING-TIER-2 (PGMA-35532)) | 206812687
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35532 | 1.9.1.2.1.46(REAR BRACING-TIER-2 (PGMA-35532)) | 206812688
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35532 | 1.9.1.2.1.46(REAR BRACING-TIER-2 (PGMA-35532)) | 206812689
REAR BRACING-TIER-3 (PGMA-35533) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35533 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812690
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35533 | 1.9.1.2.1.47(REAR BRACING-TIER-3 (PGMA-35533)) | 206812691
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35533 | 1.9.1.2.1.47(REAR BRACING-TIER-3 (PGMA-35533)) | 206812692
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35533 | 1.9.1.2.1.47(REAR BRACING-TIER-3 (PGMA-35533)) | 206812693
HSFG FASTENERS FOR PG 35 (PGMA-35700) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35700 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812694
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35700 | 1.9.1.2.1.48(HSFG FASTENERS FOR PG 35 (PGMA-35700)) | 206812695
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35700 | 1.9.1.2.1.48(HSFG FASTENERS FOR PG 35 (PGMA-35700)) | 206812696
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35700 | 1.9.1.2.1.48(HSFG FASTENERS FOR PG 35 (PGMA-35700)) | 206812697
FLOOR GRILLS AND GUARD PLATE (PGMA-35811) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35811 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812698
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35811 | 1.9.1.2.1.49(FLOOR GRILLS AND GUARD PLATE (PGMA-35811)) | 206812699
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35811 | 1.9.1.2.1.49(FLOOR GRILLS AND GUARD PLATE (PGMA-35811)) | 206812700
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35811 | 1.9.1.2.1.49(FLOOR GRILLS AND GUARD PLATE (PGMA-35811)) | 206812701
STAIRS-LOWER (PGMA-35821) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35821 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812702
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35821 | 1.9.1.2.1.50(STAIRS-LOWER (PGMA-35821)) | 206812703
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35821 | 1.9.1.2.1.50(STAIRS-LOWER (PGMA-35821)) | 206812704
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35821 | 1.9.1.2.1.50(STAIRS-LOWER (PGMA-35821)) | 206812705
STAIRS-MIDDLE (PGMA-35822) | SUP | 2022-10-27 08:00 | 2024-01-31 17:00 |  |  |  | 35822 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812706
Engineering | ENG | 2022-10-27 08:00 | 2023-07-05 17:00 |  |  |  | 35822 | 1.9.1.2.1.51(STAIRS-MIDDLE (PGMA-35822)) | 206812707
Manufacturing | MFG | 2023-04-17 08:00 | 2023-11-02 17:00 |  |  |  | 35822 | 1.9.1.2.1.51(STAIRS-MIDDLE (PGMA-35822)) | 206812708
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-31 17:00 |  |  |  | 35822 | 1.9.1.2.1.51(STAIRS-MIDDLE (PGMA-35822)) | 206812709
STAIRS-UPPER (PGMA-35823) | SUP | 2022-10-27 08:00 | 2024-03-09 17:00 |  |  |  | 35823 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812710
Engineering | ENG | 2022-10-27 08:00 | 2023-07-03 17:00 |  |  |  | 35823 | 1.9.1.2.1.52(STAIRS-UPPER (PGMA-35823)) | 206812711
Manufacturing | MFG | 2023-04-15 08:00 | 2024-02-08 17:00 |  |  |  | 35823 | 1.9.1.2.1.52(STAIRS-UPPER (PGMA-35823)) | 206812712
Dispatch | DIS | 2024-02-09 08:00 | 2024-03-09 17:00 |  |  |  | 35823 | 1.9.1.2.1.52(STAIRS-UPPER (PGMA-35823)) | 206812713
HAND RAILS & POSTS (PGMA-35851) | SUP | 2022-10-27 08:00 | 2024-03-11 17:00 |  |  |  | 35851 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812714
Engineering | ENG | 2022-10-27 08:00 | 2023-07-03 17:00 |  |  |  | 35851 | 1.9.1.2.1.53(HAND RAILS & POSTS (PGMA-35851)) | 206812715
Manufacturing | MFG | 2023-04-17 08:00 | 2024-02-10 17:00 |  |  |  | 35851 | 1.9.1.2.1.53(HAND RAILS & POSTS (PGMA-35851)) | 206812716
Dispatch | DIS | 2024-02-11 08:00 | 2024-03-11 17:00 |  |  |  | 35851 | 1.9.1.2.1.53(HAND RAILS & POSTS (PGMA-35851)) | 206812717
CONSUMABLES &Erection MATERIALS (PGMA-35993) | SUP | 2022-10-27 08:00 | 2023-07-27 17:00 |  |  |  | 35993 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812718
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35993 | 1.9.1.2.1.54(CONSUMABLES &Erection MATERIALS (PGMA-35993)) | 206812719
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35993 | 1.9.1.2.1.54(CONSUMABLES &Erection MATERIALS (PGMA-35993)) | 206812720
Dispatch | DIS | 2023-06-28 08:00 | 2023-07-27 17:00 |  |  |  | 35993 | 1.9.1.2.1.54(CONSUMABLES &Erection MATERIALS (PGMA-35993)) | 206812721
CHUTE PIPE AND LADDERS (PGMA-35995) | SUP | 2022-10-27 08:00 | 2023-07-27 17:00 |  |  |  | 35995 | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | 206812722
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 35995 | 1.9.1.2.1.55(CHUTE PIPE AND LADDERS (PGMA-35995)) | 206812723
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 35995 | 1.9.1.2.1.55(CHUTE PIPE AND LADDERS (PGMA-35995)) | 206812724
Dispatch | DIS | 2023-06-28 08:00 | 2023-07-27 17:00 |  |  |  | 35995 | 1.9.1.2.1.55(CHUTE PIPE AND LADDERS (PGMA-35995)) | 206812725
Galleries & Stairways (PG-36) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | PG36 | 1.9.1.2(Supply (BHEL TRY)) | 206812726
COLUMNS NEAR AIR PRE HEATERS (PGMA-36110) | SUP | 2022-12-26 08:00 | 2023-11-27 17:00 |  |  |  | 36110 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812727
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36110 | 1.9.1.2.2.1(COLUMNS NEAR AIR PRE HEATERS (PGMA-36110)) | 206812728
Manufacturing | MFG | 2023-04-27 08:00 | 2023-10-28 17:00 |  |  |  | 36110 | 1.9.1.2.2.1(COLUMNS NEAR AIR PRE HEATERS (PGMA-36110)) | 206812729
Dispatch | DIS | 2023-10-29 08:00 | 2023-11-27 17:00 |  |  |  | 36110 | 1.9.1.2.2.1(COLUMNS NEAR AIR PRE HEATERS (PGMA-36110)) | 206812730
MIDDLE COLUMNS IN BOILER (PGMA-36130) | SUP | 2022-12-26 08:00 | 2023-11-27 17:00 |  |  |  | 36130 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812731
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36130 | 1.9.1.2.2.2(MIDDLE COLUMNS IN BOILER (PGMA-36130)) | 206812732
Manufacturing | MFG | 2023-04-27 08:00 | 2023-10-28 17:00 |  |  |  | 36130 | 1.9.1.2.2.2(MIDDLE COLUMNS IN BOILER (PGMA-36130)) | 206812733
Dispatch | DIS | 2023-10-29 08:00 | 2023-11-27 17:00 |  |  |  | 36130 | 1.9.1.2.2.2(MIDDLE COLUMNS IN BOILER (PGMA-36130)) | 206812734
BEAMS & BRACINGS NEAR AIR PRE HEATER (PGMA-36150) | SUP | 2022-12-26 08:00 | 2023-11-27 17:00 |  |  |  | 36150 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812735
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36150 | 1.9.1.2.2.3(BEAMS & BRACINGS NEAR AIR PRE HEATER (PGMA-36150)) | 206812736
Manufacturing | MFG | 2023-04-27 08:00 | 2023-10-28 17:00 |  |  |  | 36150 | 1.9.1.2.2.3(BEAMS & BRACINGS NEAR AIR PRE HEATER (PGMA-36150)) | 206812737
Dispatch | DIS | 2023-10-29 08:00 | 2023-11-27 17:00 |  |  |  | 36150 | 1.9.1.2.2.3(BEAMS & BRACINGS NEAR AIR PRE HEATER (PGMA-36150)) | 206812738
MAIN FLOOR I MBL 1ST PASS (PGMA-36311) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36311 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812739
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36311 | 1.9.1.2.2.4(MAIN FLOOR I MBL 1ST PASS (PGMA-36311)) | 206812740
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36311 | 1.9.1.2.2.4(MAIN FLOOR I MBL 1ST PASS (PGMA-36311)) | 206812741
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36311 | 1.9.1.2.2.4(MAIN FLOOR I MBL 1ST PASS (PGMA-36311)) | 206812742
MAIN FLOOR I MBL 2ND PASS (PGMA-36312) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36312 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812743
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36312 | 1.9.1.2.2.5(MAIN FLOOR I MBL 2ND PASS (PGMA-36312)) | 206812744
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36312 | 1.9.1.2.2.5(MAIN FLOOR I MBL 2ND PASS (PGMA-36312)) | 206812745
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36312 | 1.9.1.2.2.5(MAIN FLOOR I MBL 2ND PASS (PGMA-36312)) | 206812746
NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36313) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36313 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812747
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36313 | 1.9.1.2.2.6(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36313)) | 206812748
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36313 | 1.9.1.2.2.6(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36313)) | 206812749
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36313 | 1.9.1.2.2.6(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36313)) | 206812750
NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36314) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36314 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812751
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36314 | 1.9.1.2.2.7(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36314)) | 206812752
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36314 | 1.9.1.2.2.7(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36314)) | 206812753
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36314 | 1.9.1.2.2.7(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36314)) | 206812754
NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36315) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36315 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812755
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36315 | 1.9.1.2.2.8(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36315)) | 206812756
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36315 | 1.9.1.2.2.8(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36315)) | 206812757
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36315 | 1.9.1.2.2.8(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36315)) | 206812758
NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36316) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36316 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812759
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36316 | 1.9.1.2.2.9(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36316)) | 206812760
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36316 | 1.9.1.2.2.9(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36316)) | 206812761
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36316 | 1.9.1.2.2.9(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36316)) | 206812762
MAIN FLOOR II MBL IST PASS (PGMA-36321) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36321 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812763
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36321 | 1.9.1.2.2.10(MAIN FLOOR II MBL IST PASS (PGMA-36321)) | 206812764
Manufacturing | MFG | 2023-08-07 08:00 | 2024-02-28 17:00 |  |  |  | 36321 | 1.9.1.2.2.10(MAIN FLOOR II MBL IST PASS (PGMA-36321)) | 206812765
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36321 | 1.9.1.2.2.10(MAIN FLOOR II MBL IST PASS (PGMA-36321)) | 206812766
MAIN FLOOR II MBL 2ND PASS (PGMA-36322) | SUP | 2022-12-26 08:00 | 2024-02-28 17:00 |  |  |  | 36322 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812767
Engineering | ENG | 2022-12-26 08:00 | 2023-08-06 17:00 |  |  |  | 36322 | 1.9.1.2.2.11(MAIN FLOOR II MBL 2ND PASS (PGMA-36322)) | 206812768
Manufacturing | MFG | 2023-07-08 08:00 | 2024-01-29 17:00 |  |  |  | 36322 | 1.9.1.2.2.11(MAIN FLOOR II MBL 2ND PASS (PGMA-36322)) | 206812769
Dispatch | DIS | 2024-01-30 08:00 | 2024-02-28 17:00 |  |  |  | 36322 | 1.9.1.2.2.11(MAIN FLOOR II MBL 2ND PASS (PGMA-36322)) | 206812770
NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36323) | SUP | 2023-01-25 08:00 | 2024-09-15 17:00 |  |  |  | 36323 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812771
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 36323 | 1.9.1.2.2.12(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36323)) | 206812772
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-16 17:00 |  |  |  | 36323 | 1.9.1.2.2.12(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36323)) | 206812773
Dispatch | DIS | 2024-08-17 08:00 | 2024-09-15 17:00 |  |  |  | 36323 | 1.9.1.2.2.12(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36323)) | 206812774
NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36324) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36324 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812775
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36324 | 1.9.1.2.2.13(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36324)) | 206812776
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36324 | 1.9.1.2.2.13(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36324)) | 206812777
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36324 | 1.9.1.2.2.13(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36324)) | 206812778
NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36325) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36325 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812779
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36325 | 1.9.1.2.2.14(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36325)) | 206812780
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36325 | 1.9.1.2.2.14(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36325)) | 206812781
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36325 | 1.9.1.2.2.14(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36325)) | 206812782
NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36326) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36326 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812783
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36326 | 1.9.1.2.2.15(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36326)) | 206812784
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36326 | 1.9.1.2.2.15(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36326)) | 206812785
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36326 | 1.9.1.2.2.15(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36326)) | 206812786
NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36327) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36327 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812787
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36327 | 1.9.1.2.2.16(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36327)) | 206812788
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36327 | 1.9.1.2.2.16(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36327)) | 206812789
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36327 | 1.9.1.2.2.16(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36327)) | 206812790
MAIN FLOOR III MBL 1ST PASS (PGMA-36331) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36331 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812791
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36331 | 1.9.1.2.2.17(MAIN FLOOR III MBL 1ST PASS (PGMA-36331)) | 206812792
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36331 | 1.9.1.2.2.17(MAIN FLOOR III MBL 1ST PASS (PGMA-36331)) | 206812793
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36331 | 1.9.1.2.2.17(MAIN FLOOR III MBL 1ST PASS (PGMA-36331)) | 206812794
MAIN FLOOR III MBL 2ND PASS (PGMA-36332) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36332 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812795
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36332 | 1.9.1.2.2.18(MAIN FLOOR III MBL 2ND PASS (PGMA-36332)) | 206812796
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36332 | 1.9.1.2.2.18(MAIN FLOOR III MBL 2ND PASS (PGMA-36332)) | 206812797
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36332 | 1.9.1.2.2.18(MAIN FLOOR III MBL 2ND PASS (PGMA-36332)) | 206812798
NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36333) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36333 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812799
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36333 | 1.9.1.2.2.19(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36333)) | 206812800
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36333 | 1.9.1.2.2.19(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36333)) | 206812801
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36333 | 1.9.1.2.2.19(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36333)) | 206812802
NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36334) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36334 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812803
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36334 | 1.9.1.2.2.20(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36334)) | 206812804
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36334 | 1.9.1.2.2.20(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36334)) | 206812805
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36334 | 1.9.1.2.2.20(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36334)) | 206812806
NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36335) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36335 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812807
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36335 | 1.9.1.2.2.21(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36335)) | 206812808
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36335 | 1.9.1.2.2.21(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36335)) | 206812809
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36335 | 1.9.1.2.2.21(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36335)) | 206812810
FLOOR IN II PASS (PGMA-36336) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36336 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812811
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36336 | 1.9.1.2.2.22(FLOOR IN II PASS (PGMA-36336)) | 206812812
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36336 | 1.9.1.2.2.22(FLOOR IN II PASS (PGMA-36336)) | 206812813
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36336 | 1.9.1.2.2.22(FLOOR IN II PASS (PGMA-36336)) | 206812814
FLOOR IN I PASS (PGMA-36337) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36337 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812815
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36337 | 1.9.1.2.2.23(FLOOR IN I PASS (PGMA-36337)) | 206812816
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36337 | 1.9.1.2.2.23(FLOOR IN I PASS (PGMA-36337)) | 206812817
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36337 | 1.9.1.2.2.23(FLOOR IN I PASS (PGMA-36337)) | 206812818
FLOOR IN II PASS (PGMA-36338) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36338 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812819
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36338 | 1.9.1.2.2.24(FLOOR IN II PASS (PGMA-36338)) | 206812820
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36338 | 1.9.1.2.2.24(FLOOR IN II PASS (PGMA-36338)) | 206812821
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36338 | 1.9.1.2.2.24(FLOOR IN II PASS (PGMA-36338)) | 206812822
MAIN FLOOR IV MBL 1ST PASS (PGMA-36341) | SUP | 2023-01-25 08:00 | 2024-01-27 17:00 |  |  |  | 36341 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812823
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36341 | 1.9.1.2.2.25(MAIN FLOOR IV MBL 1ST PASS (PGMA-36341)) | 206812824
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 36341 | 1.9.1.2.2.25(MAIN FLOOR IV MBL 1ST PASS (PGMA-36341)) | 206812825
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 36341 | 1.9.1.2.2.25(MAIN FLOOR IV MBL 1ST PASS (PGMA-36341)) | 206812826
MAIN FLOOR IV MBL 2ND PASS (PGMA-36342) | SUP | 2023-01-25 08:00 | 2024-01-27 17:00 |  |  |  | 36342 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812827
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36342 | 1.9.1.2.2.26(MAIN FLOOR IV MBL 2ND PASS (PGMA-36342)) | 206812828
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 36342 | 1.9.1.2.2.26(MAIN FLOOR IV MBL 2ND PASS (PGMA-36342)) | 206812829
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 36342 | 1.9.1.2.2.26(MAIN FLOOR IV MBL 2ND PASS (PGMA-36342)) | 206812830
NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36343) | SUP | 2023-01-25 08:00 | 2024-01-27 17:00 |  |  |  | 36343 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812831
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36343 | 1.9.1.2.2.27(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36343)) | 206812832
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 36343 | 1.9.1.2.2.27(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36343)) | 206812833
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 36343 | 1.9.1.2.2.27(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36343)) | 206812834
NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36344) | SUP | 2023-01-25 08:00 | 2024-01-27 17:00 |  |  |  | 36344 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812835
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36344 | 1.9.1.2.2.28(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36344)) | 206812836
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 36344 | 1.9.1.2.2.28(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36344)) | 206812837
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 36344 | 1.9.1.2.2.28(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36344)) | 206812838
NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36345) | SUP | 2023-01-25 08:00 | 2024-01-27 17:00 |  |  |  | 36345 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812839
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36345 | 1.9.1.2.2.29(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36345)) | 206812840
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 36345 | 1.9.1.2.2.29(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36345)) | 206812841
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 36345 | 1.9.1.2.2.29(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36345)) | 206812842
MAIN FLOOR V MBL I ST PASS (PGMA-36351) | SUP | 2022-12-26 08:00 | 2023-12-28 17:00 |  |  |  | 36351 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812843
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 36351 | 1.9.1.2.2.30(MAIN FLOOR V MBL I ST PASS (PGMA-36351)) | 206812844
Manufacturing | MFG | 2023-06-06 08:00 | 2023-11-28 17:00 |  |  |  | 36351 | 1.9.1.2.2.30(MAIN FLOOR V MBL I ST PASS (PGMA-36351)) | 206812845
Dispatch | DIS | 2023-11-29 08:00 | 2023-12-28 17:00 |  |  |  | 36351 | 1.9.1.2.2.30(MAIN FLOOR V MBL I ST PASS (PGMA-36351)) | 206812846
MAIN FLOOR V MBL II ND PASS (PGMA-36352) | SUP | 2022-12-26 08:00 | 2023-12-28 17:00 |  |  |  | 36352 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812847
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 36352 | 1.9.1.2.2.31(MAIN FLOOR V MBL II ND PASS (PGMA-36352)) | 206812848
Manufacturing | MFG | 2023-06-06 08:00 | 2023-11-28 17:00 |  |  |  | 36352 | 1.9.1.2.2.31(MAIN FLOOR V MBL II ND PASS (PGMA-36352)) | 206812849
Dispatch | DIS | 2023-11-29 08:00 | 2023-12-28 17:00 |  |  |  | 36352 | 1.9.1.2.2.31(MAIN FLOOR V MBL II ND PASS (PGMA-36352)) | 206812850
NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36353) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | 36353 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812851
Engineering | ENG | 2022-12-26 08:00 | 2024-01-29 17:00 |  |  |  | 36353 | 1.9.1.2.2.32(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36353)) | 206812852
Manufacturing | MFG | 2023-12-31 08:00 | 2025-02-02 17:00 |  |  |  | 36353 | 1.9.1.2.2.32(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36353)) | 206812853
Dispatch | DIS | 2025-02-03 08:00 | 2025-03-04 17:00 |  |  |  | 36353 | 1.9.1.2.2.32(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36353)) | 206812854
NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36354) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | 36354 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812855
Engineering | ENG | 2022-12-26 08:00 | 2024-01-29 17:00 |  |  |  | 36354 | 1.9.1.2.2.33(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36354)) | 206812856
Manufacturing | MFG | 2023-12-31 08:00 | 2025-02-02 17:00 |  |  |  | 36354 | 1.9.1.2.2.33(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36354)) | 206812857
Dispatch | DIS | 2025-02-03 08:00 | 2025-03-04 17:00 |  |  |  | 36354 | 1.9.1.2.2.33(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36354)) | 206812858
NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36355) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | 36355 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812859
Engineering | ENG | 2022-12-26 08:00 | 2024-01-29 17:00 |  |  |  | 36355 | 1.9.1.2.2.34(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36355)) | 206812860
Manufacturing | MFG | 2023-12-31 08:00 | 2025-02-02 17:00 |  |  |  | 36355 | 1.9.1.2.2.34(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36355)) | 206812861
Dispatch | DIS | 2025-02-03 08:00 | 2025-03-04 17:00 |  |  |  | 36355 | 1.9.1.2.2.34(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36355)) | 206812862
MAIN FLOOR VI MBL 1ST PASS (PGMA-36361) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | 36361 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812863
Engineering | ENG | 2022-12-26 08:00 | 2024-01-29 17:00 |  |  |  | 36361 | 1.9.1.2.2.35(MAIN FLOOR VI MBL 1ST PASS (PGMA-36361)) | 206812864
Manufacturing | MFG | 2023-12-31 08:00 | 2025-02-02 17:00 |  |  |  | 36361 | 1.9.1.2.2.35(MAIN FLOOR VI MBL 1ST PASS (PGMA-36361)) | 206812865
Dispatch | DIS | 2025-02-03 08:00 | 2025-03-04 17:00 |  |  |  | 36361 | 1.9.1.2.2.35(MAIN FLOOR VI MBL 1ST PASS (PGMA-36361)) | 206812866
MAIN FLOOR VI MBL 2ND PASS (PGMA-36362) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | 36362 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812867
Engineering | ENG | 2022-12-26 08:00 | 2024-01-29 17:00 |  |  |  | 36362 | 1.9.1.2.2.36(MAIN FLOOR VI MBL 2ND PASS (PGMA-36362)) | 206812868
Manufacturing | MFG | 2023-12-31 08:00 | 2025-02-02 17:00 |  |  |  | 36362 | 1.9.1.2.2.36(MAIN FLOOR VI MBL 2ND PASS (PGMA-36362)) | 206812869
Dispatch | DIS | 2025-02-03 08:00 | 2025-03-04 17:00 |  |  |  | 36362 | 1.9.1.2.2.36(MAIN FLOOR VI MBL 2ND PASS (PGMA-36362)) | 206812870
NON-MBL FLOOR ABOVE MBL VI (PGMA-36363) | SUP | 2022-12-26 08:00 | 2025-03-04 17:00 |  |  |  | 36363 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812871
Engineering | ENG | 2022-12-26 08:00 | 2024-01-29 17:00 |  |  |  | 36363 | 1.9.1.2.2.37(NON-MBL FLOOR ABOVE MBL VI (PGMA-36363)) | 206812872
Manufacturing | MFG | 2023-12-31 08:00 | 2025-02-02 17:00 |  |  |  | 36363 | 1.9.1.2.2.37(NON-MBL FLOOR ABOVE MBL VI (PGMA-36363)) | 206812873
Dispatch | DIS | 2025-02-03 08:00 | 2025-03-04 17:00 |  |  |  | 36363 | 1.9.1.2.2.37(NON-MBL FLOOR ABOVE MBL VI (PGMA-36363)) | 206812874
MISCELLANEOUS PLATFORMS-PART I (PGMA-36391) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36391 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812875
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36391 | 1.9.1.2.2.38(MISCELLANEOUS PLATFORMS-PART I (PGMA-36391)) | 206812876
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36391 | 1.9.1.2.2.38(MISCELLANEOUS PLATFORMS-PART I (PGMA-36391)) | 206812877
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36391 | 1.9.1.2.2.38(MISCELLANEOUS PLATFORMS-PART I (PGMA-36391)) | 206812878
MISCELLANEOUS PLATFORMS-PART II (PGMA-36392) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36392 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812879
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36392 | 1.9.1.2.2.39(MISCELLANEOUS PLATFORMS-PART II (PGMA-36392)) | 206812880
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36392 | 1.9.1.2.2.39(MISCELLANEOUS PLATFORMS-PART II (PGMA-36392)) | 206812881
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36392 | 1.9.1.2.2.39(MISCELLANEOUS PLATFORMS-PART II (PGMA-36392)) | 206812882
MISCELLANEOUS PLATFORMS-PART III (PGMA-36393) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36393 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812883
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36393 | 1.9.1.2.2.40(MISCELLANEOUS PLATFORMS-PART III (PGMA-36393)) | 206812884
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36393 | 1.9.1.2.2.40(MISCELLANEOUS PLATFORMS-PART III (PGMA-36393)) | 206812885
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36393 | 1.9.1.2.2.40(MISCELLANEOUS PLATFORMS-PART III (PGMA-36393)) | 206812886
MISCELLANEOUS PLATFORMS-PART IV (PGMA-36394) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36394 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812887
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36394 | 1.9.1.2.2.41(MISCELLANEOUS PLATFORMS-PART IV (PGMA-36394)) | 206812888
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36394 | 1.9.1.2.2.41(MISCELLANEOUS PLATFORMS-PART IV (PGMA-36394)) | 206812889
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36394 | 1.9.1.2.2.41(MISCELLANEOUS PLATFORMS-PART IV (PGMA-36394)) | 206812890
MISCELLANEOUS PLATFORMS-PART V (PGMA-36395) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36395 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812891
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36395 | 1.9.1.2.2.42(MISCELLANEOUS PLATFORMS-PART V (PGMA-36395)) | 206812892
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36395 | 1.9.1.2.2.42(MISCELLANEOUS PLATFORMS-PART V (PGMA-36395)) | 206812893
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36395 | 1.9.1.2.2.42(MISCELLANEOUS PLATFORMS-PART V (PGMA-36395)) | 206812894
BOILER ROOF STRUCTURE (PGMA-36610) | SUP | 2022-12-26 08:00 | 2023-12-28 17:00 |  |  |  | 36610 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812895
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 36610 | 1.9.1.2.2.43(BOILER ROOF STRUCTURE (PGMA-36610)) | 206812896
Manufacturing | MFG | 2023-06-06 08:00 | 2023-11-28 17:00 |  |  |  | 36610 | 1.9.1.2.2.43(BOILER ROOF STRUCTURE (PGMA-36610)) | 206812897
Dispatch | DIS | 2023-11-29 08:00 | 2023-12-28 17:00 |  |  |  | 36610 | 1.9.1.2.2.43(BOILER ROOF STRUCTURE (PGMA-36610)) | 206812898
BOILER ROOF SHEETING (PGMA-36611) | SUP | 2022-12-26 08:00 | 2023-12-28 17:00 |  |  |  | 36611 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812899
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 36611 | 1.9.1.2.2.44(BOILER ROOF SHEETING (PGMA-36611)) | 206812900
Manufacturing | MFG | 2023-06-06 08:00 | 2023-11-28 17:00 |  |  |  | 36611 | 1.9.1.2.2.44(BOILER ROOF SHEETING (PGMA-36611)) | 206812901
Dispatch | DIS | 2023-11-29 08:00 | 2023-12-28 17:00 |  |  |  | 36611 | 1.9.1.2.2.44(BOILER ROOF SHEETING (PGMA-36611)) | 206812902
RAIN WATER PIPES & GUTTER (PGMA-36613) | SUP | 2023-01-25 08:00 | 2024-02-27 17:00 |  |  |  | 36613 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812903
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 36613 | 1.9.1.2.2.45(RAIN WATER PIPES & GUTTER (PGMA-36613)) | 206812904
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-28 17:00 |  |  |  | 36613 | 1.9.1.2.2.45(RAIN WATER PIPES & GUTTER (PGMA-36613)) | 206812905
Dispatch | DIS | 2024-01-29 08:00 | 2024-02-27 17:00 |  |  |  | 36613 | 1.9.1.2.2.45(RAIN WATER PIPES & GUTTER (PGMA-36613)) | 206812906
BOILER SIDE CLADDING STRUCTURE (PGMA-36620) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36620 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812907
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36620 | 1.9.1.2.2.46(BOILER SIDE CLADDING STRUCTURE (PGMA-36620)) | 206812908
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36620 | 1.9.1.2.2.46(BOILER SIDE CLADDING STRUCTURE (PGMA-36620)) | 206812909
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36620 | 1.9.1.2.2.46(BOILER SIDE CLADDING STRUCTURE (PGMA-36620)) | 206812910
BOILER SIDE CLADDING STRUCTURE (PGMA-36621) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 36621 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812911
Engineering | ENG | 2023-01-25 08:00 | 2023-08-17 17:00 |  |  |  | 36621 | 1.9.1.2.2.47(BOILER SIDE CLADDING STRUCTURE (PGMA-36621)) | 206812912
Manufacturing | MFG | 2023-07-19 08:00 | 2024-02-28 17:00 |  |  |  | 36621 | 1.9.1.2.2.47(BOILER SIDE CLADDING STRUCTURE (PGMA-36621)) | 206812913
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 36621 | 1.9.1.2.2.47(BOILER SIDE CLADDING STRUCTURE (PGMA-36621)) | 206812914
POSTS AND HANGERS (PGMA-36740) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 36740 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812915
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36740 | 1.9.1.2.2.48(POSTS AND HANGERS (PGMA-36740)) | 206812916
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 36740 | 1.9.1.2.2.48(POSTS AND HANGERS (PGMA-36740)) | 206812917
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 36740 | 1.9.1.2.2.48(POSTS AND HANGERS (PGMA-36740)) | 206812918
FLOOR GRILLS AND GUARD PLATES-LOWER (PGMA-36811) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 36811 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812919
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36811 | 1.9.1.2.2.49(FLOOR GRILLS AND GUARD PLATES-LOWER (PGMA-36811)) | 206812920
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 36811 | 1.9.1.2.2.49(FLOOR GRILLS AND GUARD PLATES-LOWER (PGMA-36811)) | 206812921
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 36811 | 1.9.1.2.2.49(FLOOR GRILLS AND GUARD PLATES-LOWER (PGMA-36811)) | 206812922
FLOOR GRILLS&GUARD PLATE MIDDLE (PGMA-36812) | SUP | 2023-07-24 08:00 | 2024-09-25 17:00 |  |  |  | 36812 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812923
Engineering | ENG | 2023-07-24 08:00 | 2024-02-10 17:00 |  |  |  | 36812 | 1.9.1.2.2.50(FLOOR GRILLS&GUARD PLATE MIDDLE (PGMA-36812)) | 206812924
Manufacturing | MFG | 2024-02-11 08:00 | 2024-08-26 17:00 |  |  |  | 36812 | 1.9.1.2.2.50(FLOOR GRILLS&GUARD PLATE MIDDLE (PGMA-36812)) | 206812925
Dispatch | DIS | 2024-08-27 08:00 | 2024-09-25 17:00 |  |  |  | 36812 | 1.9.1.2.2.50(FLOOR GRILLS&GUARD PLATE MIDDLE (PGMA-36812)) | 206812926
FLOOR GRILLS&GUARD PLATES- UPPER (PGMA-36813) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 36813 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812927
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36813 | 1.9.1.2.2.51(FLOOR GRILLS&GUARD PLATES- UPPER (PGMA-36813)) | 206812928
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 36813 | 1.9.1.2.2.51(FLOOR GRILLS&GUARD PLATES- UPPER (PGMA-36813)) | 206812929
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 36813 | 1.9.1.2.2.51(FLOOR GRILLS&GUARD PLATES- UPPER (PGMA-36813)) | 206812930
FLOOR GRILLS&GUARD PLATE MISCELLANEOUS (PGMA-36814) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 36814 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812931
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36814 | 1.9.1.2.2.52(FLOOR GRILLS&GUARD PLATE MISCELLANEOUS (PGMA-36814)) | 206812932
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 36814 | 1.9.1.2.2.52(FLOOR GRILLS&GUARD PLATE MISCELLANEOUS (PGMA-36814)) | 206812933
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 36814 | 1.9.1.2.2.52(FLOOR GRILLS&GUARD PLATE MISCELLANEOUS (PGMA-36814)) | 206812934
STAIRS AND LADDERS (PGMA-36820) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 36820 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812935
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36820 | 1.9.1.2.2.53(STAIRS AND LADDERS (PGMA-36820)) | 206812936
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 36820 | 1.9.1.2.2.53(STAIRS AND LADDERS (PGMA-36820)) | 206812937
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 36820 | 1.9.1.2.2.53(STAIRS AND LADDERS (PGMA-36820)) | 206812938
HAND RAILS &POSTS LOWER (PGMA-36851) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 36851 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812939
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 36851 | 1.9.1.2.2.54(HAND RAILS &POSTS LOWER (PGMA-36851)) | 206812940
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 36851 | 1.9.1.2.2.54(HAND RAILS &POSTS LOWER (PGMA-36851)) | 206812941
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 36851 | 1.9.1.2.2.54(HAND RAILS &POSTS LOWER (PGMA-36851)) | 206812942
HANDRAILS & POSTS MIDDLE (PGMA-36852) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 36852 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812943
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 36852 | 1.9.1.2.2.55(HANDRAILS & POSTS MIDDLE (PGMA-36852)) | 206812944
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 36852 | 1.9.1.2.2.55(HANDRAILS & POSTS MIDDLE (PGMA-36852)) | 206812945
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 36852 | 1.9.1.2.2.55(HANDRAILS & POSTS MIDDLE (PGMA-36852)) | 206812946
HANDRAILS & POSTS UPPER (PGMA-36853) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 36853 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812947
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36853 | 1.9.1.2.2.56(HANDRAILS & POSTS UPPER (PGMA-36853)) | 206812948
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 36853 | 1.9.1.2.2.56(HANDRAILS & POSTS UPPER (PGMA-36853)) | 206812949
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 36853 | 1.9.1.2.2.56(HANDRAILS & POSTS UPPER (PGMA-36853)) | 206812950
CONSUMABLES &Erection MATERIALS (PGMA-36993) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 36993 | 1.9.1.2.2(Galleries & Stairways (PG-36)) | 206812951
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 36993 | 1.9.1.2.2.57(CONSUMABLES &Erection MATERIALS (PGMA-36993)) | 206812952
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 36993 | 1.9.1.2.2.57(CONSUMABLES &Erection MATERIALS (PGMA-36993)) | 206812953
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 36993 | 1.9.1.2.2.57(CONSUMABLES &Erection MATERIALS (PGMA-36993)) | 206812954
Inter - Connecting Walkways (PG-38) | SUP | 2022-09-27 08:00 | 2025-05-30 17:00 |  |  |  | PG38 | 1.9.1.2(Supply (BHEL TRY)) | 206812955
LIFT COLUMNS (PGMA-38110) | SUP | 2022-09-27 08:00 | 2023-06-29 17:00 |  |  |  | 38110 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812956
Engineering | ENG | 2022-09-27 08:00 | 2023-04-08 17:00 |  |  |  | 38110 | 1.9.1.2.3.1(LIFT COLUMNS (PGMA-38110)) | 206812957
Manufacturing | MFG | 2023-01-21 08:00 | 2023-05-30 17:00 |  |  |  | 38110 | 1.9.1.2.3.1(LIFT COLUMNS (PGMA-38110)) | 206812958
Dispatch | DIS | 2023-05-31 08:00 | 2023-06-29 17:00 |  |  |  | 38110 | 1.9.1.2.3.1(LIFT COLUMNS (PGMA-38110)) | 206812959
INTER CONN PLATFORMSBETN BOILER/ELEVAT (PGMA-38210) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 38210 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812960
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 38210 | 1.9.1.2.3.2(INTER CONN PLATFORMSBETN BOILER/ELEVAT (PGMA-38210)) | 206812961
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 38210 | 1.9.1.2.3.2(INTER CONN PLATFORMSBETN BOILER/ELEVAT (PGMA-38210)) | 206812962
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 38210 | 1.9.1.2.3.2(INTER CONN PLATFORMSBETN BOILER/ELEVAT (PGMA-38210)) | 206812963
MILL HANDLING MONORAILS (PGMA-38299) | SUP | 2023-06-12 08:00 | 2025-01-17 17:00 |  |  |  | 38299 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812964
Engineering | ENG | 2023-06-12 08:00 | 2024-03-07 17:00 |  |  |  | 38299 | 1.9.1.2.3.3(MILL HANDLING MONORAILS (PGMA-38299)) | 206812965
Manufacturing | MFG | 2024-03-08 08:00 | 2024-12-18 17:00 |  |  |  | 38299 | 1.9.1.2.3.3(MILL HANDLING MONORAILS (PGMA-38299)) | 206812966
Dispatch | DIS | 2024-12-19 08:00 | 2025-01-17 17:00 |  |  |  | 38299 | 1.9.1.2.3.3(MILL HANDLING MONORAILS (PGMA-38299)) | 206812967
CONN PLATFORMS TO MILL/DEAERATOR BAY (PGMA-38310) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 38310 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812968
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 38310 | 1.9.1.2.3.4(CONN PLATFORMS TO MILL/DEAERATOR BAY (PGMA-38310)) | 206812969
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 38310 | 1.9.1.2.3.4(CONN PLATFORMS TO MILL/DEAERATOR BAY (PGMA-38310)) | 206812970
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 38310 | 1.9.1.2.3.4(CONN PLATFORMS TO MILL/DEAERATOR BAY (PGMA-38310)) | 206812971
ECO HANDLING STRUCTURE (PGMA-38381) | SUP | 2023-03-23 08:00 | 2024-10-28 17:00 |  |  |  | 38381 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812972
Engineering | ENG | 2023-03-23 08:00 | 2023-12-17 17:00 |  |  |  | 38381 | 1.9.1.2.3.5(ECO HANDLING STRUCTURE (PGMA-38381)) | 206812973
Manufacturing | MFG | 2023-12-18 08:00 | 2024-09-28 17:00 |  |  |  | 38381 | 1.9.1.2.3.5(ECO HANDLING STRUCTURE (PGMA-38381)) | 206812974
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 38381 | 1.9.1.2.3.5(ECO HANDLING STRUCTURE (PGMA-38381)) | 206812975
MILL MAINTANANCE PLATFORMS (PGMA-38410) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 38410 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812976
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 38410 | 1.9.1.2.3.6(MILL MAINTANANCE PLATFORMS (PGMA-38410)) | 206812977
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 38410 | 1.9.1.2.3.6(MILL MAINTANANCE PLATFORMS (PGMA-38410)) | 206812978
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 38410 | 1.9.1.2.3.6(MILL MAINTANANCE PLATFORMS (PGMA-38410)) | 206812979
LIFT BEAMS & BRACINGS (PGMA-38510) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 38510 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812980
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 38510 | 1.9.1.2.3.7(LIFT BEAMS & BRACINGS (PGMA-38510)) | 206812981
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 38510 | 1.9.1.2.3.7(LIFT BEAMS & BRACINGS (PGMA-38510)) | 206812982
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 38510 | 1.9.1.2.3.7(LIFT BEAMS & BRACINGS (PGMA-38510)) | 206812983
PASSENGER ELEVATOR BRACINGS-MIDDLE (PGMA-38512) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 38512 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812984
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 38512 | 1.9.1.2.3.8(PASSENGER ELEVATOR BRACINGS-MIDDLE (PGMA-38512)) | 206812985
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 38512 | 1.9.1.2.3.8(PASSENGER ELEVATOR BRACINGS-MIDDLE (PGMA-38512)) | 206812986
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 38512 | 1.9.1.2.3.8(PASSENGER ELEVATOR BRACINGS-MIDDLE (PGMA-38512)) | 206812987
ELEVATOR CLADDING STRUCTURE (PGMA-38610) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 38610 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812988
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 38610 | 1.9.1.2.3.9(ELEVATOR CLADDING STRUCTURE (PGMA-38610)) | 206812989
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 38610 | 1.9.1.2.3.9(ELEVATOR CLADDING STRUCTURE (PGMA-38610)) | 206812990
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 38610 | 1.9.1.2.3.9(ELEVATOR CLADDING STRUCTURE (PGMA-38610)) | 206812991
ELEVATOR CLADDING (PGMA-38611) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 38611 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812992
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 38611 | 1.9.1.2.3.10(ELEVATOR CLADDING (PGMA-38611)) | 206812993
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 38611 | 1.9.1.2.3.10(ELEVATOR CLADDING (PGMA-38611)) | 206812994
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 38611 | 1.9.1.2.3.10(ELEVATOR CLADDING (PGMA-38611)) | 206812995
CONN PLATFORM ROOF STRUCTURE (PGMA-38612) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 38612 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206812996
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 38612 | 1.9.1.2.3.11(CONN PLATFORM ROOF STRUCTURE (PGMA-38612)) | 206812997
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 38612 | 1.9.1.2.3.11(CONN PLATFORM ROOF STRUCTURE (PGMA-38612)) | 206812998
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 38612 | 1.9.1.2.3.11(CONN PLATFORM ROOF STRUCTURE (PGMA-38612)) | 206812999
LIFT MACHINE ROOM DETAILS &MISC STRUCT (PGMA-38710) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 38710 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206813000
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 38710 | 1.9.1.2.3.12(LIFT MACHINE ROOM DETAILS &MISC STRUCT (PGMA-38710)) | 206813001
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 38710 | 1.9.1.2.3.12(LIFT MACHINE ROOM DETAILS &MISC STRUCT (PGMA-38710)) | 206813002
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 38710 | 1.9.1.2.3.12(LIFT MACHINE ROOM DETAILS &MISC STRUCT (PGMA-38710)) | 206813003
ELEVATOR CLADDING STRUCTURES (PGMA-38712) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 38712 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206813004
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 38712 | 1.9.1.2.3.13(ELEVATOR CLADDING STRUCTURES (PGMA-38712)) | 206813005
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 38712 | 1.9.1.2.3.13(ELEVATOR CLADDING STRUCTURES (PGMA-38712)) | 206813006
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 38712 | 1.9.1.2.3.13(ELEVATOR CLADDING STRUCTURES (PGMA-38712)) | 206813007
FLOORGRILLS AND GUARD PLATE (PGMA-38810) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 38810 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206813008
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 38810 | 1.9.1.2.3.14(FLOORGRILLS AND GUARD PLATE (PGMA-38810)) | 206813009
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 38810 | 1.9.1.2.3.14(FLOORGRILLS AND GUARD PLATE (PGMA-38810)) | 206813010
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 38810 | 1.9.1.2.3.14(FLOORGRILLS AND GUARD PLATE (PGMA-38810)) | 206813011
STAIRS AND LADDERS (PGMA-38820) | SUP | 2023-05-18 08:00 | 2025-02-14 17:00 |  |  |  | 38820 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206813012
Engineering | ENG | 2023-05-18 08:00 | 2024-03-14 17:00 |  |  |  | 38820 | 1.9.1.2.3.15(STAIRS AND LADDERS (PGMA-38820)) | 206813013
Manufacturing | MFG | 2024-03-15 08:00 | 2025-01-15 17:00 |  |  |  | 38820 | 1.9.1.2.3.15(STAIRS AND LADDERS (PGMA-38820)) | 206813014
Dispatch | DIS | 2025-01-16 08:00 | 2025-02-14 17:00 |  |  |  | 38820 | 1.9.1.2.3.15(STAIRS AND LADDERS (PGMA-38820)) | 206813015
HAND RAILS AND HAND RAIL POSTS (PGMA-38850) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 38850 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206813016
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 38850 | 1.9.1.2.3.16(HAND RAILS AND HAND RAIL POSTS (PGMA-38850)) | 206813017
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 38850 | 1.9.1.2.3.16(HAND RAILS AND HAND RAIL POSTS (PGMA-38850)) | 206813018
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 38850 | 1.9.1.2.3.16(HAND RAILS AND HAND RAIL POSTS (PGMA-38850)) | 206813019
CONSUMABLES &Erection MATERIALS (PGMA-38993) | SUP | 2023-08-31 08:00 | 2025-05-30 17:00 |  |  |  | 38993 | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | 206813020
Engineering | ENG | 2023-08-31 08:00 | 2024-06-27 17:00 |  |  |  | 38993 | 1.9.1.2.3.17(CONSUMABLES &Erection MATERIALS (PGMA-38993)) | 206813021
Manufacturing | MFG | 2024-06-28 08:00 | 2025-04-30 17:00 |  |  |  | 38993 | 1.9.1.2.3.17(CONSUMABLES &Erection MATERIALS (PGMA-38993)) | 206813022
Dispatch | DIS | 2025-05-01 08:00 | 2025-05-30 17:00 |  |  |  | 38993 | 1.9.1.2.3.17(CONSUMABLES &Erection MATERIALS (PGMA-38993)) | 206813023
Coal bunker Bay Structures (PG-34) | SUP | 2022-10-27 08:00 | 2024-01-25 17:00 |  |  |  | PG34 | 1.9.1.2(Supply (BHEL TRY)) | 206813024
FOUN.MATLS FOR BUNKER COLOMNS (PGMA-34010) | SUP | 2022-10-27 08:00 | 2023-05-28 17:00 |  |  |  | 34010 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813025
Engineering | ENG | 2022-10-27 08:00 | 2023-01-19 17:00 |  |  |  | 34010 | 1.9.1.2.4.1(FOUN.MATLS FOR BUNKER COLOMNS (PGMA-34010)) | 206813026
Manufacturing | MFG | 2022-12-21 08:00 | 2023-03-28 17:00 |  |  |  | 34010 | 1.9.1.2.4.1(FOUN.MATLS FOR BUNKER COLOMNS (PGMA-34010)) | 206813027
Dispatch | DIS | 2023-03-29 08:00 | 2023-05-28 17:00 |  |  |  | 34010 | 1.9.1.2.4.1(FOUN.MATLS FOR BUNKER COLOMNS (PGMA-34010)) | 206813028
BUNKER COLUMNS (PGMA-34100) | SUP | 2022-10-27 08:00 | 2023-09-10 17:00 |  |  |  | 34100 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813029
Engineering | ENG | 2022-10-27 08:00 | 2023-05-08 17:00 |  |  |  | 34100 | 1.9.1.2.4.2(BUNKER COLUMNS (PGMA-34100)) | 206813030
Manufacturing | MFG | 2023-02-18 08:00 | 2023-06-27 17:00 |  |  |  | 34100 | 1.9.1.2.4.2(BUNKER COLUMNS (PGMA-34100)) | 206813031
Dispatch | DIS | 2023-06-28 08:00 | 2023-09-10 17:00 |  |  |  | 34100 | 1.9.1.2.4.2(BUNKER COLUMNS (PGMA-34100)) | 206813032
BUNKER SUPPORT FRAMES (PGMA-34200) | SUP | 2022-10-27 08:00 | 2023-09-27 17:00 |  |  |  | 34200 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813033
Engineering | ENG | 2022-10-27 08:00 | 2023-03-27 17:00 |  |  |  | 34200 | 1.9.1.2.4.3(BUNKER SUPPORT FRAMES (PGMA-34200)) | 206813034
Manufacturing | MFG | 2023-02-26 08:00 | 2023-08-28 17:00 |  |  |  | 34200 | 1.9.1.2.4.3(BUNKER SUPPORT FRAMES (PGMA-34200)) | 206813035
Dispatch | DIS | 2023-08-29 08:00 | 2023-09-27 17:00 |  |  |  | 34200 | 1.9.1.2.4.3(BUNKER SUPPORT FRAMES (PGMA-34200)) | 206813036
PLATFORMS (PGMA-34300) | SUP | 2023-02-24 08:00 | 2024-01-25 17:00 |  |  |  | 34300 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813037
Engineering | ENG | 2023-02-24 08:00 | 2023-07-25 17:00 |  |  |  | 34300 | 1.9.1.2.4.4(PLATFORMS (PGMA-34300)) | 206813038
Manufacturing | MFG | 2023-06-26 08:00 | 2023-12-26 17:00 |  |  |  | 34300 | 1.9.1.2.4.4(PLATFORMS (PGMA-34300)) | 206813039
Dispatch | DIS | 2023-12-27 08:00 | 2024-01-25 17:00 |  |  |  | 34300 | 1.9.1.2.4.4(PLATFORMS (PGMA-34300)) | 206813040
BUNKER BAY FLOOR BEAMS (PGMA-34390) | SUP | 2023-02-24 08:00 | 2024-01-25 17:00 |  |  |  | 34390 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813041
Engineering | ENG | 2023-02-24 08:00 | 2023-07-25 17:00 |  |  |  | 34390 | 1.9.1.2.4.5(BUNKER BAY FLOOR BEAMS (PGMA-34390)) | 206813042
Manufacturing | MFG | 2023-06-26 08:00 | 2023-12-26 17:00 |  |  |  | 34390 | 1.9.1.2.4.5(BUNKER BAY FLOOR BEAMS (PGMA-34390)) | 206813043
Dispatch | DIS | 2023-12-27 08:00 | 2024-01-25 17:00 |  |  |  | 34390 | 1.9.1.2.4.5(BUNKER BAY FLOOR BEAMS (PGMA-34390)) | 206813044
HORIZONTAL BEAMS BETWEEN COLUMNS (PGMA-34400) | SUP | 2022-12-26 08:00 | 2023-11-26 17:00 |  |  |  | 34400 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813045
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 34400 | 1.9.1.2.4.6(HORIZONTAL BEAMS BETWEEN COLUMNS (PGMA-34400)) | 206813046
Manufacturing | MFG | 2023-04-27 08:00 | 2023-10-27 17:00 |  |  |  | 34400 | 1.9.1.2.4.6(HORIZONTAL BEAMS BETWEEN COLUMNS (PGMA-34400)) | 206813047
Dispatch | DIS | 2023-10-28 08:00 | 2023-11-26 17:00 |  |  |  | 34400 | 1.9.1.2.4.6(HORIZONTAL BEAMS BETWEEN COLUMNS (PGMA-34400)) | 206813048
VERTICAL BRACINGS (PGMA-34500) | SUP | 2022-12-26 08:00 | 2023-11-26 17:00 |  |  |  | 34500 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813049
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 34500 | 1.9.1.2.4.7(VERTICAL BRACINGS (PGMA-34500)) | 206813050
Manufacturing | MFG | 2023-04-27 08:00 | 2023-10-27 17:00 |  |  |  | 34500 | 1.9.1.2.4.7(VERTICAL BRACINGS (PGMA-34500)) | 206813051
Dispatch | DIS | 2023-10-28 08:00 | 2023-11-26 17:00 |  |  |  | 34500 | 1.9.1.2.4.7(VERTICAL BRACINGS (PGMA-34500)) | 206813052
FLOORGRILLS AND GUARD PLATES (PGMA-34810) | SUP | 2023-02-24 08:00 | 2024-01-25 17:00 |  |  |  | 34810 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813053
Engineering | ENG | 2023-02-24 08:00 | 2023-07-25 17:00 |  |  |  | 34810 | 1.9.1.2.4.8(FLOORGRILLS AND GUARD PLATES (PGMA-34810)) | 206813054
Manufacturing | MFG | 2023-06-26 08:00 | 2023-12-26 17:00 |  |  |  | 34810 | 1.9.1.2.4.8(FLOORGRILLS AND GUARD PLATES (PGMA-34810)) | 206813055
Dispatch | DIS | 2023-12-27 08:00 | 2024-01-25 17:00 |  |  |  | 34810 | 1.9.1.2.4.8(FLOORGRILLS AND GUARD PLATES (PGMA-34810)) | 206813056
STAIRS AND LADDERS (PGMA-34820) | SUP | 2023-02-24 08:00 | 2024-01-25 17:00 |  |  |  | 34820 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813057
Engineering | ENG | 2023-02-24 08:00 | 2023-07-25 17:00 |  |  |  | 34820 | 1.9.1.2.4.9(STAIRS AND LADDERS (PGMA-34820)) | 206813058
Manufacturing | MFG | 2023-06-26 08:00 | 2023-12-26 17:00 |  |  |  | 34820 | 1.9.1.2.4.9(STAIRS AND LADDERS (PGMA-34820)) | 206813059
Dispatch | DIS | 2023-12-27 08:00 | 2024-01-25 17:00 |  |  |  | 34820 | 1.9.1.2.4.9(STAIRS AND LADDERS (PGMA-34820)) | 206813060
HANDRAILS & HANDRAIL POSTS (PGMA-34850) | SUP | 2023-02-24 08:00 | 2024-01-25 17:00 |  |  |  | 34850 | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | 206813061
Engineering | ENG | 2023-02-24 08:00 | 2023-07-25 17:00 |  |  |  | 34850 | 1.9.1.2.4.10(HANDRAILS & HANDRAIL POSTS (PGMA-34850)) | 206813062
Manufacturing | MFG | 2023-06-26 08:00 | 2023-12-26 17:00 |  |  |  | 34850 | 1.9.1.2.4.10(HANDRAILS & HANDRAIL POSTS (PGMA-34850)) | 206813063
Dispatch | DIS | 2023-12-27 08:00 | 2024-01-25 17:00 |  |  |  | 34850 | 1.9.1.2.4.10(HANDRAILS & HANDRAIL POSTS (PGMA-34850)) | 206813064
Manholes and Furnace Openings (PG-28) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | PG28 | 1.9.1.2(Supply (BHEL TRY)) | 206813065
DOORS (PGMA-28220) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 28220 | 1.9.1.2.5(Manholes and Furnace Openings (PG-28)) | 206813066
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 28220 | 1.9.1.2.5.1(DOORS (PGMA-28220)) | 206813067
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 28220 | 1.9.1.2.5.1(DOORS (PGMA-28220)) | 206813068
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 28220 | 1.9.1.2.5.1(DOORS (PGMA-28220)) | 206813069
BPS FASTENERS (PGMA-28700) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 28700 | 1.9.1.2.5(Manholes and Furnace Openings (PG-28)) | 206813070
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 28700 | 1.9.1.2.5.2(BPS FASTENERS (PGMA-28700)) | 206813071
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 28700 | 1.9.1.2.5.2(BPS FASTENERS (PGMA-28700)) | 206813072
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 28700 | 1.9.1.2.5.2(BPS FASTENERS (PGMA-28700)) | 206813073
BOI- HT- Boiler Elevator | SUP | 2023-04-15 08:00 | 2024-04-29 17:00 |  |  |  |  | 1.9.1.2(Supply (BHEL TRY)) | 206813074
NIT | ENQ | 2023-04-15 08:00 | 2023-04-15 17:00 |  |  |  |  | 1.9.1.2.6( BOI- HT- Boiler Elevator) | 206813075
Ordering | ORD | 2023-04-16 08:00 | 2023-09-12 17:00 |  |  |  |  | 1.9.1.2.6( BOI- HT- Boiler Elevator) | 206813076
Manufacturing | MFG | 2023-09-13 08:00 | 2024-03-30 17:00 |  |  |  |  | 1.9.1.2.6( BOI- HT- Boiler Elevator) | 206813077
Dispatch | DIS | 2024-03-31 08:00 | 2024-04-29 17:00 |  |  |  |  | 1.9.1.2.6( BOI- HT- Boiler Elevator) | 206813078
BOI- FL- Quick erect scaffold | SUP | 2023-10-12 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.9.1.2(Supply (BHEL TRY)) | 206813079
NIT | ENQ | 2023-10-12 08:00 | 2023-10-12 17:00 |  |  |  |  | 1.9.1.2.7( BOI- FL- Quick erect scaffold) | 206813080
Ordering | ORD | 2023-10-13 08:00 | 2024-07-18 17:00 |  |  |  |  | 1.9.1.2.7( BOI- FL- Quick erect scaffold) | 206813081
Manufacturing | MFG | 2024-07-19 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.9.1.2.7( BOI- FL- Quick erect scaffold) | 206813082
Dispatch | DIS | 2025-05-15 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.9.1.2.7( BOI- FL- Quick erect scaffold) | 206813083
Civil | CIV | 2023-02-23 17:00 | 2024-12-15 17:00 |  |  |  |  | 1.9.1(Boiler Structure) | 206813084
REL OF DWG FOR SG Foundation | PE - RFC | 2023-02-23 17:00 | 2023-02-23 17:00 |  |  |  |  | 1.9.1.3(Civil) | 206813085
Boiler Foundation | CIV | 2023-02-24 08:00 | 2023-09-25 17:00 |  |  |  |  | 1.9.1.3(Civil) | 206813086
Excavation | CIV | 2023-02-24 08:00 | 2023-04-09 17:00 |  |  |  |  | 1.9.1.3.2(Boiler Foundation) | 206813087
RCC Raft | CIV | 2023-04-10 08:00 | 2023-07-03 17:00 |  |  |  |  | 1.9.1.3.2(Boiler Foundation) | 206813088
RCC Pedestal | CIV | 2023-07-04 08:00 | 2023-09-10 17:00 |  |  |  |  | 1.9.1.3.2(Boiler Foundation) | 206813089
Backfilling | CIV | 2023-09-11 08:00 | 2023-09-25 17:00 |  |  |  |  | 1.9.1.3.2(Boiler Foundation) | 206813090
Coal Bunker Bay Foundation and structure | CIV | 2023-02-23 17:00 | 2024-12-15 17:00 |  |  |  |  | 1.9.1.3(Civil) | 206813091
REL OF DWG FOR BUNKER Foundation | PE - RFC | 2023-02-23 17:00 | 2023-02-23 17:00 |  |  |  |  | 1.9.1.3.3(Coal Bunker Bay Foundation and structure) | 206813092
Coal BUNKER BAY FOUNDATIONS | CIV | 2023-02-24 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.9.1.3.3(Coal Bunker Bay Foundation and structure) | 206813093
Excavation & PCC | CIV | 2023-02-24 08:00 | 2023-04-19 17:00 |  |  |  |  | 1.9.1.3.3.2(Coal BUNKER BAY FOUNDATIONS) | 206813094
RCC foundation | CIV | 2023-04-20 08:00 | 2023-07-13 17:00 |  |  |  |  | 1.9.1.3.3.2(Coal BUNKER BAY FOUNDATIONS) | 206813095
RCC Pedestal ( Upto Bolt Lift) | CIV | 2023-07-14 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.9.1.3.3.2(Coal BUNKER BAY FOUNDATIONS) | 206813096
Backfilling | CIV | 2023-09-07 08:00 | 2023-09-18 17:00 |  |  |  |  | 1.9.1.3.3.2(Coal BUNKER BAY FOUNDATIONS) | 206813097
Finishing Work | CIV | 2023-09-19 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.9.1.3.3.2(Coal BUNKER BAY FOUNDATIONS) | 206813098
Coal Bunker Bay Floors and Roof | CIV | 2024-05-20 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.9.1.3.3(Coal Bunker Bay Foundation and structure) | 206813099
RCC Feeder Floor Slab | CIV | 2024-05-20 08:00 | 2024-07-08 17:00 |  |  |  |  | 1.9.1.3.3.3(Coal Bunker Bay Floors and Roof) | 206813100
RCC Tripper Floor Slab | CIV | 2024-07-04 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.9.1.3.3.3(Coal Bunker Bay Floors and Roof) | 206813101
RCC Roof Slab | CIV | 2024-09-27 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.9.1.3.3.3(Coal Bunker Bay Floors and Roof) | 206813102
Erection | ERC | 2023-09-26 08:00 | 2026-04-30 17:00 |  |  |  |  | 1.9.1(Boiler Structure) | 206813103
Main Boiler supporting structure (PG-35) | ERC | 2023-09-26 08:00 | 2026-04-30 17:00 |  |  |  | PG35 | 1.9.1.4(Erection) | 206813104
Erection: Main Columns | ERC | 2023-09-26 08:00 | 2024-06-21 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813105
Erection: Auxiliary Columns | ERC | 2023-09-30 08:00 | 2024-03-27 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813106
Erection: Horizontal Bracing including Chute Pipe And Ladder | ERC | 2024-02-01 08:00 | 2024-06-14 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813107
Erection: Horizontal Beams | ERC | 2024-02-01 08:00 | 2024-07-09 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813108
Erection: Land Platform | ERC | 2024-02-01 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813109
Erection: Front Bracing | ERC | 2024-02-01 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813110
Erection: Side Bracing | ERC | 2024-02-01 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813111
Erection: Rear Bracing | ERC | 2024-02-01 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813112
Erection: Floor Grills And Guard | ERC | 2024-02-03 08:00 | 2025-05-27 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813113
Erection: Stairs | ERC | 2024-02-03 08:00 | 2024-06-21 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813114
Erection: Hand Rails And Posts | ERC | 2024-03-12 08:00 | 2026-04-30 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813115
Erection: Ceiling Girder Main Structure | ERC | 2024-06-22 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813116
Erection: CEIL STRUCT-CROSS WELDED BEAMS | ERC | 2024-04-23 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813117
Erection: Ceiling Structure Rolled beam | ERC | 2024-06-22 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813118
Erection: Ceiling Structure Horizontal beam | ERC | 2024-04-23 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813119
Erection: Ceiling Girder Lifting Complete | ERC | 2024-07-25 17:00 | 2024-07-25 17:00 |  |  |  |  | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | 206813120
Galleries & Stairways (PG-36) | ERC | 2024-03-30 08:00 | 2025-12-27 17:00 |  |  |  | PG36 | 1.9.1.4(Erection) | 206813121
Erection: COLUMNS NEAR AIR PRE HEATERS | ERC | 2024-07-26 08:00 | 2024-11-22 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813122
Erection: MIDDLE COLUMNS IN BOILER | ERC | 2024-05-27 08:00 | 2024-09-23 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813123
Erection: BEAMS & BRACINGS NEAR AIR PRE HEATER | ERC | 2024-07-26 08:00 | 2025-01-21 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813124
Erection: Main Floor MBL- 1st and 2nd Pass | ERC | 2024-04-27 08:00 | 2025-12-27 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813125
Erection: NON MBL Floor - 1st and 2nd Pass | ERC | 2024-03-30 08:00 | 2025-11-29 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813126
Erection: Miscellaneous Platform | ERC | 2024-06-26 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813127
Erection: Boiler Roof Structure | ERC | 2024-06-26 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813128
Erection: Boiler Roof Sheeting | ERC | 2024-06-26 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813129
Erection: Rain Water Pipes And Gutter | ERC | 2024-07-26 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813130
Erection: Boiler Side Cladding Structure | ERC | 2024-07-26 08:00 | 2024-09-23 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813131
Erection: Floor grills and guard plate | ERC | 2024-09-26 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813132
Erection: Stairs And Ladders | ERC | 2024-11-23 08:00 | 2025-04-21 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813133
Erection: Handrails And Posts | ERC | 2024-06-26 08:00 | 2025-09-18 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813134
Erection: Silencer and supports | ERC | 2024-07-26 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.9.1.4.2(Galleries & Stairways (PG-36)) | 206813135
Inter - Connecting Walkways (PG-38) | ERC | 2024-10-29 08:00 | 2026-01-05 17:00 |  |  |  | PG38 | 1.9.1.4(Erection) | 206813136
Erection: LIFT COLUMNS, Beams & Bracing | ERC | 2024-10-29 08:00 | 2025-02-25 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813137
Erection: INTER CONN PLATFORMSBETN BOILER/ELEVATOR | ERC | 2025-06-20 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813138
Erection: MILL HANDLING MONORAILS | ERC | 2025-01-18 08:00 | 2025-03-18 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813139
Erection: CONN PLATFORMS TO MILL/DEAERATOR BAY | ERC | 2025-11-07 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813140
Erection: ECO HANDLING STRUCTURE | ERC | 2025-09-18 08:00 | 2025-11-06 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813141
Erection: MILL MAINTANANCE PLATFORMS | ERC | 2024-11-28 08:00 | 2025-01-11 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813142
Erection: ELEVATOR CLADDING STRUCTURE | ERC | 2025-02-26 08:00 | 2025-07-25 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813143
Erection: ELEVATOR CLADDING | ERC | 2025-07-26 08:00 | 2025-09-23 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813144
Erection: CONN PLATFORM ROOF STRUCTURE | ERC | 2025-08-19 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813145
Erection: LIFT MACHINE ROOM DETAILS &MISC STRUCT | ERC | 2025-02-26 08:00 | 2025-07-25 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813146
Erection: FLOORGRILLS AND GUARD PLATE | ERC | 2025-07-26 08:00 | 2025-08-24 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813147
Erection: STAIRS AND LADDERS | ERC | 2025-08-25 08:00 | 2025-09-23 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813148
Erection: HAND RAILS AND HAND RAIL POSTS | ERC | 2025-09-24 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | 206813149
Coal bunker Bay Structures (PG-34) | ERC | 2024-01-26 08:00 | 2024-11-05 17:00 |  |  |  | PG34 | 1.9.1.4(Erection) | 206813150
Erection: BUNKER COLUMNS, SUPPORT FRAME,PLATFORM, BEAMS & BRACINGS Upto Feeder Floor | ERC | 2024-01-26 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813151
Erection: BUNKER COLUMNS, SUPPORT FRAME,PLATFORM, BEAMS & BRACINGS Upto Tripper Floor | ERC | 2024-03-06 08:00 | 2024-04-19 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813152
Erection: BUNKER COLUMNS, SUPPORT FRAME,PLATFORM, BEAMS & BRACINGS Upto Roof | ERC | 2024-04-20 08:00 | 2024-06-08 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813153
Erection: Cladding | ERC | 2024-06-09 08:00 | 2024-08-07 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813154
Erection: FLOORGRILLS AND GUARD PLATES | ERC | 2024-06-09 08:00 | 2024-09-06 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813155
Erection: STAIRS AND LADDERS | ERC | 2024-07-09 08:00 | 2024-10-06 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813156
Erection: HANDRAILS & HANDRAIL POSTS | ERC | 2024-08-08 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | 206813157
Manholes and Furnace Openings (PG-28) | ERC | 2025-04-05 08:00 | 2025-06-03 17:00 |  |  |  | PG28 | 1.9.1.4(Erection) | 206813158
Erection: DOORS | ERC | 2025-04-05 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.9.1.4.5(Manholes and Furnace Openings (PG-28)) | 206813159
Water Circulation System, Super Heaters and Re-Heaters | ERC | 2022-09-27 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206813160
Supply (BHEL TRY) | SUP | 2022-09-27 08:00 | 2025-11-11 17:00 |  |  |  |  | 1.9.2(Water Circulation System, Super Heaters and Re-Heaters ) | 206813161
Water Circulation System | SUP | 2022-09-27 08:00 | 2025-11-11 17:00 |  |  |  |  | 1.9.2.1(Supply (BHEL TRY)) | 206813162
Separator, Storage Tanks and Supports (PG-04) | SUP | 2022-09-27 08:00 | 2024-03-27 17:00 |  |  |  | PG04 | 1.9.2.1.1(Water Circulation System) | 206813163
SUPPORTS FOR COLLECTOR & SEPERATOR VESSEL (PGMA-4147) | SUP | 2022-09-27 08:00 | 2024-01-26 17:00 |  |  |  | 4147 | 1.9.2.1.1.1(Separator, Storage Tanks and Supports (PG-04)) | 206813164
Engineering | ENG | 2022-09-27 08:00 | 2023-08-04 17:00 |  |  |  | 04147 | 1.9.2.1.1.1.1(SUPPORTS FOR COLLECTOR & SEPERATOR VESSEL (PGMA-4147)) | 206813165
Manufacturing | MFG | 2023-05-05 08:00 | 2023-12-12 17:00 |  |  |  | 04147 | 1.9.2.1.1.1.1(SUPPORTS FOR COLLECTOR & SEPERATOR VESSEL (PGMA-4147)) | 206813166
Dispatch | DIS | 2023-12-13 08:00 | 2024-01-26 17:00 |  |  |  | 04147 | 1.9.2.1.1.1.1(SUPPORTS FOR COLLECTOR & SEPERATOR VESSEL (PGMA-4147)) | 206813167
Separator Vessels with Internals & Attach (PGMA-4321) | SUP | 2023-01-25 08:00 | 2024-03-27 17:00 |  |  |  | 4321 | 1.9.2.1.1.1(Separator, Storage Tanks and Supports (PG-04)) | 206813168
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 04321 | 1.9.2.1.1.1.2(Separator Vessels with Internals & Attach (PGMA-4321)) | 206813169
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-26 17:00 |  |  |  | 04321 | 1.9.2.1.1.1.2(Separator Vessels with Internals & Attach (PGMA-4321)) | 206813170
Dispatch | DIS | 2024-02-27 08:00 | 2024-03-27 17:00 |  |  |  | 04321 | 1.9.2.1.1.1.2(Separator Vessels with Internals & Attach (PGMA-4321)) | 206813171
SUPP FOR COLLECTING & SEPERATOR VESSEL(DD) (PGMA-4347) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 04347 | 1.9.2.1.1.1(Separator, Storage Tanks and Supports (PG-04)) | 206813172
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 04347 | 1.9.2.1.1.1.3(SUPP FOR COLLECTING & SEPERATOR VESSEL(DD) (PGMA-4347)) | 206813173
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 04347 | 1.9.2.1.1.1.3(SUPP FOR COLLECTING & SEPERATOR VESSEL(DD) (PGMA-4347)) | 206813174
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 04347 | 1.9.2.1.1.1.3(SUPP FOR COLLECTING & SEPERATOR VESSEL(DD) (PGMA-4347)) | 206813175
SUPP FOR COLLECTING & SEPERATOR VESSEL (PGMA-4547) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 4547 | 1.9.2.1.1.1(Separator, Storage Tanks and Supports (PG-04)) | 206813176
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 04547 | 1.9.2.1.1.1.4(SUPP FOR COLLECTING & SEPERATOR VESSEL (PGMA-4547)) | 206813177
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 04547 | 1.9.2.1.1.1.4(SUPP FOR COLLECTING & SEPERATOR VESSEL (PGMA-4547)) | 206813178
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 04547 | 1.9.2.1.1.1.4(SUPP FOR COLLECTING & SEPERATOR VESSEL (PGMA-4547)) | 206813179
Waterwall Headers (PG-05) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | PG05 | 1.9.2.1.1(Water Circulation System) | 206813180
INLET FRONT LOWER WW HEADER (PGMA-5137) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 5137 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813181
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 05137 | 1.9.2.1.1.2.1(INLET FRONT LOWER WW HEADER (PGMA-5137)) | 206813182
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 05137 | 1.9.2.1.1.2.1(INLET FRONT LOWER WW HEADER (PGMA-5137)) | 206813183
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 05137 | 1.9.2.1.1.2.1(INLET FRONT LOWER WW HEADER (PGMA-5137)) | 206813184
INLET REAR LOWER WW HEADER (PGMA-5147) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 5147 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813185
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 05147 | 1.9.2.1.1.2.2(INLET REAR LOWER WW HEADER (PGMA-5147)) | 206813186
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 05147 | 1.9.2.1.1.2.2(INLET REAR LOWER WW HEADER (PGMA-5147)) | 206813187
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 05147 | 1.9.2.1.1.2.2(INLET REAR LOWER WW HEADER (PGMA-5147)) | 206813188
INLET SIDE LOWER WW HEADER (PGMA-5155) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 5155 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813189
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 05155 | 1.9.2.1.1.2.3(INLET SIDE LOWER WW HEADER (PGMA-5155)) | 206813190
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 05155 | 1.9.2.1.1.2.3(INLET SIDE LOWER WW HEADER (PGMA-5155)) | 206813191
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 05155 | 1.9.2.1.1.2.3(INLET SIDE LOWER WW HEADER (PGMA-5155)) | 206813192
WATERWALL REAR HANGER OUTLET HDR (PGMA-5227) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 5227 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813193
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 05227 | 1.9.2.1.1.2.4(WATERWALL REAR HANGER OUTLET HDR (PGMA-5227)) | 206813194
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 05227 | 1.9.2.1.1.2.4(WATERWALL REAR HANGER OUTLET HDR (PGMA-5227)) | 206813195
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 05227 | 1.9.2.1.1.2.4(WATERWALL REAR HANGER OUTLET HDR (PGMA-5227)) | 206813196
OUTLET FRONT UPPER WW HEADER (PGMA-5231) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 5231 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813197
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 05231 | 1.9.2.1.1.2.5(OUTLET FRONT UPPER WW HEADER (PGMA-5231)) | 206813198
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 05231 | 1.9.2.1.1.2.5(OUTLET FRONT UPPER WW HEADER (PGMA-5231)) | 206813199
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 05231 | 1.9.2.1.1.2.5(OUTLET FRONT UPPER WW HEADER (PGMA-5231)) | 206813200
OUTLET SIDE UPPER WW HEADER (PGMA-5251) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 5251 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813201
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 05251 | 1.9.2.1.1.2.6(OUTLET SIDE UPPER WW HEADER (PGMA-5251)) | 206813202
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 05251 | 1.9.2.1.1.2.6(OUTLET SIDE UPPER WW HEADER (PGMA-5251)) | 206813203
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 05251 | 1.9.2.1.1.2.6(OUTLET SIDE UPPER WW HEADER (PGMA-5251)) | 206813204
Furnace Rear wall Intermediate header (PGMA-5327) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 5327 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813205
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 05327 | 1.9.2.1.1.2.7(Furnace Rear wall Intermediate header (PGMA-5327)) | 206813206
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 05327 | 1.9.2.1.1.2.7(Furnace Rear wall Intermediate header (PGMA-5327)) | 206813207
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 05327 | 1.9.2.1.1.2.7(Furnace Rear wall Intermediate header (PGMA-5327)) | 206813208
FRONT INTERMEDIATE HEADER (PGMA-5330) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 5330 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813209
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 05330 | 1.9.2.1.1.2.8(FRONT INTERMEDIATE HEADER (PGMA-5330)) | 206813210
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 05330 | 1.9.2.1.1.2.8(FRONT INTERMEDIATE HEADER (PGMA-5330)) | 206813211
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 05330 | 1.9.2.1.1.2.8(FRONT INTERMEDIATE HEADER (PGMA-5330)) | 206813212
SIDE INTERMEDIATE HEADER (PGMA-5350) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 5350 | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | 206813213
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 05350 | 1.9.2.1.1.2.9(SIDE INTERMEDIATE HEADER (PGMA-5350)) | 206813214
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 05350 | 1.9.2.1.1.2.9(SIDE INTERMEDIATE HEADER (PGMA-5350)) | 206813215
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 05350 | 1.9.2.1.1.2.9(SIDE INTERMEDIATE HEADER (PGMA-5350)) | 206813216
Waterwall Panels (PG-06) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | PG06 | 1.9.2.1.1(Water Circulation System) | 206813217
UNCLASSIFIED BURNER PANEL (PGMA-6400) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 6400 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813218
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 06400 | 1.9.2.1.1.3.1(UNCLASSIFIED BURNER PANEL (PGMA-6400)) | 206813219
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 06400 | 1.9.2.1.1.3.1(UNCLASSIFIED BURNER PANEL (PGMA-6400)) | 206813220
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 06400 | 1.9.2.1.1.3.1(UNCLASSIFIED BURNER PANEL (PGMA-6400)) | 206813221
BURNER PNL- OS (PGMA-6401) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 6401 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813222
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 06401 | 1.9.2.1.1.3.2(BURNER PNL- OS (PGMA-6401)) | 206813223
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 06401 | 1.9.2.1.1.3.2(BURNER PNL- OS (PGMA-6401)) | 206813224
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 06401 | 1.9.2.1.1.3.2(BURNER PNL- OS (PGMA-6401)) | 206813225
FRONT INTERMEDIATE WW PNL -OS (PGMA-6434) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 6434 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813226
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 06434 | 1.9.2.1.1.3.3(FRONT INTERMEDIATE WW PNL -OS (PGMA-6434)) | 206813227
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 06434 | 1.9.2.1.1.3.3(FRONT INTERMEDIATE WW PNL -OS (PGMA-6434)) | 206813228
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 06434 | 1.9.2.1.1.3.3(FRONT INTERMEDIATE WW PNL -OS (PGMA-6434)) | 206813229
FRONT WW LOWER PANEL-OS (PGMA-6437) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 6437 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813230
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 06437 | 1.9.2.1.1.3.4(FRONT WW LOWER PANEL-OS (PGMA-6437)) | 206813231
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 06437 | 1.9.2.1.1.3.4(FRONT WW LOWER PANEL-OS (PGMA-6437)) | 206813232
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 06437 | 1.9.2.1.1.3.4(FRONT WW LOWER PANEL-OS (PGMA-6437)) | 206813233
REAR INTERMEDIATE WW PNL -OS (PGMA-6444) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 6444 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813234
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 06444 | 1.9.2.1.1.3.5(REAR INTERMEDIATE WW PNL -OS (PGMA-6444)) | 206813235
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 06444 | 1.9.2.1.1.3.5(REAR INTERMEDIATE WW PNL -OS (PGMA-6444)) | 206813236
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 06444 | 1.9.2.1.1.3.5(REAR INTERMEDIATE WW PNL -OS (PGMA-6444)) | 206813237
SIDE UPPER WW PNL -OS (PGMA-6451) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 6451 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813238
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 06451 | 1.9.2.1.1.3.6(SIDE UPPER WW PNL -OS (PGMA-6451)) | 206813239
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 06451 | 1.9.2.1.1.3.6(SIDE UPPER WW PNL -OS (PGMA-6451)) | 206813240
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 06451 | 1.9.2.1.1.3.6(SIDE UPPER WW PNL -OS (PGMA-6451)) | 206813241
SIDE INTERMEDIATE WW PNL -OS (PGMA-6453) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 6453 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813242
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 06453 | 1.9.2.1.1.3.7(SIDE INTERMEDIATE WW PNL -OS (PGMA-6453)) | 206813243
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 06453 | 1.9.2.1.1.3.7(SIDE INTERMEDIATE WW PNL -OS (PGMA-6453)) | 206813244
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 06453 | 1.9.2.1.1.3.7(SIDE INTERMEDIATE WW PNL -OS (PGMA-6453)) | 206813245
SIDE LOWER WW PNL -OS (PGMA-6455) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 6455 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813246
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 06455 | 1.9.2.1.1.3.8(SIDE LOWER WW PNL -OS (PGMA-6455)) | 206813247
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 06455 | 1.9.2.1.1.3.8(SIDE LOWER WW PNL -OS (PGMA-6455)) | 206813248
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 06455 | 1.9.2.1.1.3.8(SIDE LOWER WW PNL -OS (PGMA-6455)) | 206813249
BURNER PANELS WITH ATTACHMENT (PGMA-6500) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 6500 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813250
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 06500 | 1.9.2.1.1.3.9(BURNER PANELS WITH ATTACHMENT (PGMA-6500)) | 206813251
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 06500 | 1.9.2.1.1.3.9(BURNER PANELS WITH ATTACHMENT (PGMA-6500)) | 206813252
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 06500 | 1.9.2.1.1.3.9(BURNER PANELS WITH ATTACHMENT (PGMA-6500)) | 206813253
SOFA PANELS -OS (PGMA-6501) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 6501 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813254
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 06501 | 1.9.2.1.1.3.10(SOFA PANELS -OS (PGMA-6501)) | 206813255
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 06501 | 1.9.2.1.1.3.10(SOFA PANELS -OS (PGMA-6501)) | 206813256
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 06501 | 1.9.2.1.1.3.10(SOFA PANELS -OS (PGMA-6501)) | 206813257
FRONT UPPER WW PNL + ATCH (PGMA-6731) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 6731 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813258
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 06731 | 1.9.2.1.1.3.11(FRONT UPPER WW PNL + ATCH (PGMA-6731)) | 206813259
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 06731 | 1.9.2.1.1.3.11(FRONT UPPER WW PNL + ATCH (PGMA-6731)) | 206813260
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 06731 | 1.9.2.1.1.3.11(FRONT UPPER WW PNL + ATCH (PGMA-6731)) | 206813261
Front Upper Corners Ww Panel + attachment (PGMA-6732) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 6732 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813262
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 06732 | 1.9.2.1.1.3.12(Front Upper Corners Ww Panel + attachment (PGMA-6732)) | 206813263
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 06732 | 1.9.2.1.1.3.12(Front Upper Corners Ww Panel + attachment (PGMA-6732)) | 206813264
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 06732 | 1.9.2.1.1.3.12(Front Upper Corners Ww Panel + attachment (PGMA-6732)) | 206813265
FRONT INTERMEDIATE WW PNL + ATCH (PGMA-6734) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 6734 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813266
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 06734 | 1.9.2.1.1.3.13(FRONT INTERMEDIATE WW PNL + ATCH (PGMA-6734)) | 206813267
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 06734 | 1.9.2.1.1.3.13(FRONT INTERMEDIATE WW PNL + ATCH (PGMA-6734)) | 206813268
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 06734 | 1.9.2.1.1.3.13(FRONT INTERMEDIATE WW PNL + ATCH (PGMA-6734)) | 206813269
FUR LWR FRNT SPIRAL PANELS WITH I/L TERM TUBES (PGMA-6737) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 6737 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813270
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 06737 | 1.9.2.1.1.3.14(FUR LWR FRNT SPIRAL PANELS WITH I/L TERM TUBES (PGMA-6737)) | 206813271
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 06737 | 1.9.2.1.1.3.14(FUR LWR FRNT SPIRAL PANELS WITH I/L TERM TUBES (PGMA-6737)) | 206813272
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 06737 | 1.9.2.1.1.3.14(FUR LWR FRNT SPIRAL PANELS WITH I/L TERM TUBES (PGMA-6737)) | 206813273
REAR UPPER WW PNL + ATCH (PGMA-6741) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 6741 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813274
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 06741 | 1.9.2.1.1.3.15(REAR UPPER WW PNL + ATCH (PGMA-6741)) | 206813275
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 06741 | 1.9.2.1.1.3.15(REAR UPPER WW PNL + ATCH (PGMA-6741)) | 206813276
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 06741 | 1.9.2.1.1.3.15(REAR UPPER WW PNL + ATCH (PGMA-6741)) | 206813277
FUR UPPER REAR SPIRAL PANEL (PGMA-6744) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 6744 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813278
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 06744 | 1.9.2.1.1.3.16(FUR UPPER REAR SPIRAL PANEL (PGMA-6744)) | 206813279
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 06744 | 1.9.2.1.1.3.16(FUR UPPER REAR SPIRAL PANEL (PGMA-6744)) | 206813280
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 06744 | 1.9.2.1.1.3.16(FUR UPPER REAR SPIRAL PANEL (PGMA-6744)) | 206813281
FUR LWR REAR SPIRAL PANELS WITH I/T TERM TUBES (PGMA-6747) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 6747 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813282
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 06747 | 1.9.2.1.1.3.17(FUR LWR REAR SPIRAL PANELS WITH I/T TERM TUBES (PGMA-6747)) | 206813283
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 06747 | 1.9.2.1.1.3.17(FUR LWR REAR SPIRAL PANELS WITH I/T TERM TUBES (PGMA-6747)) | 206813284
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 06747 | 1.9.2.1.1.3.17(FUR LWR REAR SPIRAL PANELS WITH I/T TERM TUBES (PGMA-6747)) | 206813285
SIDE UPPER WW PNL + ATCH (PGMA-6751) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 6751 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813286
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 06751 | 1.9.2.1.1.3.18(SIDE UPPER WW PNL + ATCH (PGMA-6751)) | 206813287
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 06751 | 1.9.2.1.1.3.18(SIDE UPPER WW PNL + ATCH (PGMA-6751)) | 206813288
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 06751 | 1.9.2.1.1.3.18(SIDE UPPER WW PNL + ATCH (PGMA-6751)) | 206813289
Furnace vertical wall panels sides L&R (PGMA-6752) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 6752 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813290
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 06752 | 1.9.2.1.1.3.19(Furnace vertical wall panels sides L&R (PGMA-6752)) | 206813291
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 06752 | 1.9.2.1.1.3.19(Furnace vertical wall panels sides L&R (PGMA-6752)) | 206813292
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 06752 | 1.9.2.1.1.3.19(Furnace vertical wall panels sides L&R (PGMA-6752)) | 206813293
FUR UPPER SIDE SPIRAL PANELS (PGMA-6753) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 6753 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813294
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 06753 | 1.9.2.1.1.3.20(FUR UPPER SIDE SPIRAL PANELS (PGMA-6753)) | 206813295
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 06753 | 1.9.2.1.1.3.20(FUR UPPER SIDE SPIRAL PANELS (PGMA-6753)) | 206813296
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 06753 | 1.9.2.1.1.3.20(FUR UPPER SIDE SPIRAL PANELS (PGMA-6753)) | 206813297
SIDE LOWER WW PNL + ATCH (PGMA-6755) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 6755 | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | 206813298
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 06755 | 1.9.2.1.1.3.21(SIDE LOWER WW PNL + ATCH (PGMA-6755)) | 206813299
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 06755 | 1.9.2.1.1.3.21(SIDE LOWER WW PNL + ATCH (PGMA-6755)) | 206813300
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 06755 | 1.9.2.1.1.3.21(SIDE LOWER WW PNL + ATCH (PGMA-6755)) | 206813301
Circulation System Components (PG-07) | SUP | 2022-12-26 08:00 | 2024-09-27 17:00 |  |  |  | PG07 | 1.9.2.1.1(Water Circulation System) | 206813302
Separator-Collecting Vessel Connecting Link (PGMA-7110) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 7110 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813303
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 07110 | 1.9.2.1.1.4.1(Separator-Collecting Vessel Connecting Link (PGMA-7110)) | 206813304
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 07110 | 1.9.2.1.1.4.1(Separator-Collecting Vessel Connecting Link (PGMA-7110)) | 206813305
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 07110 | 1.9.2.1.1.4.1(Separator-Collecting Vessel Connecting Link (PGMA-7110)) | 206813306
Mixing Sphere (PGMA-7125) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 7125 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813307
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 07125 | 1.9.2.1.1.4.2(Mixing Sphere (PGMA-7125)) | 206813308
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 07125 | 1.9.2.1.1.4.2(Mixing Sphere (PGMA-7125)) | 206813309
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 07125 | 1.9.2.1.1.4.2(Mixing Sphere (PGMA-7125)) | 206813310
FURNACE SCREEN TUBES (PGMA-7223) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 7223 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813311
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 07223 | 1.9.2.1.1.4.3(FURNACE SCREEN TUBES (PGMA-7223)) | 206813312
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 07223 | 1.9.2.1.1.4.3(FURNACE SCREEN TUBES (PGMA-7223)) | 206813313
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 07223 | 1.9.2.1.1.4.3(FURNACE SCREEN TUBES (PGMA-7223)) | 206813314
LOWER CORNER TRANSITION TUBES (PGMA-7231) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 7231 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813315
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 07231 | 1.9.2.1.1.4.4(LOWER CORNER TRANSITION TUBES (PGMA-7231)) | 206813316
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 07231 | 1.9.2.1.1.4.4(LOWER CORNER TRANSITION TUBES (PGMA-7231)) | 206813317
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 07231 | 1.9.2.1.1.4.4(LOWER CORNER TRANSITION TUBES (PGMA-7231)) | 206813318
UPPER CORNER TRANSITION TUBES (PGMA-7232) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7232 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813319
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07232 | 1.9.2.1.1.4.5(UPPER CORNER TRANSITION TUBES (PGMA-7232)) | 206813320
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07232 | 1.9.2.1.1.4.5(UPPER CORNER TRANSITION TUBES (PGMA-7232)) | 206813321
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07232 | 1.9.2.1.1.4.5(UPPER CORNER TRANSITION TUBES (PGMA-7232)) | 206813322
WW FRONT HEADER SUSPENSION-DD (PGMA-7302) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7302 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813323
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07302 | 1.9.2.1.1.4.6(WW FRONT HEADER SUSPENSION-DD (PGMA-7302)) | 206813324
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07302 | 1.9.2.1.1.4.6(WW FRONT HEADER SUSPENSION-DD (PGMA-7302)) | 206813325
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07302 | 1.9.2.1.1.4.6(WW FRONT HEADER SUSPENSION-DD (PGMA-7302)) | 206813326
WW SIDE HEADER SUSPENSION-DD (PGMA-7303) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7303 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813327
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07303 | 1.9.2.1.1.4.7(WW SIDE HEADER SUSPENSION-DD (PGMA-7303)) | 206813328
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07303 | 1.9.2.1.1.4.7(WW SIDE HEADER SUSPENSION-DD (PGMA-7303)) | 206813329
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07303 | 1.9.2.1.1.4.7(WW SIDE HEADER SUSPENSION-DD (PGMA-7303)) | 206813330
FURNACE WALL SUPPORTS FRONT-DD (PGMA-7309) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7309 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813331
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07309 | 1.9.2.1.1.4.8(FURNACE WALL SUPPORTS FRONT-DD (PGMA-7309)) | 206813332
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07309 | 1.9.2.1.1.4.8(FURNACE WALL SUPPORTS FRONT-DD (PGMA-7309)) | 206813333
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07309 | 1.9.2.1.1.4.8(FURNACE WALL SUPPORTS FRONT-DD (PGMA-7309)) | 206813334
FUR SIDE RISERS (PGMA-7315) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7315 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813335
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07315 | 1.9.2.1.1.4.9(FUR SIDE RISERS (PGMA-7315)) | 206813336
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07315 | 1.9.2.1.1.4.9(FUR SIDE RISERS (PGMA-7315)) | 206813337
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07315 | 1.9.2.1.1.4.9(FUR SIDE RISERS (PGMA-7315)) | 206813338
FUR REAR RISERS (PGMA-7316) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7316 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813339
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07316 | 1.9.2.1.1.4.10(FUR REAR RISERS (PGMA-7316)) | 206813340
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07316 | 1.9.2.1.1.4.10(FUR REAR RISERS (PGMA-7316)) | 206813341
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07316 | 1.9.2.1.1.4.10(FUR REAR RISERS (PGMA-7316)) | 206813342
FUR FRNT RISERS (PGMA-7318) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7318 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813343
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07318 | 1.9.2.1.1.4.11(FUR FRNT RISERS (PGMA-7318)) | 206813344
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07318 | 1.9.2.1.1.4.11(FUR FRNT RISERS (PGMA-7318)) | 206813345
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07318 | 1.9.2.1.1.4.11(FUR FRNT RISERS (PGMA-7318)) | 206813346
RISER TUBE SUPPORT-DD (PGMA-7331) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 7331 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813347
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 07331 | 1.9.2.1.1.4.12(RISER TUBE SUPPORT-DD (PGMA-7331)) | 206813348
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 07331 | 1.9.2.1.1.4.12(RISER TUBE SUPPORT-DD (PGMA-7331)) | 206813349
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 07331 | 1.9.2.1.1.4.12(RISER TUBE SUPPORT-DD (PGMA-7331)) | 206813350
FURNACE SPIRAL WALL SUPPORTS-DD (PGMA-7360) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 7360 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813351
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 07360 | 1.9.2.1.1.4.13(FURNACE SPIRAL WALL SUPPORTS-DD (PGMA-7360)) | 206813352
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 07360 | 1.9.2.1.1.4.13(FURNACE SPIRAL WALL SUPPORTS-DD (PGMA-7360)) | 206813353
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 07360 | 1.9.2.1.1.4.13(FURNACE SPIRAL WALL SUPPORTS-DD (PGMA-7360)) | 206813354
FURNACE WALL SUPP REAR-DD (PGMA-7361) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7361 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813355
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07361 | 1.9.2.1.1.4.14(FURNACE WALL SUPP REAR-DD (PGMA-7361)) | 206813356
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07361 | 1.9.2.1.1.4.14(FURNACE WALL SUPP REAR-DD (PGMA-7361)) | 206813357
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07361 | 1.9.2.1.1.4.14(FURNACE WALL SUPP REAR-DD (PGMA-7361)) | 206813358
FURNACE WALL SUPPORTS SIDES L & R-DD (PGMA-7362) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7362 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813359
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07362 | 1.9.2.1.1.4.15(FURNACE WALL SUPPORTS SIDES L & R-DD (PGMA-7362)) | 206813360
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07362 | 1.9.2.1.1.4.15(FURNACE WALL SUPPORTS SIDES L & R-DD (PGMA-7362)) | 206813361
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07362 | 1.9.2.1.1.4.15(FURNACE WALL SUPPORTS SIDES L & R-DD (PGMA-7362)) | 206813362
CONSUMABLES &Erection MATERIALS-DD (PGMA-7393) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 7393 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813363
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 07393 | 1.9.2.1.1.4.16(CONSUMABLES &Erection MATERIALS-DD (PGMA-7393)) | 206813364
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 07393 | 1.9.2.1.1.4.16(CONSUMABLES &Erection MATERIALS-DD (PGMA-7393)) | 206813365
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 07393 | 1.9.2.1.1.4.16(CONSUMABLES &Erection MATERIALS-DD (PGMA-7393)) | 206813366
COMBUSTOR OUTLET HEADER SUPPORTS (PGMA-7402) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7402 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813367
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07402 | 1.9.2.1.1.4.17(COMBUSTOR OUTLET HEADER SUPPORTS (PGMA-7402)) | 206813368
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07402 | 1.9.2.1.1.4.17(COMBUSTOR OUTLET HEADER SUPPORTS (PGMA-7402)) | 206813369
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07402 | 1.9.2.1.1.4.17(COMBUSTOR OUTLET HEADER SUPPORTS (PGMA-7402)) | 206813370
WW SIDE HEADER SUSPENSION (PGMA-7403) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7403 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813371
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07403 | 1.9.2.1.1.4.18(WW SIDE HEADER SUSPENSION (PGMA-7403)) | 206813372
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07403 | 1.9.2.1.1.4.18(WW SIDE HEADER SUSPENSION (PGMA-7403)) | 206813373
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07403 | 1.9.2.1.1.4.18(WW SIDE HEADER SUSPENSION (PGMA-7403)) | 206813374
WW SCREEN HEADER SUSPENSION (PGMA-7405) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7405 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813375
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07405 | 1.9.2.1.1.4.19(WW SCREEN HEADER SUSPENSION (PGMA-7405)) | 206813376
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07405 | 1.9.2.1.1.4.19(WW SCREEN HEADER SUSPENSION (PGMA-7405)) | 206813377
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07405 | 1.9.2.1.1.4.19(WW SCREEN HEADER SUSPENSION (PGMA-7405)) | 206813378
Furnace wall Supports front (PGMA-7409) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7409 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813379
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07409 | 1.9.2.1.1.4.20(Furnace wall Supports front (PGMA-7409)) | 206813380
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07409 | 1.9.2.1.1.4.20(Furnace wall Supports front (PGMA-7409)) | 206813381
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07409 | 1.9.2.1.1.4.20(Furnace wall Supports front (PGMA-7409)) | 206813382
FURNACE SCREEN TUBES-OS (PGMA-7423) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 7423 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813383
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 07423 | 1.9.2.1.1.4.21(FURNACE SCREEN TUBES-OS (PGMA-7423)) | 206813384
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 07423 | 1.9.2.1.1.4.21(FURNACE SCREEN TUBES-OS (PGMA-7423)) | 206813385
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 07423 | 1.9.2.1.1.4.21(FURNACE SCREEN TUBES-OS (PGMA-7423)) | 206813386
RISER TUBE SUPPORT (PGMA-7431) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 7431 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813387
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 07431 | 1.9.2.1.1.4.22(RISER TUBE SUPPORT (PGMA-7431)) | 206813388
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 07431 | 1.9.2.1.1.4.22(RISER TUBE SUPPORT (PGMA-7431)) | 206813389
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 07431 | 1.9.2.1.1.4.22(RISER TUBE SUPPORT (PGMA-7431)) | 206813390
Furnace Spiral Wall supports Misc. items (PGMA-7460) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 7460 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813391
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 07460 | 1.9.2.1.1.4.23(Furnace Spiral Wall supports Misc. items (PGMA-7460)) | 206813392
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 07460 | 1.9.2.1.1.4.23(Furnace Spiral Wall supports Misc. items (PGMA-7460)) | 206813393
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 07460 | 1.9.2.1.1.4.23(Furnace Spiral Wall supports Misc. items (PGMA-7460)) | 206813394
Furnace wall Supports rear (PGMA-7461) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7461 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813395
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07461 | 1.9.2.1.1.4.24(Furnace wall Supports rear (PGMA-7461)) | 206813396
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07461 | 1.9.2.1.1.4.24(Furnace wall Supports rear (PGMA-7461)) | 206813397
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07461 | 1.9.2.1.1.4.24(Furnace wall Supports rear (PGMA-7461)) | 206813398
Furnace wall Supports Sides L & R (PGMA-7462) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7462 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813399
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07462 | 1.9.2.1.1.4.25(Furnace wall Supports Sides L & R (PGMA-7462)) | 206813400
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07462 | 1.9.2.1.1.4.25(Furnace wall Supports Sides L & R (PGMA-7462)) | 206813401
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07462 | 1.9.2.1.1.4.25(Furnace wall Supports Sides L & R (PGMA-7462)) | 206813402
EVAPORATOR COILS (PGMA-7502) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7502 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813403
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07502 | 1.9.2.1.1.4.26(EVAPORATOR COILS (PGMA-7502)) | 206813404
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07502 | 1.9.2.1.1.4.26(EVAPORATOR COILS (PGMA-7502)) | 206813405
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07502 | 1.9.2.1.1.4.26(EVAPORATOR COILS (PGMA-7502)) | 206813406
EVAPORATOR COILS (PGMA-7503) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7503 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813407
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07503 | 1.9.2.1.1.4.27(EVAPORATOR COILS (PGMA-7503)) | 206813408
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07503 | 1.9.2.1.1.4.27(EVAPORATOR COILS (PGMA-7503)) | 206813409
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07503 | 1.9.2.1.1.4.27(EVAPORATOR COILS (PGMA-7503)) | 206813410
MODULE SUPPORT - IP (PGMA-7505) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 7505 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813411
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 07505 | 1.9.2.1.1.4.28(MODULE SUPPORT - IP (PGMA-7505)) | 206813412
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 07505 | 1.9.2.1.1.4.28(MODULE SUPPORT - IP (PGMA-7505)) | 206813413
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 07505 | 1.9.2.1.1.4.28(MODULE SUPPORT - IP (PGMA-7505)) | 206813414
RISER TUBE SUPPORT-SHOP (PGMA-7531) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 7531 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813415
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 07531 | 1.9.2.1.1.4.29(RISER TUBE SUPPORT-SHOP (PGMA-7531)) | 206813416
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 07531 | 1.9.2.1.1.4.29(RISER TUBE SUPPORT-SHOP (PGMA-7531)) | 206813417
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 07531 | 1.9.2.1.1.4.29(RISER TUBE SUPPORT-SHOP (PGMA-7531)) | 206813418
FURNACE SPIRAL WALL MISC ITEMS-SHOP (PGMA-7560) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 7560 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813419
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 07560 | 1.9.2.1.1.4.30(FURNACE SPIRAL WALL MISC ITEMS-SHOP (PGMA-7560)) | 206813420
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 07560 | 1.9.2.1.1.4.30(FURNACE SPIRAL WALL MISC ITEMS-SHOP (PGMA-7560)) | 206813421
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 07560 | 1.9.2.1.1.4.30(FURNACE SPIRAL WALL MISC ITEMS-SHOP (PGMA-7560)) | 206813422
INDEGENOUS ELECTRODE (PGMA-7991) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 7991 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813423
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 07991 | 1.9.2.1.1.4.31(INDEGENOUS ELECTRODE (PGMA-7991)) | 206813424
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 07991 | 1.9.2.1.1.4.31(INDEGENOUS ELECTRODE (PGMA-7991)) | 206813425
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 07991 | 1.9.2.1.1.4.31(INDEGENOUS ELECTRODE (PGMA-7991)) | 206813426
IMPORTED ELECTRODES (PGMA-7992) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 7992 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813427
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 07992 | 1.9.2.1.1.4.32(IMPORTED ELECTRODES (PGMA-7992)) | 206813428
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 07992 | 1.9.2.1.1.4.32(IMPORTED ELECTRODES (PGMA-7992)) | 206813429
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 07992 | 1.9.2.1.1.4.32(IMPORTED ELECTRODES (PGMA-7992)) | 206813430
CONSUMABLES &Erection MATERIALS (PGMA-7993) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 7993 | 1.9.2.1.1.4(Circulation System Components (PG-07)) | 206813431
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 07993 | 1.9.2.1.1.4.33(CONSUMABLES &Erection MATERIALS (PGMA-7993)) | 206813432
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 07993 | 1.9.2.1.1.4.33(CONSUMABLES &Erection MATERIALS (PGMA-7993)) | 206813433
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 07993 | 1.9.2.1.1.4.33(CONSUMABLES &Erection MATERIALS (PGMA-7993)) | 206813434
Buckstays and Framing (PG-08) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | PG08 | 1.9.2.1.1(Water Circulation System) | 206813435
FURNACE UPPER BUCKSTAYS- FRONT & REAR (PGMA-8001) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 8001 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813436
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 08001 | 1.9.2.1.1.5.1(FURNACE UPPER BUCKSTAYS- FRONT & REAR (PGMA-8001)) | 206813437
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 08001 | 1.9.2.1.1.5.1(FURNACE UPPER BUCKSTAYS- FRONT & REAR (PGMA-8001)) | 206813438
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 08001 | 1.9.2.1.1.5.1(FURNACE UPPER BUCKSTAYS- FRONT & REAR (PGMA-8001)) | 206813439
FURNACE UPPER BUCKSTAYS - SIDE (PGMA-8003) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 8003 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813440
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 08003 | 1.9.2.1.1.5.2(FURNACE UPPER BUCKSTAYS - SIDE (PGMA-8003)) | 206813441
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 08003 | 1.9.2.1.1.5.2(FURNACE UPPER BUCKSTAYS - SIDE (PGMA-8003)) | 206813442
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 08003 | 1.9.2.1.1.5.2(FURNACE UPPER BUCKSTAYS - SIDE (PGMA-8003)) | 206813443
FURNACE INTER BUCKSTAYS (PGMA-8006) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 8006 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813444
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 08006 | 1.9.2.1.1.5.3(FURNACE INTER BUCKSTAYS (PGMA-8006)) | 206813445
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 08006 | 1.9.2.1.1.5.3(FURNACE INTER BUCKSTAYS (PGMA-8006)) | 206813446
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 08006 | 1.9.2.1.1.5.3(FURNACE INTER BUCKSTAYS (PGMA-8006)) | 206813447
FURNACE LOWER BUCKSTAYS (PGMA-8007) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 8007 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813448
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 08007 | 1.9.2.1.1.5.4(FURNACE LOWER BUCKSTAYS (PGMA-8007)) | 206813449
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 08007 | 1.9.2.1.1.5.4(FURNACE LOWER BUCKSTAYS (PGMA-8007)) | 206813450
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 08007 | 1.9.2.1.1.5.4(FURNACE LOWER BUCKSTAYS (PGMA-8007)) | 206813451
FURNACE REAR ARCH BUCKSTAYS (PGMA-8111) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 8111 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813452
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 08111 | 1.9.2.1.1.5.5(FURNACE REAR ARCH BUCKSTAYS (PGMA-8111)) | 206813453
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 08111 | 1.9.2.1.1.5.5(FURNACE REAR ARCH BUCKSTAYS (PGMA-8111)) | 206813454
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 08111 | 1.9.2.1.1.5.5(FURNACE REAR ARCH BUCKSTAYS (PGMA-8111)) | 206813455
UPPER BACK PASS BUCKSTAY (PGMA-8501) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 8501 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813456
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 08501 | 1.9.2.1.1.5.6(UPPER BACK PASS BUCKSTAY (PGMA-8501)) | 206813457
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 08501 | 1.9.2.1.1.5.6(UPPER BACK PASS BUCKSTAY (PGMA-8501)) | 206813458
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 08501 | 1.9.2.1.1.5.6(UPPER BACK PASS BUCKSTAY (PGMA-8501)) | 206813459
FURNACE BACK PASS BUCKSTAYS -SIDE (PGMA-8503) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 8503 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813460
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 08503 | 1.9.2.1.1.5.7(FURNACE BACK PASS BUCKSTAYS -SIDE (PGMA-8503)) | 206813461
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 08503 | 1.9.2.1.1.5.7(FURNACE BACK PASS BUCKSTAYS -SIDE (PGMA-8503)) | 206813462
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 08503 | 1.9.2.1.1.5.7(FURNACE BACK PASS BUCKSTAYS -SIDE (PGMA-8503)) | 206813463
FURNACE KEY BUCKSTAYS - UPPER (PGMA-8901) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 8901 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813464
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 08901 | 1.9.2.1.1.5.8(FURNACE KEY BUCKSTAYS - UPPER (PGMA-8901)) | 206813465
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 08901 | 1.9.2.1.1.5.8(FURNACE KEY BUCKSTAYS - UPPER (PGMA-8901)) | 206813466
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 08901 | 1.9.2.1.1.5.8(FURNACE KEY BUCKSTAYS - UPPER (PGMA-8901)) | 206813467
EXPN. MOVEMENT MEASUREMENT COMPONENTS (PGMA-8910) | SUP | 2023-01-25 08:00 | 2024-05-16 17:00 |  |  |  | 8910 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813468
Engineering | ENG | 2023-01-25 08:00 | 2023-08-27 17:00 |  |  |  | 08910 | 1.9.2.1.1.5.9(EXPN. MOVEMENT MEASUREMENT COMPONENTS (PGMA-8910)) | 206813469
Manufacturing | MFG | 2023-08-28 08:00 | 2024-04-16 17:00 |  |  |  | 08910 | 1.9.2.1.1.5.9(EXPN. MOVEMENT MEASUREMENT COMPONENTS (PGMA-8910)) | 206813470
Dispatch | DIS | 2024-04-17 08:00 | 2024-05-16 17:00 |  |  |  | 08910 | 1.9.2.1.1.5.9(EXPN. MOVEMENT MEASUREMENT COMPONENTS (PGMA-8910)) | 206813471
BULKED B.P.S ITEMS FOR UPPER BUCKSTAYS (PGMA-8911) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 8911 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813472
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 08911 | 1.9.2.1.1.5.10(BULKED B.P.S ITEMS FOR UPPER BUCKSTAYS (PGMA-8911)) | 206813473
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 08911 | 1.9.2.1.1.5.10(BULKED B.P.S ITEMS FOR UPPER BUCKSTAYS (PGMA-8911)) | 206813474
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 08911 | 1.9.2.1.1.5.10(BULKED B.P.S ITEMS FOR UPPER BUCKSTAYS (PGMA-8911)) | 206813475
BULKED B.P.S ITEMS FOR INTERMEDIATE BUCKSTAYS (PGMA-8912) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 8912 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813476
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 08912 | 1.9.2.1.1.5.11(BULKED B.P.S ITEMS FOR INTERMEDIATE BUCKSTAYS (PGMA-8912)) | 206813477
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 08912 | 1.9.2.1.1.5.11(BULKED B.P.S ITEMS FOR INTERMEDIATE BUCKSTAYS (PGMA-8912)) | 206813478
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 08912 | 1.9.2.1.1.5.11(BULKED B.P.S ITEMS FOR INTERMEDIATE BUCKSTAYS (PGMA-8912)) | 206813479
BULKED B.P.S ITEMS FOR LOWER BUCKSTAYS (PGMA-8913) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 8913 | 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | 206813480
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 08913 | 1.9.2.1.1.5.12(BULKED B.P.S ITEMS FOR LOWER BUCKSTAYS (PGMA-8913)) | 206813481
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 08913 | 1.9.2.1.1.5.12(BULKED B.P.S ITEMS FOR LOWER BUCKSTAYS (PGMA-8913)) | 206813482
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 08913 | 1.9.2.1.1.5.12(BULKED B.P.S ITEMS FOR LOWER BUCKSTAYS (PGMA-8913)) | 206813483
Economiser Headers, Coils and Components (PG-19) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | PG19 | 1.9.2.1.1(Water Circulation System) | 206813484
Economiser Supports above Roof- DD (PGMA-19304) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19304 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813485
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19304 | 1.9.2.1.1.6.1(Economiser Supports above Roof- DD (PGMA-19304)) | 206813486
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19304 | 1.9.2.1.1.6.1(Economiser Supports above Roof- DD (PGMA-19304)) | 206813487
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19304 | 1.9.2.1.1.6.1(Economiser Supports above Roof- DD (PGMA-19304)) | 206813488
ECO. LINES & LINKS SUPPORTS-DD (PGMA-19306) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19306 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813489
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19306 | 1.9.2.1.1.6.2(ECO. LINES & LINKS SUPPORTS-DD (PGMA-19306)) | 206813490
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19306 | 1.9.2.1.1.6.2(ECO. LINES & LINKS SUPPORTS-DD (PGMA-19306)) | 206813491
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19306 | 1.9.2.1.1.6.2(ECO. LINES & LINKS SUPPORTS-DD (PGMA-19306)) | 206813492
ECO FEED PIPE SUPPORT-DD (PGMA-19307) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19307 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813493
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19307 | 1.9.2.1.1.6.3(ECO FEED PIPE SUPPORT-DD (PGMA-19307)) | 206813494
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19307 | 1.9.2.1.1.6.3(ECO FEED PIPE SUPPORT-DD (PGMA-19307)) | 206813495
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19307 | 1.9.2.1.1.6.3(ECO FEED PIPE SUPPORT-DD (PGMA-19307)) | 206813496
ECO HANGER TUBE ATTACHMENT (PGMA-19402) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19402 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813497
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19402 | 1.9.2.1.1.6.4(ECO HANGER TUBE ATTACHMENT (PGMA-19402)) | 206813498
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19402 | 1.9.2.1.1.6.4(ECO HANGER TUBE ATTACHMENT (PGMA-19402)) | 206813499
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19402 | 1.9.2.1.1.6.4(ECO HANGER TUBE ATTACHMENT (PGMA-19402)) | 206813500
ECO. LINES & LINKS SUPPORTS-SHOP (PGMA-19506) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19506 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813501
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19506 | 1.9.2.1.1.6.5(ECO. LINES & LINKS SUPPORTS-SHOP (PGMA-19506)) | 206813502
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19506 | 1.9.2.1.1.6.5(ECO. LINES & LINKS SUPPORTS-SHOP (PGMA-19506)) | 206813503
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19506 | 1.9.2.1.1.6.5(ECO. LINES & LINKS SUPPORTS-SHOP (PGMA-19506)) | 206813504
ECO FEED PIPE SUPPORT-SHOP (PGMA-19507) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19507 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813505
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19507 | 1.9.2.1.1.6.6(ECO FEED PIPE SUPPORT-SHOP (PGMA-19507)) | 206813506
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19507 | 1.9.2.1.1.6.6(ECO FEED PIPE SUPPORT-SHOP (PGMA-19507)) | 206813507
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19507 | 1.9.2.1.1.6.6(ECO FEED PIPE SUPPORT-SHOP (PGMA-19507)) | 206813508
ECONOMISER INLET HEADERS (PGMA-19701) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 19701 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813509
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 19701 | 1.9.2.1.1.6.7(ECONOMISER INLET HEADERS (PGMA-19701)) | 206813510
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 19701 | 1.9.2.1.1.6.7(ECONOMISER INLET HEADERS (PGMA-19701)) | 206813511
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 19701 | 1.9.2.1.1.6.7(ECONOMISER INLET HEADERS (PGMA-19701)) | 206813512
ECONOMISER OUTLET HEADERS (PGMA-19702) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19702 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813513
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19702 | 1.9.2.1.1.6.8(ECONOMISER OUTLET HEADERS (PGMA-19702)) | 206813514
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19702 | 1.9.2.1.1.6.8(ECONOMISER OUTLET HEADERS (PGMA-19702)) | 206813515
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19702 | 1.9.2.1.1.6.8(ECONOMISER OUTLET HEADERS (PGMA-19702)) | 206813516
ECONOMISER INTERMEDIATE HEADER - REAR (PGMA-19753) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 19753 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813517
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 19753 | 1.9.2.1.1.6.9(ECONOMISER INTERMEDIATE HEADER - REAR (PGMA-19753)) | 206813518
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 19753 | 1.9.2.1.1.6.9(ECONOMISER INTERMEDIATE HEADER - REAR (PGMA-19753)) | 206813519
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 19753 | 1.9.2.1.1.6.9(ECONOMISER INTERMEDIATE HEADER - REAR (PGMA-19753)) | 206813520
ECONOMISER INTERMEDIATE HEADER - FRONT (PGMA-19763) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 19763 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813521
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 19763 | 1.9.2.1.1.6.10(ECONOMISER INTERMEDIATE HEADER - FRONT (PGMA-19763)) | 206813522
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 19763 | 1.9.2.1.1.6.10(ECONOMISER INTERMEDIATE HEADER - FRONT (PGMA-19763)) | 206813523
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 19763 | 1.9.2.1.1.6.10(ECONOMISER INTERMEDIATE HEADER - FRONT (PGMA-19763)) | 206813524
ECONOMISER INTERMEDIATE HEADER - INTER (PGMA-19783) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 19783 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813525
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 19783 | 1.9.2.1.1.6.11(ECONOMISER INTERMEDIATE HEADER - INTER (PGMA-19783)) | 206813526
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 19783 | 1.9.2.1.1.6.11(ECONOMISER INTERMEDIATE HEADER - INTER (PGMA-19783)) | 206813527
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 19783 | 1.9.2.1.1.6.11(ECONOMISER INTERMEDIATE HEADER - INTER (PGMA-19783)) | 206813528
HEADERS OF CENTER INTER (PGMA-19793) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 19793 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813529
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 19793 | 1.9.2.1.1.6.12(HEADERS OF CENTER INTER (PGMA-19793)) | 206813530
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 19793 | 1.9.2.1.1.6.12(HEADERS OF CENTER INTER (PGMA-19793)) | 206813531
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 19793 | 1.9.2.1.1.6.12(HEADERS OF CENTER INTER (PGMA-19793)) | 206813532
ECONOMISER HANGER TUBES (PGMA-19802) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19802 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813533
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19802 | 1.9.2.1.1.6.13(ECONOMISER HANGER TUBES (PGMA-19802)) | 206813534
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19802 | 1.9.2.1.1.6.13(ECONOMISER HANGER TUBES (PGMA-19802)) | 206813535
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19802 | 1.9.2.1.1.6.13(ECONOMISER HANGER TUBES (PGMA-19802)) | 206813536
PLAIN TUBE ECONO. UPPER COIL ASSY(LEFT) (PGMA-19814) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  |  | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813537
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 19814 | 1.9.2.1.1.6.14(PLAIN TUBE ECONO. UPPER COIL ASSY(LEFT) (PGMA-19814)) | 206813538
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 19814 | 1.9.2.1.1.6.14(PLAIN TUBE ECONO. UPPER COIL ASSY(LEFT) (PGMA-19814)) | 206813539
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 19814 | 1.9.2.1.1.6.14(PLAIN TUBE ECONO. UPPER COIL ASSY(LEFT) (PGMA-19814)) | 206813540
ECO LOWER ASSY -LEFT (PGMA-19824) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 19824 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813541
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 19824 | 1.9.2.1.1.6.15(ECO LOWER ASSY -LEFT (PGMA-19824)) | 206813542
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 19824 | 1.9.2.1.1.6.15(ECO LOWER ASSY -LEFT (PGMA-19824)) | 206813543
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 19824 | 1.9.2.1.1.6.15(ECO LOWER ASSY -LEFT (PGMA-19824)) | 206813544
ECONOMISER FEED PIPE (PGMA-19850) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19850 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813545
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19850 | 1.9.2.1.1.6.16(ECONOMISER FEED PIPE (PGMA-19850)) | 206813546
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19850 | 1.9.2.1.1.6.16(ECONOMISER FEED PIPE (PGMA-19850)) | 206813547
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19850 | 1.9.2.1.1.6.16(ECONOMISER FEED PIPE (PGMA-19850)) | 206813548
LINK FROM ECO OUTLET HEADER TO ECO MIX LINE(PGMA-19851) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19851 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813549
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19851 | 1.9.2.1.1.6.17(LINK FROM ECO OUTLET HEADER TO ECO MIX LINE(PGMA-19851)) | 206813550
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19851 | 1.9.2.1.1.6.17(LINK FROM ECO OUTLET HEADER TO ECO MIX LINE(PGMA-19851)) | 206813551
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19851 | 1.9.2.1.1.6.17(LINK FROM ECO OUTLET HEADER TO ECO MIX LINE(PGMA-19851)) | 206813552
ECONOMISER-I TO ECONOMISER-II LINK (PGMA-19852) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19852 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813553
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19852 | 1.9.2.1.1.6.18(ECONOMISER-I TO ECONOMISER-II LINK (PGMA-19852)) | 206813554
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19852 | 1.9.2.1.1.6.18(ECONOMISER-I TO ECONOMISER-II LINK (PGMA-19852)) | 206813555
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19852 | 1.9.2.1.1.6.18(ECONOMISER-I TO ECONOMISER-II LINK (PGMA-19852)) | 206813556
ECONOMISER FEED PIPE (PGMA-19853) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19853 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813557
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19853 | 1.9.2.1.1.6.19(ECONOMISER FEED PIPE (PGMA-19853)) | 206813558
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19853 | 1.9.2.1.1.6.19(ECONOMISER FEED PIPE (PGMA-19853)) | 206813559
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19853 | 1.9.2.1.1.6.19(ECONOMISER FEED PIPE (PGMA-19853)) | 206813560
ECO INTER ASSY - LEFT (PGMA-19884) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 19884 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813561
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 19884 | 1.9.2.1.1.6.20(ECO INTER ASSY - LEFT (PGMA-19884)) | 206813562
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 19884 | 1.9.2.1.1.6.20(ECO INTER ASSY - LEFT (PGMA-19884)) | 206813563
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 19884 | 1.9.2.1.1.6.20(ECO INTER ASSY - LEFT (PGMA-19884)) | 206813564
ECONOMISER MISCELLANEOUS COMPONENTS (PGMA-19903) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 19903 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813565
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 19903 | 1.9.2.1.1.6.21(ECONOMISER MISCELLANEOUS COMPONENTS (PGMA-19903)) | 206813566
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 19903 | 1.9.2.1.1.6.21(ECONOMISER MISCELLANEOUS COMPONENTS (PGMA-19903)) | 206813567
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 19903 | 1.9.2.1.1.6.21(ECONOMISER MISCELLANEOUS COMPONENTS (PGMA-19903)) | 206813568
IP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19904) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19904 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813569
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19904 | 1.9.2.1.1.6.22(IP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19904)) | 206813570
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19904 | 1.9.2.1.1.6.22(IP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19904)) | 206813571
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19904 | 1.9.2.1.1.6.22(IP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19904)) | 206813572
ECONOMISER COIL SUPPORTS (PGMA-19905) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19905 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813573
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19905 | 1.9.2.1.1.6.23(ECONOMISER COIL SUPPORTS (PGMA-19905)) | 206813574
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19905 | 1.9.2.1.1.6.23(ECONOMISER COIL SUPPORTS (PGMA-19905)) | 206813575
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19905 | 1.9.2.1.1.6.23(ECONOMISER COIL SUPPORTS (PGMA-19905)) | 206813576
HP ECO 4 FRONT MODULE COMPONENTS(LEFT) (PGMA-19906) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19906 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813577
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19906 | 1.9.2.1.1.6.24(HP ECO 4 FRONT MODULE COMPONENTS(LEFT) (PGMA-19906)) | 206813578
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19906 | 1.9.2.1.1.6.24(HP ECO 4 FRONT MODULE COMPONENTS(LEFT) (PGMA-19906)) | 206813579
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19906 | 1.9.2.1.1.6.24(HP ECO 4 FRONT MODULE COMPONENTS(LEFT) (PGMA-19906)) | 206813580
LP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19907) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19907 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813581
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19907 | 1.9.2.1.1.6.25(LP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19907)) | 206813582
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19907 | 1.9.2.1.1.6.25(LP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19907)) | 206813583
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19907 | 1.9.2.1.1.6.25(LP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19907)) | 206813584
HP ECONOMISER-II MODULE SUPPORTS (PGMA-19914) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 19914 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813585
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 19914 | 1.9.2.1.1.6.26(HP ECONOMISER-II MODULE SUPPORTS (PGMA-19914)) | 206813586
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 19914 | 1.9.2.1.1.6.26(HP ECONOMISER-II MODULE SUPPORTS (PGMA-19914)) | 206813587
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 19914 | 1.9.2.1.1.6.26(HP ECONOMISER-II MODULE SUPPORTS (PGMA-19914)) | 206813588
PLAIN TUBE ECO. LOWER ASSY (RIGHT) (PGMA-19924) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 19924 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813589
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 19924 | 1.9.2.1.1.6.27(PLAIN TUBE ECO. LOWER ASSY (RIGHT) (PGMA-19924)) | 206813590
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 19924 | 1.9.2.1.1.6.27(PLAIN TUBE ECO. LOWER ASSY (RIGHT) (PGMA-19924)) | 206813591
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 19924 | 1.9.2.1.1.6.27(PLAIN TUBE ECO. LOWER ASSY (RIGHT) (PGMA-19924)) | 206813592
ECO INTER ASSY - RIGHT (PGMA-19984) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 19984 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813593
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 19984 | 1.9.2.1.1.6.28(ECO INTER ASSY - RIGHT (PGMA-19984)) | 206813594
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 19984 | 1.9.2.1.1.6.28(ECO INTER ASSY - RIGHT (PGMA-19984)) | 206813595
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 19984 | 1.9.2.1.1.6.28(ECO INTER ASSY - RIGHT (PGMA-19984)) | 206813596
ECONOMISER IMPORTED ELECTRODES (PGMA-19991) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 19991 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813597
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 19991 | 1.9.2.1.1.6.29(ECONOMISER IMPORTED ELECTRODES (PGMA-19991)) | 206813598
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 19991 | 1.9.2.1.1.6.29(ECONOMISER IMPORTED ELECTRODES (PGMA-19991)) | 206813599
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 19991 | 1.9.2.1.1.6.29(ECONOMISER IMPORTED ELECTRODES (PGMA-19991)) | 206813600
IMPORTED ELECTRODES (PGMA-19992) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 19992 | 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | 206813601
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 19992 | 1.9.2.1.1.6.30(IMPORTED ELECTRODES (PGMA-19992)) | 206813602
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 19992 | 1.9.2.1.1.6.30(IMPORTED ELECTRODES (PGMA-19992)) | 206813603
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 19992 | 1.9.2.1.1.6.30(IMPORTED ELECTRODES (PGMA-19992)) | 206813604
Boiler Integral Piping and Fittings (PG-24) | SUP | 2022-09-27 08:00 | 2025-11-11 17:00 |  |  |  | PG24 | 1.9.2.1.1(Water Circulation System) | 206813605
BOILER FILLING PIPING (PGMA-24350) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24350 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813606
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24350 | 1.9.2.1.1.7.1(BOILER FILLING PIPING (PGMA-24350)) | 206813607
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24350 | 1.9.2.1.1.7.1(BOILER FILLING PIPING (PGMA-24350)) | 206813608
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24350 | 1.9.2.1.1.7.1(BOILER FILLING PIPING (PGMA-24350)) | 206813609
HANGERS+SUPPORTS FOR BLR FILLING PIPING (PGMA-24351) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24351 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813610
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24351 | 1.9.2.1.1.7.2(HANGERS+SUPPORTS FOR BLR FILLING PIPING (PGMA-24351)) | 206813611
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24351 | 1.9.2.1.1.7.2(HANGERS+SUPPORTS FOR BLR FILLING PIPING (PGMA-24351)) | 206813612
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24351 | 1.9.2.1.1.7.2(HANGERS+SUPPORTS FOR BLR FILLING PIPING (PGMA-24351)) | 206813613
BOILER FILL PIPING - DD (PGMA-24352) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24352 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813614
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24352 | 1.9.2.1.1.7.3(BOILER FILL PIPING - DD (PGMA-24352)) | 206813615
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24352 | 1.9.2.1.1.7.3(BOILER FILL PIPING - DD (PGMA-24352)) | 206813616
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24352 | 1.9.2.1.1.7.3(BOILER FILL PIPING - DD (PGMA-24352)) | 206813617
HANGERS & SUPPORTS FOR BOILER FILL PIPING - OS (PGMA-24353) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24353 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813618
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24353 | 1.9.2.1.1.7.4(HANGERS & SUPPORTS FOR BOILER FILL PIPING - OS (PGMA-24353)) | 206813619
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24353 | 1.9.2.1.1.7.4(HANGERS & SUPPORTS FOR BOILER FILL PIPING - OS (PGMA-24353)) | 206813620
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24353 | 1.9.2.1.1.7.4(HANGERS & SUPPORTS FOR BOILER FILL PIPING - OS (PGMA-24353)) | 206813621
BOI items for Boiler fill piping (PGMA-24354) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24354 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813622
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24354 | 1.9.2.1.1.7.5(BOI items for Boiler fill piping (PGMA-24354)) | 206813623
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24354 | 1.9.2.1.1.7.5(BOI items for Boiler fill piping (PGMA-24354)) | 206813624
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24354 | 1.9.2.1.1.7.5(BOI items for Boiler fill piping (PGMA-24354)) | 206813625
BULKED BPS COMPONENTS FOR TRIM PIPES (PGMA-24700) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24700 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813626
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24700 | 1.9.2.1.1.7.6(BULKED BPS COMPONENTS FOR TRIM PIPES (PGMA-24700)) | 206813627
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24700 | 1.9.2.1.1.7.6(BULKED BPS COMPONENTS FOR TRIM PIPES (PGMA-24700)) | 206813628
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24700 | 1.9.2.1.1.7.6(BULKED BPS COMPONENTS FOR TRIM PIPES (PGMA-24700)) | 206813629
BOILER TRIM PIPING (PGMA-24800) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24800 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813630
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24800 | 1.9.2.1.1.7.7(BOILER TRIM PIPING (PGMA-24800)) | 206813631
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24800 | 1.9.2.1.1.7.7(BOILER TRIM PIPING (PGMA-24800)) | 206813632
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24800 | 1.9.2.1.1.7.7(BOILER TRIM PIPING (PGMA-24800)) | 206813633
Boiler Trim Piping - Dd Items (PGMA-24803) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24803 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813634
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24803 | 1.9.2.1.1.7.8(Boiler Trim Piping - Dd Items (PGMA-24803)) | 206813635
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24803 | 1.9.2.1.1.7.8(Boiler Trim Piping - Dd Items (PGMA-24803)) | 206813636
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24803 | 1.9.2.1.1.7.8(Boiler Trim Piping - Dd Items (PGMA-24803)) | 206813637
Supports - Boiler Trim Piping - Os (PGMA-24804) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24804 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813638
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24804 | 1.9.2.1.1.7.9(Supports - Boiler Trim Piping - Os (PGMA-24804)) | 206813639
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24804 | 1.9.2.1.1.7.9(Supports - Boiler Trim Piping - Os (PGMA-24804)) | 206813640
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24804 | 1.9.2.1.1.7.9(Supports - Boiler Trim Piping - Os (PGMA-24804)) | 206813641
LINK TO BOILER RECIRCULATION SYSTEM (PGMA-24805) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24805 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813642
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24805 | 1.9.2.1.1.7.10(LINK TO BOILER RECIRCULATION SYSTEM (PGMA-24805)) | 206813643
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24805 | 1.9.2.1.1.7.10(LINK TO BOILER RECIRCULATION SYSTEM (PGMA-24805)) | 206813644
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24805 | 1.9.2.1.1.7.10(LINK TO BOILER RECIRCULATION SYSTEM (PGMA-24805)) | 206813645
MIXING VESSEL (PGMA-24806) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24806 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813646
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24806 | 1.9.2.1.1.7.11(MIXING VESSEL (PGMA-24806)) | 206813647
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24806 | 1.9.2.1.1.7.11(MIXING VESSEL (PGMA-24806)) | 206813648
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24806 | 1.9.2.1.1.7.11(MIXING VESSEL (PGMA-24806)) | 206813649
RECIRCULATION PUMP SECTION LINE (PGMA-24807) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24807 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813650
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24807 | 1.9.2.1.1.7.12(RECIRCULATION PUMP SECTION LINE (PGMA-24807)) | 206813651
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24807 | 1.9.2.1.1.7.12(RECIRCULATION PUMP SECTION LINE (PGMA-24807)) | 206813652
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24807 | 1.9.2.1.1.7.12(RECIRCULATION PUMP SECTION LINE (PGMA-24807)) | 206813653
RECIRCULATION PUMP DISCHARGE LINE (PGMA-24808) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24808 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813654
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24808 | 1.9.2.1.1.7.13(RECIRCULATION PUMP DISCHARGE LINE (PGMA-24808)) | 206813655
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24808 | 1.9.2.1.1.7.13(RECIRCULATION PUMP DISCHARGE LINE (PGMA-24808)) | 206813656
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24808 | 1.9.2.1.1.7.13(RECIRCULATION PUMP DISCHARGE LINE (PGMA-24808)) | 206813657
BOILER RECIRCULATION LINK FROM BF LINE (PGMA-24809) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24809 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813658
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24809 | 1.9.2.1.1.7.14(BOILER RECIRCULATION LINK FROM BF LINE (PGMA-24809)) | 206813659
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24809 | 1.9.2.1.1.7.14(BOILER RECIRCULATION LINK FROM BF LINE (PGMA-24809)) | 206813660
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24809 | 1.9.2.1.1.7.14(BOILER RECIRCULATION LINK FROM BF LINE (PGMA-24809)) | 206813661
HANGERS + SUPPORTS FOR STARTUP SYSTEM (PGMA-24810) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24810 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813662
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24810 | 1.9.2.1.1.7.15(HANGERS + SUPPORTS FOR STARTUP SYSTEM (PGMA-24810)) | 206813663
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24810 | 1.9.2.1.1.7.15(HANGERS + SUPPORTS FOR STARTUP SYSTEM (PGMA-24810)) | 206813664
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24810 | 1.9.2.1.1.7.15(HANGERS + SUPPORTS FOR STARTUP SYSTEM (PGMA-24810)) | 206813665
FURNACE LINK TO FLASH TAND/HWL1 TO HWL2 (PGMA-24811) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24811 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813666
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24811 | 1.9.2.1.1.7.16(FURNACE LINK TO FLASH TAND/HWL1 TO HWL2 (PGMA-24811)) | 206813667
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24811 | 1.9.2.1.1.7.16(FURNACE LINK TO FLASH TAND/HWL1 TO HWL2 (PGMA-24811)) | 206813668
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24811 | 1.9.2.1.1.7.16(FURNACE LINK TO FLASH TAND/HWL1 TO HWL2 (PGMA-24811)) | 206813669
Boiler Trim Piping - Non Ht Items (PGMA-24814) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24814 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813670
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24814 | 1.9.2.1.1.7.17(Boiler Trim Piping - Non Ht Items (PGMA-24814)) | 206813671
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24814 | 1.9.2.1.1.7.17(Boiler Trim Piping - Non Ht Items (PGMA-24814)) | 206813672
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24814 | 1.9.2.1.1.7.17(Boiler Trim Piping - Non Ht Items (PGMA-24814)) | 206813673
DESUPERHEATER PIPES (PGMA-24815) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 24815 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813674
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 24815 | 1.9.2.1.1.7.18(DESUPERHEATER PIPES (PGMA-24815)) | 206813675
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 24815 | 1.9.2.1.1.7.18(DESUPERHEATER PIPES (PGMA-24815)) | 206813676
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 24815 | 1.9.2.1.1.7.18(DESUPERHEATER PIPES (PGMA-24815)) | 206813677
H&S For Start-Up System - Os Items (PGMA-24817) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24817 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813678
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24817 | 1.9.2.1.1.7.19(H&S For Start-Up System - Os Items (PGMA-24817)) | 206813679
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24817 | 1.9.2.1.1.7.19(H&S For Start-Up System - Os Items (PGMA-24817)) | 206813680
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24817 | 1.9.2.1.1.7.19(H&S For Start-Up System - Os Items (PGMA-24817)) | 206813681
H&S For Start-Up System - Dd Items (PGMA-24818) | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  | 24818 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813682
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 24818 | 1.9.2.1.1.7.20(H&S For Start-Up System - Dd Items (PGMA-24818)) | 206813683
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-28 17:00 |  |  |  | 24818 | 1.9.2.1.1.7.20(H&S For Start-Up System - Dd Items (PGMA-24818)) | 206813684
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24818 | 1.9.2.1.1.7.20(H&S For Start-Up System - Dd Items (PGMA-24818)) | 206813685
EXHAUST PIPE FOR SAFETY VALVES (PGMA-24820) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24820 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813686
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24820 | 1.9.2.1.1.7.21(EXHAUST PIPE FOR SAFETY VALVES (PGMA-24820)) | 206813687
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24820 | 1.9.2.1.1.7.21(EXHAUST PIPE FOR SAFETY VALVES (PGMA-24820)) | 206813688
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24820 | 1.9.2.1.1.7.21(EXHAUST PIPE FOR SAFETY VALVES (PGMA-24820)) | 206813689
De-Superheater Pipes - Os Items (PGMA-24822) | SUP | 2023-04-26 08:00 | 2024-06-28 17:00 |  |  |  | 24822 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813690
Engineering | ENG | 2023-04-26 08:00 | 2023-11-13 17:00 |  |  |  | 24822 | 1.9.2.1.1.7.22(De-Superheater Pipes - Os Items (PGMA-24822)) | 206813691
Manufacturing | MFG | 2023-11-14 08:00 | 2024-05-29 17:00 |  |  |  | 24822 | 1.9.2.1.1.7.22(De-Superheater Pipes - Os Items (PGMA-24822)) | 206813692
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  | 24822 | 1.9.2.1.1.7.22(De-Superheater Pipes - Os Items (PGMA-24822)) | 206813693
De-Superheater Pipes - Dd Items (PGMA-24823) | SUP | 2023-04-26 08:00 | 2024-06-28 17:00 |  |  |  | 24823 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813694
Engineering | ENG | 2023-04-26 08:00 | 2023-11-13 17:00 |  |  |  | 24823 | 1.9.2.1.1.7.23(De-Superheater Pipes - Dd Items (PGMA-24823)) | 206813695
Manufacturing | MFG | 2023-11-14 08:00 | 2024-05-29 17:00 |  |  |  | 24823 | 1.9.2.1.1.7.23(De-Superheater Pipes - Dd Items (PGMA-24823)) | 206813696
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  | 24823 | 1.9.2.1.1.7.23(De-Superheater Pipes - Dd Items (PGMA-24823)) | 206813697
Exhaust Pipe For Safety Valve - Os Items (PGMA-24824) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24824 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813698
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24824 | 1.9.2.1.1.7.24(Exhaust Pipe For Safety Valve - Os Items (PGMA-24824)) | 206813699
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24824 | 1.9.2.1.1.7.24(Exhaust Pipe For Safety Valve - Os Items (PGMA-24824)) | 206813700
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24824 | 1.9.2.1.1.7.24(Exhaust Pipe For Safety Valve - Os Items (PGMA-24824)) | 206813701
SILENCER SUPPORTS (PGMA-24825) | SUP | 2022-09-27 08:00 | 2024-03-14 17:00 |  |  |  | 24825 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813702
Engineering | ENG | 2022-09-27 08:00 | 2023-07-25 17:00 |  |  |  | 24825 | 1.9.2.1.1.7.25(SILENCER SUPPORTS (PGMA-24825)) | 206813703
Manufacturing | MFG | 2023-07-26 08:00 | 2024-02-13 17:00 |  |  |  | 24825 | 1.9.2.1.1.7.25(SILENCER SUPPORTS (PGMA-24825)) | 206813704
Dispatch | DIS | 2024-02-14 08:00 | 2024-03-14 17:00 |  |  |  | 24825 | 1.9.2.1.1.7.25(SILENCER SUPPORTS (PGMA-24825)) | 206813705
Silencer Support - Os Items (PGMA-24826) | SUP | 2022-09-27 08:00 | 2024-03-14 17:00 |  |  |  | 24826 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813706
Engineering | ENG | 2022-09-27 08:00 | 2023-07-25 17:00 |  |  |  | 24826 | 1.9.2.1.1.7.26(Silencer Support - Os Items (PGMA-24826)) | 206813707
Manufacturing | MFG | 2023-07-26 08:00 | 2024-02-13 17:00 |  |  |  | 24826 | 1.9.2.1.1.7.26(Silencer Support - Os Items (PGMA-24826)) | 206813708
Dispatch | DIS | 2024-02-14 08:00 | 2024-03-14 17:00 |  |  |  | 24826 | 1.9.2.1.1.7.26(Silencer Support - Os Items (PGMA-24826)) | 206813709
Exhaust Pipe For Safety Valve - Dd Items (PGMA-24827) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24827 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813710
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24827 | 1.9.2.1.1.7.27(Exhaust Pipe For Safety Valve - Dd Items (PGMA-24827)) | 206813711
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24827 | 1.9.2.1.1.7.27(Exhaust Pipe For Safety Valve - Dd Items (PGMA-24827)) | 206813712
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24827 | 1.9.2.1.1.7.27(Exhaust Pipe For Safety Valve - Dd Items (PGMA-24827)) | 206813713
Exhaust Pipe For Safety Valve - BOI Item (PGMA-24828) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24828 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813714
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24828 | 1.9.2.1.1.7.28(Exhaust Pipe For Safety Valve - BOI Item (PGMA-24828)) | 206813715
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24828 | 1.9.2.1.1.7.28(Exhaust Pipe For Safety Valve - BOI Item (PGMA-24828)) | 206813716
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24828 | 1.9.2.1.1.7.28(Exhaust Pipe For Safety Valve - BOI Item (PGMA-24828)) | 206813717
STARTUP VENT DIFFUSER AND SILENCER SUPPPORTS (PGMA-24835) | SUP | 2022-09-27 08:00 | 2023-12-27 17:00 |  |  |  | 24835 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813718
Engineering | ENG | 2022-09-27 08:00 | 2023-07-25 17:00 |  |  |  | 24835 | 1.9.2.1.1.7.29(STARTUP VENT DIFFUSER AND SILENCER SUPPPORTS (PGMA-24835)) | 206813719
Manufacturing | MFG | 2023-05-09 08:00 | 2023-11-27 17:00 |  |  |  | 24835 | 1.9.2.1.1.7.29(STARTUP VENT DIFFUSER AND SILENCER SUPPPORTS (PGMA-24835)) | 206813720
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 24835 | 1.9.2.1.1.7.29(STARTUP VENT DIFFUSER AND SILENCER SUPPPORTS (PGMA-24835)) | 206813721
Start-Up Vent, Diffuser, Silencer Support-Os Item (PGMA-24836) | SUP | 2022-09-27 08:00 | 2023-12-27 17:00 |  |  |  | 24836 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813722
Engineering | ENG | 2022-09-27 08:00 | 2023-07-25 17:00 |  |  |  | 24836 | 1.9.2.1.1.7.30(Start-Up Vent, Diffuser, Silencer Support-Os Item (PGMA-24836)) | 206813723
Manufacturing | MFG | 2023-05-09 08:00 | 2023-11-27 17:00 |  |  |  | 24836 | 1.9.2.1.1.7.30(Start-Up Vent, Diffuser, Silencer Support-Os Item (PGMA-24836)) | 206813724
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 24836 | 1.9.2.1.1.7.30(Start-Up Vent, Diffuser, Silencer Support-Os Item (PGMA-24836)) | 206813725
Start-Up Vent, Diffuser, Silencer Support-Dd Item (PGMA-24837) | SUP | 2022-09-27 08:00 | 2023-12-27 17:00 |  |  |  | 24837 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813726
Engineering | ENG | 2022-09-27 08:00 | 2023-07-25 17:00 |  |  |  | 24837 | 1.9.2.1.1.7.31(Start-Up Vent, Diffuser, Silencer Support-Dd Item (PGMA-24837)) | 206813727
Manufacturing | MFG | 2023-05-09 08:00 | 2023-11-27 17:00 |  |  |  | 24837 | 1.9.2.1.1.7.31(Start-Up Vent, Diffuser, Silencer Support-Dd Item (PGMA-24837)) | 206813728
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 24837 | 1.9.2.1.1.7.31(Start-Up Vent, Diffuser, Silencer Support-Dd Item (PGMA-24837)) | 206813729
SAMPLE COOLER AND SUPPORTS (PGMA-24840) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24840 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813730
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24840 | 1.9.2.1.1.7.32(SAMPLE COOLER AND SUPPORTS (PGMA-24840)) | 206813731
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24840 | 1.9.2.1.1.7.32(SAMPLE COOLER AND SUPPORTS (PGMA-24840)) | 206813732
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24840 | 1.9.2.1.1.7.32(SAMPLE COOLER AND SUPPORTS (PGMA-24840)) | 206813733
Sample Cooler & Supports - Os Items (PGMA-24841) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24841 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813734
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24841 | 1.9.2.1.1.7.33(Sample Cooler & Supports - Os Items (PGMA-24841)) | 206813735
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24841 | 1.9.2.1.1.7.33(Sample Cooler & Supports - Os Items (PGMA-24841)) | 206813736
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24841 | 1.9.2.1.1.7.33(Sample Cooler & Supports - Os Items (PGMA-24841)) | 206813737
DD items for Sample Cooler and Supports (PGMA-24842) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 24842 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813738
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 24842 | 1.9.2.1.1.7.34(DD items for Sample Cooler and Supports (PGMA-24842)) | 206813739
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 24842 | 1.9.2.1.1.7.34(DD items for Sample Cooler and Supports (PGMA-24842)) | 206813740
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 24842 | 1.9.2.1.1.7.34(DD items for Sample Cooler and Supports (PGMA-24842)) | 206813741
BOI- HT- RE-CIRCULATING PUMP COMPONENTS-SD (PGMA-24855) | SUP | 2023-08-23 08:00 | 2024-12-28 17:00 |  |  |  | 24855 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813742
NIT | ENQ | 2023-08-23 08:00 | 2023-08-23 17:00 |  |  |  | 24855 | 1.9.2.1.1.7.35( BOI- HT- RE-CIRCULATING PUMP COMPONENTS-SD (PGMA-24855)) | 206813743
Ordering | ORD | 2023-08-24 08:00 | 2024-01-20 17:00 |  |  |  | 24855 | 1.9.2.1.1.7.35( BOI- HT- RE-CIRCULATING PUMP COMPONENTS-SD (PGMA-24855)) | 206813744
Manufacturing | MFG | 2024-01-21 08:00 | 2024-11-28 17:00 |  |  |  | 24855 | 1.9.2.1.1.7.35( BOI- HT- RE-CIRCULATING PUMP COMPONENTS-SD (PGMA-24855)) | 206813745
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 24855 | 1.9.2.1.1.7.35( BOI- HT- RE-CIRCULATING PUMP COMPONENTS-SD (PGMA-24855)) | 206813746
VALVES (PGMA-24860) | SUP | 2024-01-12 08:00 | 2025-11-11 17:00 |  |  |  | 24860 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813747
Engineering | ENG | 2024-01-12 08:00 | 2024-07-09 17:00 |  |  |  | 24860 | 1.9.2.1.1.7.36(VALVES (PGMA-24860)) | 206813748
Manufacturing | MFG | 2024-07-10 08:00 | 2025-10-12 17:00 |  |  |  | 24860 | 1.9.2.1.1.7.36(VALVES (PGMA-24860)) | 206813749
Dispatch | DIS | 2025-10-13 08:00 | 2025-11-11 17:00 |  |  |  | 24860 | 1.9.2.1.1.7.36(VALVES (PGMA-24860)) | 206813750
BOI-LU-VALVES SUBDELIVERY (PGMA-24865) | SUP | 2023-08-03 08:00 | 2025-01-14 17:00 |  |  |  | 24865 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813751
NIT | ENQ | 2023-08-03 08:00 | 2023-08-03 17:00 |  |  |  | 24865 | 1.9.2.1.1.7.37(BOI-LU-VALVES SUBDELIVERY (PGMA-24865)) | 206813752
Ordering | ORD | 2023-08-04 08:00 | 2024-01-30 17:00 |  |  |  | 24865 | 1.9.2.1.1.7.37(BOI-LU-VALVES SUBDELIVERY (PGMA-24865)) | 206813753
Manufacturing | MFG | 2024-01-31 08:00 | 2024-12-15 17:00 |  |  |  | 24865 | 1.9.2.1.1.7.37(BOI-LU-VALVES SUBDELIVERY (PGMA-24865)) | 206813754
Dispatch | DIS | 2024-12-16 08:00 | 2025-01-14 17:00 |  |  |  | 24865 | 1.9.2.1.1.7.37(BOI-LU-VALVES SUBDELIVERY (PGMA-24865)) | 206813755
BOI-LU-VALVES FOR STARTUP RECIRCULATION SYSTEM-SD (PGMA-24867) | SUP | 2023-10-22 08:00 | 2025-01-12 17:00 |  |  |  | 24867 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813756
NIT | ENQ | 2023-10-22 08:00 | 2023-10-22 17:00 |  |  |  | 24867 | 1.9.2.1.1.7.38(BOI-LU-VALVES FOR STARTUP RECIRCULATION SYSTEM-SD (PGMA-24867)) | 206813757
Ordering | ORD | 2023-10-23 08:00 | 2024-03-20 17:00 |  |  |  | 24867 | 1.9.2.1.1.7.38(BOI-LU-VALVES FOR STARTUP RECIRCULATION SYSTEM-SD (PGMA-24867)) | 206813758
Manufacturing | MFG | 2024-03-21 08:00 | 2024-12-13 17:00 |  |  |  | 24867 | 1.9.2.1.1.7.38(BOI-LU-VALVES FOR STARTUP RECIRCULATION SYSTEM-SD (PGMA-24867)) | 206813759
Dispatch | DIS | 2024-12-14 08:00 | 2025-01-12 17:00 |  |  |  | 24867 | 1.9.2.1.1.7.38(BOI-LU-VALVES FOR STARTUP RECIRCULATION SYSTEM-SD (PGMA-24867)) | 206813760
SAFETY VALVES (PGMA-24880) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 24880 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813761
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 24880 | 1.9.2.1.1.7.39(SAFETY VALVES (PGMA-24880)) | 206813762
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 24880 | 1.9.2.1.1.7.39(SAFETY VALVES (PGMA-24880)) | 206813763
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 24880 | 1.9.2.1.1.7.39(SAFETY VALVES (PGMA-24880)) | 206813764
SAFETY VALVES AND ERV-SD (PGMA-24881) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 24881 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813765
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 24881 | 1.9.2.1.1.7.40(SAFETY VALVES AND ERV-SD (PGMA-24881)) | 206813766
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 24881 | 1.9.2.1.1.7.40(SAFETY VALVES AND ERV-SD (PGMA-24881)) | 206813767
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 24881 | 1.9.2.1.1.7.40(SAFETY VALVES AND ERV-SD (PGMA-24881)) | 206813768
Safety Valves (BHEL) - Non Ht (PGMA-24883) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 24883 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813769
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 24883 | 1.9.2.1.1.7.41(Safety Valves (BHEL) - Non Ht (PGMA-24883)) | 206813770
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 24883 | 1.9.2.1.1.7.41(Safety Valves (BHEL) - Non Ht (PGMA-24883)) | 206813771
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 24883 | 1.9.2.1.1.7.41(Safety Valves (BHEL) - Non Ht (PGMA-24883)) | 206813772
SILENCERS (PGMA-24885) | SUP | 2022-09-27 08:00 | 2023-12-27 17:00 |  |  |  | 24885 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813773
Engineering | ENG | 2022-09-27 08:00 | 2023-07-25 17:00 |  |  |  | 24885 | 1.9.2.1.1.7.42(SILENCERS (PGMA-24885)) | 206813774
Manufacturing | MFG | 2023-05-09 08:00 | 2023-11-27 17:00 |  |  |  | 24885 | 1.9.2.1.1.7.42(SILENCERS (PGMA-24885)) | 206813775
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 24885 | 1.9.2.1.1.7.42(SILENCERS (PGMA-24885)) | 206813776
SPECIAL TOOLS (PGMA-24950) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 24950 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813777
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 24950 | 1.9.2.1.1.7.43(SPECIAL TOOLS (PGMA-24950)) | 206813778
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 24950 | 1.9.2.1.1.7.43(SPECIAL TOOLS (PGMA-24950)) | 206813779
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 24950 | 1.9.2.1.1.7.43(SPECIAL TOOLS (PGMA-24950)) | 206813780
LAPPING TOOLS FOR SV&ERV (PGMA-24955) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 24955 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813781
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 24955 | 1.9.2.1.1.7.44(LAPPING TOOLS FOR SV&ERV (PGMA-24955)) | 206813782
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 24955 | 1.9.2.1.1.7.44(LAPPING TOOLS FOR SV&ERV (PGMA-24955)) | 206813783
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 24955 | 1.9.2.1.1.7.44(LAPPING TOOLS FOR SV&ERV (PGMA-24955)) | 206813784
LAPPING TOOLS FOR CONVENTIONAL VALVES( (PGMA-24960) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 24960 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813785
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 24960 | 1.9.2.1.1.7.45(LAPPING TOOLS FOR CONVENTIONAL VALVES( (PGMA-24960)) | 206813786
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 24960 | 1.9.2.1.1.7.45(LAPPING TOOLS FOR CONVENTIONAL VALVES( (PGMA-24960)) | 206813787
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 24960 | 1.9.2.1.1.7.45(LAPPING TOOLS FOR CONVENTIONAL VALVES( (PGMA-24960)) | 206813788
COMMG SPARES FOR SAFETY VALVES/ERV (PGMA-24987) | SUP | 2023-11-21 08:00 | 2025-07-29 17:00 |  |  |  | 24987 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813789
Engineering | ENG | 2023-11-21 08:00 | 2024-09-10 17:00 |  |  |  | 24987 | 1.9.2.1.1.7.46(COMMG SPARES FOR SAFETY VALVES/ERV (PGMA-24987)) | 206813790
Manufacturing | MFG | 2024-09-11 08:00 | 2025-06-29 17:00 |  |  |  | 24987 | 1.9.2.1.1.7.46(COMMG SPARES FOR SAFETY VALVES/ERV (PGMA-24987)) | 206813791
Dispatch | DIS | 2025-06-30 08:00 | 2025-07-29 17:00 |  |  |  | 24987 | 1.9.2.1.1.7.46(COMMG SPARES FOR SAFETY VALVES/ERV (PGMA-24987)) | 206813792
COMMG SPARES FOR IMPORTED SUB-DELY (PGMA-24988) | SUP | 2023-11-21 08:00 | 2025-07-29 17:00 |  |  |  | 24988 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813793
Engineering | ENG | 2023-11-21 08:00 | 2024-09-10 17:00 |  |  |  | 24988 | 1.9.2.1.1.7.47(COMMG SPARES FOR IMPORTED SUB-DELY (PGMA-24988)) | 206813794
Manufacturing | MFG | 2024-09-11 08:00 | 2025-06-29 17:00 |  |  |  | 24988 | 1.9.2.1.1.7.47(COMMG SPARES FOR IMPORTED SUB-DELY (PGMA-24988)) | 206813795
Dispatch | DIS | 2025-06-30 08:00 | 2025-07-29 17:00 |  |  |  | 24988 | 1.9.2.1.1.7.47(COMMG SPARES FOR IMPORTED SUB-DELY (PGMA-24988)) | 206813796
COMMG SPARES FOR CONVENTIONAL VALVES (PGMA-24989) | SUP | 2023-11-21 08:00 | 2025-07-29 17:00 |  |  |  | 24989 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813797
Engineering | ENG | 2023-11-21 08:00 | 2024-09-10 17:00 |  |  |  | 24989 | 1.9.2.1.1.7.48(COMMG SPARES FOR CONVENTIONAL VALVES (PGMA-24989)) | 206813798
Manufacturing | MFG | 2024-09-11 08:00 | 2025-06-29 17:00 |  |  |  | 24989 | 1.9.2.1.1.7.48(COMMG SPARES FOR CONVENTIONAL VALVES (PGMA-24989)) | 206813799
Dispatch | DIS | 2025-06-30 08:00 | 2025-07-29 17:00 |  |  |  | 24989 | 1.9.2.1.1.7.48(COMMG SPARES FOR CONVENTIONAL VALVES (PGMA-24989)) | 206813800
IMPORTED ELECTRODES (PGMA-24992) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24992 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813801
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24992 | 1.9.2.1.1.7.49(IMPORTED ELECTRODES (PGMA-24992)) | 206813802
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24992 | 1.9.2.1.1.7.49(IMPORTED ELECTRODES (PGMA-24992)) | 206813803
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24992 | 1.9.2.1.1.7.49(IMPORTED ELECTRODES (PGMA-24992)) | 206813804
CONSUMABLES &Erection MATERIALS (PGMA-24993) | SUP | 2023-01-25 08:00 | 2024-10-27 17:00 |  |  |  | 24993 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813805
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 24993 | 1.9.2.1.1.7.50(CONSUMABLES &Erection MATERIALS (PGMA-24993)) | 206813806
Manufacturing | MFG | 2023-12-06 08:00 | 2024-09-27 17:00 |  |  |  | 24993 | 1.9.2.1.1.7.50(CONSUMABLES &Erection MATERIALS (PGMA-24993)) | 206813807
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  | 24993 | 1.9.2.1.1.7.50(CONSUMABLES &Erection MATERIALS (PGMA-24993)) | 206813808
NAME PLATES (PGMA-24994) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 24994 | 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | 206813809
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 24994 | 1.9.2.1.1.7.51(NAME PLATES (PGMA-24994)) | 206813810
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 24994 | 1.9.2.1.1.7.51(NAME PLATES (PGMA-24994)) | 206813811
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 24994 | 1.9.2.1.1.7.51(NAME PLATES (PGMA-24994)) | 206813812
Super Heaters and Re-Heaters | SUP | 2022-12-26 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.9.2.1(Supply (BHEL TRY)) | 206813813
Superheater Headers (PG-10) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | PG10 | 1.9.2.1.2(Super Heaters and Re-Heaters ) | 206813814
SH VERTICAL SPACED INLET HEADER (PGMA-10174) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 10174 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813815
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 10174 | 1.9.2.1.2.1.1(SH VERTICAL SPACED INLET HEADER (PGMA-10174)) | 206813816
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 10174 | 1.9.2.1.2.1.1(SH VERTICAL SPACED INLET HEADER (PGMA-10174)) | 206813817
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 10174 | 1.9.2.1.2.1.1(SH VERTICAL SPACED INLET HEADER (PGMA-10174)) | 206813818
SH.VERTICAL PLATEN SH 1NLET HEADER (PGMA-10178) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 10178 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813819
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 10178 | 1.9.2.1.2.1.2(SH.VERTICAL PLATEN SH 1NLET HEADER (PGMA-10178)) | 206813820
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 10178 | 1.9.2.1.2.1.2(SH.VERTICAL PLATEN SH 1NLET HEADER (PGMA-10178)) | 206813821
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 10178 | 1.9.2.1.2.1.2(SH.VERTICAL PLATEN SH 1NLET HEADER (PGMA-10178)) | 206813822
REAR WALL SUPER HEATER INLET HEADER (PGMA-10182) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 10182 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813823
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 10182 | 1.9.2.1.2.1.3(REAR WALL SUPER HEATER INLET HEADER (PGMA-10182)) | 206813824
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 10182 | 1.9.2.1.2.1.3(REAR WALL SUPER HEATER INLET HEADER (PGMA-10182)) | 206813825
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 10182 | 1.9.2.1.2.1.3(REAR WALL SUPER HEATER INLET HEADER (PGMA-10182)) | 206813826
FRONT WALL SUPER HEATER INLET HEADER (PGMA-10183) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 10183 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813827
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 10183 | 1.9.2.1.2.1.4(FRONT WALL SUPER HEATER INLET HEADER (PGMA-10183)) | 206813828
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 10183 | 1.9.2.1.2.1.4(FRONT WALL SUPER HEATER INLET HEADER (PGMA-10183)) | 206813829
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 10183 | 1.9.2.1.2.1.4(FRONT WALL SUPER HEATER INLET HEADER (PGMA-10183)) | 206813830
SIDE WALL SUPER HEATER INLET HEADER (PGMA-10184) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 10184 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813831
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 10184 | 1.9.2.1.2.1.5(SIDE WALL SUPER HEATER INLET HEADER (PGMA-10184)) | 206813832
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 10184 | 1.9.2.1.2.1.5(SIDE WALL SUPER HEATER INLET HEADER (PGMA-10184)) | 206813833
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 10184 | 1.9.2.1.2.1.5(SIDE WALL SUPER HEATER INLET HEADER (PGMA-10184)) | 206813834
BP BOTTOM RING HDRS (PGMA-10185) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 10185 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813835
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 10185 | 1.9.2.1.2.1.6(BP BOTTOM RING HDRS (PGMA-10185)) | 206813836
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 10185 | 1.9.2.1.2.1.6(BP BOTTOM RING HDRS (PGMA-10185)) | 206813837
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 10185 | 1.9.2.1.2.1.6(BP BOTTOM RING HDRS (PGMA-10185)) | 206813838
BACK PASS RING HEADER (PGMA-10191) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 10191 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813839
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 10191 | 1.9.2.1.2.1.7(BACK PASS RING HEADER (PGMA-10191)) | 206813840
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 10191 | 1.9.2.1.2.1.7(BACK PASS RING HEADER (PGMA-10191)) | 206813841
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 10191 | 1.9.2.1.2.1.7(BACK PASS RING HEADER (PGMA-10191)) | 206813842
SH. VERTICAL SPACED OUTLET HEADER (PGMA-10274) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 10274 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813843
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 10274 | 1.9.2.1.2.1.8(SH. VERTICAL SPACED OUTLET HEADER (PGMA-10274)) | 206813844
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 10274 | 1.9.2.1.2.1.8(SH. VERTICAL SPACED OUTLET HEADER (PGMA-10274)) | 206813845
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 10274 | 1.9.2.1.2.1.8(SH. VERTICAL SPACED OUTLET HEADER (PGMA-10274)) | 206813846
SH.VERTICAL PLATEN OUTLET HEADER (PGMA-10278) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 10278 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813847
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 10278 | 1.9.2.1.2.1.9(SH.VERTICAL PLATEN OUTLET HEADER (PGMA-10278)) | 206813848
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 10278 | 1.9.2.1.2.1.9(SH.VERTICAL PLATEN OUTLET HEADER (PGMA-10278)) | 206813849
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 10278 | 1.9.2.1.2.1.9(SH.VERTICAL PLATEN OUTLET HEADER (PGMA-10278)) | 206813850
SH. BACKPASS SIDE WALL FRONT OUTLET HDR. (PGMA-10283) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 10283 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813851
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 10283 | 1.9.2.1.2.1.10(SH. BACKPASS SIDE WALL FRONT OUTLET HDR. (PGMA-10283)) | 206813852
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 10283 | 1.9.2.1.2.1.10(SH. BACKPASS SIDE WALL FRONT OUTLET HDR. (PGMA-10283)) | 206813853
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 10283 | 1.9.2.1.2.1.10(SH. BACKPASS SIDE WALL FRONT OUTLET HDR. (PGMA-10283)) | 206813854
SIDE WALL SUPER HEATER OUTLET HEADER (PGMA-10284) | SUP | 2023-01-25 08:00 | 2024-06-28 17:00 |  |  |  | 10284 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813855
Engineering | ENG | 2023-01-25 08:00 | 2023-10-06 17:00 |  |  |  | 10284 | 1.9.2.1.2.1.11(SIDE WALL SUPER HEATER OUTLET HEADER (PGMA-10284)) | 206813856
Manufacturing | MFG | 2023-10-07 08:00 | 2024-05-29 17:00 |  |  |  | 10284 | 1.9.2.1.2.1.11(SIDE WALL SUPER HEATER OUTLET HEADER (PGMA-10284)) | 206813857
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  | 10284 | 1.9.2.1.2.1.11(SIDE WALL SUPER HEATER OUTLET HEADER (PGMA-10284)) | 206813858
SH front wall outlet header (PGMA-10285) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 10285 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813859
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 10285 | 1.9.2.1.2.1.12(SH front wall outlet header (PGMA-10285)) | 206813860
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 10285 | 1.9.2.1.2.1.12(SH front wall outlet header (PGMA-10285)) | 206813861
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 10285 | 1.9.2.1.2.1.12(SH front wall outlet header (PGMA-10285)) | 206813862
SH RADIANT ROOF OUTLET HDR (PGMA-10291) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 10291 | 1.9.2.1.2.1(Superheater Headers (PG-10)) | 206813863
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 10291 | 1.9.2.1.2.1.13(SH RADIANT ROOF OUTLET HDR (PGMA-10291)) | 206813864
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 10291 | 1.9.2.1.2.1.13(SH RADIANT ROOF OUTLET HDR (PGMA-10291)) | 206813865
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 10291 | 1.9.2.1.2.1.13(SH RADIANT ROOF OUTLET HDR (PGMA-10291)) | 206813866
Superheater Coils and Walls (PG-11) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | PG11 | 1.9.2.1.2(Super Heaters and Re-Heaters ) | 206813867
FINISH SH FRNT ASSY WITH I/T TER & CROSSOVERTUBES (PGMA-11074) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 11074 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813868
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 11074 | 1.9.2.1.2.2.1(FINISH SH FRNT ASSY WITH I/T TER & CROSSOVERTUBES (PGMA-11074)) | 206813869
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 11074 | 1.9.2.1.2.2.1(FINISH SH FRNT ASSY WITH I/T TER & CROSSOVERTUBES (PGMA-11074)) | 206813870
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 11074 | 1.9.2.1.2.2.1(FINISH SH FRNT ASSY WITH I/T TER & CROSSOVERTUBES (PGMA-11074)) | 206813871
SH PLATEN ASSY WITH TERM TUBES - LEFT (PGMA-11078) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 11078 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813872
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 11078 | 1.9.2.1.2.2.2(SH PLATEN ASSY WITH TERM TUBES - LEFT (PGMA-11078)) | 206813873
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 11078 | 1.9.2.1.2.2.2(SH PLATEN ASSY WITH TERM TUBES - LEFT (PGMA-11078)) | 206813874
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 11078 | 1.9.2.1.2.2.2(SH PLATEN ASSY WITH TERM TUBES - LEFT (PGMA-11078)) | 206813875
FINISH SH REAR ASSY WITH O/T TER & CROSSOVERTUBES (PGMA-11374) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 11374 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813876
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 11374 | 1.9.2.1.2.2.3(FINISH SH REAR ASSY WITH O/T TER & CROSSOVERTUBES (PGMA-11374)) | 206813877
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 11374 | 1.9.2.1.2.2.3(FINISH SH REAR ASSY WITH O/T TER & CROSSOVERTUBES (PGMA-11374)) | 206813878
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 11374 | 1.9.2.1.2.2.3(FINISH SH REAR ASSY WITH O/T TER & CROSSOVERTUBES (PGMA-11374)) | 206813879
SH PLATEN ASSY WITH TERM TUBES - RIGHT (PGMA-11378) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 11378 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813880
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 11378 | 1.9.2.1.2.2.4(SH PLATEN ASSY WITH TERM TUBES - RIGHT (PGMA-11378)) | 206813881
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 11378 | 1.9.2.1.2.2.4(SH PLATEN ASSY WITH TERM TUBES - RIGHT (PGMA-11378)) | 206813882
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 11378 | 1.9.2.1.2.2.4(SH PLATEN ASSY WITH TERM TUBES - RIGHT (PGMA-11378)) | 206813883
SH. FRONT WALL PANELS UPPER- OS (PGMA-11406) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 11406 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813884
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 11406 | 1.9.2.1.2.2.5(SH. FRONT WALL PANELS UPPER- OS (PGMA-11406)) | 206813885
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 11406 | 1.9.2.1.2.2.5(SH. FRONT WALL PANELS UPPER- OS (PGMA-11406)) | 206813886
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 11406 | 1.9.2.1.2.2.5(SH. FRONT WALL PANELS UPPER- OS (PGMA-11406)) | 206813887
SH LOWER PNL ATTACHMENT (PGMA-11408) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 11408 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813888
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 11408 | 1.9.2.1.2.2.6(SH LOWER PNL ATTACHMENT (PGMA-11408)) | 206813889
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 11408 | 1.9.2.1.2.2.6(SH LOWER PNL ATTACHMENT (PGMA-11408)) | 206813890
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 11408 | 1.9.2.1.2.2.6(SH LOWER PNL ATTACHMENT (PGMA-11408)) | 206813891
SH REAR WALL PANELS UPPER (LEFT)-OS (PGMA-11416) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  |  | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813892
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 11416 | 1.9.2.1.2.2.7(SH REAR WALL PANELS UPPER (LEFT)-OS (PGMA-11416)) | 206813893
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 11416 | 1.9.2.1.2.2.7(SH REAR WALL PANELS UPPER (LEFT)-OS (PGMA-11416)) | 206813894
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 11416 | 1.9.2.1.2.2.7(SH REAR WALL PANELS UPPER (LEFT)-OS (PGMA-11416)) | 206813895
SH SW PANELS UPPER REAR (L&R)-OS (PGMA-11467) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813896
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 11467 | 1.9.2.1.2.2.8(SH SW PANELS UPPER REAR (L&R)-OS (PGMA-11467)) | 206813897
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 11467 | 1.9.2.1.2.2.8(SH SW PANELS UPPER REAR (L&R)-OS (PGMA-11467)) | 206813898
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 11467 | 1.9.2.1.2.2.8(SH SW PANELS UPPER REAR (L&R)-OS (PGMA-11467)) | 206813899
SH REAR ROOF PANELS (RIGHT)-OS (PGMA-11487) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813900
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 11487 | 1.9.2.1.2.2.9(SH REAR ROOF PANELS (RIGHT)-OS (PGMA-11487)) | 206813901
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 11487 | 1.9.2.1.2.2.9(SH REAR ROOF PANELS (RIGHT)-OS (PGMA-11487)) | 206813902
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 11487 | 1.9.2.1.2.2.9(SH REAR ROOF PANELS (RIGHT)-OS (PGMA-11487)) | 206813903
SH. RADIENT ROOF TUBES -OS (PGMA-11491) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 11491 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813904
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 11491 | 1.9.2.1.2.2.10(SH. RADIENT ROOF TUBES -OS (PGMA-11491)) | 206813905
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 11491 | 1.9.2.1.2.2.10(SH. RADIENT ROOF TUBES -OS (PGMA-11491)) | 206813906
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 11491 | 1.9.2.1.2.2.10(SH. RADIENT ROOF TUBES -OS (PGMA-11491)) | 206813907
SH. FRONT WALL PANELS UPPER (PGMA-11606) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 11606 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813908
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 11606 | 1.9.2.1.2.2.11(SH. FRONT WALL PANELS UPPER (PGMA-11606)) | 206813909
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 11606 | 1.9.2.1.2.2.11(SH. FRONT WALL PANELS UPPER (PGMA-11606)) | 206813910
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 11606 | 1.9.2.1.2.2.11(SH. FRONT WALL PANELS UPPER (PGMA-11606)) | 206813911
SH.FRONT WALL PANELS LOWER (PGMA-11608) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 11608 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813912
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 11608 | 1.9.2.1.2.2.12(SH.FRONT WALL PANELS LOWER (PGMA-11608)) | 206813913
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 11608 | 1.9.2.1.2.2.12(SH.FRONT WALL PANELS LOWER (PGMA-11608)) | 206813914
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 11608 | 1.9.2.1.2.2.12(SH.FRONT WALL PANELS LOWER (PGMA-11608)) | 206813915
SH EXTENDED SIDE WALL PANELS (PGMA-11684) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 11684 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813916
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 11684 | 1.9.2.1.2.2.13(SH EXTENDED SIDE WALL PANELS (PGMA-11684)) | 206813917
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 11684 | 1.9.2.1.2.2.13(SH EXTENDED SIDE WALL PANELS (PGMA-11684)) | 206813918
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 11684 | 1.9.2.1.2.2.13(SH EXTENDED SIDE WALL PANELS (PGMA-11684)) | 206813919
SH.EXTENDED BOTTOM PANELS (PGMA-11694) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 11694 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813920
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 11694 | 1.9.2.1.2.2.14(SH.EXTENDED BOTTOM PANELS (PGMA-11694)) | 206813921
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 11694 | 1.9.2.1.2.2.14(SH.EXTENDED BOTTOM PANELS (PGMA-11694)) | 206813922
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 11694 | 1.9.2.1.2.2.14(SH.EXTENDED BOTTOM PANELS (PGMA-11694)) | 206813923
SH REAR WALL PANELS UPPER (LEFT) (PGMA-11716) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 11716 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813924
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 11716 | 1.9.2.1.2.2.15(SH REAR WALL PANELS UPPER (LEFT) (PGMA-11716)) | 206813925
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 11716 | 1.9.2.1.2.2.15(SH REAR WALL PANELS UPPER (LEFT) (PGMA-11716)) | 206813926
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 11716 | 1.9.2.1.2.2.15(SH REAR WALL PANELS UPPER (LEFT) (PGMA-11716)) | 206813927
SH. REAR WALL PANELS LOWER (LEFT) (PGMA-11718) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 11718 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813928
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 11718 | 1.9.2.1.2.2.16(SH. REAR WALL PANELS LOWER (LEFT) (PGMA-11718)) | 206813929
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 11718 | 1.9.2.1.2.2.16(SH. REAR WALL PANELS LOWER (LEFT) (PGMA-11718)) | 206813930
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 11718 | 1.9.2.1.2.2.16(SH. REAR WALL PANELS LOWER (LEFT) (PGMA-11718)) | 206813931
SH SIDE WALL PANELS UPPER FRONT (L&R) (PGMA-11767) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 11767 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813932
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 11767 | 1.9.2.1.2.2.17(SH SIDE WALL PANELS UPPER FRONT (L&R) (PGMA-11767)) | 206813933
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 11767 | 1.9.2.1.2.2.17(SH SIDE WALL PANELS UPPER FRONT (L&R) (PGMA-11767)) | 206813934
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 11767 | 1.9.2.1.2.2.17(SH SIDE WALL PANELS UPPER FRONT (L&R) (PGMA-11767)) | 206813935
SH. SIDE WALL PANELS LOWER FRONT (L&R) (PGMA-11769) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 11769 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813936
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 11769 | 1.9.2.1.2.2.18(SH. SIDE WALL PANELS LOWER FRONT (L&R) (PGMA-11769)) | 206813937
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 11769 | 1.9.2.1.2.2.18(SH. SIDE WALL PANELS LOWER FRONT (L&R) (PGMA-11769)) | 206813938
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 11769 | 1.9.2.1.2.2.18(SH. SIDE WALL PANELS LOWER FRONT (L&R) (PGMA-11769)) | 206813939
SH REAR ROOF PANELS (LEFT) (PGMA-11787) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 11787 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813940
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 11787 | 1.9.2.1.2.2.19(SH REAR ROOF PANELS (LEFT) (PGMA-11787)) | 206813941
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 11787 | 1.9.2.1.2.2.19(SH REAR ROOF PANELS (LEFT) (PGMA-11787)) | 206813942
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 11787 | 1.9.2.1.2.2.19(SH REAR ROOF PANELS (LEFT) (PGMA-11787)) | 206813943
SH. RADIENT ROOF TUBES (LEFT) (PGMA-11791) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 11791 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813944
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 11791 | 1.9.2.1.2.2.20(SH. RADIENT ROOF TUBES (LEFT) (PGMA-11791)) | 206813945
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 11791 | 1.9.2.1.2.2.20(SH. RADIENT ROOF TUBES (LEFT) (PGMA-11791)) | 206813946
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 11791 | 1.9.2.1.2.2.20(SH. RADIENT ROOF TUBES (LEFT) (PGMA-11791)) | 206813947
SH. REAR WALL PANEL UPPER (RIGHT) (PGMA-11916) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 11916 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813948
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 11916 | 1.9.2.1.2.2.21(SH. REAR WALL PANEL UPPER (RIGHT) (PGMA-11916)) | 206813949
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 11916 | 1.9.2.1.2.2.21(SH. REAR WALL PANEL UPPER (RIGHT) (PGMA-11916)) | 206813950
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 11916 | 1.9.2.1.2.2.21(SH. REAR WALL PANEL UPPER (RIGHT) (PGMA-11916)) | 206813951
SH. REAR WALL PANELS LOWER (RIGHT) (PGMA-11918) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 11918 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813952
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 11918 | 1.9.2.1.2.2.22(SH. REAR WALL PANELS LOWER (RIGHT) (PGMA-11918)) | 206813953
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 11918 | 1.9.2.1.2.2.22(SH. REAR WALL PANELS LOWER (RIGHT) (PGMA-11918)) | 206813954
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 11918 | 1.9.2.1.2.2.22(SH. REAR WALL PANELS LOWER (RIGHT) (PGMA-11918)) | 206813955
SH. SIDE WALL PANELS UPPER REAR (L&R) (PGMA-11967) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 11967 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813956
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 11967 | 1.9.2.1.2.2.23(SH. SIDE WALL PANELS UPPER REAR (L&R) (PGMA-11967)) | 206813957
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 11967 | 1.9.2.1.2.2.23(SH. SIDE WALL PANELS UPPER REAR (L&R) (PGMA-11967)) | 206813958
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 11967 | 1.9.2.1.2.2.23(SH. SIDE WALL PANELS UPPER REAR (L&R) (PGMA-11967)) | 206813959
SH. SIDE WALL PANELS LOWER REAR ( L&R) (PGMA-11969) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 11969 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813960
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 11969 | 1.9.2.1.2.2.24(SH. SIDE WALL PANELS LOWER REAR ( L&R) (PGMA-11969)) | 206813961
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 11969 | 1.9.2.1.2.2.24(SH. SIDE WALL PANELS LOWER REAR ( L&R) (PGMA-11969)) | 206813962
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 11969 | 1.9.2.1.2.2.24(SH. SIDE WALL PANELS LOWER REAR ( L&R) (PGMA-11969)) | 206813963
SH REAR ROOF PANELS (RIGHT) (PGMA-11987) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 11987 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813964
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 11987 | 1.9.2.1.2.2.25(SH REAR ROOF PANELS (RIGHT) (PGMA-11987)) | 206813965
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 11987 | 1.9.2.1.2.2.25(SH REAR ROOF PANELS (RIGHT) (PGMA-11987)) | 206813966
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 11987 | 1.9.2.1.2.2.25(SH REAR ROOF PANELS (RIGHT) (PGMA-11987)) | 206813967
SH. RADIENT ROOF TUBES (RIGHT) (PGMA-11991) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 11991 | 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | 206813968
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 11991 | 1.9.2.1.2.2.26(SH. RADIENT ROOF TUBES (RIGHT) (PGMA-11991)) | 206813969
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 11991 | 1.9.2.1.2.2.26(SH. RADIENT ROOF TUBES (RIGHT) (PGMA-11991)) | 206813970
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 11991 | 1.9.2.1.2.2.26(SH. RADIENT ROOF TUBES (RIGHT) (PGMA-11991)) | 206813971
Superheater Components (PG-12) | SUP | 2022-12-26 08:00 | 2024-06-28 17:00 |  |  |  | PG12 | 1.9.2.1.2(Super Heaters and Re-Heaters ) | 206813972
LP SH CROSSOVERS(RIGHT) (PGMA-12178) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 12178 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813973
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 12178 | 1.9.2.1.2.3.1(LP SH CROSSOVERS(RIGHT) (PGMA-12178)) | 206813974
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 12178 | 1.9.2.1.2.3.1(LP SH CROSSOVERS(RIGHT) (PGMA-12178)) | 206813975
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 12178 | 1.9.2.1.2.3.1(LP SH CROSSOVERS(RIGHT) (PGMA-12178)) | 206813976
SH.EXTD. SIDE WALL INLET PIPE (PGMA-12184) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12184 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813977
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12184 | 1.9.2.1.2.3.2(SH.EXTD. SIDE WALL INLET PIPE (PGMA-12184)) | 206813978
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12184 | 1.9.2.1.2.3.2(SH.EXTD. SIDE WALL INLET PIPE (PGMA-12184)) | 206813979
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12184 | 1.9.2.1.2.3.2(SH.EXTD. SIDE WALL INLET PIPE (PGMA-12184)) | 206813980
SH. EXTD.SIDE WALL OUTLET PIPE (PGMA-12187) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 12187 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813981
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 12187 | 1.9.2.1.2.3.3(SH. EXTD.SIDE WALL OUTLET PIPE (PGMA-12187)) | 206813982
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 12187 | 1.9.2.1.2.3.3(SH. EXTD.SIDE WALL OUTLET PIPE (PGMA-12187)) | 206813983
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 12187 | 1.9.2.1.2.3.3(SH. EXTD.SIDE WALL OUTLET PIPE (PGMA-12187)) | 206813984
SH SUPPORT FOR LINES AND LINKS DD ITEM (PGMA-12306) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12306 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813985
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12306 | 1.9.2.1.2.3.4(SH SUPPORT FOR LINES AND LINKS DD ITEM (PGMA-12306)) | 206813986
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12306 | 1.9.2.1.2.3.4(SH SUPPORT FOR LINES AND LINKS DD ITEM (PGMA-12306)) | 206813987
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12306 | 1.9.2.1.2.3.4(SH SUPPORT FOR LINES AND LINKS DD ITEM (PGMA-12306)) | 206813988
SUSPN OF SH RAD ROOF HDRS-DD (PGMA-12314) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12314 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813989
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12314 | 1.9.2.1.2.3.5(SUSPN OF SH RAD ROOF HDRS-DD (PGMA-12314)) | 206813990
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12314 | 1.9.2.1.2.3.5(SUSPN OF SH RAD ROOF HDRS-DD (PGMA-12314)) | 206813991
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12314 | 1.9.2.1.2.3.5(SUSPN OF SH RAD ROOF HDRS-DD (PGMA-12314)) | 206813992
SUSPN OF RADIANT ROOF-DD (PGMA-12317) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12317 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813993
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12317 | 1.9.2.1.2.3.6(SUSPN OF RADIANT ROOF-DD (PGMA-12317)) | 206813994
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12317 | 1.9.2.1.2.3.6(SUSPN OF RADIANT ROOF-DD (PGMA-12317)) | 206813995
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12317 | 1.9.2.1.2.3.6(SUSPN OF RADIANT ROOF-DD (PGMA-12317)) | 206813996
SUSPN OF BP TOP HEADERS-DD (PGMA-12324) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12324 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206813997
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12324 | 1.9.2.1.2.3.7(SUSPN OF BP TOP HEADERS-DD (PGMA-12324)) | 206813998
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12324 | 1.9.2.1.2.3.7(SUSPN OF BP TOP HEADERS-DD (PGMA-12324)) | 206813999
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12324 | 1.9.2.1.2.3.7(SUSPN OF BP TOP HEADERS-DD (PGMA-12324)) | 206814000
SUSPN OF REAR ROOF-DD (PGMA-12327) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12327 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814001
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12327 | 1.9.2.1.2.3.8(SUSPN OF REAR ROOF-DD (PGMA-12327)) | 206814002
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12327 | 1.9.2.1.2.3.8(SUSPN OF REAR ROOF-DD (PGMA-12327)) | 206814003
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12327 | 1.9.2.1.2.3.8(SUSPN OF REAR ROOF-DD (PGMA-12327)) | 206814004
SUSPN SH H.TUBES FT&REAR WL-DD (PGMA-12328) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12328 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814005
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12328 | 1.9.2.1.2.3.9(SUSPN SH H.TUBES FT&REAR WL-DD (PGMA-12328)) | 206814006
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12328 | 1.9.2.1.2.3.9(SUSPN SH H.TUBES FT&REAR WL-DD (PGMA-12328)) | 206814007
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12328 | 1.9.2.1.2.3.9(SUSPN SH H.TUBES FT&REAR WL-DD (PGMA-12328)) | 206814008
SUSPN OF SH PLA&SH DIVI PANTE HDR-DD (PGMA-12344) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12344 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814009
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12344 | 1.9.2.1.2.3.10(SUSPN OF SH PLA&SH DIVI PANTE HDR-DD (PGMA-12344)) | 206814010
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12344 | 1.9.2.1.2.3.10(SUSPN OF SH PLA&SH DIVI PANTE HDR-DD (PGMA-12344)) | 206814011
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12344 | 1.9.2.1.2.3.10(SUSPN OF SH PLA&SH DIVI PANTE HDR-DD (PGMA-12344)) | 206814012
SUSPN OF SHFL.SHSPD.CL.ASY&SH TT.SPD-DD (PGMA-12348) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12348 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814013
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12348 | 1.9.2.1.2.3.11(SUSPN OF SHFL.SHSPD.CL.ASY&SH TT.SPD-DD (PGMA-12348)) | 206814014
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12348 | 1.9.2.1.2.3.11(SUSPN OF SHFL.SHSPD.CL.ASY&SH TT.SPD-DD (PGMA-12348)) | 206814015
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12348 | 1.9.2.1.2.3.11(SUSPN OF SHFL.SHSPD.CL.ASY&SH TT.SPD-DD (PGMA-12348)) | 206814016
SUSPN OF SH PLN &FINAL SPD. HDR-DD (PGMA-12354) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12354 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814017
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12354 | 1.9.2.1.2.3.12(SUSPN OF SH PLN &FINAL SPD. HDR-DD (PGMA-12354)) | 206814018
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12354 | 1.9.2.1.2.3.12(SUSPN OF SH PLN &FINAL SPD. HDR-DD (PGMA-12354)) | 206814019
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12354 | 1.9.2.1.2.3.12(SUSPN OF SH PLN &FINAL SPD. HDR-DD (PGMA-12354)) | 206814020
SUSPN OF SH PLATEN COIL ASSY-DD (PGMA-12368) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12368 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814021
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12368 | 1.9.2.1.2.3.13(SUSPN OF SH PLATEN COIL ASSY-DD (PGMA-12368)) | 206814022
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12368 | 1.9.2.1.2.3.13(SUSPN OF SH PLATEN COIL ASSY-DD (PGMA-12368)) | 206814023
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12368 | 1.9.2.1.2.3.13(SUSPN OF SH PLATEN COIL ASSY-DD (PGMA-12368)) | 206814024
ERECTION MATERIALS & CONSLE-DD (PGMA-12393) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 12393 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814025
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 12393 | 1.9.2.1.2.3.14(ERECTION MATERIALS & CONSLE-DD (PGMA-12393)) | 206814026
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 12393 | 1.9.2.1.2.3.14(ERECTION MATERIALS & CONSLE-DD (PGMA-12393)) | 206814027
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 12393 | 1.9.2.1.2.3.14(ERECTION MATERIALS & CONSLE-DD (PGMA-12393)) | 206814028
SH. HANGER TUBES-OS (PGMA-12405) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12405 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814029
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12405 | 1.9.2.1.2.3.15(SH. HANGER TUBES-OS (PGMA-12405)) | 206814030
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12405 | 1.9.2.1.2.3.15(SH. HANGER TUBES-OS (PGMA-12405)) | 206814031
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12405 | 1.9.2.1.2.3.15(SH. HANGER TUBES-OS (PGMA-12405)) | 206814032
SH SUPPORT FOR LINES AND LINKS SHOP ITEM (PGMA-12506) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12506 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814033
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12506 | 1.9.2.1.2.3.16(SH SUPPORT FOR LINES AND LINKS SHOP ITEM (PGMA-12506)) | 206814034
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12506 | 1.9.2.1.2.3.16(SH SUPPORT FOR LINES AND LINKS SHOP ITEM (PGMA-12506)) | 206814035
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12506 | 1.9.2.1.2.3.16(SH SUPPORT FOR LINES AND LINKS SHOP ITEM (PGMA-12506)) | 206814036
SUSPEN OF SH RAD ROOF HDRS-SHOP (PGMA-12514) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12514 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814037
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12514 | 1.9.2.1.2.3.17(SUSPEN OF SH RAD ROOF HDRS-SHOP (PGMA-12514)) | 206814038
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12514 | 1.9.2.1.2.3.17(SUSPEN OF SH RAD ROOF HDRS-SHOP (PGMA-12514)) | 206814039
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12514 | 1.9.2.1.2.3.17(SUSPEN OF SH RAD ROOF HDRS-SHOP (PGMA-12514)) | 206814040
BP STEAM COOLED HANGER TUBES (PGMA-12515) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12515 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814041
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12515 | 1.9.2.1.2.3.18(BP STEAM COOLED HANGER TUBES (PGMA-12515)) | 206814042
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12515 | 1.9.2.1.2.3.18(BP STEAM COOLED HANGER TUBES (PGMA-12515)) | 206814043
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12515 | 1.9.2.1.2.3.18(BP STEAM COOLED HANGER TUBES (PGMA-12515)) | 206814044
Suspension Of Sh Back Pass Headers-SH (PGMA-12524) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12524 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814045
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12524 | 1.9.2.1.2.3.19(Suspension Of Sh Back Pass Headers-SH (PGMA-12524)) | 206814046
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12524 | 1.9.2.1.2.3.19(Suspension Of Sh Back Pass Headers-SH (PGMA-12524)) | 206814047
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12524 | 1.9.2.1.2.3.19(Suspension Of Sh Back Pass Headers-SH (PGMA-12524)) | 206814048
SUSPN OF SH PLA&SH DIVI PANTE HDR-SHOP (PGMA-12544) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12544 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814049
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12544 | 1.9.2.1.2.3.20(SUSPN OF SH PLA&SH DIVI PANTE HDR-SHOP (PGMA-12544)) | 206814050
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12544 | 1.9.2.1.2.3.20(SUSPN OF SH PLA&SH DIVI PANTE HDR-SHOP (PGMA-12544)) | 206814051
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12544 | 1.9.2.1.2.3.20(SUSPN OF SH PLA&SH DIVI PANTE HDR-SHOP (PGMA-12544)) | 206814052
SUSPN OF SH PLN &FINAL SPD. HDR-SHOP (PGMA-12554) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12554 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814053
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12554 | 1.9.2.1.2.3.21(SUSPN OF SH PLN &FINAL SPD. HDR-SHOP (PGMA-12554)) | 206814054
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12554 | 1.9.2.1.2.3.21(SUSPN OF SH PLN &FINAL SPD. HDR-SHOP (PGMA-12554)) | 206814055
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12554 | 1.9.2.1.2.3.21(SUSPN OF SH PLN &FINAL SPD. HDR-SHOP (PGMA-12554)) | 206814056
SH STEAM COOLED SPACER TUBES (PGMA-12803) | SUP | 2023-01-25 08:00 | 2024-05-29 17:00 |  |  |  | 12803 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814057
Engineering | ENG | 2023-01-25 08:00 | 2023-09-26 17:00 |  |  |  | 12803 | 1.9.2.1.2.3.22(SH STEAM COOLED SPACER TUBES (PGMA-12803)) | 206814058
Manufacturing | MFG | 2023-09-27 08:00 | 2024-04-29 17:00 |  |  |  | 12803 | 1.9.2.1.2.3.22(SH STEAM COOLED SPACER TUBES (PGMA-12803)) | 206814059
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 12803 | 1.9.2.1.2.3.22(SH STEAM COOLED SPACER TUBES (PGMA-12803)) | 206814060
SH. HANGER TUBES (PGMA-12805) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12805 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814061
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12805 | 1.9.2.1.2.3.23(SH. HANGER TUBES (PGMA-12805)) | 206814062
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12805 | 1.9.2.1.2.3.23(SH. HANGER TUBES (PGMA-12805)) | 206814063
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12805 | 1.9.2.1.2.3.23(SH. HANGER TUBES (PGMA-12805)) | 206814064
SATURATED STEAM CONNECTING PIPE (PGMA-12850) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12850 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814065
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12850 | 1.9.2.1.2.3.24(SATURATED STEAM CONNECTING PIPE (PGMA-12850)) | 206814066
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12850 | 1.9.2.1.2.3.24(SATURATED STEAM CONNECTING PIPE (PGMA-12850)) | 206814067
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12850 | 1.9.2.1.2.3.24(SATURATED STEAM CONNECTING PIPE (PGMA-12850)) | 206814068
SUPER HEATER DESH LINKS (PGMA-12852) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12852 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814069
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12852 | 1.9.2.1.2.3.25(SUPER HEATER DESH LINKS (PGMA-12852)) | 206814070
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12852 | 1.9.2.1.2.3.25(SUPER HEATER DESH LINKS (PGMA-12852)) | 206814071
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12852 | 1.9.2.1.2.3.25(SUPER HEATER DESH LINKS (PGMA-12852)) | 206814072
SUPER HEATER DESH (PGMA-12900) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 12900 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814073
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 12900 | 1.9.2.1.2.3.26(SUPER HEATER DESH (PGMA-12900)) | 206814074
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 12900 | 1.9.2.1.2.3.26(SUPER HEATER DESH (PGMA-12900)) | 206814075
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 12900 | 1.9.2.1.2.3.26(SUPER HEATER DESH (PGMA-12900)) | 206814076
SUPER HEATER MISCELLANEOUS COMPONENTS (PGMA-12903) | SUP | 2023-01-25 08:00 | 2024-06-28 17:00 |  |  |  | 12903 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814077
Engineering | ENG | 2023-01-25 08:00 | 2023-10-06 17:00 |  |  |  | 12903 | 1.9.2.1.2.3.27(SUPER HEATER MISCELLANEOUS COMPONENTS (PGMA-12903)) | 206814078
Manufacturing | MFG | 2023-10-07 08:00 | 2024-05-29 17:00 |  |  |  | 12903 | 1.9.2.1.2.3.27(SUPER HEATER MISCELLANEOUS COMPONENTS (PGMA-12903)) | 206814079
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  | 12903 | 1.9.2.1.2.3.27(SUPER HEATER MISCELLANEOUS COMPONENTS (PGMA-12903)) | 206814080
SUPER HEATER LINK SUPPORTS (PGMA-12906) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12906 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814081
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12906 | 1.9.2.1.2.3.28(SUPER HEATER LINK SUPPORTS (PGMA-12906)) | 206814082
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12906 | 1.9.2.1.2.3.28(SUPER HEATER LINK SUPPORTS (PGMA-12906)) | 206814083
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12906 | 1.9.2.1.2.3.28(SUPER HEATER LINK SUPPORTS (PGMA-12906)) | 206814084
BACKPASS ROOF SUPPORTS (PGMA-12907) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12907 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814085
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12907 | 1.9.2.1.2.3.29(BACKPASS ROOF SUPPORTS (PGMA-12907)) | 206814086
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12907 | 1.9.2.1.2.3.29(BACKPASS ROOF SUPPORTS (PGMA-12907)) | 206814087
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12907 | 1.9.2.1.2.3.29(BACKPASS ROOF SUPPORTS (PGMA-12907)) | 206814088
SUSPENSION OF SH RADIANT ROOF HEADERS (PGMA-12914) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12914 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814089
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12914 | 1.9.2.1.2.3.30(SUSPENSION OF SH RADIANT ROOF HEADERS (PGMA-12914)) | 206814090
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12914 | 1.9.2.1.2.3.30(SUSPENSION OF SH RADIANT ROOF HEADERS (PGMA-12914)) | 206814091
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12914 | 1.9.2.1.2.3.30(SUSPENSION OF SH RADIANT ROOF HEADERS (PGMA-12914)) | 206814092
SUSPENSION OF RADIANT ROOF (PGMA-12917) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12917 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814093
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12917 | 1.9.2.1.2.3.31(SUSPENSION OF RADIANT ROOF (PGMA-12917)) | 206814094
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12917 | 1.9.2.1.2.3.31(SUSPENSION OF RADIANT ROOF (PGMA-12917)) | 206814095
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12917 | 1.9.2.1.2.3.31(SUSPENSION OF RADIANT ROOF (PGMA-12917)) | 206814096
SUPER HEATER BACK PASS HEADER SUSPENSION (PGMA-12924) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12924 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814097
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12924 | 1.9.2.1.2.3.32(SUPER HEATER BACK PASS HEADER SUSPENSION (PGMA-12924)) | 206814098
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12924 | 1.9.2.1.2.3.32(SUPER HEATER BACK PASS HEADER SUSPENSION (PGMA-12924)) | 206814099
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12924 | 1.9.2.1.2.3.32(SUPER HEATER BACK PASS HEADER SUSPENSION (PGMA-12924)) | 206814100
SUSPENSION OF REAR ROOF (PGMA-12927) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12927 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814101
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12927 | 1.9.2.1.2.3.33(SUSPENSION OF REAR ROOF (PGMA-12927)) | 206814102
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12927 | 1.9.2.1.2.3.33(SUSPENSION OF REAR ROOF (PGMA-12927)) | 206814103
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12927 | 1.9.2.1.2.3.33(SUSPENSION OF REAR ROOF (PGMA-12927)) | 206814104
SUSPENSIONOFSH HAN.TUBES FT.WL.&REAR WL. (PGMA-12928) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12928 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814105
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12928 | 1.9.2.1.2.3.34(SUSPENSIONOFSH HAN.TUBES FT.WL.&REAR WL. (PGMA-12928)) | 206814106
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12928 | 1.9.2.1.2.3.34(SUSPENSIONOFSH HAN.TUBES FT.WL.&REAR WL. (PGMA-12928)) | 206814107
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12928 | 1.9.2.1.2.3.34(SUSPENSIONOFSH HAN.TUBES FT.WL.&REAR WL. (PGMA-12928)) | 206814108
SUSPENSION OF SH PLA.&SH DIVI.PANTE. HDR (PGMA-12944) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12944 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814109
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12944 | 1.9.2.1.2.3.35(SUSPENSION OF SH PLA.&SH DIVI.PANTE. HDR (PGMA-12944)) | 206814110
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12944 | 1.9.2.1.2.3.35(SUSPENSION OF SH PLA.&SH DIVI.PANTE. HDR (PGMA-12944)) | 206814111
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12944 | 1.9.2.1.2.3.35(SUSPENSION OF SH PLA.&SH DIVI.PANTE. HDR (PGMA-12944)) | 206814112
SUSPN.OFSHFL.SHSPD.CL.ASY&LTSHTER.TE.SPD (PGMA-12948) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12948 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814113
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12948 | 1.9.2.1.2.3.36(SUSPN.OFSHFL.SHSPD.CL.ASY&LTSHTER.TE.SPD (PGMA-12948)) | 206814114
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12948 | 1.9.2.1.2.3.36(SUSPN.OFSHFL.SHSPD.CL.ASY&LTSHTER.TE.SPD (PGMA-12948)) | 206814115
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12948 | 1.9.2.1.2.3.36(SUSPN.OFSHFL.SHSPD.CL.ASY&LTSHTER.TE.SPD (PGMA-12948)) | 206814116
SUSPENSION OF SH PLN HDR&FINAL SPD. HDR (PGMA-12954) | SUP | 2022-12-26 08:00 | 2024-01-27 17:00 |  |  |  | 12954 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814117
Engineering | ENG | 2022-12-26 08:00 | 2023-07-05 17:00 |  |  |  | 12954 | 1.9.2.1.2.3.37(SUSPENSION OF SH PLN HDR&FINAL SPD. HDR (PGMA-12954)) | 206814118
Manufacturing | MFG | 2023-07-06 08:00 | 2023-12-28 17:00 |  |  |  | 12954 | 1.9.2.1.2.3.37(SUSPENSION OF SH PLN HDR&FINAL SPD. HDR (PGMA-12954)) | 206814119
Dispatch | DIS | 2023-12-29 08:00 | 2024-01-27 17:00 |  |  |  | 12954 | 1.9.2.1.2.3.37(SUSPENSION OF SH PLN HDR&FINAL SPD. HDR (PGMA-12954)) | 206814120
SUSPENSION OF SH PLATEN COIL ASSY (PGMA-12968) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 12968 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814121
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 12968 | 1.9.2.1.2.3.38(SUSPENSION OF SH PLATEN COIL ASSY (PGMA-12968)) | 206814122
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 12968 | 1.9.2.1.2.3.38(SUSPENSION OF SH PLATEN COIL ASSY (PGMA-12968)) | 206814123
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 12968 | 1.9.2.1.2.3.38(SUSPENSION OF SH PLATEN COIL ASSY (PGMA-12968)) | 206814124
SH. IMPORTED ELECTRODES (PGMA-12991) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 12991 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814125
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 12991 | 1.9.2.1.2.3.39(SH. IMPORTED ELECTRODES (PGMA-12991)) | 206814126
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 12991 | 1.9.2.1.2.3.39(SH. IMPORTED ELECTRODES (PGMA-12991)) | 206814127
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 12991 | 1.9.2.1.2.3.39(SH. IMPORTED ELECTRODES (PGMA-12991)) | 206814128
IMPORTED ELECTRODES (PGMA-12992) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 12992 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814129
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 12992 | 1.9.2.1.2.3.40(IMPORTED ELECTRODES (PGMA-12992)) | 206814130
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 12992 | 1.9.2.1.2.3.40(IMPORTED ELECTRODES (PGMA-12992)) | 206814131
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 12992 | 1.9.2.1.2.3.40(IMPORTED ELECTRODES (PGMA-12992)) | 206814132
ERECTION MATERIALS (PGMA-12993) | SUP | 2022-12-26 08:00 | 2023-12-27 17:00 |  |  |  | 12993 | 1.9.2.1.2.3(Superheater Components (PG-12)) | 206814133
Engineering | ENG | 2022-12-26 08:00 | 2023-05-26 17:00 |  |  |  | 12993 | 1.9.2.1.2.3.41(ERECTION MATERIALS (PGMA-12993)) | 206814134
Manufacturing | MFG | 2023-05-27 08:00 | 2023-11-27 17:00 |  |  |  | 12993 | 1.9.2.1.2.3.41(ERECTION MATERIALS (PGMA-12993)) | 206814135
Dispatch | DIS | 2023-11-28 08:00 | 2023-12-27 17:00 |  |  |  | 12993 | 1.9.2.1.2.3.41(ERECTION MATERIALS (PGMA-12993)) | 206814136
Reheater Headers (PG-15) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | PG15 | 1.9.2.1.2(Super Heaters and Re-Heaters ) | 206814137
REHEATER-I INLET HEADER (PGMA-15136) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 15136 | 1.9.2.1.2.4(Reheater Headers (PG-15)) | 206814138
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 15136 | 1.9.2.1.2.4.1(REHEATER-I INLET HEADER (PGMA-15136)) | 206814139
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 15136 | 1.9.2.1.2.4.1(REHEATER-I INLET HEADER (PGMA-15136)) | 206814140
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 15136 | 1.9.2.1.2.4.1(REHEATER-I INLET HEADER (PGMA-15136)) | 206814141
FINISH RH I/L HDR (PGMA-15178) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 15178 | 1.9.2.1.2.4(Reheater Headers (PG-15)) | 206814142
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 15178 | 1.9.2.1.2.4.2(FINISH RH I/L HDR (PGMA-15178)) | 206814143
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 15178 | 1.9.2.1.2.4.2(FINISH RH I/L HDR (PGMA-15178)) | 206814144
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 15178 | 1.9.2.1.2.4.2(FINISH RH I/L HDR (PGMA-15178)) | 206814145
REHEATER-I OUTLET HEADER (PGMA-15236) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 15236 | 1.9.2.1.2.4(Reheater Headers (PG-15)) | 206814146
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 15236 | 1.9.2.1.2.4.3(REHEATER-I OUTLET HEADER (PGMA-15236)) | 206814147
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 15236 | 1.9.2.1.2.4.3(REHEATER-I OUTLET HEADER (PGMA-15236)) | 206814148
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 15236 | 1.9.2.1.2.4.3(REHEATER-I OUTLET HEADER (PGMA-15236)) | 206814149
REHEATER VERT PLATEN OUTLET HEADER RHH (PGMA-15278) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 15278 | 1.9.2.1.2.4(Reheater Headers (PG-15)) | 206814150
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 15278 | 1.9.2.1.2.4.4(REHEATER VERT PLATEN OUTLET HEADER RHH (PGMA-15278)) | 206814151
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 15278 | 1.9.2.1.2.4.4(REHEATER VERT PLATEN OUTLET HEADER RHH (PGMA-15278)) | 206814152
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 15278 | 1.9.2.1.2.4.4(REHEATER VERT PLATEN OUTLET HEADER RHH (PGMA-15278)) | 206814153
Reheater Coils and Walls (PG-16) | SUP | 2023-01-25 08:00 | 2024-06-28 17:00 |  |  |  | PG16 | 1.9.2.1.2(Super Heaters and Re-Heaters ) | 206814154
RH VER PLATEN FRONT COIL ASY LEFT (PGMA-16079) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 16079 | 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | 206814155
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 16079 | 1.9.2.1.2.5.1(RH VER PLATEN FRONT COIL ASY LEFT (PGMA-16079)) | 206814156
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 16079 | 1.9.2.1.2.5.1(RH VER PLATEN FRONT COIL ASY LEFT (PGMA-16079)) | 206814157
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 16079 | 1.9.2.1.2.5.1(RH VER PLATEN FRONT COIL ASY LEFT (PGMA-16079)) | 206814158
LTRH UPPER ASSY (PGMA-16201) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 16201 | 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | 206814159
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 16201 | 1.9.2.1.2.5.2(LTRH UPPER ASSY (PGMA-16201)) | 206814160
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 16201 | 1.9.2.1.2.5.2(LTRH UPPER ASSY (PGMA-16201)) | 206814161
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 16201 | 1.9.2.1.2.5.2(LTRH UPPER ASSY (PGMA-16201)) | 206814162
LTRH INTERMEDIATE ASSY (PGMA-16202) | SUP | 2023-01-25 08:00 | 2024-04-28 17:00 |  |  |  | 16202 | 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | 206814163
Engineering | ENG | 2023-01-25 08:00 | 2023-09-05 17:00 |  |  |  | 16202 | 1.9.2.1.2.5.3(LTRH INTERMEDIATE ASSY (PGMA-16202)) | 206814164
Manufacturing | MFG | 2023-09-06 08:00 | 2024-03-29 17:00 |  |  |  | 16202 | 1.9.2.1.2.5.3(LTRH INTERMEDIATE ASSY (PGMA-16202)) | 206814165
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 16202 | 1.9.2.1.2.5.3(LTRH INTERMEDIATE ASSY (PGMA-16202)) | 206814166
LTRH coils lower (PGMA-16203) | SUP | 2023-01-25 08:00 | 2024-06-28 17:00 |  |  |  | 16203 | 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | 206814167
Engineering | ENG | 2023-01-25 08:00 | 2023-10-06 17:00 |  |  |  | 16203 | 1.9.2.1.2.5.4(LTRH coils lower (PGMA-16203)) | 206814168
Manufacturing | MFG | 2023-10-07 08:00 | 2024-05-29 17:00 |  |  |  | 16203 | 1.9.2.1.2.5.4(LTRH coils lower (PGMA-16203)) | 206814169
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  | 16203 | 1.9.2.1.2.5.4(LTRH coils lower (PGMA-16203)) | 206814170
LTRH PENDANT ASSY WITH OUTLET TERM TUBES (PGMA-16270) | SUP | 2023-01-25 08:00 | 2024-06-28 17:00 |  |  |  | 16270 | 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | 206814171
Engineering | ENG | 2023-01-25 08:00 | 2023-10-06 17:00 |  |  |  | 16270 | 1.9.2.1.2.5.5(LTRH PENDANT ASSY WITH OUTLET TERM TUBES (PGMA-16270)) | 206814172
Manufacturing | MFG | 2023-10-07 08:00 | 2024-05-29 17:00 |  |  |  | 16270 | 1.9.2.1.2.5.5(LTRH PENDANT ASSY WITH OUTLET TERM TUBES (PGMA-16270)) | 206814173
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  | 16270 | 1.9.2.1.2.5.5(LTRH PENDANT ASSY WITH OUTLET TERM TUBES (PGMA-16270)) | 206814174
RHVERTICAL PLATEN FRONT COIL ASSY. (RIT) (PGMA-16379) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 16379 | 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | 206814175
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 16379 | 1.9.2.1.2.5.6(RHVERTICAL PLATEN FRONT COIL ASSY. (RIT) (PGMA-16379)) | 206814176
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 16379 | 1.9.2.1.2.5.6(RHVERTICAL PLATEN FRONT COIL ASSY. (RIT) (PGMA-16379)) | 206814177
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 16379 | 1.9.2.1.2.5.6(RHVERTICAL PLATEN FRONT COIL ASSY. (RIT) (PGMA-16379)) | 206814178
Reheater Components (PG-17) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | PG17 | 1.9.2.1.2(Super Heaters and Re-Heaters ) | 206814179
LINK TO RH DESUPERHEATER (PGMA-17174) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17174 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814180
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17174 | 1.9.2.1.2.6.1(LINK TO RH DESUPERHEATER (PGMA-17174)) | 206814181
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17174 | 1.9.2.1.2.6.1(LINK TO RH DESUPERHEATER (PGMA-17174)) | 206814182
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17174 | 1.9.2.1.2.6.1(LINK TO RH DESUPERHEATER (PGMA-17174)) | 206814183
Rh Hdr Supports & Suspensions Above Roof-DD (PGMA-17304) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 17304 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814184
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 17304 | 1.9.2.1.2.6.2(Rh Hdr Supports & Suspensions Above Roof-DD (PGMA-17304)) | 206814185
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 17304 | 1.9.2.1.2.6.2(Rh Hdr Supports & Suspensions Above Roof-DD (PGMA-17304)) | 206814186
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 17304 | 1.9.2.1.2.6.2(Rh Hdr Supports & Suspensions Above Roof-DD (PGMA-17304)) | 206814187
RH LINKS SUPPORTS-DD (PGMA-17306) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17306 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814188
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17306 | 1.9.2.1.2.6.3(RH LINKS SUPPORTS-DD (PGMA-17306)) | 206814189
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17306 | 1.9.2.1.2.6.3(RH LINKS SUPPORTS-DD (PGMA-17306)) | 206814190
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17306 | 1.9.2.1.2.6.3(RH LINKS SUPPORTS-DD (PGMA-17306)) | 206814191
RH FRONT COIL SUSPENSION-DD (PGMA-17319) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 17319 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814192
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 17319 | 1.9.2.1.2.6.4(RH FRONT COIL SUSPENSION-DD (PGMA-17319)) | 206814193
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 17319 | 1.9.2.1.2.6.4(RH FRONT COIL SUSPENSION-DD (PGMA-17319)) | 206814194
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 17319 | 1.9.2.1.2.6.4(RH FRONT COIL SUSPENSION-DD (PGMA-17319)) | 206814195
SC SPACER TUBES FOR RH. COIL-OS (PGMA-17407) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17407 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814196
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17407 | 1.9.2.1.2.6.5(SC SPACER TUBES FOR RH. COIL-OS (PGMA-17407)) | 206814197
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17407 | 1.9.2.1.2.6.5(SC SPACER TUBES FOR RH. COIL-OS (PGMA-17407)) | 206814198
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17407 | 1.9.2.1.2.6.5(SC SPACER TUBES FOR RH. COIL-OS (PGMA-17407)) | 206814199
RH HEADER SUPPORTS-SHOP (PGMA-17504) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 17504 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814200
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 17504 | 1.9.2.1.2.6.6(RH HEADER SUPPORTS-SHOP (PGMA-17504)) | 206814201
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 17504 | 1.9.2.1.2.6.6(RH HEADER SUPPORTS-SHOP (PGMA-17504)) | 206814202
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 17504 | 1.9.2.1.2.6.6(RH HEADER SUPPORTS-SHOP (PGMA-17504)) | 206814203
RH LINKS SUPPORTS-SHOP (PGMA-17506) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17506 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814204
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17506 | 1.9.2.1.2.6.7(RH LINKS SUPPORTS-SHOP (PGMA-17506)) | 206814205
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17506 | 1.9.2.1.2.6.7(RH LINKS SUPPORTS-SHOP (PGMA-17506)) | 206814206
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17506 | 1.9.2.1.2.6.7(RH LINKS SUPPORTS-SHOP (PGMA-17506)) | 206814207
STEAM COOLED SPACER TUBES FOR RH. COIL (PGMA-17807) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 17807 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814208
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 17807 | 1.9.2.1.2.6.8(STEAM COOLED SPACER TUBES FOR RH. COIL (PGMA-17807)) | 206814209
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 17807 | 1.9.2.1.2.6.8(STEAM COOLED SPACER TUBES FOR RH. COIL (PGMA-17807)) | 206814210
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 17807 | 1.9.2.1.2.6.8(STEAM COOLED SPACER TUBES FOR RH. COIL (PGMA-17807)) | 206814211
REHEATER DE-SUPER HEATER (PGMA-17900) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17900 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814212
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17900 | 1.9.2.1.2.6.9(REHEATER DE-SUPER HEATER (PGMA-17900)) | 206814213
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17900 | 1.9.2.1.2.6.9(REHEATER DE-SUPER HEATER (PGMA-17900)) | 206814214
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17900 | 1.9.2.1.2.6.9(REHEATER DE-SUPER HEATER (PGMA-17900)) | 206814215
RH HEADER SUPPORTS (PGMA-17904) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 17904 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814216
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 17904 | 1.9.2.1.2.6.10(RH HEADER SUPPORTS (PGMA-17904)) | 206814217
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 17904 | 1.9.2.1.2.6.10(RH HEADER SUPPORTS (PGMA-17904)) | 206814218
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 17904 | 1.9.2.1.2.6.10(RH HEADER SUPPORTS (PGMA-17904)) | 206814219
RH LINKS SUPPORTS (PGMA-17906) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17906 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814220
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17906 | 1.9.2.1.2.6.11(RH LINKS SUPPORTS (PGMA-17906)) | 206814221
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17906 | 1.9.2.1.2.6.11(RH LINKS SUPPORTS (PGMA-17906)) | 206814222
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17906 | 1.9.2.1.2.6.11(RH LINKS SUPPORTS (PGMA-17906)) | 206814223
RH FRONT COIL SUSPENSION (PGMA-17919) | SUP | 2023-01-25 08:00 | 2024-02-26 17:00 |  |  |  | 17919 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814224
Engineering | ENG | 2023-01-25 08:00 | 2023-08-04 17:00 |  |  |  | 17919 | 1.9.2.1.2.6.12(RH FRONT COIL SUSPENSION (PGMA-17919)) | 206814225
Manufacturing | MFG | 2023-08-05 08:00 | 2024-01-27 17:00 |  |  |  | 17919 | 1.9.2.1.2.6.12(RH FRONT COIL SUSPENSION (PGMA-17919)) | 206814226
Dispatch | DIS | 2024-01-28 08:00 | 2024-02-26 17:00 |  |  |  | 17919 | 1.9.2.1.2.6.12(RH FRONT COIL SUSPENSION (PGMA-17919)) | 206814227
RH IMPORTED ELECTRODES (PGMA-17991) | SUP | 2023-01-25 08:00 | 2024-03-29 17:00 |  |  |  | 17991 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814228
Engineering | ENG | 2023-01-25 08:00 | 2023-08-14 17:00 |  |  |  | 17991 | 1.9.2.1.2.6.13(RH IMPORTED ELECTRODES (PGMA-17991)) | 206814229
Manufacturing | MFG | 2023-08-15 08:00 | 2024-02-28 17:00 |  |  |  | 17991 | 1.9.2.1.2.6.13(RH IMPORTED ELECTRODES (PGMA-17991)) | 206814230
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 17991 | 1.9.2.1.2.6.13(RH IMPORTED ELECTRODES (PGMA-17991)) | 206814231
RH SITE ELECTRODES IMPORTED (PGMA-17992) | SUP | 2023-01-25 08:00 | 2024-09-27 17:00 |  |  |  | 17992 | 1.9.2.1.2.6(Reheater Components (PG-17)) | 206814232
Engineering | ENG | 2023-01-25 08:00 | 2023-11-20 17:00 |  |  |  | 17992 | 1.9.2.1.2.6.14(RH SITE ELECTRODES IMPORTED (PGMA-17992)) | 206814233
Manufacturing | MFG | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  | 17992 | 1.9.2.1.2.6.14(RH SITE ELECTRODES IMPORTED (PGMA-17992)) | 206814234
Dispatch | DIS | 2024-08-29 08:00 | 2024-09-27 17:00 |  |  |  | 17992 | 1.9.2.1.2.6.14(RH SITE ELECTRODES IMPORTED (PGMA-17992)) | 206814235
Erection | ERC | 2024-07-26 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.2(Water Circulation System, Super Heaters and Re-Heaters ) | 206814236
Erection: Separator, Storage Tanks including Supports | ERC | 2024-07-26 08:00 | 2024-09-23 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814237
Erection & commissioning of Boiler Re-circulation pump | ERC | 2025-01-28 08:00 | 2025-07-21 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814238
Erection: PP complete | ERC | 2025-06-10 17:00 | 2025-06-10 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814239
Water Circulation system, Super Heaters and Re-Heaters | ERC | 2024-08-30 08:00 | 2025-11-29 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814240
BACKPASS | ERC | 2024-08-30 08:00 | 2025-06-10 17:00 |  |  |  |  | 1.9.2.2.4(Water Circulation system, Super Heaters and Re-Heaters ) | 206814241
BACKPASS: Erection of Pressure Part Support Steel and Hanger Rods | ERC | 2024-08-30 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814242
BACKPASS: Erection of Headers, Links and Connecting Tubes above the Roof Line. | ERC | 2024-09-29 08:00 | 2024-11-12 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814243
BACKPASS: Erection of BP Front Outlet Header and BP Front Screen Tubes | ERC | 2024-11-10 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814244
BACKPASS: Erection of Backpass Front Fin Weld Panel | ERC | 2024-11-22 08:00 | 2024-12-03 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814245
Back pass of LTRH Outlet Header and Terminal Tubes | ERC | 2024-12-04 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814246
Back pass of Backpass SC Support Outlet Header and Hanger Tubes | ERC | 2024-12-22 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814247
Back pass of Finish SH Inlet Header, SH Outlet Header and Terminal Tubes | ERC | 2025-01-06 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814248
Back pass of BP Upper Side Fin Weld Panels | ERC | 2025-01-12 08:00 | 2025-01-20 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814249
Back pass of BP Roof Panels and BP Hanger tubes | ERC | 2025-01-21 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814250
Back pass of LTRH Pendant Assembly | ERC | 2025-02-08 08:00 | 2025-02-19 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814251
Back pass of BP Rear FW Panels and BP Lower Side FW Panels | ERC | 2025-02-20 08:00 | 2025-03-03 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814252
Back pass of LTRH Upper and Upper Intermediate Horizontal Assemblies | ERC | 2025-03-04 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814253
Back pass of LTRH Lower and Lower Intermediate Horizontal Assemblies | ERC | 2025-03-16 08:00 | 2025-03-27 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814254
Back pass of LTRH Inlet Header Assembly | ERC | 2025-03-28 08:00 | 2025-04-06 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814255
Back pass of Economizer Outlet Header Assembly | ERC | 2025-04-07 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814256
Back pass of Economizer Assemblies | ERC | 2025-04-11 08:00 | 2025-04-24 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814257
Back pass of Economizer Outlet Link | ERC | 2025-04-25 08:00 | 2025-04-30 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814258
Back pass of BP Lower Headers | ERC | 2025-05-01 08:00 | 2025-05-12 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814259
Back pass of Economizer Inlet Header | ERC | 2025-05-13 08:00 | 2025-05-21 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814260
BACKPASS: Final weld out of BP | ERC | 2025-05-22 08:00 | 2025-06-10 17:00 |  |  |  |  | 1.9.2.2.4.1(BACKPASS) | 206814261
FURNACE PASS AND BP EXTENDED | ERC | 2024-11-03 08:00 | 2025-06-05 17:00 |  |  |  |  | 1.9.2.2.4(Water Circulation system, Super Heaters and Re-Heaters ) | 206814262
FURNACE PASS AND BP EXTENDED: Erection of Superheater Connecting Pipe | ERC | 2024-11-03 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814263
FURNACE PASS AND BP EXTENDED: Erection of BP Extended Side Inlet Headers | ERC | 2024-11-14 08:00 | 2024-11-22 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814264
FURNACE PASS AND BP EXTENDED: Erection of BP Extended Side Panels | ERC | 2024-11-18 08:00 | 2024-12-01 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814265
FURNACE PASS AND BP EXTENDED: Erection of Furnace Roof Panels | ERC | 2024-11-30 08:00 | 2024-12-09 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814266
FURNACE PASS AND BP Back pass of Furnace Upper Sidewall Panels | ERC | 2024-12-10 08:00 | 2024-12-19 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814267
FURNACE PASS AND BP Back pass of Finishing Superheater Rear Assembly | ERC | 2024-12-17 08:00 | 2024-12-28 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814268
FURNACE PASS AND BP Back pass of Finishing Superheater Front Assembly | ERC | 2024-12-26 08:00 | 2025-01-06 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814269
FURNACE PASS AND BP Back pass of Furnace Rear Screen Tubes and Furnace Rear Hanger tubes | ERC | 2025-01-04 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814270
FURNACE PASS AND BP Back pass of Finish Reheater Inlet Header and Finish Reheater Outlet Header Assemblies | ERC | 2025-01-13 08:00 | 2025-01-24 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814271
FURNACE PASS AND BP Back pass of SH Platen Inlet Header and SH Platen Outlet Assemblies | ERC | 2025-01-20 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814272
FURNACE PASS AND BP Back pass of Finishing Reheater Assembly | ERC | 2025-01-29 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814273
FURNACE PASS AND BP Back pass of SH Platen Assembly | ERC | 2025-02-09 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814274
FURNACE PASS AND BP Back pass of Furnace Upper Front Panels | ERC | 2025-02-18 08:00 | 2025-03-01 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814275
FURNACE PASS AND BP Back pass of Backpass Extended Side Floor Assembly | ERC | 2025-02-25 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814276
FURNACE PASS AND BP Back pass of Furnace Rear Arch | ERC | 2025-03-06 08:00 | 2025-03-17 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814277
FURNACE PASS AND BP Back pass of Buckstays and levellers | ERC | 2025-03-15 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814278
FURNACE PASS AND BP levellers of SOFA panel | ERC | 2025-03-22 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814279
FURNACE PASS AND BP levellers of Transition Headers | ERC | 2025-03-31 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814280
FURNACE PASS AND BP levellers of windbox and burner panel | ERC | 2025-03-27 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814281
FURNACE PASS AND BP winebox of Upper Spiral Wall Panels | ERC | 2025-04-16 08:00 | 2025-04-25 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814282
FURNACE PASS AND BP winebox of Lower Spiral Walls and Ring Header | ERC | 2025-04-14 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814283
FURNACE PASS AND BP winebox of Hopper panel | ERC | 2025-04-22 08:00 | 2025-05-11 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814284
FURNACE PASS AND BP EXTENDED: Final welding of the furnace | ERC | 2025-05-12 08:00 | 2025-06-05 17:00 |  |  |  |  | 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | 206814285
Erection of Boiler Fill Piping and Trim Piping | ERC | 2025-04-05 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.9.2.2.4(Water Circulation system, Super Heaters and Re-Heaters ) | 206814286
Erection of Startup system and Safety Valve (Required for Drainable HT) | ERC | 2025-04-05 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.9.2.2.4(Water Circulation system, Super Heaters and Re-Heaters ) | 206814287
Erection: Balance welding of PP for Non Drainable HT | ERC | 2025-06-14 08:00 | 2025-11-29 17:00 |  |  |  |  | 1.9.2.2.4(Water Circulation system, Super Heaters and Re-Heaters ) | 206814288
DRAINABLE Hydro TEST | ERC | 2025-06-11 08:00 | 2025-06-19 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814289
DRAINABLE Hydro TEST: Air fill test | ERC | 2025-06-11 08:00 | 2025-06-13 17:00 |  |  |  |  | 1.9.2.2.5(DRAINABLE Hydro TEST) | 206814290
DRAINABLE Hydro TEST: Readiness of Boiler for HT | ERC | 2025-06-14 08:00 | 2025-06-19 17:00 |  |  |  |  | 1.9.2.2.5(DRAINABLE Hydro TEST) | 206814291
Non Drainable HT | ERC | 2025-11-29 17:00 | 2025-11-29 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814292
FOR CHEMICAL CLEANING AND EDTA | ERC | 2026-01-05 08:00 | 2026-01-24 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814293
FOR CHEMICAL CLEANING AND EDTA: Placememnt of temporary tanks | ERC | 2026-01-05 08:00 | 2026-01-09 17:00 |  |  |  |  | 1.9.2.2.7(FOR CHEMICAL CLEANING AND EDTA) | 206814294
FOR CHEMICAL CLEANING AND EDTA: Erection of temporary piping for bulk chemicals | ERC | 2026-01-10 08:00 | 2026-01-24 17:00 |  |  |  |  | 1.9.2.2.7(FOR CHEMICAL CLEANING AND EDTA) | 206814295
FOR STEAM BLOWING | ERC | 2026-02-08 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.2.2(Erection) | 206814296
FOR STEAM BLOWING: Erection of temporary piping | ERC | 2026-02-08 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.2.2.8(FOR STEAM BLOWING) | 206814297
Soot Blower | OTH | 2023-08-22 08:00 | 2026-01-25 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206814298
Supply (BHEL TRY) | SUP | 2023-08-22 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.9.3(Soot Blower) | 206814299
Soot Blowers (PG-20) | SUP | 2023-08-22 08:00 | 2025-07-29 17:00 |  |  |  | PG20 | 1.9.3.1(Supply (BHEL TRY)) | 206814300
LONG RETRACTABLE SOO (PGMA-20051) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 20051 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814301
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 20051 | 1.9.3.1.1.1(LONG RETRACTABLE SOO (PGMA-20051)) | 206814302
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 20051 | 1.9.3.1.1.1(LONG RETRACTABLE SOO (PGMA-20051)) | 206814303
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 20051 | 1.9.3.1.1.1(LONG RETRACTABLE SOO (PGMA-20051)) | 206814304
WALL BOX NON PRESSUR (PGMA-20054) | SUP | 2023-09-27 08:00 | 2025-04-29 17:00 |  |  |  | 20054 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814305
Engineering | ENG | 2023-09-27 08:00 | 2024-06-21 17:00 |  |  |  | 20054 | 1.9.3.1.1.2(WALL BOX NON PRESSUR (PGMA-20054)) | 206814306
Manufacturing | MFG | 2024-06-22 08:00 | 2025-03-30 17:00 |  |  |  | 20054 | 1.9.3.1.1.2(WALL BOX NON PRESSUR (PGMA-20054)) | 206814307
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 20054 | 1.9.3.1.1.2(WALL BOX NON PRESSUR (PGMA-20054)) | 206814308
WALL DESLAGGER RW5E (PGMA-20201) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 20201 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814309
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 20201 | 1.9.3.1.1.3(WALL DESLAGGER RW5E (PGMA-20201)) | 206814310
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 20201 | 1.9.3.1.1.3(WALL DESLAGGER RW5E (PGMA-20201)) | 206814311
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 20201 | 1.9.3.1.1.3(WALL DESLAGGER RW5E (PGMA-20201)) | 206814312
WALL BOX NON PRESSUR (PGMA-20204) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 20204 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814313
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 20204 | 1.9.3.1.1.4(WALL BOX NON PRESSUR (PGMA-20204)) | 206814314
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 20204 | 1.9.3.1.1.4(WALL BOX NON PRESSUR (PGMA-20204)) | 206814315
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 20204 | 1.9.3.1.1.4(WALL BOX NON PRESSUR (PGMA-20204)) | 206814316
DA HEAD VALVE ASSY (PGMA-20511) | SUP | 2023-11-06 08:00 | 2025-06-29 17:00 |  |  |  | 20511 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814317
Engineering | ENG | 2023-11-06 08:00 | 2024-08-13 17:00 |  |  |  | 20511 | 1.9.3.1.1.5(DA HEAD VALVE ASSY (PGMA-20511)) | 206814318
Manufacturing | MFG | 2024-08-14 08:00 | 2025-05-30 17:00 |  |  |  | 20511 | 1.9.3.1.1.5(DA HEAD VALVE ASSY (PGMA-20511)) | 206814319
Dispatch | DIS | 2025-05-31 08:00 | 2025-06-29 17:00 |  |  |  | 20511 | 1.9.3.1.1.5(DA HEAD VALVE ASSY (PGMA-20511)) | 206814320
WALL BOX NON PRESSUR (PGMA-20794) | SUP | 2023-09-27 08:00 | 2025-04-29 17:00 |  |  |  | 20794 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814321
Engineering | ENG | 2023-09-27 08:00 | 2024-06-21 17:00 |  |  |  | 20794 | 1.9.3.1.1.6(WALL BOX NON PRESSUR (PGMA-20794)) | 206814322
Manufacturing | MFG | 2024-06-22 08:00 | 2025-03-30 17:00 |  |  |  | 20794 | 1.9.3.1.1.6(WALL BOX NON PRESSUR (PGMA-20794)) | 206814323
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 20794 | 1.9.3.1.1.6(WALL BOX NON PRESSUR (PGMA-20794)) | 206814324
TEMP PROBE DUPLEX WI (PGMA-20962) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 20962 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814325
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 20962 | 1.9.3.1.1.7(TEMP PROBE DUPLEX WI (PGMA-20962)) | 206814326
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 20962 | 1.9.3.1.1.7(TEMP PROBE DUPLEX WI (PGMA-20962)) | 206814327
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 20962 | 1.9.3.1.1.7(TEMP PROBE DUPLEX WI (PGMA-20962)) | 206814328
SOOT BLOWER COMMISSIONING SPARES (PGMA-20988) | SUP | 2023-11-21 08:00 | 2025-07-29 17:00 |  |  |  | 20988 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814329
Engineering | ENG | 2023-11-21 08:00 | 2024-09-10 17:00 |  |  |  | 20988 | 1.9.3.1.1.8(SOOT BLOWER COMMISSIONING SPARES (PGMA-20988)) | 206814330
Manufacturing | MFG | 2024-09-11 08:00 | 2025-06-29 17:00 |  |  |  | 20988 | 1.9.3.1.1.8(SOOT BLOWER COMMISSIONING SPARES (PGMA-20988)) | 206814331
Dispatch | DIS | 2025-06-30 08:00 | 2025-07-29 17:00 |  |  |  | 20988 | 1.9.3.1.1.8(SOOT BLOWER COMMISSIONING SPARES (PGMA-20988)) | 206814332
SPECIAL TOOLS FOR SO (PGMA-20998) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 20998 | 1.9.3.1.1(Soot Blowers (PG-20)) | 206814333
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 20998 | 1.9.3.1.1.9(SPECIAL TOOLS FOR SO (PGMA-20998)) | 206814334
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 20998 | 1.9.3.1.1.9(SPECIAL TOOLS FOR SO (PGMA-20998)) | 206814335
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 20998 | 1.9.3.1.1.9(SPECIAL TOOLS FOR SO (PGMA-20998)) | 206814336
Soot Blowing system (PG-21) | SUP | 2023-09-12 08:00 | 2025-09-27 17:00 |  |  |  | PG21 | 1.9.3.1(Supply (BHEL TRY)) | 206814337
SOOT BLOWER PIPING AND FITTINGS (PGMA-21600) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21600 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814338
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21600 | 1.9.3.1.2.1(SOOT BLOWER PIPING AND FITTINGS (PGMA-21600)) | 206814339
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21600 | 1.9.3.1.2.1(SOOT BLOWER PIPING AND FITTINGS (PGMA-21600)) | 206814340
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21600 | 1.9.3.1.2.1(SOOT BLOWER PIPING AND FITTINGS (PGMA-21600)) | 206814341
SOOTBLOWER PIPING SUPPORTS (PGMA-21601) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21601 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814342
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21601 | 1.9.3.1.2.2(SOOTBLOWER PIPING SUPPORTS (PGMA-21601)) | 206814343
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21601 | 1.9.3.1.2.2(SOOTBLOWER PIPING SUPPORTS (PGMA-21601)) | 206814344
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21601 | 1.9.3.1.2.2(SOOTBLOWER PIPING SUPPORTS (PGMA-21601)) | 206814345
SOOT BLOWER PIPING & FITTINGS - DD (PGMA-21602) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21602 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814346
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21602 | 1.9.3.1.2.3(SOOT BLOWER PIPING & FITTINGS - DD (PGMA-21602)) | 206814347
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21602 | 1.9.3.1.2.3(SOOT BLOWER PIPING & FITTINGS - DD (PGMA-21602)) | 206814348
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21602 | 1.9.3.1.2.3(SOOT BLOWER PIPING & FITTINGS - DD (PGMA-21602)) | 206814349
SOOT BLOWER PIPING & FITTINGS - BOI (PGMA-21603) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21603 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814350
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21603 | 1.9.3.1.2.4(SOOT BLOWER PIPING & FITTINGS - BOI (PGMA-21603)) | 206814351
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21603 | 1.9.3.1.2.4(SOOT BLOWER PIPING & FITTINGS - BOI (PGMA-21603)) | 206814352
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21603 | 1.9.3.1.2.4(SOOT BLOWER PIPING & FITTINGS - BOI (PGMA-21603)) | 206814353
SOOT BLOWER PIPING SUPPORTS - OS (PGMA-21604) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21604 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814354
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21604 | 1.9.3.1.2.5(SOOT BLOWER PIPING SUPPORTS - OS (PGMA-21604)) | 206814355
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21604 | 1.9.3.1.2.5(SOOT BLOWER PIPING SUPPORTS - OS (PGMA-21604)) | 206814356
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21604 | 1.9.3.1.2.5(SOOT BLOWER PIPING SUPPORTS - OS (PGMA-21604)) | 206814357
Soot Blower Piping Supports - Dd (PGMA-21605) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21605 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814358
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21605 | 1.9.3.1.2.6(Soot Blower Piping Supports - Dd (PGMA-21605)) | 206814359
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21605 | 1.9.3.1.2.6(Soot Blower Piping Supports - Dd (PGMA-21605)) | 206814360
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21605 | 1.9.3.1.2.6(Soot Blower Piping Supports - Dd (PGMA-21605)) | 206814361
Soot Blower Piping Supports - BOI (PGMA-21606) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21606 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814362
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21606 | 1.9.3.1.2.7(Soot Blower Piping Supports - BOI (PGMA-21606)) | 206814363
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21606 | 1.9.3.1.2.7(Soot Blower Piping Supports - BOI (PGMA-21606)) | 206814364
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21606 | 1.9.3.1.2.7(Soot Blower Piping Supports - BOI (PGMA-21606)) | 206814365
BULKED BPS COMPONENTS FOR SB PIPING (PGMA-21700) | SUP | 2023-09-27 08:00 | 2025-04-29 17:00 |  |  |  | 21700 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814366
Engineering | ENG | 2023-09-27 08:00 | 2024-06-21 17:00 |  |  |  | 21700 | 1.9.3.1.2.8(BULKED BPS COMPONENTS FOR SB PIPING (PGMA-21700)) | 206814367
Manufacturing | MFG | 2024-06-22 08:00 | 2025-03-30 17:00 |  |  |  | 21700 | 1.9.3.1.2.8(BULKED BPS COMPONENTS FOR SB PIPING (PGMA-21700)) | 206814368
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 21700 | 1.9.3.1.2.8(BULKED BPS COMPONENTS FOR SB PIPING (PGMA-21700)) | 206814369
SB VALVES (BHEL) (PGMA-21800) | SUP | 2023-09-27 08:00 | 2025-04-29 17:00 |  |  |  | 21800 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814370
Engineering | ENG | 2023-09-27 08:00 | 2024-06-21 17:00 |  |  |  | 21800 | 1.9.3.1.2.9(SB VALVES (BHEL) (PGMA-21800)) | 206814371
Manufacturing | MFG | 2024-06-22 08:00 | 2025-03-30 17:00 |  |  |  | 21800 | 1.9.3.1.2.9(SB VALVES (BHEL) (PGMA-21800)) | 206814372
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 21800 | 1.9.3.1.2.9(SB VALVES (BHEL) (PGMA-21800)) | 206814373
SB VALVES (SUB DELIVERY) (PGMA-21825) | SUP | 2023-10-17 08:00 | 2025-05-30 17:00 |  |  |  | 21825 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814374
Ordering & Engineering | ENG | 2023-10-17 08:00 | 2024-07-22 17:00 |  |  |  | 21825 | 1.9.3.1.2.10(SB VALVES (SUB DELIVERY) (PGMA-21825)) | 206814375
Manufacturing | MFG | 2024-07-23 08:00 | 2025-04-30 17:00 |  |  |  | 21825 | 1.9.3.1.2.10(SB VALVES (SUB DELIVERY) (PGMA-21825)) | 206814376
Dispatch | DIS | 2025-05-01 08:00 | 2025-05-30 17:00 |  |  |  | 21825 | 1.9.3.1.2.10(SB VALVES (SUB DELIVERY) (PGMA-21825)) | 206814377
SOOT BLOWER SAFETY VALVE (BHEL) (PGMA-21850) | SUP | 2023-10-17 08:00 | 2025-05-30 17:00 |  |  |  | 21850 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814378
Engineering | ENG | 2023-10-17 08:00 | 2024-07-22 17:00 |  |  |  | 21850 | 1.9.3.1.2.11(SOOT BLOWER SAFETY VALVE (BHEL) (PGMA-21850)) | 206814379
Manufacturing | MFG | 2024-07-23 08:00 | 2025-04-30 17:00 |  |  |  | 21850 | 1.9.3.1.2.11(SOOT BLOWER SAFETY VALVE (BHEL) (PGMA-21850)) | 206814380
Dispatch | DIS | 2025-05-01 08:00 | 2025-05-30 17:00 |  |  |  | 21850 | 1.9.3.1.2.11(SOOT BLOWER SAFETY VALVE (BHEL) (PGMA-21850)) | 206814381
COMMG SPARES FOR SB SAFETY VALVE (PGMA-21987) | SUP | 2023-12-09 08:00 | 2025-09-27 17:00 |  |  |  | 21987 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814382
Engineering | ENG | 2023-12-09 08:00 | 2024-10-23 17:00 |  |  |  | 21987 | 1.9.3.1.2.12(COMMG SPARES FOR SB SAFETY VALVE (PGMA-21987)) | 206814383
Manufacturing | MFG | 2024-10-24 08:00 | 2025-08-28 17:00 |  |  |  | 21987 | 1.9.3.1.2.12(COMMG SPARES FOR SB SAFETY VALVE (PGMA-21987)) | 206814384
Dispatch | DIS | 2025-08-29 08:00 | 2025-09-27 17:00 |  |  |  | 21987 | 1.9.3.1.2.12(COMMG SPARES FOR SB SAFETY VALVE (PGMA-21987)) | 206814385
COMMG SPARES FOR SUB DELIVERIES (PGMA-21988) | SUP | 2023-12-09 08:00 | 2025-09-27 17:00 |  |  |  | 21988 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814386
Engineering | ENG | 2023-12-09 08:00 | 2024-10-23 17:00 |  |  |  | 21988 | 1.9.3.1.2.13(COMMG SPARES FOR SUB DELIVERIES (PGMA-21988)) | 206814387
Manufacturing | MFG | 2024-10-24 08:00 | 2025-08-28 17:00 |  |  |  | 21988 | 1.9.3.1.2.13(COMMG SPARES FOR SUB DELIVERIES (PGMA-21988)) | 206814388
Dispatch | DIS | 2025-08-29 08:00 | 2025-09-27 17:00 |  |  |  | 21988 | 1.9.3.1.2.13(COMMG SPARES FOR SUB DELIVERIES (PGMA-21988)) | 206814389
IMPORTED ELECTRODES (PGMA-21992) | SUP | 2023-09-12 08:00 | 2025-03-30 17:00 |  |  |  | 21992 | 1.9.3.1.2(Soot Blowing system (PG-21)) | 206814390
Engineering | ENG | 2023-09-12 08:00 | 2024-05-30 17:00 |  |  |  | 21992 | 1.9.3.1.2.14(IMPORTED ELECTRODES (PGMA-21992)) | 206814391
Manufacturing | MFG | 2024-05-31 08:00 | 2025-02-28 17:00 |  |  |  | 21992 | 1.9.3.1.2.14(IMPORTED ELECTRODES (PGMA-21992)) | 206814392
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 21992 | 1.9.3.1.2.14(IMPORTED ELECTRODES (PGMA-21992)) | 206814393
Erection | ERC | 2025-06-30 08:00 | 2026-01-25 17:00 |  |  |  |  | 1.9.3(Soot Blower) | 206814394
Erection of wall blowers, soot blowers & piping | ERC | 2025-06-30 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.9.3.2(Erection) | 206814395
Mineral wool for soot blowing piping | ERC | 2025-12-27 08:00 | 2026-01-25 17:00 |  |  |  |  | 1.9.3.2(Erection) | 206814396
Lining and Insulation System | ERC | 2023-01-25 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206814397
Supply (BHEL TRY) | SUP | 2023-01-25 08:00 | 2025-04-27 17:00 |  |  |  |  | 1.9.4(Lining and Insulation System) | 206814398
Seal Boxes (PG-09) | SUP | 2023-06-04 08:00 | 2024-09-26 17:00 |  |  |  | PG09 | 1.9.4.1(Supply (BHEL TRY)) | 206814399
MATERIAL FOR INSTRUMENT INSERTS (PGMA-9003) | SUP | 2023-06-04 08:00 | 2024-09-26 17:00 |  |  |  | 9003 | 1.9.4.1.1(Seal Boxes (PG-09)) | 206814400
Engineering | ENG | 2023-06-04 08:00 | 2024-02-23 17:00 |  |  |  | 09003 | 1.9.4.1.1.1(MATERIAL FOR INSTRUMENT INSERTS (PGMA-9003)) | 206814401
Manufacturing | MFG | 2024-02-24 08:00 | 2024-08-27 17:00 |  |  |  | 09003 | 1.9.4.1.1.1(MATERIAL FOR INSTRUMENT INSERTS (PGMA-9003)) | 206814402
Dispatch | DIS | 2024-08-28 08:00 | 2024-09-26 17:00 |  |  |  | 09003 | 1.9.4.1.1.1(MATERIAL FOR INSTRUMENT INSERTS (PGMA-9003)) | 206814403
Seal boxes for Furnace Openings (PGMA-9004) | SUP | 2023-06-12 08:00 | 2024-09-26 17:00 |  |  |  | 9004 | 1.9.4.1.1(Seal Boxes (PG-09)) | 206814404
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 09004 | 1.9.4.1.1.2(Seal boxes for Furnace Openings (PGMA-9004)) | 206814405
Manufacturing | MFG | 2024-02-29 08:00 | 2024-08-27 17:00 |  |  |  | 09004 | 1.9.4.1.1.2(Seal boxes for Furnace Openings (PGMA-9004)) | 206814406
Dispatch | DIS | 2024-08-28 08:00 | 2024-09-26 17:00 |  |  |  | 09004 | 1.9.4.1.1.2(Seal boxes for Furnace Openings (PGMA-9004)) | 206814407
Seal boxes for Instrument Tappings (PGMA-9005) | SUP | 2023-06-04 08:00 | 2024-09-26 17:00 |  |  |  | 9005 | 1.9.4.1.1(Seal Boxes (PG-09)) | 206814408
Engineering | ENG | 2023-06-04 08:00 | 2024-02-28 17:00 |  |  |  | 09005 | 1.9.4.1.1.3(Seal boxes for Instrument Tappings (PGMA-9005)) | 206814409
Manufacturing | MFG | 2024-02-29 08:00 | 2024-08-27 17:00 |  |  |  | 09005 | 1.9.4.1.1.3(Seal boxes for Instrument Tappings (PGMA-9005)) | 206814410
Dispatch | DIS | 2024-08-28 08:00 | 2024-09-26 17:00 |  |  |  | 09005 | 1.9.4.1.1.3(Seal boxes for Instrument Tappings (PGMA-9005)) | 206814411
Material For Instrument Inserts-DD (PGMA-9303) | SUP | 2023-06-04 08:00 | 2024-09-26 17:00 |  |  |  | 9303 | 1.9.4.1.1(Seal Boxes (PG-09)) | 206814412
Engineering | ENG | 2023-06-04 08:00 | 2024-02-23 17:00 |  |  |  | 09303 | 1.9.4.1.1.4(Material For Instrument Inserts-DD (PGMA-9303)) | 206814413
Manufacturing | MFG | 2024-02-24 08:00 | 2024-08-27 17:00 |  |  |  | 09303 | 1.9.4.1.1.4(Material For Instrument Inserts-DD (PGMA-9303)) | 206814414
Dispatch | DIS | 2024-08-28 08:00 | 2024-09-26 17:00 |  |  |  | 09303 | 1.9.4.1.1.4(Material For Instrument Inserts-DD (PGMA-9303)) | 206814415
SEAL BOXES FOR FURNACE OPENINGS-DD (PGMA-9304) | SUP | 2023-06-12 08:00 | 2024-09-26 17:00 |  |  |  | 9304 | 1.9.4.1.1(Seal Boxes (PG-09)) | 206814416
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 09304 | 1.9.4.1.1.5(SEAL BOXES FOR FURNACE OPENINGS-DD (PGMA-9304)) | 206814417
Manufacturing | MFG | 2024-02-29 08:00 | 2024-08-27 17:00 |  |  |  | 09304 | 1.9.4.1.1.5(SEAL BOXES FOR FURNACE OPENINGS-DD (PGMA-9304)) | 206814418
Dispatch | DIS | 2024-08-28 08:00 | 2024-09-26 17:00 |  |  |  | 09304 | 1.9.4.1.1.5(SEAL BOXES FOR FURNACE OPENINGS-DD (PGMA-9304)) | 206814419
Material For Instrument Inserts-SH (PGMA-9503) | SUP | 2023-06-04 08:00 | 2024-09-26 17:00 |  |  |  | 9503 | 1.9.4.1.1(Seal Boxes (PG-09)) | 206814420
Engineering | ENG | 2023-06-04 08:00 | 2024-02-23 17:00 |  |  |  | 09503 | 1.9.4.1.1.6(Material For Instrument Inserts-SH (PGMA-9503)) | 206814421
Manufacturing | MFG | 2024-02-24 08:00 | 2024-08-27 17:00 |  |  |  | 09503 | 1.9.4.1.1.6(Material For Instrument Inserts-SH (PGMA-9503)) | 206814422
Dispatch | DIS | 2024-08-28 08:00 | 2024-09-26 17:00 |  |  |  | 09503 | 1.9.4.1.1.6(Material For Instrument Inserts-SH (PGMA-9503)) | 206814423
Roof Skin Casing (PG-18) | SUP | 2023-01-25 08:00 | 2024-08-28 17:00 |  |  |  | PG18 | 1.9.4.1(Supply (BHEL TRY)) | 206814424
ROOF SKIN CASING (PGMA-18001) | SUP | 2023-06-12 08:00 | 2024-08-28 17:00 |  |  |  | 18001 | 1.9.4.1.2(Roof Skin Casing (PG-18)) | 206814425
Engineering | ENG | 2023-06-12 08:00 | 2023-12-28 17:00 |  |  |  | 18001 | 1.9.4.1.2.1(ROOF SKIN CASING (PGMA-18001)) | 206814426
Manufacturing | MFG | 2023-12-29 08:00 | 2024-07-29 17:00 |  |  |  | 18001 | 1.9.4.1.2.1(ROOF SKIN CASING (PGMA-18001)) | 206814427
Dispatch | DIS | 2024-07-30 08:00 | 2024-08-28 17:00 |  |  |  | 18001 | 1.9.4.1.2.1(ROOF SKIN CASING (PGMA-18001)) | 206814428
PR PTS ATTACHMNTS IN FURN ROOF SKN CAS (PGMA-18010) | SUP | 2023-01-25 08:00 | 2024-08-28 17:00 |  |  |  | 18010 | 1.9.4.1.2(Roof Skin Casing (PG-18)) | 206814429
Engineering | ENG | 2023-01-25 08:00 | 2023-12-05 17:00 |  |  |  | 18010 | 1.9.4.1.2.2(PR PTS ATTACHMNTS IN FURN ROOF SKN CAS (PGMA-18010)) | 206814430
Manufacturing | MFG | 2023-12-06 08:00 | 2024-07-29 17:00 |  |  |  | 18010 | 1.9.4.1.2.2(PR PTS ATTACHMNTS IN FURN ROOF SKN CAS (PGMA-18010)) | 206814431
Dispatch | DIS | 2024-07-30 08:00 | 2024-08-28 17:00 |  |  |  | 18010 | 1.9.4.1.2.2(PR PTS ATTACHMNTS IN FURN ROOF SKN CAS (PGMA-18010)) | 206814432
FURN ROO SKIN CASING - BOI (PGMA-18701) | SUP | 2023-06-12 08:00 | 2024-08-28 17:00 |  |  |  | 18701 | 1.9.4.1.2(Roof Skin Casing (PG-18)) | 206814433
Engineering | ENG | 2023-06-12 08:00 | 2023-12-28 17:00 |  |  |  | 18701 | 1.9.4.1.2.3(FURN ROO SKIN CASING - BOI (PGMA-18701)) | 206814434
Manufacturing | MFG | 2023-12-29 08:00 | 2024-07-29 17:00 |  |  |  | 18701 | 1.9.4.1.2.3(FURN ROO SKIN CASING - BOI (PGMA-18701)) | 206814435
Dispatch | DIS | 2024-07-30 08:00 | 2024-08-28 17:00 |  |  |  | 18701 | 1.9.4.1.2.3(FURN ROO SKIN CASING - BOI (PGMA-18701)) | 206814436
Fixing Components for Main Boiler Lining and Insulation (PG-30) | SUP | 2023-01-25 08:00 | 2025-01-25 17:00 |  |  |  | PG30 | 1.9.4.1(Supply (BHEL TRY)) | 206814437
SEAL PLATE ASSY (PGMA-30103) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 30103 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814438
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 30103 | 1.9.4.1.3.1(SEAL PLATE ASSY (PGMA-30103)) | 206814439
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 30103 | 1.9.4.1.3.1(SEAL PLATE ASSY (PGMA-30103)) | 206814440
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 30103 | 1.9.4.1.3.1(SEAL PLATE ASSY (PGMA-30103)) | 206814441
MAIN BOILER INSULATION (PGMA-30215) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 30215 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814442
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 30215 | 1.9.4.1.3.2(MAIN BOILER INSULATION (PGMA-30215)) | 206814443
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 30215 | 1.9.4.1.3.2(MAIN BOILER INSULATION (PGMA-30215)) | 206814444
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 30215 | 1.9.4.1.3.2(MAIN BOILER INSULATION (PGMA-30215)) | 206814445
VERTICAL ROOF ENCLOSURE FRAMING (PGMA-30219) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 30219 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814446
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 30219 | 1.9.4.1.3.3(VERTICAL ROOF ENCLOSURE FRAMING (PGMA-30219)) | 206814447
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 30219 | 1.9.4.1.3.3(VERTICAL ROOF ENCLOSURE FRAMING (PGMA-30219)) | 206814448
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 30219 | 1.9.4.1.3.3(VERTICAL ROOF ENCLOSURE FRAMING (PGMA-30219)) | 206814449
GAS DISTRIBUTION BAFFLES (PGMA-30223) | SUP | 2023-05-18 08:00 | 2024-11-25 17:00 |  |  |  | 30223 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814450
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 30223 | 1.9.4.1.3.4(GAS DISTRIBUTION BAFFLES (PGMA-30223)) | 206814451
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-26 17:00 |  |  |  | 30223 | 1.9.4.1.3.4(GAS DISTRIBUTION BAFFLES (PGMA-30223)) | 206814452
Dispatch | DIS | 2024-10-27 08:00 | 2024-11-25 17:00 |  |  |  | 30223 | 1.9.4.1.3.4(GAS DISTRIBUTION BAFFLES (PGMA-30223)) | 206814453
Antivibration Baffles (PGMA-30224) | SUP | 2023-01-25 08:00 | 2024-08-27 17:00 |  |  |  | 30224 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814454
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 30224 | 1.9.4.1.3.5(Antivibration Baffles (PGMA-30224)) | 206814455
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-28 17:00 |  |  |  | 30224 | 1.9.4.1.3.5(Antivibration Baffles (PGMA-30224)) | 206814456
Dispatch | DIS | 2024-07-29 08:00 | 2024-08-27 17:00 |  |  |  | 30224 | 1.9.4.1.3.5(Antivibration Baffles (PGMA-30224)) | 206814457
FIRST PASS DECK SPRT AND SEAL (PGMA-30233) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 30233 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814458
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 30233 | 1.9.4.1.3.6(FIRST PASS DECK SPRT AND SEAL (PGMA-30233)) | 206814459
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 30233 | 1.9.4.1.3.6(FIRST PASS DECK SPRT AND SEAL (PGMA-30233)) | 206814460
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 30233 | 1.9.4.1.3.6(FIRST PASS DECK SPRT AND SEAL (PGMA-30233)) | 206814461
SECOND PASS DECK SPRT AND SEAL (PGMA-30234) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 30234 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814462
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 30234 | 1.9.4.1.3.7(SECOND PASS DECK SPRT AND SEAL (PGMA-30234)) | 206814463
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 30234 | 1.9.4.1.3.7(SECOND PASS DECK SPRT AND SEAL (PGMA-30234)) | 206814464
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 30234 | 1.9.4.1.3.7(SECOND PASS DECK SPRT AND SEAL (PGMA-30234)) | 206814465
ENCLOSURE SUPPORT STEEL (PGMA-30235) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 30235 | 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814466
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 30235 | 1.9.4.1.3.8(ENCLOSURE SUPPORT STEEL (PGMA-30235)) | 206814467
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 30235 | 1.9.4.1.3.8(ENCLOSURE SUPPORT STEEL (PGMA-30235)) | 206814468
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 30235 | 1.9.4.1.3.8(ENCLOSURE SUPPORT STEEL (PGMA-30235)) | 206814469
Boiler Skin Casing (PG-31) | SUP | 2023-01-25 08:00 | 2024-12-26 17:00 |  |  |  | PG31 | 1.9.4.1(Supply (BHEL TRY)) | 206814470
SKIN CASING COMPS WELDED TO PR. PARTS (PGMA-31010) | SUP | 2023-01-25 08:00 | 2024-11-25 17:00 |  |  |  | 31010 | 1.9.4.1.4(Boiler Skin Casing (PG-31)) | 206814471
Engineering | ENG | 2023-01-25 08:00 | 2023-12-20 17:00 |  |  |  | 31010 | 1.9.4.1.4.1(SKIN CASING COMPS WELDED TO PR. PARTS (PGMA-31010)) | 206814472
Manufacturing | MFG | 2023-12-21 08:00 | 2024-10-26 17:00 |  |  |  | 31010 | 1.9.4.1.4.1(SKIN CASING COMPS WELDED TO PR. PARTS (PGMA-31010)) | 206814473
Dispatch | DIS | 2024-10-27 08:00 | 2024-11-25 17:00 |  |  |  | 31010 | 1.9.4.1.4.1(SKIN CASING COMPS WELDED TO PR. PARTS (PGMA-31010)) | 206814474
FURNACE REAR ARCH SKIN CASING (PGMA-31104) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 31104 | 1.9.4.1.4(Boiler Skin Casing (PG-31)) | 206814475
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 31104 | 1.9.4.1.4.2(FURNACE REAR ARCH SKIN CASING (PGMA-31104)) | 206814476
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 31104 | 1.9.4.1.4.2(FURNACE REAR ARCH SKIN CASING (PGMA-31104)) | 206814477
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 31104 | 1.9.4.1.4.2(FURNACE REAR ARCH SKIN CASING (PGMA-31104)) | 206814478
Fixing Components for Boiler Auxiliaries Insulation (PG-32) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | PG32 | 1.9.4.1(Supply (BHEL TRY)) | 206814479
FIXING COMPONENTS FOR BLR PR PARTS INSUL (PGMA-32010) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 32010 | 1.9.4.1.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | 206814480
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 32010 | 1.9.4.1.5.1(FIXING COMPONENTS FOR BLR PR PARTS INSUL (PGMA-32010)) | 206814481
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 32010 | 1.9.4.1.5.1(FIXING COMPONENTS FOR BLR PR PARTS INSUL (PGMA-32010)) | 206814482
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 32010 | 1.9.4.1.5.1(FIXING COMPONENTS FOR BLR PR PARTS INSUL (PGMA-32010)) | 206814483
FIXING COMPONENTS FOR DUCT INSUL (PGMA-32210) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 32210 | 1.9.4.1.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | 206814484
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 32210 | 1.9.4.1.5.2(FIXING COMPONENTS FOR DUCT INSUL (PGMA-32210)) | 206814485
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 32210 | 1.9.4.1.5.2(FIXING COMPONENTS FOR DUCT INSUL (PGMA-32210)) | 206814486
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 32210 | 1.9.4.1.5.2(FIXING COMPONENTS FOR DUCT INSUL (PGMA-32210)) | 206814487
BULKED BPS COMPONENT (PGMA-32700) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 32700 | 1.9.4.1.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | 206814488
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 32700 | 1.9.4.1.5.3(BULKED BPS COMPONENT (PGMA-32700)) | 206814489
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 32700 | 1.9.4.1.5.3(BULKED BPS COMPONENT (PGMA-32700)) | 206814490
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 32700 | 1.9.4.1.5.3(BULKED BPS COMPONENT (PGMA-32700)) | 206814491
FIXING COMPONENT FOR OUTLET DUCT (PGMA-32810) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 32810 | 1.9.4.1.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | 206814492
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 32810 | 1.9.4.1.5.4(FIXING COMPONENT FOR OUTLET DUCT (PGMA-32810)) | 206814493
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 32810 | 1.9.4.1.5.4(FIXING COMPONENT FOR OUTLET DUCT (PGMA-32810)) | 206814494
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 32810 | 1.9.4.1.5.4(FIXING COMPONENT FOR OUTLET DUCT (PGMA-32810)) | 206814495
Lining and Insulation Materials (PG-33) | SUP | 2023-06-12 08:00 | 2025-04-27 17:00 |  |  |  | PG33 | 1.9.4.1(Supply (BHEL TRY)) | 206814496
BLR PR PARTS MINERAL WOOL (PGMA-33021) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 33021 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814497
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 33021 | 1.9.4.1.6.1(BLR PR PARTS MINERAL WOOL (PGMA-33021)) | 206814498
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 33021 | 1.9.4.1.6.1(BLR PR PARTS MINERAL WOOL (PGMA-33021)) | 206814499
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 33021 | 1.9.4.1.6.1(BLR PR PARTS MINERAL WOOL (PGMA-33021)) | 206814500
MAIN BLR CASTABLE REFRACTORY GR A (PGMA-33210) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 33210 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814501
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 33210 | 1.9.4.1.6.2(MAIN BLR CASTABLE REFRACTORY GR A (PGMA-33210)) | 206814502
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 33210 | 1.9.4.1.6.2(MAIN BLR CASTABLE REFRACTORY GR A (PGMA-33210)) | 206814503
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 33210 | 1.9.4.1.6.2(MAIN BLR CASTABLE REFRACTORY GR A (PGMA-33210)) | 206814504
DUCT MINERAL WOOL (PGMA-33221) | SUP | 2023-08-07 08:00 | 2025-03-27 17:00 |  |  |  | 33221 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814505
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 33221 | 1.9.4.1.6.3(DUCT MINERAL WOOL (PGMA-33221)) | 206814506
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-25 17:00 |  |  |  | 33221 | 1.9.4.1.6.3(DUCT MINERAL WOOL (PGMA-33221)) | 206814507
Dispatch | DIS | 2025-02-26 08:00 | 2025-03-27 17:00 |  |  |  | 33221 | 1.9.4.1.6.3(DUCT MINERAL WOOL (PGMA-33221)) | 206814508
MAIN BLR POURABLE INSULATION (PGMA-33230) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 33230 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814509
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 33230 | 1.9.4.1.6.4(MAIN BLR POURABLE INSULATION (PGMA-33230)) | 206814510
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 33230 | 1.9.4.1.6.4(MAIN BLR POURABLE INSULATION (PGMA-33230)) | 206814511
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 33230 | 1.9.4.1.6.4(MAIN BLR POURABLE INSULATION (PGMA-33230)) | 206814512
MISC EQPTS SEAL MATERIALS (PGMA-33924) | SUP | 2023-08-22 08:00 | 2025-04-27 17:00 |  |  |  | 33924 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814513
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 33924 | 1.9.4.1.6.5(MISC EQPTS SEAL MATERIALS (PGMA-33924)) | 206814514
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-28 17:00 |  |  |  | 33924 | 1.9.4.1.6.5(MISC EQPTS SEAL MATERIALS (PGMA-33924)) | 206814515
Dispatch | DIS | 2025-03-29 08:00 | 2025-04-27 17:00 |  |  |  | 33924 | 1.9.4.1.6.5(MISC EQPTS SEAL MATERIALS (PGMA-33924)) | 206814516
MISC EQPTS EXPANDED METAL (PGMA-33970) | SUP | 2023-07-02 08:00 | 2025-01-25 17:00 |  |  |  | 33970 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814517
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 33970 | 1.9.4.1.6.6(MISC EQPTS EXPANDED METAL (PGMA-33970)) | 206814518
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-26 17:00 |  |  |  | 33970 | 1.9.4.1.6.6(MISC EQPTS EXPANDED METAL (PGMA-33970)) | 206814519
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 33970 | 1.9.4.1.6.6(MISC EQPTS EXPANDED METAL (PGMA-33970)) | 206814520
MISC EQPTS WOVEN WIRE CLOTH (PGMA-33971) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 33971 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814521
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 33971 | 1.9.4.1.6.7(MISC EQPTS WOVEN WIRE CLOTH (PGMA-33971)) | 206814522
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 33971 | 1.9.4.1.6.7(MISC EQPTS WOVEN WIRE CLOTH (PGMA-33971)) | 206814523
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 33971 | 1.9.4.1.6.7(MISC EQPTS WOVEN WIRE CLOTH (PGMA-33971)) | 206814524
MISC EQPTS SEALING COMPOUND (PGMA-33975) | SUP | 2023-08-22 08:00 | 2025-04-27 17:00 |  |  |  | 33975 | 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | 206814525
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 33975 | 1.9.4.1.6.8(MISC EQPTS SEALING COMPOUND (PGMA-33975)) | 206814526
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-28 17:00 |  |  |  | 33975 | 1.9.4.1.6.8(MISC EQPTS SEALING COMPOUND (PGMA-33975)) | 206814527
Dispatch | DIS | 2025-03-29 08:00 | 2025-04-27 17:00 |  |  |  | 33975 | 1.9.4.1.6.8(MISC EQPTS SEALING COMPOUND (PGMA-33975)) | 206814528
Boiler Outer Casing (PG-37) | SUP | 2023-06-12 08:00 | 2024-08-28 17:00 |  |  |  | PG37 | 1.9.4.1(Supply (BHEL TRY)) | 206814529
BLR OUTER CASING COMPONENTS (PGMA-37010) | SUP | 2023-06-12 08:00 | 2024-08-28 17:00 |  |  |  | 37010 | 1.9.4.1.7(Boiler Outer Casing (PG-37)) | 206814530
Engineering | ENG | 2023-06-12 08:00 | 2023-12-28 17:00 |  |  |  | 37010 | 1.9.4.1.7.1(BLR OUTER CASING COMPONENTS (PGMA-37010)) | 206814531
Manufacturing | MFG | 2023-12-29 08:00 | 2024-07-29 17:00 |  |  |  | 37010 | 1.9.4.1.7.1(BLR OUTER CASING COMPONENTS (PGMA-37010)) | 206814532
Dispatch | DIS | 2024-07-30 08:00 | 2024-08-28 17:00 |  |  |  | 37010 | 1.9.4.1.7.1(BLR OUTER CASING COMPONENTS (PGMA-37010)) | 206814533
BLR OUTER CASING (PGMA-37810) | SUP | 2023-06-12 08:00 | 2024-08-28 17:00 |  |  |  | 37810 | 1.9.4.1.7(Boiler Outer Casing (PG-37)) | 206814534
Engineering | ENG | 2023-06-12 08:00 | 2023-12-28 17:00 |  |  |  | 37810 | 1.9.4.1.7.2(BLR OUTER CASING (PGMA-37810)) | 206814535
Manufacturing | MFG | 2023-12-29 08:00 | 2024-07-29 17:00 |  |  |  | 37810 | 1.9.4.1.7.2(BLR OUTER CASING (PGMA-37810)) | 206814536
Dispatch | DIS | 2024-07-30 08:00 | 2024-08-28 17:00 |  |  |  | 37810 | 1.9.4.1.7.2(BLR OUTER CASING (PGMA-37810)) | 206814537
Erection | ERC | 2025-04-01 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.9.4(Lining and Insulation System) | 206814538
Seal Boxes (PG-09) | ERC | 2025-04-01 08:00 | 2025-05-30 17:00 |  |  |  | PG09 | 1.9.4.2(Erection) | 206814539
Erection: Seal Boxes for Furnace Opening | ERC | 2025-04-21 08:00 | 2025-05-30 17:00 |  |  |  |  | 1.9.4.2.1(Seal Boxes (PG-09)) | 206814540
Erection: Seal Boxes for Instrument tapping | ERC | 2025-04-01 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.9.4.2.1(Seal Boxes (PG-09)) | 206814541
Roof Skin Casing (PG-18) | ERC | 2025-06-30 08:00 | 2025-11-16 17:00 |  |  |  | PG18 | 1.9.4.2(Erection) | 206814542
Erection: Roof Skin Casing and PP attachment | ERC | 2025-06-30 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.2(Roof Skin Casing (PG-18)) | 206814543
Fixing Components for Main Boiler Lining and Insulation (PG-30) | ERC | 2025-08-19 08:00 | 2025-11-16 17:00 |  |  |  | PG30 | 1.9.4.2(Erection) | 206814544
Erection: SEAL PLATE ASSY | ERC | 2025-10-18 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814545
Erection: MAIN BOILER INSULATION | ERC | 2025-08-19 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814546
Erection: VERTICAL ROOF ENCLOSURE FRAMING | ERC | 2025-08-19 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814547
Erection: GAS DISTRIBUTION BAFFLES | ERC | 2025-08-19 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814548
Erection: Antivibration Baffles | ERC | 2025-08-19 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814549
Erection: FIRST PASS DECK SPRT AND SEAL | ERC | 2025-08-19 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814550
Erection: SECOND PASS DECK SPRT AND SEAL | ERC | 2025-08-19 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814551
Erection: ENCLOSURE SUPPORT STEEL | ERC | 2025-08-19 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | 206814552
Boiler Skin Casing (PG-31) | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  | PG31 | 1.9.4.2(Erection) | 206814553
Erection: SKIN CASING COMPS WELDED TO PR. PARTS | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.4.2.4(Boiler Skin Casing (PG-31)) | 206814554
Erection: FURNACE REAR ARCH SKIN CASING | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.4.2.4(Boiler Skin Casing (PG-31)) | 206814555
Fixing Components for Boiler Auxiliaries Insulation (PG-32) | ERC | 2025-07-20 08:00 | 2025-11-16 17:00 |  |  |  | PG32 | 1.9.4.2(Erection) | 206814556
Erection: FIXING COMPONENTS FOR BLR PR PARTS INSUL | ERC | 2025-07-20 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.4.2.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | 206814557
Lining and Insulation Materials (PG-33) | ERC | 2025-08-09 08:00 | 2026-01-15 17:00 |  |  |  | PG33 | 1.9.4.2(Erection) | 206814558
Erection: BLR PR PARTS MINERAL WOOL | ERC | 2025-08-19 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.4.2.6(Lining and Insulation Materials (PG-33)) | 206814559
Erection: MAIN BLR CASTABLE REFRACTORY GR A | ERC | 2025-08-09 08:00 | 2025-12-06 17:00 |  |  |  |  | 1.9.4.2.6(Lining and Insulation Materials (PG-33)) | 206814560
Erection: MAIN BLR POURABLE INSULATION | ERC | 2025-08-09 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.9.4.2.6(Lining and Insulation Materials (PG-33)) | 206814561
Boiler Outer Casing (PG-37) | ERC | 2025-07-20 08:00 | 2025-12-06 17:00 |  |  |  | PG37 | 1.9.4.2(Erection) | 206814562
Erection: BLR OUTER CASING COMPONENTS | ERC | 2025-07-20 08:00 | 2025-12-06 17:00 |  |  |  |  | 1.9.4.2.7(Boiler Outer Casing (PG-37)) | 206814563
Erection: BLR OUTER CASING | ERC | 2025-07-20 08:00 | 2025-12-06 17:00 |  |  |  |  | 1.9.4.2.7(Boiler Outer Casing (PG-37)) | 206814564
Ignition and Burning System | ERC | 2023-01-25 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206814565
Supply (BHEL TRY) | SUP | 2023-01-25 08:00 | 2025-04-29 17:00 |  |  |  |  | 1.9.5(Ignition and Burning System) | 206814566
Oil & Gas Burners and Ignitors & Scanners (PG-41) | SUP | 2023-06-12 08:00 | 2025-01-27 17:00 |  |  |  | PG41 | 1.9.5.1(Supply (BHEL TRY)) | 206814567
AIR COOLED OIL GUN ASSY, (PGMA-41350) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 41350 | 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814568
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 41350 | 1.9.5.1.1.1(AIR COOLED OIL GUN ASSY, (PGMA-41350)) | 206814569
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 41350 | 1.9.5.1.1.1(AIR COOLED OIL GUN ASSY, (PGMA-41350)) | 206814570
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 41350 | 1.9.5.1.1.1(AIR COOLED OIL GUN ASSY, (PGMA-41350)) | 206814571
OIL GUN VICE ASSEMBLY AND RACK (PGMA-41390) | SUP | 2023-06-12 08:00 | 2024-12-26 17:00 |  |  |  | 41390 | 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814572
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 41390 | 1.9.5.1.1.2(OIL GUN VICE ASSEMBLY AND RACK (PGMA-41390)) | 206814573
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-26 17:00 |  |  |  | 41390 | 1.9.5.1.1.2(OIL GUN VICE ASSEMBLY AND RACK (PGMA-41390)) | 206814574
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 41390 | 1.9.5.1.1.2(OIL GUN VICE ASSEMBLY AND RACK (PGMA-41390)) | 206814575
HIGH ENERGY ARC IGNITOR (PGMA-41500) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 41500 | 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814576
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 41500 | 1.9.5.1.1.3(HIGH ENERGY ARC IGNITOR (PGMA-41500)) | 206814577
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 41500 | 1.9.5.1.1.3(HIGH ENERGY ARC IGNITOR (PGMA-41500)) | 206814578
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 41500 | 1.9.5.1.1.3(HIGH ENERGY ARC IGNITOR (PGMA-41500)) | 206814579
Oil Gun Assembly - DD items (PGMA-41710) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 41710 | 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814580
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 41710 | 1.9.5.1.1.4(Oil Gun Assembly - DD items (PGMA-41710)) | 206814581
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 41710 | 1.9.5.1.1.4(Oil Gun Assembly - DD items (PGMA-41710)) | 206814582
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 41710 | 1.9.5.1.1.4(Oil Gun Assembly - DD items (PGMA-41710)) | 206814583
OIL&GAS BURNER COMMISSIONING SPARE (PGMA-41988) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 41988 | 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814584
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 41988 | 1.9.5.1.1.5(OIL&GAS BURNER COMMISSIONING SPARE (PGMA-41988)) | 206814585
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 41988 | 1.9.5.1.1.5(OIL&GAS BURNER COMMISSIONING SPARE (PGMA-41988)) | 206814586
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 41988 | 1.9.5.1.1.5(OIL&GAS BURNER COMMISSIONING SPARE (PGMA-41988)) | 206814587
OIL/GAS BURNER MANDATORY SPARES (PGMA-41997) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 41997 | 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814588
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 41997 | 1.9.5.1.1.6(OIL/GAS BURNER MANDATORY SPARES (PGMA-41997)) | 206814589
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 41997 | 1.9.5.1.1.6(OIL/GAS BURNER MANDATORY SPARES (PGMA-41997)) | 206814590
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 41997 | 1.9.5.1.1.6(OIL/GAS BURNER MANDATORY SPARES (PGMA-41997)) | 206814591
Oil & Gas Systems (PG-42) | OTH | 2023-06-12 08:00 | 2025-04-29 17:00 |  |  |  | PG42 | 1.9.5.1(Supply (BHEL TRY)) | 206814592
PNEUMATIC FITTINGS (PGMA-42001) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42001 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814593
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42001 | 1.9.5.1.2.1(PNEUMATIC FITTINGS (PGMA-42001)) | 206814594
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42001 | 1.9.5.1.2.1(PNEUMATIC FITTINGS (PGMA-42001)) | 206814595
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42001 | 1.9.5.1.2.1(PNEUMATIC FITTINGS (PGMA-42001)) | 206814596
STEAM BLOW MATERIALS (PGMA-42002) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 42002 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814597
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 42002 | 1.9.5.1.2.2(STEAM BLOW MATERIALS (PGMA-42002)) | 206814598
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 42002 | 1.9.5.1.2.2(STEAM BLOW MATERIALS (PGMA-42002)) | 206814599
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 42002 | 1.9.5.1.2.2(STEAM BLOW MATERIALS (PGMA-42002)) | 206814600
INSTRUMENT FITTINGS (PGMA-42005) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42005 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814601
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42005 | 1.9.5.1.2.3(INSTRUMENT FITTINGS (PGMA-42005)) | 206814602
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42005 | 1.9.5.1.2.3(INSTRUMENT FITTINGS (PGMA-42005)) | 206814603
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42005 | 1.9.5.1.2.3(INSTRUMENT FITTINGS (PGMA-42005)) | 206814604
BOI-LU-LIGHT FUEL OIL PUMP SET (PGMA-42010) | SUP | 2023-12-01 08:00 | 2025-02-04 17:00 |  |  |  | 42010 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814605
NIT | ENQ | 2023-12-01 08:00 | 2023-12-01 17:00 |  |  |  | 42010 | 1.9.5.1.2.4(BOI-LU-LIGHT FUEL OIL PUMP SET (PGMA-42010)) | 206814606
Ordering | ORD | 2023-12-02 08:00 | 2024-03-30 17:00 |  |  |  | 42010 | 1.9.5.1.2.4(BOI-LU-LIGHT FUEL OIL PUMP SET (PGMA-42010)) | 206814607
Manufacturing | MFG | 2024-03-31 08:00 | 2025-01-05 17:00 |  |  |  | 42010 | 1.9.5.1.2.4(BOI-LU-LIGHT FUEL OIL PUMP SET (PGMA-42010)) | 206814608
Dispatch | DIS | 2025-01-06 08:00 | 2025-02-04 17:00 |  |  |  | 42010 | 1.9.5.1.2.4(BOI-LU-LIGHT FUEL OIL PUMP SET (PGMA-42010)) | 206814609
BOI-LU-DRAIN OIL PUMP-MOTOR ASSY (PGMA-42046) | SUP | 2023-08-03 08:00 | 2025-02-07 17:00 |  |  |  | 42046 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814610
NIT | ENQ | 2023-08-03 08:00 | 2023-08-03 17:00 |  |  |  | 42046 | 1.9.5.1.2.5(BOI-LU-DRAIN OIL PUMP-MOTOR ASSY (PGMA-42046)) | 206814611
Ordering | ORD | 2023-08-04 08:00 | 2023-12-31 17:00 |  |  |  | 42046 | 1.9.5.1.2.5(BOI-LU-DRAIN OIL PUMP-MOTOR ASSY (PGMA-42046)) | 206814612
Manufacturing | MFG | 2024-04-10 08:00 | 2025-01-08 17:00 |  |  |  | 42046 | 1.9.5.1.2.5(BOI-LU-DRAIN OIL PUMP-MOTOR ASSY (PGMA-42046)) | 206814613
Dispatch | DIS | 2025-01-09 08:00 | 2025-02-07 17:00 |  |  |  | 42046 | 1.9.5.1.2.5(BOI-LU-DRAIN OIL PUMP-MOTOR ASSY (PGMA-42046)) | 206814614
DRAIN OIL TANK (PGMA-42065) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 42065 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814615
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 42065 | 1.9.5.1.2.6(DRAIN OIL TANK (PGMA-42065)) | 206814616
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 42065 | 1.9.5.1.2.6(DRAIN OIL TANK (PGMA-42065)) | 206814617
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 42065 | 1.9.5.1.2.6(DRAIN OIL TANK (PGMA-42065)) | 206814618
BURNER STATION SKID ASSY (PGMA-42070) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42070 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814619
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42070 | 1.9.5.1.2.7(BURNER STATION SKID ASSY (PGMA-42070)) | 206814620
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42070 | 1.9.5.1.2.7(BURNER STATION SKID ASSY (PGMA-42070)) | 206814621
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42070 | 1.9.5.1.2.7(BURNER STATION SKID ASSY (PGMA-42070)) | 206814622
PIPING, PUMP HOUSE-FUEL OIL (PGMA-42120) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 42120 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814623
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 42120 | 1.9.5.1.2.8(PIPING, PUMP HOUSE-FUEL OIL (PGMA-42120)) | 206814624
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 42120 | 1.9.5.1.2.8(PIPING, PUMP HOUSE-FUEL OIL (PGMA-42120)) | 206814625
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 42120 | 1.9.5.1.2.8(PIPING, PUMP HOUSE-FUEL OIL (PGMA-42120)) | 206814626
PIPING,PUMP HOUSE STEAM - IBR (PGMA-42128) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 42128 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814627
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 42128 | 1.9.5.1.2.9(PIPING,PUMP HOUSE STEAM - IBR (PGMA-42128)) | 206814628
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 42128 | 1.9.5.1.2.9(PIPING,PUMP HOUSE STEAM - IBR (PGMA-42128)) | 206814629
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 42128 | 1.9.5.1.2.9(PIPING,PUMP HOUSE STEAM - IBR (PGMA-42128)) | 206814630
PIPING,OPERATING FLOOR LIGHT FUEL OIL (PGMA-42152) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42152 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814631
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42152 | 1.9.5.1.2.10(PIPING,OPERATING FLOOR LIGHT FUEL OIL (PGMA-42152)) | 206814632
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42152 | 1.9.5.1.2.10(PIPING,OPERATING FLOOR LIGHT FUEL OIL (PGMA-42152)) | 206814633
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42152 | 1.9.5.1.2.10(PIPING,OPERATING FLOOR LIGHT FUEL OIL (PGMA-42152)) | 206814634
PIPING,OPRG FLOOR DRAIN OIL (PGMA-42154) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42154 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814635
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42154 | 1.9.5.1.2.11(PIPING,OPRG FLOOR DRAIN OIL (PGMA-42154)) | 206814636
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42154 | 1.9.5.1.2.11(PIPING,OPRG FLOOR DRAIN OIL (PGMA-42154)) | 206814637
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42154 | 1.9.5.1.2.11(PIPING,OPRG FLOOR DRAIN OIL (PGMA-42154)) | 206814638
PIPING,OPERATING FLOOR ATOMIZING AIR (PGMA-42157) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 42157 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814639
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 42157 | 1.9.5.1.2.12(PIPING,OPERATING FLOOR ATOMIZING AIR (PGMA-42157)) | 206814640
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 42157 | 1.9.5.1.2.12(PIPING,OPERATING FLOOR ATOMIZING AIR (PGMA-42157)) | 206814641
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 42157 | 1.9.5.1.2.12(PIPING,OPERATING FLOOR ATOMIZING AIR (PGMA-42157)) | 206814642
PIPING,OPERATING FLOOR STEAM-IBR (PGMA-42158) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42158 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814643
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42158 | 1.9.5.1.2.13(PIPING,OPERATING FLOOR STEAM-IBR (PGMA-42158)) | 206814644
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42158 | 1.9.5.1.2.13(PIPING,OPERATING FLOOR STEAM-IBR (PGMA-42158)) | 206814645
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42158 | 1.9.5.1.2.13(PIPING,OPERATING FLOOR STEAM-IBR (PGMA-42158)) | 206814646
BOI-LU-SUBDELIVERY FUEL OIL SYSTEM (PGMA-42200) | SUP | 2023-11-01 08:00 | 2025-02-04 17:00 |  |  |  | 42200 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814647
NIT | ENQ | 2023-11-01 08:00 | 2023-11-01 17:00 |  |  |  | 42200 | 1.9.5.1.2.14(BOI-LU-SUBDELIVERY FUEL OIL SYSTEM (PGMA-42200)) | 206814648
Ordering | ORD | 2023-11-02 08:00 | 2024-03-30 17:00 |  |  |  | 42200 | 1.9.5.1.2.14(BOI-LU-SUBDELIVERY FUEL OIL SYSTEM (PGMA-42200)) | 206814649
Manufacturing | MFG | 2024-03-31 08:00 | 2025-01-05 17:00 |  |  |  | 42200 | 1.9.5.1.2.14(BOI-LU-SUBDELIVERY FUEL OIL SYSTEM (PGMA-42200)) | 206814650
Dispatch | DIS | 2025-01-06 08:00 | 2025-02-04 17:00 |  |  |  | 42200 | 1.9.5.1.2.14(BOI-LU-SUBDELIVERY FUEL OIL SYSTEM (PGMA-42200)) | 206814651
BHEL VALVE F.O. SYSTEM (PGMA-42300) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 42300 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814652
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 42300 | 1.9.5.1.2.15(BHEL VALVE F.O. SYSTEM (PGMA-42300)) | 206814653
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 42300 | 1.9.5.1.2.15(BHEL VALVE F.O. SYSTEM (PGMA-42300)) | 206814654
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 42300 | 1.9.5.1.2.15(BHEL VALVE F.O. SYSTEM (PGMA-42300)) | 206814655
BHEL VALVE,OPERATING FLOOR STM-IBR (PGMA-42358) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 42358 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814656
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 42358 | 1.9.5.1.2.16(BHEL VALVE,OPERATING FLOOR STM-IBR (PGMA-42358)) | 206814657
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 42358 | 1.9.5.1.2.16(BHEL VALVE,OPERATING FLOOR STM-IBR (PGMA-42358)) | 206814658
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 42358 | 1.9.5.1.2.16(BHEL VALVE,OPERATING FLOOR STM-IBR (PGMA-42358)) | 206814659
BULKED BPS COMPONENTS (PGMA-42700) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 42700 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814660
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 42700 | 1.9.5.1.2.17(BULKED BPS COMPONENTS (PGMA-42700)) | 206814661
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 42700 | 1.9.5.1.2.17(BULKED BPS COMPONENTS (PGMA-42700)) | 206814662
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 42700 | 1.9.5.1.2.17(BULKED BPS COMPONENTS (PGMA-42700)) | 206814663
Fuel Oil System - DD Items (PGMA-42710) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 42710 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814664
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 42710 | 1.9.5.1.2.18(Fuel Oil System - DD Items (PGMA-42710)) | 206814665
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 42710 | 1.9.5.1.2.18(Fuel Oil System - DD Items (PGMA-42710)) | 206814666
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 42710 | 1.9.5.1.2.18(Fuel Oil System - DD Items (PGMA-42710)) | 206814667
Fuel Oil System - Shop items (PGMA-42858) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 42858 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814668
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 42858 | 1.9.5.1.2.19(Fuel Oil System - Shop items (PGMA-42858)) | 206814669
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 42858 | 1.9.5.1.2.19(Fuel Oil System - Shop items (PGMA-42858)) | 206814670
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 42858 | 1.9.5.1.2.19(Fuel Oil System - Shop items (PGMA-42858)) | 206814671
OIL&GAS SYSTEM COMMISSIONING SPARE (PGMA-42988) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 42988 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814672
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 42988 | 1.9.5.1.2.20(OIL&GAS SYSTEM COMMISSIONING SPARE (PGMA-42988)) | 206814673
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 42988 | 1.9.5.1.2.20(OIL&GAS SYSTEM COMMISSIONING SPARE (PGMA-42988)) | 206814674
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 42988 | 1.9.5.1.2.20(OIL&GAS SYSTEM COMMISSIONING SPARE (PGMA-42988)) | 206814675
IMPORTED ELECTRODES (PGMA-42992) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 42992 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814676
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 42992 | 1.9.5.1.2.21(IMPORTED ELECTRODES (PGMA-42992)) | 206814677
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 42992 | 1.9.5.1.2.21(IMPORTED ELECTRODES (PGMA-42992)) | 206814678
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 42992 | 1.9.5.1.2.21(IMPORTED ELECTRODES (PGMA-42992)) | 206814679
OIL SYSTEM-MANDATORY SPARES (PGMA-42997) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 42997 | 1.9.5.1.2(Oil & Gas Systems (PG-42)) | 206814680
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 42997 | 1.9.5.1.2.22(OIL SYSTEM-MANDATORY SPARES (PGMA-42997)) | 206814681
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 42997 | 1.9.5.1.2.22(OIL SYSTEM-MANDATORY SPARES (PGMA-42997)) | 206814682
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 42997 | 1.9.5.1.2.22(OIL SYSTEM-MANDATORY SPARES (PGMA-42997)) | 206814683
Ignitor and Scanner Air System (PG-43) | OTH | 2023-08-07 08:00 | 2025-04-29 17:00 |  |  |  | PG43 | 1.9.5.1(Supply (BHEL TRY)) | 206814684
ASSY COMP SCANNER & GUN AIR SYSTEM (PGMA-43004) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 43004 | 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | 206814685
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 43004 | 1.9.5.1.3.1(ASSY COMP SCANNER & GUN AIR SYSTEM (PGMA-43004)) | 206814686
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 43004 | 1.9.5.1.3.1(ASSY COMP SCANNER & GUN AIR SYSTEM (PGMA-43004)) | 206814687
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 43004 | 1.9.5.1.3.1(ASSY COMP SCANNER & GUN AIR SYSTEM (PGMA-43004)) | 206814688
ASSY COMP MILL SEAL AIR SYSTEM (PGMA-43005) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 43005 | 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | 206814689
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 43005 | 1.9.5.1.3.2(ASSY COMP MILL SEAL AIR SYSTEM (PGMA-43005)) | 206814690
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 43005 | 1.9.5.1.3.2(ASSY COMP MILL SEAL AIR SYSTEM (PGMA-43005)) | 206814691
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 43005 | 1.9.5.1.3.2(ASSY COMP MILL SEAL AIR SYSTEM (PGMA-43005)) | 206814692
M/C COMP SCANNER & GUN AIR SYSTEM (PGMA-43104) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 43104 | 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | 206814693
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 43104 | 1.9.5.1.3.3(M/C COMP SCANNER & GUN AIR SYSTEM (PGMA-43104)) | 206814694
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 43104 | 1.9.5.1.3.3(M/C COMP SCANNER & GUN AIR SYSTEM (PGMA-43104)) | 206814695
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 43104 | 1.9.5.1.3.3(M/C COMP SCANNER & GUN AIR SYSTEM (PGMA-43104)) | 206814696
M/C COMP MILL SEAL AIR SYSTEM (PGMA-43105) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 43105 | 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | 206814697
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 43105 | 1.9.5.1.3.4(M/C COMP MILL SEAL AIR SYSTEM (PGMA-43105)) | 206814698
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 43105 | 1.9.5.1.3.4(M/C COMP MILL SEAL AIR SYSTEM (PGMA-43105)) | 206814699
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 43105 | 1.9.5.1.3.4(M/C COMP MILL SEAL AIR SYSTEM (PGMA-43105)) | 206814700
BOI-LU-SUBDEL, AIR SYSTEM (PGMA-43200) | SUP | 2023-09-22 08:00 | 2025-03-15 17:00 |  |  |  | 43200 | 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | 206814701
NIT | ENQ | 2023-09-22 08:00 | 2023-09-22 17:00 |  |  |  | 43200 | 1.9.5.1.3.5(BOI-LU-SUBDEL, AIR SYSTEM (PGMA-43200)) | 206814702
Ordering | ORD | 2023-09-23 08:00 | 2024-04-09 17:00 |  |  |  | 43200 | 1.9.5.1.3.5(BOI-LU-SUBDEL, AIR SYSTEM (PGMA-43200)) | 206814703
Manufacturing | MFG | 2024-04-10 08:00 | 2025-02-13 17:00 |  |  |  | 43200 | 1.9.5.1.3.5(BOI-LU-SUBDEL, AIR SYSTEM (PGMA-43200)) | 206814704
Dispatch | DIS | 2025-02-14 08:00 | 2025-03-15 17:00 |  |  |  | 43200 | 1.9.5.1.3.5(BOI-LU-SUBDEL, AIR SYSTEM (PGMA-43200)) | 206814705
Seal Air & Scanner Air System - DD items (PGMA-43710) | SUP | 2023-08-07 08:00 | 2025-03-30 17:00 |  |  |  | 43710 | 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | 206814706
Engineering | ENG | 2023-08-07 08:00 | 2024-05-14 17:00 |  |  |  | 43710 | 1.9.5.1.3.6(Seal Air & Scanner Air System - DD items (PGMA-43710)) | 206814707
Manufacturing | MFG | 2024-05-15 08:00 | 2025-02-28 17:00 |  |  |  | 43710 | 1.9.5.1.3.6(Seal Air & Scanner Air System - DD items (PGMA-43710)) | 206814708
Dispatch | DIS | 2025-03-01 08:00 | 2025-03-30 17:00 |  |  |  | 43710 | 1.9.5.1.3.6(Seal Air & Scanner Air System - DD items (PGMA-43710)) | 206814709
Coal Burner System (PG-45) | OTH | 2023-01-25 08:00 | 2025-04-29 17:00 |  |  |  | PG45 | 1.9.5.1(Supply (BHEL TRY)) | 206814710
SA DAMPER & BURNER TILT ACTUATORS (PGMA-45200) | SUP | 2023-04-09 08:00 | 2024-08-29 17:00 |  |  |  | 45200 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814711
Engineering | ENG | 2023-04-09 08:00 | 2023-11-29 17:00 |  |  |  | 45200 | 1.9.5.1.4.1(SA DAMPER & BURNER TILT ACTUATORS (PGMA-45200)) | 206814712
Manufacturing | MFG | 2023-11-30 08:00 | 2024-07-30 17:00 |  |  |  | 45200 | 1.9.5.1.4.1(SA DAMPER & BURNER TILT ACTUATORS (PGMA-45200)) | 206814713
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 45200 | 1.9.5.1.4.1(SA DAMPER & BURNER TILT ACTUATORS (PGMA-45200)) | 206814714
Wind Box & SOFA Assembly - DD items (PGMA-45710) | SUP | 2023-01-25 08:00 | 2024-08-29 17:00 |  |  |  | 45710 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814715
Engineering | ENG | 2023-01-25 08:00 | 2023-11-05 17:00 |  |  |  | 45710 | 1.9.5.1.4.2(Wind Box & SOFA Assembly - DD items (PGMA-45710)) | 206814716
Manufacturing | MFG | 2023-11-06 08:00 | 2024-07-30 17:00 |  |  |  | 45710 | 1.9.5.1.4.2(Wind Box & SOFA Assembly - DD items (PGMA-45710)) | 206814717
Dispatch | DIS | 2024-07-31 08:00 | 2024-08-29 17:00 |  |  |  | 45710 | 1.9.5.1.4.2(Wind Box & SOFA Assembly - DD items (PGMA-45710)) | 206814718
Windbox assembly and SOFA tube attachment (PGMA-45801) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 45801 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814719
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 45801 | 1.9.5.1.4.3(Windbox assembly and SOFA tube attachment (PGMA-45801)) | 206814720
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 45801 | 1.9.5.1.4.3(Windbox assembly and SOFA tube attachment (PGMA-45801)) | 206814721
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 45801 | 1.9.5.1.4.3(Windbox assembly and SOFA tube attachment (PGMA-45801)) | 206814722
Windbox assembly - 32" width (PGMA-45802) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 45802 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814723
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 45802 | 1.9.5.1.4.4(Windbox assembly - 32" width (PGMA-45802)) | 206814724
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 45802 | 1.9.5.1.4.4(Windbox assembly - 32" width (PGMA-45802)) | 206814725
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 45802 | 1.9.5.1.4.4(Windbox assembly - 32" width (PGMA-45802)) | 206814726
Windbox assembly - SOFA (PGMA-45804) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 45804 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814727
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 45804 | 1.9.5.1.4.5(Windbox assembly - SOFA (PGMA-45804)) | 206814728
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 45804 | 1.9.5.1.4.5(Windbox assembly - SOFA (PGMA-45804)) | 206814729
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 45804 | 1.9.5.1.4.5(Windbox assembly - SOFA (PGMA-45804)) | 206814730
Windbox support and air cylinder mounting (PGMA-45805) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 45805 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814731
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 45805 | 1.9.5.1.4.6(Windbox support and air cylinder mounting (PGMA-45805)) | 206814732
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 45805 | 1.9.5.1.4.6(Windbox support and air cylinder mounting (PGMA-45805)) | 206814733
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 45805 | 1.9.5.1.4.6(Windbox support and air cylinder mounting (PGMA-45805)) | 206814734
Wind Box & SOFA Assy - Shop items (PGMA-45858) | SUP | 2023-01-25 08:00 | 2024-07-29 17:00 |  |  |  | 45858 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814735
Engineering | ENG | 2023-01-25 08:00 | 2023-10-26 17:00 |  |  |  | 45858 | 1.9.5.1.4.7(Wind Box & SOFA Assy - Shop items (PGMA-45858)) | 206814736
Manufacturing | MFG | 2023-10-27 08:00 | 2024-06-29 17:00 |  |  |  | 45858 | 1.9.5.1.4.7(Wind Box & SOFA Assy - Shop items (PGMA-45858)) | 206814737
Dispatch | DIS | 2024-06-30 08:00 | 2024-07-29 17:00 |  |  |  | 45858 | 1.9.5.1.4.7(Wind Box & SOFA Assy - Shop items (PGMA-45858)) | 206814738
COAL BURNER-MANDATORY SPARES (PGMA-45997) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 45997 | 1.9.5.1.4(Coal Burner System (PG-45)) | 206814739
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 45997 | 1.9.5.1.4.8(COAL BURNER-MANDATORY SPARES (PGMA-45997)) | 206814740
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 45997 | 1.9.5.1.4.8(COAL BURNER-MANDATORY SPARES (PGMA-45997)) | 206814741
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 45997 | 1.9.5.1.4.8(COAL BURNER-MANDATORY SPARES (PGMA-45997)) | 206814742
Erection | ERC | 2024-08-30 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.9.5(Ignition and Burning System) | 206814743
Oil & Gas Burners and Ignitors & Scanners (PG-41) | ERC | 2025-12-02 08:00 | 2025-12-09 17:00 |  |  |  | PG41 | 1.9.5.2(Erection) | 206814744
Erection: AIR COOLED OIL GUN ASSY | ERC | 2025-12-02 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.9.5.2.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814745
Erection: OIL GUN VICE ASSEMBLY AND RACK | ERC | 2025-12-02 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.9.5.2.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814746
Erection: HIGH ENERGY ARC IGNITOR | ERC | 2025-12-02 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.9.5.2.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | 206814747
Oil & Gas Systems (PG-42) | ERC | 2025-09-01 08:00 | 2025-10-30 17:00 |  |  |  | PG42 | 1.9.5.2(Erection) | 206814748
Erection: PNEUMATIC FITTINGS | ERC | 2025-10-01 08:00 | 2025-10-08 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814749
Erection: STEAM BLOW MATERIALS | ERC | 2025-10-01 08:00 | 2025-10-08 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814750
Erection: INSTRUMENT FITTINGS | ERC | 2025-10-01 08:00 | 2025-10-08 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814751
Erection: BURNER STATION SKID ASSY | ERC | 2025-09-01 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814752
Erection: PIPING & Valves, OPERATING FLOOR & TRACER | ERC | 2025-10-01 08:00 | 2025-10-30 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814753
Erection: PIPING & Valves, OPERATING FLOOR LIGHT FUEL OIL | ERC | 2025-10-01 08:00 | 2025-10-30 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814754
Erection: PIPING & Valves,OPRG FLOOR DRAIN OIL | ERC | 2025-10-01 08:00 | 2025-10-30 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814755
Erection: PIPING & Valves, OPERATING FLOOR ATOMIZING AIR | ERC | 2025-10-01 08:00 | 2025-10-30 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814756
Erection: PIPING & Valves, OPERATING FLOOR STEAM-IBR | ERC | 2025-10-01 08:00 | 2025-10-30 17:00 |  |  |  |  | 1.9.5.2.2(Oil & Gas Systems (PG-42)) | 206814757
Ignitor and Scanner Air System (PG-43) | ERC | 2025-04-30 08:00 | 2025-10-15 17:00 |  |  |  | PG43 | 1.9.5.2(Erection) | 206814758
Erection: ASSY COMP SCANNER & GUN AIR SYSTEM | ERC | 2025-10-01 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.9.5.2.3(Ignitor and Scanner Air System (PG-43)) | 206814759
Erection: ASSY COMP MILL SEAL AIR SYSTEM | ERC | 2025-04-30 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.9.5.2.3(Ignitor and Scanner Air System (PG-43)) | 206814760
Erection: M/C COMP SCANNER & GUN AIR SYSTEM | ERC | 2025-10-01 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.9.5.2.3(Ignitor and Scanner Air System (PG-43)) | 206814761
Erection: M/C COMP MILL SEAL AIR SYSTEM | ERC | 2025-05-15 08:00 | 2025-05-29 17:00 |  |  |  |  | 1.9.5.2.3(Ignitor and Scanner Air System (PG-43)) | 206814762
Erection: Seal Air & Scanner Air System | ERC | 2025-09-01 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.9.5.2.3(Ignitor and Scanner Air System (PG-43)) | 206814763
Coal Burner System (PG-45) | ERC | 2024-08-30 08:00 | 2024-09-13 17:00 |  |  |  | PG45 | 1.9.5.2(Erection) | 206814764
Erection: SA DAMPER & BURNER TILT ACTUATORS | ERC | 2024-08-30 08:00 | 2024-09-13 17:00 |  |  |  |  | 1.9.5.2.4(Coal Burner System (PG-45)) | 206814765
Air & Flue Gas System | OTH | 2022-09-27 08:00 | 2026-05-28 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206814766
Rel of DWG for Duct Boiler to ESP | PE - RFC | 2023-11-03 08:00 | 2023-11-03 17:00 |  |  |  | PCE-00400 | 1.9.6(Air & Flue Gas System) | 206814767
Rel of DWG for Duct ESP to Chimney | PE - RFC | 2023-12-29 08:00 | 2023-12-29 17:00 |  |  |  | PCE-00450 | 1.9.6(Air & Flue Gas System) | 206814768
Civil Work | CIV | 2023-11-04 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.6(Air & Flue Gas System) | 206814769
BOF to ESP Duct Foundation | CIV | 2023-11-04 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.6.3(Civil Work) | 206814770
Priority (First) Pass | CIV | 2023-11-04 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.6.3.1( BOF to ESP Duct Foundation) | 206814771
BOF to ESP Duct Foundation (PP):- Excavation | CIV | 2023-11-04 08:00 | 2023-12-03 17:00 |  |  |  |  | 1.9.6.3.1.1(Priority (First) Pass) | 206814772
BOF to ESP Duct Foundation (PP):- RCC in substructure including PCC | CIV | 2023-12-04 08:00 | 2024-02-01 17:00 |  |  |  |  | 1.9.6.3.1.1(Priority (First) Pass) | 206814773
BOF to ESP Duct Foundation (PP):- RCC in superstructure | CIV | 2024-12-02 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.9.6.3.1.1(Priority (First) Pass) | 206814774
BOF to ESP Duct Foundation (PP):- Backfilling | CIV | 2025-04-01 08:00 | 2025-04-10 17:00 |  |  |  |  | 1.9.6.3.1.1(Priority (First) Pass) | 206814775
BOF to ESP Duct Foundation (PP):- Finishing works | CIV | 2025-04-11 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.6.3.1.1(Priority (First) Pass) | 206814776
Second Pass | CIV | 2023-11-04 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.6.3.1( BOF to ESP Duct Foundation) | 206814777
BOF to ESP Duct Foundation (SP):- Excavation | CIV | 2023-11-04 08:00 | 2023-12-03 17:00 |  |  |  |  | 1.9.6.3.1.2(Second Pass) | 206814778
BOF to ESP Duct Foundation (SP):- RCC in substructure including PCC | CIV | 2023-12-04 08:00 | 2024-02-01 17:00 |  |  |  |  | 1.9.6.3.1.2(Second Pass) | 206814779
BOF to ESP Duct Foundation (SP):- RCC in superstructure | CIV | 2024-12-02 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.9.6.3.1.2(Second Pass) | 206814780
BOF to ESP Duct Foundation (SP):- Backfilling | CIV | 2025-04-01 08:00 | 2025-04-10 17:00 |  |  |  |  | 1.9.6.3.1.2(Second Pass) | 206814781
BOF to ESP Duct Foundation (SP):- Finishing works | CIV | 2025-04-11 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.6.3.1.2(Second Pass) | 206814782
ESP Outlet to ID Fan Inlet Duct Foundation | CIV | 2024-02-13 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.9.6.3(Civil Work) | 206814783
Priority (First) Pass | CIV | 2024-02-13 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.9.6.3.2( ESP Outlet to ID Fan Inlet Duct Foundation) | 206814784
ESP Outlet to ID Fan Inlet Duct Foundation (PP) :- EXCAVATION | CIV | 2024-02-13 08:00 | 2024-04-07 17:00 |  |  |  |  | 1.9.6.3.2.1(Priority (First) Pass) | 206814785
ESP Outlet to ID Fan Inlet Duct Foundation (PP) :- RCC in substructure including PCC | CIV | 2024-02-28 08:00 | 2024-05-22 17:00 |  |  |  |  | 1.9.6.3.2.1(Priority (First) Pass) | 206814786
ESP Outlet to ID Fan Inlet Duct Foundation (PP) :- RCC in superstructure | CIV | 2024-04-13 08:00 | 2024-08-10 17:00 |  |  |  |  | 1.9.6.3.2.1(Priority (First) Pass) | 206814787
ESP Outlet to ID Fan Inlet Duct Foundation (PP) :- Backfilling | CIV | 2024-08-11 08:00 | 2024-08-22 17:00 |  |  |  |  | 1.9.6.3.2.1(Priority (First) Pass) | 206814788
ESP Outlet to ID Fan Inlet Duct Foundation (PP) :- Finishing works | CIV | 2024-08-23 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.9.6.3.2.1(Priority (First) Pass) | 206814789
Second Pass | CIV | 2024-03-14 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.9.6.3.2( ESP Outlet to ID Fan Inlet Duct Foundation) | 206814790
ESP Outlet to ID Fan Inlet Duct Foundation (SP) :- Excavation | CIV | 2024-03-14 08:00 | 2024-05-07 17:00 |  |  |  |  | 1.9.6.3.2.2(Second Pass) | 206814791
ESP Outlet to ID Fan Inlet Duct Foundation (SP) :- RCC in substructure including PCC | CIV | 2024-03-29 08:00 | 2024-06-21 17:00 |  |  |  |  | 1.9.6.3.2.2(Second Pass) | 206814792
ESP Outlet to ID Fan Inlet Duct Foundation (SP) :- RCC in superstructure | CIV | 2024-05-13 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.9.6.3.2.2(Second Pass) | 206814793
ESP Outlet to ID Fan Inlet Duct Foundation (SP) :- Backfilling | CIV | 2024-09-10 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.9.6.3.2.2(Second Pass) | 206814794
ESP Outlet to ID Fan Inlet Duct Foundation (SP) :- Finishing works | CIV | 2024-09-22 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.9.6.3.2.2(Second Pass) | 206814795
ID Fan Outlet to Chimney Duct Foundation | CIV | 2024-05-08 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.9.6.3(Civil Work) | 206814796
Priority (First) Pass | CIV | 2024-05-08 08:00 | 2024-10-27 17:00 |  |  |  |  | 1.9.6.3.3( ID Fan Outlet to Chimney Duct Foundation) | 206814797
ID Fan Outlet to Chimney Duct Foundation (PP):- EXCAVATION | CIV | 2024-05-08 08:00 | 2024-06-21 17:00 |  |  |  |  | 1.9.6.3.3.1(Priority (First) Pass) | 206814798
ID Fan Outlet to Chimney Duct Foundation (PP):- RCC in substructure including PCC | CIV | 2024-05-24 08:00 | 2024-08-06 17:00 |  |  |  |  | 1.9.6.3.3.1(Priority (First) Pass) | 206814799
ID Fan Outlet to Chimney Duct Foundation (PP):- RCC in superstructure | CIV | 2024-07-08 08:00 | 2024-10-10 17:00 |  |  |  |  | 1.9.6.3.3.1(Priority (First) Pass) | 206814800
ID Fan Outlet to Chimney Duct Foundation (PP):- Backfilling | CIV | 2024-10-11 08:00 | 2024-10-22 17:00 |  |  |  |  | 1.9.6.3.3.1(Priority (First) Pass) | 206814801
ID Fan Outlet to Chimney Duct Foundation (PP):- Finishing works | CIV | 2024-10-23 08:00 | 2024-10-27 17:00 |  |  |  |  | 1.9.6.3.3.1(Priority (First) Pass) | 206814802
Second Pass | CIV | 2024-06-08 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.9.6.3.3( ID Fan Outlet to Chimney Duct Foundation) | 206814803
ID Fan Outlet to Chimney Duct Foundation (SP):- Excavation | CIV | 2024-06-08 08:00 | 2024-07-22 17:00 |  |  |  |  | 1.9.6.3.3.2(Second Pass) | 206814804
ID Fan Outlet to Chimney Duct Foundation (SP):- RCC in substructure including PCC | CIV | 2024-06-24 08:00 | 2024-09-06 17:00 |  |  |  |  | 1.9.6.3.3.2(Second Pass) | 206814805
ID Fan Outlet to Chimney Duct Foundation (SP):- RCC in superstructure | CIV | 2024-08-08 08:00 | 2024-11-10 17:00 |  |  |  |  | 1.9.6.3.3.2(Second Pass) | 206814806
ID Fan Outlet to Chimney Duct Foundation (SP):- Backfilling | CIV | 2024-11-11 08:00 | 2024-11-22 17:00 |  |  |  |  | 1.9.6.3.3.2(Second Pass) | 206814807
ID Fan Outlet to Chimney Duct Foundation (SP):- Finishing works | CIV | 2024-11-23 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.9.6.3.3.2(Second Pass) | 206814808
Supply | SUP | 2022-09-27 08:00 | 2025-04-29 17:00 |  |  |  |  | 1.9.6(Air & Flue Gas System) | 206814809
BHEL TRY | SUP | 2022-09-27 08:00 | 2025-04-29 17:00 |  |  |  |  | 1.9.6.4(Supply ) | 206814810
External Structures ( Supporting Structures for Duct, PG-39 ) | OTH | 2022-09-27 08:00 | 2025-01-27 17:00 |  |  |  | PG39 | 1.9.6.4.1(BHEL TRY) | 206814811
FOUNDATION MATERIALS (PGMA-39010) | SUP | 2022-09-27 08:00 | 2023-05-28 17:00 |  |  |  | 39010 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814812
Engineering | ENG | 2022-09-27 08:00 | 2022-12-20 17:00 |  |  |  | 39010 | 1.9.6.4.1.1.1(FOUNDATION MATERIALS (PGMA-39010)) | 206814813
Manufacturing | MFG | 2022-12-21 08:00 | 2023-03-28 17:00 |  |  |  | 39010 | 1.9.6.4.1.1.1(FOUNDATION MATERIALS (PGMA-39010)) | 206814814
Dispatch | DIS | 2023-03-29 08:00 | 2023-05-28 17:00 |  |  |  | 39010 | 1.9.6.4.1.1.1(FOUNDATION MATERIALS (PGMA-39010)) | 206814815
FOUNDATION MATERIALS I.D.DUCT SUPPORTS (PGMA-39012) | SUP | 2022-09-27 08:00 | 2023-05-28 17:00 |  |  |  | 39012 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814816
Engineering | ENG | 2022-09-27 08:00 | 2022-12-20 17:00 |  |  |  | 39012 | 1.9.6.4.1.1.2(FOUNDATION MATERIALS I.D.DUCT SUPPORTS (PGMA-39012)) | 206814817
Manufacturing | MFG | 2022-12-21 08:00 | 2023-03-28 17:00 |  |  |  | 39012 | 1.9.6.4.1.1.2(FOUNDATION MATERIALS I.D.DUCT SUPPORTS (PGMA-39012)) | 206814818
Dispatch | DIS | 2023-03-29 08:00 | 2023-05-28 17:00 |  |  |  | 39012 | 1.9.6.4.1.1.2(FOUNDATION MATERIALS I.D.DUCT SUPPORTS (PGMA-39012)) | 206814819
COLUMNS/FRAMES BEFORE ESP- LEFT (PGMA-39101) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 39101 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814820
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 39101 | 1.9.6.4.1.1.3(COLUMNS/FRAMES BEFORE ESP- LEFT (PGMA-39101)) | 206814821
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 39101 | 1.9.6.4.1.1.3(COLUMNS/FRAMES BEFORE ESP- LEFT (PGMA-39101)) | 206814822
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 39101 | 1.9.6.4.1.1.3(COLUMNS/FRAMES BEFORE ESP- LEFT (PGMA-39101)) | 206814823
COLUMNS/FRAMES BEFORE ESP- RIGHT (PGMA-39102) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 39102 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814824
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 39102 | 1.9.6.4.1.1.4(COLUMNS/FRAMES BEFORE ESP- RIGHT (PGMA-39102)) | 206814825
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 39102 | 1.9.6.4.1.1.4(COLUMNS/FRAMES BEFORE ESP- RIGHT (PGMA-39102)) | 206814826
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 39102 | 1.9.6.4.1.1.4(COLUMNS/FRAMES BEFORE ESP- RIGHT (PGMA-39102)) | 206814827
COLS/FRAMES NEAR I.D.FAN -LEFT (PGMA-39141) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 39141 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814828
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 39141 | 1.9.6.4.1.1.5(COLS/FRAMES NEAR I.D.FAN -LEFT (PGMA-39141)) | 206814829
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 39141 | 1.9.6.4.1.1.5(COLS/FRAMES NEAR I.D.FAN -LEFT (PGMA-39141)) | 206814830
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 39141 | 1.9.6.4.1.1.5(COLS/FRAMES NEAR I.D.FAN -LEFT (PGMA-39141)) | 206814831
COLS/FRAMES NEAR ID FAN-RIGHT (PGMA-39142) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 39142 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814832
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 39142 | 1.9.6.4.1.1.6(COLS/FRAMES NEAR ID FAN-RIGHT (PGMA-39142)) | 206814833
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 39142 | 1.9.6.4.1.1.6(COLS/FRAMES NEAR ID FAN-RIGHT (PGMA-39142)) | 206814834
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 39142 | 1.9.6.4.1.1.6(COLS/FRAMES NEAR ID FAN-RIGHT (PGMA-39142)) | 206814835
COL/FRAMES BETN I.D.FAN AND Chimney (PGMA-39150) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 39150 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814836
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 39150 | 1.9.6.4.1.1.7(COL/FRAMES BETN I.D.FAN AND Chimney (PGMA-39150)) | 206814837
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 39150 | 1.9.6.4.1.1.7(COL/FRAMES BETN I.D.FAN AND Chimney (PGMA-39150)) | 206814838
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 39150 | 1.9.6.4.1.1.7(COL/FRAMES BETN I.D.FAN AND Chimney (PGMA-39150)) | 206814839
PLATFORMS EXTL STRUC BOF TO ESP (PGMA-39299) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 39299 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814840
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 39299 | 1.9.6.4.1.1.8(PLATFORMS EXTL STRUC BOF TO ESP (PGMA-39299)) | 206814841
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 39299 | 1.9.6.4.1.1.8(PLATFORMS EXTL STRUC BOF TO ESP (PGMA-39299)) | 206814842
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 39299 | 1.9.6.4.1.1.8(PLATFORMS EXTL STRUC BOF TO ESP (PGMA-39299)) | 206814843
PLATFORMS -EXTERNAL STRUCTURE (PGMA-39300) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 39300 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814844
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 39300 | 1.9.6.4.1.1.9(PLATFORMS -EXTERNAL STRUCTURE (PGMA-39300)) | 206814845
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 39300 | 1.9.6.4.1.1.9(PLATFORMS -EXTERNAL STRUCTURE (PGMA-39300)) | 206814846
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 39300 | 1.9.6.4.1.1.9(PLATFORMS -EXTERNAL STRUCTURE (PGMA-39300)) | 206814847
STRUC AND PLATFORM/FOR FANS (PGMA-39301) | SUP | 2023-07-02 08:00 | 2024-11-27 17:00 |  |  |  | 39301 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814848
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 39301 | 1.9.6.4.1.1.10(STRUC AND PLATFORM/FOR FANS (PGMA-39301)) | 206814849
Manufacturing | MFG | 2024-03-23 08:00 | 2024-10-28 17:00 |  |  |  | 39301 | 1.9.6.4.1.1.10(STRUC AND PLATFORM/FOR FANS (PGMA-39301)) | 206814850
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 39301 | 1.9.6.4.1.1.10(STRUC AND PLATFORM/FOR FANS (PGMA-39301)) | 206814851
STRUC FOR MOTOR HOOD/COVERING (PGMA-39302) | SUP | 2023-07-02 08:00 | 2025-01-27 17:00 |  |  |  | 39302 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814852
Engineering | ENG | 2023-07-02 08:00 | 2024-03-22 17:00 |  |  |  | 39302 | 1.9.6.4.1.1.11(STRUC FOR MOTOR HOOD/COVERING (PGMA-39302)) | 206814853
Manufacturing | MFG | 2024-03-23 08:00 | 2024-12-28 17:00 |  |  |  | 39302 | 1.9.6.4.1.1.11(STRUC FOR MOTOR HOOD/COVERING (PGMA-39302)) | 206814854
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 39302 | 1.9.6.4.1.1.11(STRUC FOR MOTOR HOOD/COVERING (PGMA-39302)) | 206814855
FAN HANDLING STRUCTURE FOR FD FAN (PGMA-39304) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 39304 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814856
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 39304 | 1.9.6.4.1.1.12(FAN HANDLING STRUCTURE FOR FD FAN (PGMA-39304)) | 206814857
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 39304 | 1.9.6.4.1.1.12(FAN HANDLING STRUCTURE FOR FD FAN (PGMA-39304)) | 206814858
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 39304 | 1.9.6.4.1.1.12(FAN HANDLING STRUCTURE FOR FD FAN (PGMA-39304)) | 206814859
FAN HANDLING STRUCTURE FOR PA FAN (PGMA-39305) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 39305 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814860
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 39305 | 1.9.6.4.1.1.13(FAN HANDLING STRUCTURE FOR PA FAN (PGMA-39305)) | 206814861
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 39305 | 1.9.6.4.1.1.13(FAN HANDLING STRUCTURE FOR PA FAN (PGMA-39305)) | 206814862
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 39305 | 1.9.6.4.1.1.13(FAN HANDLING STRUCTURE FOR PA FAN (PGMA-39305)) | 206814863
FAN HANDLING STRUCTURE FOR ID FAN (PGMA-39306) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 39306 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814864
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 39306 | 1.9.6.4.1.1.14(FAN HANDLING STRUCTURE FOR ID FAN (PGMA-39306)) | 206814865
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 39306 | 1.9.6.4.1.1.14(FAN HANDLING STRUCTURE FOR ID FAN (PGMA-39306)) | 206814866
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 39306 | 1.9.6.4.1.1.14(FAN HANDLING STRUCTURE FOR ID FAN (PGMA-39306)) | 206814867
HSFG FASTENERS FOR PG 39 (PGMA-39700) | SUP | 2023-02-08 08:00 | 2024-05-29 17:00 |  |  |  | 39700 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814868
Engineering | ENG | 2023-02-08 08:00 | 2023-09-10 17:00 |  |  |  | 39700 | 1.9.6.4.1.1.15(HSFG FASTENERS FOR PG 39 (PGMA-39700)) | 206814869
Manufacturing | MFG | 2023-09-11 08:00 | 2024-04-29 17:00 |  |  |  | 39700 | 1.9.6.4.1.1.15(HSFG FASTENERS FOR PG 39 (PGMA-39700)) | 206814870
Dispatch | DIS | 2024-04-30 08:00 | 2024-05-29 17:00 |  |  |  | 39700 | 1.9.6.4.1.1.15(HSFG FASTENERS FOR PG 39 (PGMA-39700)) | 206814871
FLOOR GRILL (PGMA-39810) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 39810 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814872
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 39810 | 1.9.6.4.1.1.16(FLOOR GRILL (PGMA-39810)) | 206814873
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 39810 | 1.9.6.4.1.1.16(FLOOR GRILL (PGMA-39810)) | 206814874
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 39810 | 1.9.6.4.1.1.16(FLOOR GRILL (PGMA-39810)) | 206814875
STAIRS (PGMA-39820) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 39820 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814876
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 39820 | 1.9.6.4.1.1.17(STAIRS (PGMA-39820)) | 206814877
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 39820 | 1.9.6.4.1.1.17(STAIRS (PGMA-39820)) | 206814878
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 39820 | 1.9.6.4.1.1.17(STAIRS (PGMA-39820)) | 206814879
HAND RAIL AND HAND RAIL POSTS (PGMA-39850) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 39850 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814880
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 39850 | 1.9.6.4.1.1.18(HAND RAIL AND HAND RAIL POSTS (PGMA-39850)) | 206814881
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 39850 | 1.9.6.4.1.1.18(HAND RAIL AND HAND RAIL POSTS (PGMA-39850)) | 206814882
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 39850 | 1.9.6.4.1.1.18(HAND RAIL AND HAND RAIL POSTS (PGMA-39850)) | 206814883
CONSUMABLES &Erection MATERIALS (PGMA-39993) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 39993 | 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206814884
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 39993 | 1.9.6.4.1.1.19(CONSUMABLES &Erection MATERIALS (PGMA-39993)) | 206814885
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 39993 | 1.9.6.4.1.1.19(CONSUMABLES &Erection MATERIALS (PGMA-39993)) | 206814886
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 39993 | 1.9.6.4.1.1.19(CONSUMABLES &Erection MATERIALS (PGMA-39993)) | 206814887
Duct., Dampers and Expn. Joints (PG-48) | SUP | 2022-09-27 08:00 | 2025-04-29 17:00 |  |  |  | PG48 | 1.9.6.4.1(BHEL TRY) | 206814888
RECT DUCT BET F.D FAN AND AIRHEATER (PGMA-48012) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48012 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814889
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48012 | 1.9.6.4.1.2.1(RECT DUCT BET F.D FAN AND AIRHEATER (PGMA-48012)) | 206814890
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48012 | 1.9.6.4.1.2.1(RECT DUCT BET F.D FAN AND AIRHEATER (PGMA-48012)) | 206814891
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48012 | 1.9.6.4.1.2.1(RECT DUCT BET F.D FAN AND AIRHEATER (PGMA-48012)) | 206814892
EXPN PIECESBET F.D FAN AND AIRHEATER (PGMA-48014) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48014 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814893
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48014 | 1.9.6.4.1.2.2(EXPN PIECESBET F.D FAN AND AIRHEATER (PGMA-48014)) | 206814894
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48014 | 1.9.6.4.1.2.2(EXPN PIECESBET F.D FAN AND AIRHEATER (PGMA-48014)) | 206814895
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48014 | 1.9.6.4.1.2.2(EXPN PIECESBET F.D FAN AND AIRHEATER (PGMA-48014)) | 206814896
SUPPORTSETCBET F.D FAN AND AIRHEATER (PGMA-48015) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48015 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814897
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48015 | 1.9.6.4.1.2.3(SUPPORTSETCBET F.D FAN AND AIRHEATER (PGMA-48015)) | 206814898
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48015 | 1.9.6.4.1.2.3(SUPPORTSETCBET F.D FAN AND AIRHEATER (PGMA-48015)) | 206814899
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48015 | 1.9.6.4.1.2.3(SUPPORTSETCBET F.D FAN AND AIRHEATER (PGMA-48015)) | 206814900
DUCTS - SCAPH TO SAH (PGMA-48018) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48018 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814901
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48018 | 1.9.6.4.1.2.4(DUCTS - SCAPH TO SAH (PGMA-48018)) | 206814902
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48018 | 1.9.6.4.1.2.4(DUCTS - SCAPH TO SAH (PGMA-48018)) | 206814903
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48018 | 1.9.6.4.1.2.4(DUCTS - SCAPH TO SAH (PGMA-48018)) | 206814904
FOUNDATION MATERIALS (PGMA-48019) | SUP | 2022-09-27 08:00 | 2023-10-27 17:00 |  |  |  | 48019 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814905
Engineering | ENG | 2022-09-27 08:00 | 2023-03-26 17:00 |  |  |  | 48019 | 1.9.6.4.1.2.5(FOUNDATION MATERIALS (PGMA-48019)) | 206814906
Manufacturing | MFG | 2023-03-27 08:00 | 2023-09-27 17:00 |  |  |  | 48019 | 1.9.6.4.1.2.5(FOUNDATION MATERIALS (PGMA-48019)) | 206814907
Dispatch | DIS | 2023-09-28 08:00 | 2023-10-27 17:00 |  |  |  | 48019 | 1.9.6.4.1.2.5(FOUNDATION MATERIALS (PGMA-48019)) | 206814908
RECT DUCTS PRI FAN TO AIRHEATER PRISID (PGMA-48112) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48112 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814909
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48112 | 1.9.6.4.1.2.6(RECT DUCTS PRI FAN TO AIRHEATER PRISID (PGMA-48112)) | 206814910
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48112 | 1.9.6.4.1.2.6(RECT DUCTS PRI FAN TO AIRHEATER PRISID (PGMA-48112)) | 206814911
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48112 | 1.9.6.4.1.2.6(RECT DUCTS PRI FAN TO AIRHEATER PRISID (PGMA-48112)) | 206814912
EXPN PIECESPRI FAN TO AIRHEATER PRISID (PGMA-48114) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48114 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814913
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48114 | 1.9.6.4.1.2.7(EXPN PIECESPRI FAN TO AIRHEATER PRISID (PGMA-48114)) | 206814914
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48114 | 1.9.6.4.1.2.7(EXPN PIECESPRI FAN TO AIRHEATER PRISID (PGMA-48114)) | 206814915
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48114 | 1.9.6.4.1.2.7(EXPN PIECESPRI FAN TO AIRHEATER PRISID (PGMA-48114)) | 206814916
SUPPORTSETCPRI FAN TO AIRHEATER PRISID (PGMA-48115) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48115 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814917
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48115 | 1.9.6.4.1.2.8(SUPPORTSETCPRI FAN TO AIRHEATER PRISID (PGMA-48115)) | 206814918
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48115 | 1.9.6.4.1.2.8(SUPPORTSETCPRI FAN TO AIRHEATER PRISID (PGMA-48115)) | 206814919
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48115 | 1.9.6.4.1.2.8(SUPPORTSETCPRI FAN TO AIRHEATER PRISID (PGMA-48115)) | 206814920
SEAL AIR HAG AND ID FAN OUTGATE (PGMA-48141) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48141 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814921
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48141 | 1.9.6.4.1.2.9(SEAL AIR HAG AND ID FAN OUTGATE (PGMA-48141)) | 206814922
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48141 | 1.9.6.4.1.2.9(SEAL AIR HAG AND ID FAN OUTGATE (PGMA-48141)) | 206814923
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48141 | 1.9.6.4.1.2.9(SEAL AIR HAG AND ID FAN OUTGATE (PGMA-48141)) | 206814924
RECT DUCT COLDAIRBUS(TEMP AIR TO MILL (PGMA-48142) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48142 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814925
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48142 | 1.9.6.4.1.2.10(RECT DUCT COLDAIRBUS(TEMP AIR TO MILL (PGMA-48142)) | 206814926
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48142 | 1.9.6.4.1.2.10(RECT DUCT COLDAIRBUS(TEMP AIR TO MILL (PGMA-48142)) | 206814927
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48142 | 1.9.6.4.1.2.10(RECT DUCT COLDAIRBUS(TEMP AIR TO MILL (PGMA-48142)) | 206814928
EXPN PIECESCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48144) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48144 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814929
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48144 | 1.9.6.4.1.2.11(EXPN PIECESCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48144)) | 206814930
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48144 | 1.9.6.4.1.2.11(EXPN PIECESCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48144)) | 206814931
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48144 | 1.9.6.4.1.2.11(EXPN PIECESCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48144)) | 206814932
SUPPORTSETCCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48145) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48145 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814933
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48145 | 1.9.6.4.1.2.12(SUPPORTSETCCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48145)) | 206814934
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48145 | 1.9.6.4.1.2.12(SUPPORTSETCCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48145)) | 206814935
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48145 | 1.9.6.4.1.2.12(SUPPORTSETCCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48145)) | 206814936
INSTRUMENT TAPPINGS ON DUCTING (PGMA-48200) | SUP | 2023-08-22 08:00 | 2025-04-29 17:00 |  |  |  | 48200 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814937
Engineering | ENG | 2023-08-22 08:00 | 2024-06-11 17:00 |  |  |  | 48200 | 1.9.6.4.1.2.13(INSTRUMENT TAPPINGS ON DUCTING (PGMA-48200)) | 206814938
Manufacturing | MFG | 2024-06-12 08:00 | 2025-03-30 17:00 |  |  |  | 48200 | 1.9.6.4.1.2.13(INSTRUMENT TAPPINGS ON DUCTING (PGMA-48200)) | 206814939
Dispatch | DIS | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  | 48200 | 1.9.6.4.1.2.13(INSTRUMENT TAPPINGS ON DUCTING (PGMA-48200)) | 206814940
RECT DUCTSAIRHEATER TO WINDBOXDUCT (PGMA-48202) | SUP | 2023-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48202 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814941
Engineering | ENG | 2023-08-22 08:00 | 2024-02-18 17:00 |  |  |  | 48202 | 1.9.6.4.1.2.14(RECT DUCTSAIRHEATER TO WINDBOXDUCT (PGMA-48202)) | 206814942
Manufacturing | MFG | 2024-02-19 08:00 | 2024-08-21 17:00 |  |  |  | 48202 | 1.9.6.4.1.2.14(RECT DUCTSAIRHEATER TO WINDBOXDUCT (PGMA-48202)) | 206814943
Dispatch | DIS | 2024-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48202 | 1.9.6.4.1.2.14(RECT DUCTSAIRHEATER TO WINDBOXDUCT (PGMA-48202)) | 206814944
EXPN PIECESAIRHEATER TO WINDBOXDUCT (PGMA-48204) | SUP | 2023-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48204 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814945
Engineering | ENG | 2023-08-22 08:00 | 2024-02-18 17:00 |  |  |  | 48204 | 1.9.6.4.1.2.15(EXPN PIECESAIRHEATER TO WINDBOXDUCT (PGMA-48204)) | 206814946
Manufacturing | MFG | 2024-02-19 08:00 | 2024-08-21 17:00 |  |  |  | 48204 | 1.9.6.4.1.2.15(EXPN PIECESAIRHEATER TO WINDBOXDUCT (PGMA-48204)) | 206814947
Dispatch | DIS | 2024-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48204 | 1.9.6.4.1.2.15(EXPN PIECESAIRHEATER TO WINDBOXDUCT (PGMA-48204)) | 206814948
SUPPORTSETCAIRHEATER TO WINDBOXDUCT (PGMA-48205) | SUP | 2023-08-22 08:00 | 2024-10-21 17:00 |  |  |  | 48205 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814949
Engineering | ENG | 2023-08-22 08:00 | 2024-02-25 17:00 |  |  |  | 48205 | 1.9.6.4.1.2.16(SUPPORTSETCAIRHEATER TO WINDBOXDUCT (PGMA-48205)) | 206814950
Manufacturing | MFG | 2024-02-26 08:00 | 2024-09-21 17:00 |  |  |  | 48205 | 1.9.6.4.1.2.16(SUPPORTSETCAIRHEATER TO WINDBOXDUCT (PGMA-48205)) | 206814951
Dispatch | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  | 48205 | 1.9.6.4.1.2.16(SUPPORTSETCAIRHEATER TO WINDBOXDUCT (PGMA-48205)) | 206814952
CLH/VLH -HOT AIR (PGMA-48206) | SUP | 2023-08-22 08:00 | 2024-10-21 17:00 |  |  |  | 48206 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814953
Engineering | ENG | 2023-08-22 08:00 | 2024-02-25 17:00 |  |  |  | 48206 | 1.9.6.4.1.2.17(CLH/VLH -HOT AIR (PGMA-48206)) | 206814954
Manufacturing | MFG | 2024-02-26 08:00 | 2024-09-21 17:00 |  |  |  | 48206 | 1.9.6.4.1.2.17(CLH/VLH -HOT AIR (PGMA-48206)) | 206814955
Dispatch | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  | 48206 | 1.9.6.4.1.2.17(CLH/VLH -HOT AIR (PGMA-48206)) | 206814956
FLOWMETERS FOR SECONDARY AIR FLOW (PGMA-48207) | SUP | 2023-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48207 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814957
Engineering | ENG | 2023-08-22 08:00 | 2024-02-18 17:00 |  |  |  | 48207 | 1.9.6.4.1.2.18(FLOWMETERS FOR SECONDARY AIR FLOW (PGMA-48207)) | 206814958
Manufacturing | MFG | 2024-02-19 08:00 | 2024-08-21 17:00 |  |  |  | 48207 | 1.9.6.4.1.2.18(FLOWMETERS FOR SECONDARY AIR FLOW (PGMA-48207)) | 206814959
Dispatch | DIS | 2024-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48207 | 1.9.6.4.1.2.18(FLOWMETERS FOR SECONDARY AIR FLOW (PGMA-48207)) | 206814960
DUCT-SEC.AIR TO WB (PGMA-48208) | SUP | 2023-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48208 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814961
Engineering | ENG | 2023-08-22 08:00 | 2024-02-18 17:00 |  |  |  | 48208 | 1.9.6.4.1.2.19(DUCT-SEC.AIR TO WB (PGMA-48208)) | 206814962
Manufacturing | MFG | 2024-02-19 08:00 | 2024-08-21 17:00 |  |  |  | 48208 | 1.9.6.4.1.2.19(DUCT-SEC.AIR TO WB (PGMA-48208)) | 206814963
Dispatch | DIS | 2024-08-22 08:00 | 2024-09-20 17:00 |  |  |  | 48208 | 1.9.6.4.1.2.19(DUCT-SEC.AIR TO WB (PGMA-48208)) | 206814964
WIND BOX CONNECTING DUCTS - RECTANGULA (PGMA-48212) | SUP | 2023-08-22 08:00 | 2024-11-21 17:00 |  |  |  | 48212 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814965
Engineering | ENG | 2023-08-22 08:00 | 2024-02-25 17:00 |  |  |  | 48212 | 1.9.6.4.1.2.20(WIND BOX CONNECTING DUCTS - RECTANGULA (PGMA-48212)) | 206814966
Manufacturing | MFG | 2024-02-26 08:00 | 2024-10-22 17:00 |  |  |  | 48212 | 1.9.6.4.1.2.20(WIND BOX CONNECTING DUCTS - RECTANGULA (PGMA-48212)) | 206814967
Dispatch | DIS | 2024-10-23 08:00 | 2024-11-21 17:00 |  |  |  | 48212 | 1.9.6.4.1.2.20(WIND BOX CONNECTING DUCTS - RECTANGULA (PGMA-48212)) | 206814968
EXPN PIECESWINDBOX CONNECTING DUCT (PGMA-48214) | SUP | 2023-08-22 08:00 | 2024-11-21 17:00 |  |  |  | 48214 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814969
Engineering | ENG | 2023-08-22 08:00 | 2024-02-25 17:00 |  |  |  | 48214 | 1.9.6.4.1.2.21(EXPN PIECESWINDBOX CONNECTING DUCT (PGMA-48214)) | 206814970
Manufacturing | MFG | 2024-02-26 08:00 | 2024-10-22 17:00 |  |  |  | 48214 | 1.9.6.4.1.2.21(EXPN PIECESWINDBOX CONNECTING DUCT (PGMA-48214)) | 206814971
Dispatch | DIS | 2024-10-23 08:00 | 2024-11-21 17:00 |  |  |  | 48214 | 1.9.6.4.1.2.21(EXPN PIECESWINDBOX CONNECTING DUCT (PGMA-48214)) | 206814972
RECT DUCT-AIRHEATER PRISIDETOHOTAIR B (PGMA-48222) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48222 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814973
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48222 | 1.9.6.4.1.2.22(RECT DUCT-AIRHEATER PRISIDETOHOTAIR B (PGMA-48222)) | 206814974
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48222 | 1.9.6.4.1.2.22(RECT DUCT-AIRHEATER PRISIDETOHOTAIR B (PGMA-48222)) | 206814975
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48222 | 1.9.6.4.1.2.22(RECT DUCT-AIRHEATER PRISIDETOHOTAIR B (PGMA-48222)) | 206814976
EXPN PIECES AIRHEATER PREECEDE TO HOTAIR B (PGMA-48224) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48224 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814977
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48224 | 1.9.6.4.1.2.23(EXPN PIECES AIRHEATER PREECEDE TO HOTAIR B (PGMA-48224)) | 206814978
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48224 | 1.9.6.4.1.2.23(EXPN PIECES AIRHEATER PREECEDE TO HOTAIR B (PGMA-48224)) | 206814979
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48224 | 1.9.6.4.1.2.23(EXPN PIECES AIRHEATER PREECEDE TO HOTAIR B (PGMA-48224)) | 206814980
SUPPORTS FOR HOT P.A (AH TO HOT BUS) (PGMA-48225) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814981
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48225 | 1.9.6.4.1.2.24(SUPPORTS FOR HOT P.A (AH TO HOT BUS) (PGMA-48225)) | 206814982
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48225 | 1.9.6.4.1.2.24(SUPPORTS FOR HOT P.A (AH TO HOT BUS) (PGMA-48225)) | 206814983
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48225 | 1.9.6.4.1.2.24(SUPPORTS FOR HOT P.A (AH TO HOT BUS) (PGMA-48225)) | 206814984
RECT DUCTS HOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48232) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48232 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814985
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48232 | 1.9.6.4.1.2.25(RECT DUCTS HOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48232)) | 206814986
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48232 | 1.9.6.4.1.2.25(RECT DUCTS HOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48232)) | 206814987
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48232 | 1.9.6.4.1.2.25(RECT DUCTS HOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48232)) | 206814988
EXPN PIECESHOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48234) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48234 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814989
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48234 | 1.9.6.4.1.2.26(EXPN PIECESHOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48234)) | 206814990
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48234 | 1.9.6.4.1.2.26(EXPN PIECESHOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48234)) | 206814991
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48234 | 1.9.6.4.1.2.26(EXPN PIECESHOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48234)) | 206814992
SUPPORT HOT AIR BUS (PGMA-48235) | SUP | 2023-08-17 08:00 | 2025-01-27 17:00 |  |  |  | 48235 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814993
Engineering | ENG | 2023-08-17 08:00 | 2024-04-17 17:00 |  |  |  | 48235 | 1.9.6.4.1.2.27(SUPPORT HOT AIR BUS (PGMA-48235)) | 206814994
Manufacturing | MFG | 2024-04-18 08:00 | 2024-12-28 17:00 |  |  |  | 48235 | 1.9.6.4.1.2.27(SUPPORT HOT AIR BUS (PGMA-48235)) | 206814995
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  | 48235 | 1.9.6.4.1.2.27(SUPPORT HOT AIR BUS (PGMA-48235)) | 206814996
RECT DUCT AIRHTR TOPRINOZZLE AND SECA (PGMA-48262) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48262 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206814997
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48262 | 1.9.6.4.1.2.28(RECT DUCT AIRHTR TOPRINOZZLE AND SECA (PGMA-48262)) | 206814998
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48262 | 1.9.6.4.1.2.28(RECT DUCT AIRHTR TOPRINOZZLE AND SECA (PGMA-48262)) | 206814999
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48262 | 1.9.6.4.1.2.28(RECT DUCT AIRHTR TOPRINOZZLE AND SECA (PGMA-48262)) | 206815000
EXPN PIECESAIRHTR TOPRINOZZLE AND SECA (PGMA-48264) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48264 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815001
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48264 | 1.9.6.4.1.2.29(EXPN PIECESAIRHTR TOPRINOZZLE AND SECA (PGMA-48264)) | 206815002
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48264 | 1.9.6.4.1.2.29(EXPN PIECESAIRHTR TOPRINOZZLE AND SECA (PGMA-48264)) | 206815003
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48264 | 1.9.6.4.1.2.29(EXPN PIECESAIRHTR TOPRINOZZLE AND SECA (PGMA-48264)) | 206815004
SUPPORTSETCAIRHTR TOPRINOZZLE AND SECA (PGMA-48265) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48265 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815005
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48265 | 1.9.6.4.1.2.30(SUPPORTSETCAIRHTR TOPRINOZZLE AND SECA (PGMA-48265)) | 206815006
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48265 | 1.9.6.4.1.2.30(SUPPORTSETCAIRHTR TOPRINOZZLE AND SECA (PGMA-48265)) | 206815007
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48265 | 1.9.6.4.1.2.30(SUPPORTSETCAIRHTR TOPRINOZZLE AND SECA (PGMA-48265)) | 206815008
FLOW METER (PGMA-48267) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48267 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815009
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48267 | 1.9.6.4.1.2.31(FLOW METER (PGMA-48267)) | 206815010
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48267 | 1.9.6.4.1.2.31(FLOW METER (PGMA-48267)) | 206815011
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48267 | 1.9.6.4.1.2.31(FLOW METER (PGMA-48267)) | 206815012
RECT DUCT CASCADE EVAPORATOR TO EP (PGMA-48372) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48372 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815013
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48372 | 1.9.6.4.1.2.32(RECT DUCT CASCADE EVAPORATOR TO EP (PGMA-48372)) | 206815014
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48372 | 1.9.6.4.1.2.32(RECT DUCT CASCADE EVAPORATOR TO EP (PGMA-48372)) | 206815015
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48372 | 1.9.6.4.1.2.32(RECT DUCT CASCADE EVAPORATOR TO EP (PGMA-48372)) | 206815016
RECT DUCT ECONOMISER TO AIRHEATER2NOP (PGMA-48382) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48382 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815017
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48382 | 1.9.6.4.1.2.33(RECT DUCT ECONOMISER TO AIRHEATER2NOP (PGMA-48382)) | 206815018
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48382 | 1.9.6.4.1.2.33(RECT DUCT ECONOMISER TO AIRHEATER2NOP (PGMA-48382)) | 206815019
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48382 | 1.9.6.4.1.2.33(RECT DUCT ECONOMISER TO AIRHEATER2NOP (PGMA-48382)) | 206815020
EXPN PIECESECONOMISER TO AIRHEATER2NOP (PGMA-48384) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48384 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815021
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48384 | 1.9.6.4.1.2.34(EXPN PIECESECONOMISER TO AIRHEATER2NOP (PGMA-48384)) | 206815022
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48384 | 1.9.6.4.1.2.34(EXPN PIECESECONOMISER TO AIRHEATER2NOP (PGMA-48384)) | 206815023
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48384 | 1.9.6.4.1.2.34(EXPN PIECESECONOMISER TO AIRHEATER2NOP (PGMA-48384)) | 206815024
SUPPORTSETCECONOMISER TO AIRHEATER2NOP (PGMA-48385) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48385 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815025
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48385 | 1.9.6.4.1.2.35(SUPPORTSETCECONOMISER TO AIRHEATER2NOP (PGMA-48385)) | 206815026
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48385 | 1.9.6.4.1.2.35(SUPPORTSETCECONOMISER TO AIRHEATER2NOP (PGMA-48385)) | 206815027
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48385 | 1.9.6.4.1.2.35(SUPPORTSETCECONOMISER TO AIRHEATER2NOP (PGMA-48385)) | 206815028
DUCT BELOW DIVERTOR & SCR SYSTEM(PGMA-48386) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48386 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815029
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48386 | 1.9.6.4.1.2.36(DUCT BELOW DIVERTOR & SCR SYSTEM(PGMA-48386)) | 206815030
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48386 | 1.9.6.4.1.2.36(DUCT BELOW DIVERTOR & SCR SYSTEM(PGMA-48386)) | 206815031
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48386 | 1.9.6.4.1.2.36(DUCT BELOW DIVERTOR & SCR SYSTEM(PGMA-48386)) | 206815032
CLH/VLH-FLUE GAS (PGMA-48395) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  | 48395 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815033
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48395 | 1.9.6.4.1.2.37(CLH/VLH-FLUE GAS (PGMA-48395)) | 206815034
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48395 | 1.9.6.4.1.2.37(CLH/VLH-FLUE GAS (PGMA-48395)) | 206815035
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48395 | 1.9.6.4.1.2.37(CLH/VLH-FLUE GAS (PGMA-48395)) | 206815036
RECT DUCT AIRHEATER BOILER OUTLET-GAS (PGMA-48432) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 48432 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815037
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 48432 | 1.9.6.4.1.2.38(RECT DUCT AIRHEATER BOILER OUTLET-GAS (PGMA-48432)) | 206815038
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 48432 | 1.9.6.4.1.2.38(RECT DUCT AIRHEATER BOILER OUTLET-GAS (PGMA-48432)) | 206815039
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 48432 | 1.9.6.4.1.2.38(RECT DUCT AIRHEATER BOILER OUTLET-GAS (PGMA-48432)) | 206815040
EXPN PIECESAIRHEATER BOILER OUTLET-GAS (PGMA-48434) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 48434 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815041
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 48434 | 1.9.6.4.1.2.39(EXPN PIECESAIRHEATER BOILER OUTLET-GAS (PGMA-48434)) | 206815042
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 48434 | 1.9.6.4.1.2.39(EXPN PIECESAIRHEATER BOILER OUTLET-GAS (PGMA-48434)) | 206815043
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 48434 | 1.9.6.4.1.2.39(EXPN PIECESAIRHEATER BOILER OUTLET-GAS (PGMA-48434)) | 206815044
SUPPORTSETCAIRHEATER BOILER OUTLET-GAS (PGMA-48435) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 48435 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815045
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 48435 | 1.9.6.4.1.2.40(SUPPORTSETCAIRHEATER BOILER OUTLET-GAS (PGMA-48435)) | 206815046
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 48435 | 1.9.6.4.1.2.40(SUPPORTSETCAIRHEATER BOILER OUTLET-GAS (PGMA-48435)) | 206815047
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 48435 | 1.9.6.4.1.2.40(SUPPORTSETCAIRHEATER BOILER OUTLET-GAS (PGMA-48435)) | 206815048
RECT DUCT BOILER OUTLET TO ELEC PRECP (PGMA-48462) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 48462 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815049
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 48462 | 1.9.6.4.1.2.41(RECT DUCT BOILER OUTLET TO ELEC PRECP (PGMA-48462)) | 206815050
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 48462 | 1.9.6.4.1.2.41(RECT DUCT BOILER OUTLET TO ELEC PRECP (PGMA-48462)) | 206815051
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 48462 | 1.9.6.4.1.2.41(RECT DUCT BOILER OUTLET TO ELEC PRECP (PGMA-48462)) | 206815052
EXPN PIECESBOILER OUTLET TO ELEC PRECP (PGMA-48464) | SUP | 2023-06-12 08:00 | 2024-12-28 17:00 |  |  |  | 48464 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815053
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 48464 | 1.9.6.4.1.2.42(EXPN PIECESBOILER OUTLET TO ELEC PRECP (PGMA-48464)) | 206815054
Manufacturing | MFG | 2024-02-29 08:00 | 2024-11-28 17:00 |  |  |  | 48464 | 1.9.6.4.1.2.42(EXPN PIECESBOILER OUTLET TO ELEC PRECP (PGMA-48464)) | 206815055
Dispatch | DIS | 2024-11-29 08:00 | 2024-12-28 17:00 |  |  |  | 48464 | 1.9.6.4.1.2.42(EXPN PIECESBOILER OUTLET TO ELEC PRECP (PGMA-48464)) | 206815056
BOF TO EP DUCTING SUPPORTS (PGMA-48465) | SUP | 2023-06-12 08:00 | 2024-10-28 17:00 |  |  |  | 48465 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815057
Engineering | ENG | 2023-06-12 08:00 | 2024-02-28 17:00 |  |  |  | 48465 | 1.9.6.4.1.2.43(BOF TO EP DUCTING SUPPORTS (PGMA-48465)) | 206815058
Manufacturing | MFG | 2024-02-29 08:00 | 2024-09-28 17:00 |  |  |  | 48465 | 1.9.6.4.1.2.43(BOF TO EP DUCTING SUPPORTS (PGMA-48465)) | 206815059
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48465 | 1.9.6.4.1.2.43(BOF TO EP DUCTING SUPPORTS (PGMA-48465)) | 206815060
RECT DUCTS-ELEC PRPTR/M.S TO INDDRAFTF (PGMA-48482) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48482 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815061
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48482 | 1.9.6.4.1.2.44(RECT DUCTS-ELEC PRPTR/M.S TO INDDRAFTF (PGMA-48482)) | 206815062
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48482 | 1.9.6.4.1.2.44(RECT DUCTS-ELEC PRPTR/M.S TO INDDRAFTF (PGMA-48482)) | 206815063
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48482 | 1.9.6.4.1.2.44(RECT DUCTS-ELEC PRPTR/M.S TO INDDRAFTF (PGMA-48482)) | 206815064
EXPN PIECESELEC PRPTR/M.S TO INDDRAFTF (PGMA-48484) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48484 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815065
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48484 | 1.9.6.4.1.2.45(EXPN PIECESELEC PRPTR/M.S TO INDDRAFTF (PGMA-48484)) | 206815066
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48484 | 1.9.6.4.1.2.45(EXPN PIECESELEC PRPTR/M.S TO INDDRAFTF (PGMA-48484)) | 206815067
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48484 | 1.9.6.4.1.2.45(EXPN PIECESELEC PRPTR/M.S TO INDDRAFTF (PGMA-48484)) | 206815068
SUPPORTSETCELEC PRPTR/M.S TO INDDRAFTF (PGMA-48485) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48485 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815069
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48485 | 1.9.6.4.1.2.46(SUPPORTSETCELEC PRPTR/M.S TO INDDRAFTF (PGMA-48485)) | 206815070
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48485 | 1.9.6.4.1.2.46(SUPPORTSETCELEC PRPTR/M.S TO INDDRAFTF (PGMA-48485)) | 206815071
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48485 | 1.9.6.4.1.2.46(SUPPORTSETCELEC PRPTR/M.S TO INDDRAFTF (PGMA-48485)) | 206815072
RECT DUCT IND DRAFT FAN TO Chimney (PGMA-48492) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48492 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815073
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48492 | 1.9.6.4.1.2.47(RECT DUCT IND DRAFT FAN TO Chimney (PGMA-48492)) | 206815074
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48492 | 1.9.6.4.1.2.47(RECT DUCT IND DRAFT FAN TO Chimney (PGMA-48492)) | 206815075
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48492 | 1.9.6.4.1.2.47(RECT DUCT IND DRAFT FAN TO Chimney (PGMA-48492)) | 206815076
EXPN PIECESIND DRAFT FAN TO Chimney (PGMA-48494) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48494 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815077
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48494 | 1.9.6.4.1.2.48(EXPN PIECESIND DRAFT FAN TO Chimney (PGMA-48494)) | 206815078
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48494 | 1.9.6.4.1.2.48(EXPN PIECESIND DRAFT FAN TO Chimney (PGMA-48494)) | 206815079
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48494 | 1.9.6.4.1.2.48(EXPN PIECESIND DRAFT FAN TO Chimney (PGMA-48494)) | 206815080
I.D.SYSTEM DUCT SUPPORTS (PGMA-48495) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48495 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815081
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48495 | 1.9.6.4.1.2.49(I.D.SYSTEM DUCT SUPPORTS (PGMA-48495)) | 206815082
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48495 | 1.9.6.4.1.2.49(I.D.SYSTEM DUCT SUPPORTS (PGMA-48495)) | 206815083
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48495 | 1.9.6.4.1.2.49(I.D.SYSTEM DUCT SUPPORTS (PGMA-48495)) | 206815084
RECT DUCT HOT AIR BUS TO MILLS (PGMA-48662) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 48662 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815085
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 48662 | 1.9.6.4.1.2.50(RECT DUCT HOT AIR BUS TO MILLS (PGMA-48662)) | 206815086
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 48662 | 1.9.6.4.1.2.50(RECT DUCT HOT AIR BUS TO MILLS (PGMA-48662)) | 206815087
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 48662 | 1.9.6.4.1.2.50(RECT DUCT HOT AIR BUS TO MILLS (PGMA-48662)) | 206815088
EXPN PIECESHOT AIR BUS TO MILLS (PGMA-48664) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 48664 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815089
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 48664 | 1.9.6.4.1.2.51(EXPN PIECESHOT AIR BUS TO MILLS (PGMA-48664)) | 206815090
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 48664 | 1.9.6.4.1.2.51(EXPN PIECESHOT AIR BUS TO MILLS (PGMA-48664)) | 206815091
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 48664 | 1.9.6.4.1.2.51(EXPN PIECESHOT AIR BUS TO MILLS (PGMA-48664)) | 206815092
SUPPORTS FOR HOT PA TO MILLS (PGMA-48665) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 48665 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815093
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 48665 | 1.9.6.4.1.2.52(SUPPORTS FOR HOT PA TO MILLS (PGMA-48665)) | 206815094
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 48665 | 1.9.6.4.1.2.52(SUPPORTS FOR HOT PA TO MILLS (PGMA-48665)) | 206815095
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 48665 | 1.9.6.4.1.2.52(SUPPORTS FOR HOT PA TO MILLS (PGMA-48665)) | 206815096
VENTURI-PRIMARY AIR FLOW (PGMA-48667) | SUP | 2023-05-18 08:00 | 2024-11-27 17:00 |  |  |  | 48667 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815097
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 48667 | 1.9.6.4.1.2.53(VENTURI-PRIMARY AIR FLOW (PGMA-48667)) | 206815098
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-28 17:00 |  |  |  | 48667 | 1.9.6.4.1.2.53(VENTURI-PRIMARY AIR FLOW (PGMA-48667)) | 206815099
Dispatch | DIS | 2024-10-29 08:00 | 2024-11-27 17:00 |  |  |  | 48667 | 1.9.6.4.1.2.53(VENTURI-PRIMARY AIR FLOW (PGMA-48667)) | 206815100
BULKED BPS COMPONENTS (PGMA-48700) | SUP | 2022-09-27 08:00 | 2023-10-27 17:00 |  |  |  | 48700 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815101
Engineering | ENG | 2022-09-27 08:00 | 2023-03-26 17:00 |  |  |  | 48700 | 1.9.6.4.1.2.54(BULKED BPS COMPONENTS (PGMA-48700)) | 206815102
Manufacturing | MFG | 2023-03-27 08:00 | 2023-09-27 17:00 |  |  |  | 48700 | 1.9.6.4.1.2.54(BULKED BPS COMPONENTS (PGMA-48700)) | 206815103
Dispatch | DIS | 2023-09-28 08:00 | 2023-10-27 17:00 |  |  |  | 48700 | 1.9.6.4.1.2.54(BULKED BPS COMPONENTS (PGMA-48700)) | 206815104
SLIDE BRG PLATE & PACIFIC BELLOW-BOILER (PGMA-48911) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48911 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815105
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48911 | 1.9.6.4.1.2.55(SLIDE BRG PLATE & PACIFIC BELLOW-BOILER (PGMA-48911)) | 206815106
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48911 | 1.9.6.4.1.2.55(SLIDE BRG PLATE & PACIFIC BELLOW-BOILER (PGMA-48911)) | 206815107
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48911 | 1.9.6.4.1.2.55(SLIDE BRG PLATE & PACIFIC BELLOW-BOILER (PGMA-48911)) | 206815108
SLIDE BRG PLATE-ID SYSTEM (PGMA-48912) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48912 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815109
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48912 | 1.9.6.4.1.2.56(SLIDE BRG PLATE-ID SYSTEM (PGMA-48912)) | 206815110
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48912 | 1.9.6.4.1.2.56(SLIDE BRG PLATE-ID SYSTEM (PGMA-48912)) | 206815111
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48912 | 1.9.6.4.1.2.56(SLIDE BRG PLATE-ID SYSTEM (PGMA-48912)) | 206815112
MAN HOLE DOORS (450x450) (PGMA-48915) | SUP | 2023-05-18 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815113
Engineering | ENG | 2023-05-18 08:00 | 2024-01-17 17:00 |  |  |  | 48915 | 1.9.6.4.1.2.57(MAN HOLE DOORS (450x450) (PGMA-48915)) | 206815114
Manufacturing | MFG | 2024-01-18 08:00 | 2024-09-28 17:00 |  |  |  | 48915 | 1.9.6.4.1.2.57(MAN HOLE DOORS (450x450) (PGMA-48915)) | 206815115
Dispatch | DIS | 2024-09-29 08:00 | 2024-10-28 17:00 |  |  |  | 48915 | 1.9.6.4.1.2.57(MAN HOLE DOORS (450x450) (PGMA-48915)) | 206815116
ERECTION MATERIALS (PGMA-48993) | SUP | 2023-01-09 08:00 | 2024-04-28 17:00 |  |  |  | 48993 | 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | 206815117
Engineering | ENG | 2023-01-09 08:00 | 2023-07-27 17:00 |  |  |  | 48993 | 1.9.6.4.1.2.58(ERECTION MATERIALS (PGMA-48993)) | 206815118
Manufacturing | MFG | 2023-07-28 08:00 | 2024-03-29 17:00 |  |  |  | 48993 | 1.9.6.4.1.2.58(ERECTION MATERIALS (PGMA-48993)) | 206815119
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  | 48993 | 1.9.6.4.1.2.58(ERECTION MATERIALS (PGMA-48993)) | 206815120
BHEL BAP | SUP | 2023-03-16 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.9.6.4(Supply ) | 206815121
GATES AND DAMPERS | SUP | 2023-03-16 08:00 | 2024-11-04 17:00 |  |  |  | PG57 | 1.9.6.4.2(BHEL BAP) | 206815122
BAP - GATE-ESP OUTLET(PGMA 57470) | SUP | 2023-03-16 08:00 | 2023-12-10 17:00 |  |  |  | 57470 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815123
Engineering | ENG | 2023-03-16 08:00 | 2023-04-14 17:00 |  |  |  | 57470 | 1.9.6.4.2.1.1(BAP - GATE-ESP OUTLET(PGMA 57470)) | 206815124
Manufacturing | MFG | 2023-04-15 08:00 | 2023-07-23 17:00 |  |  |  | 57470 | 1.9.6.4.2.1.1(BAP - GATE-ESP OUTLET(PGMA 57470)) | 206815125
Dispatch | DIS | 2023-07-24 08:00 | 2023-12-10 17:00 |  |  |  | 57470 | 1.9.6.4.2.1.1(BAP - GATE-ESP OUTLET(PGMA 57470)) | 206815126
BAP - GATE-ID FAN OUTLET(PGMA 57490) | SUP | 2023-03-16 08:00 | 2023-12-10 17:00 |  |  |  | 57490 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815127
Engineering | ENG | 2023-03-16 08:00 | 2023-04-14 17:00 |  |  |  | 57490 | 1.9.6.4.2.1.2(BAP - GATE-ID FAN OUTLET(PGMA 57490)) | 206815128
Manufacturing | MFG | 2023-04-15 08:00 | 2023-07-23 17:00 |  |  |  | 57490 | 1.9.6.4.2.1.2(BAP - GATE-ID FAN OUTLET(PGMA 57490)) | 206815129
Dispatch | DIS | 2023-07-24 08:00 | 2023-12-10 17:00 |  |  |  | 57490 | 1.9.6.4.2.1.2(BAP - GATE-ID FAN OUTLET(PGMA 57490)) | 206815130
BAP - GATE-ID FAN INLET(PGMA 57480) | SUP | 2023-03-16 08:00 | 2023-12-10 17:00 |  |  |  | 57480 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815131
Engineering | ENG | 2023-03-16 08:00 | 2023-04-14 17:00 |  |  |  | 57480 | 1.9.6.4.2.1.3(BAP - GATE-ID FAN INLET(PGMA 57480)) | 206815132
Manufacturing | MFG | 2023-04-15 08:00 | 2023-07-23 17:00 |  |  |  | 57480 | 1.9.6.4.2.1.3(BAP - GATE-ID FAN INLET(PGMA 57480)) | 206815133
Dispatch | DIS | 2023-07-24 08:00 | 2023-12-10 17:00 |  |  |  | 57480 | 1.9.6.4.2.1.3(BAP - GATE-ID FAN INLET(PGMA 57480)) | 206815134
BAP - DAMPER-SCR BYPASS(PGMA 57620) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 57620 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815135
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 57620 | 1.9.6.4.2.1.4(BAP - DAMPER-SCR BYPASS(PGMA 57620)) | 206815136
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 57620 | 1.9.6.4.2.1.4(BAP - DAMPER-SCR BYPASS(PGMA 57620)) | 206815137
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 57620 | 1.9.6.4.2.1.4(BAP - DAMPER-SCR BYPASS(PGMA 57620)) | 206815138
BAP - PLATFORMS AND LADDERS– SCR GD(PGMA 57666) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 57666 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815139
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 57666 | 1.9.6.4.2.1.5(BAP - PLATFORMS AND LADDERS– SCR GD(PGMA 57666)) | 206815140
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 57666 | 1.9.6.4.2.1.5(BAP - PLATFORMS AND LADDERS– SCR GD(PGMA 57666)) | 206815141
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 57666 | 1.9.6.4.2.1.5(BAP - PLATFORMS AND LADDERS– SCR GD(PGMA 57666)) | 206815142
BAP - SPL MTL ELECTRODES(PGMA 57992) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 57992 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815143
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 57992 | 1.9.6.4.2.1.6(BAP - SPL MTL ELECTRODES(PGMA 57992)) | 206815144
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 57992 | 1.9.6.4.2.1.6(BAP - SPL MTL ELECTRODES(PGMA 57992)) | 206815145
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 57992 | 1.9.6.4.2.1.6(BAP - SPL MTL ELECTRODES(PGMA 57992)) | 206815146
BAP - GATE-FD FAN OUTLET(PGMA 57010) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 57010 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815147
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 57010 | 1.9.6.4.2.1.7(BAP - GATE-FD FAN OUTLET(PGMA 57010)) | 206815148
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 57010 | 1.9.6.4.2.1.7(BAP - GATE-FD FAN OUTLET(PGMA 57010)) | 206815149
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 57010 | 1.9.6.4.2.1.7(BAP - GATE-FD FAN OUTLET(PGMA 57010)) | 206815150
BAP - FLUE GAS AH OUT GATE(PGMA 57430) | SUP | 2023-08-13 08:00 | 2024-04-08 17:00 |  |  |  | 57430 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815151
Engineering | ENG | 2023-08-13 08:00 | 2023-09-11 17:00 |  |  |  | 57430 | 1.9.6.4.2.1.8(BAP - FLUE GAS AH OUT GATE(PGMA 57430)) | 206815152
Manufacturing | MFG | 2023-09-12 08:00 | 2023-12-20 17:00 |  |  |  | 57430 | 1.9.6.4.2.1.8(BAP - FLUE GAS AH OUT GATE(PGMA 57430)) | 206815153
Dispatch | DIS | 2023-12-21 08:00 | 2024-04-08 17:00 |  |  |  | 57430 | 1.9.6.4.2.1.8(BAP - FLUE GAS AH OUT GATE(PGMA 57430)) | 206815154
BAP - GATE-ESP INLET(PGMA 57460) | SUP | 2023-08-13 08:00 | 2024-04-08 17:00 |  |  |  | 57460 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815155
Engineering | ENG | 2023-08-13 08:00 | 2023-09-11 17:00 |  |  |  | 57460 | 1.9.6.4.2.1.9(BAP - GATE-ESP INLET(PGMA 57460)) | 206815156
Manufacturing | MFG | 2023-09-12 08:00 | 2023-12-20 17:00 |  |  |  | 57460 | 1.9.6.4.2.1.9(BAP - GATE-ESP INLET(PGMA 57460)) | 206815157
Dispatch | DIS | 2023-12-21 08:00 | 2024-04-08 17:00 |  |  |  | 57460 | 1.9.6.4.2.1.9(BAP - GATE-ESP INLET(PGMA 57460)) | 206815158
BAP - DAMPER-SA SCAPH INLET(PGMA 57033) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 57033 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815159
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57033 | 1.9.6.4.2.1.10(BAP - DAMPER-SA SCAPH INLET(PGMA 57033)) | 206815160
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57033 | 1.9.6.4.2.1.10(BAP - DAMPER-SA SCAPH INLET(PGMA 57033)) | 206815161
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 57033 | 1.9.6.4.2.1.10(BAP - DAMPER-SA SCAPH INLET(PGMA 57033)) | 206815162
BAP - DAMPER-SA SCAPH OUTLET(PGMA 57063) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 57063 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815163
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57063 | 1.9.6.4.2.1.11(BAP - DAMPER-SA SCAPH OUTLET(PGMA 57063)) | 206815164
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57063 | 1.9.6.4.2.1.11(BAP - DAMPER-SA SCAPH OUTLET(PGMA 57063)) | 206815165
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 57063 | 1.9.6.4.2.1.11(BAP - DAMPER-SA SCAPH OUTLET(PGMA 57063)) | 206815166
BAP - DAMPER-SA APH OUTLET(PGMA 57203) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 57203 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815167
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57203 | 1.9.6.4.2.1.12(BAP - DAMPER-SA APH OUTLET(PGMA 57203)) | 206815168
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57203 | 1.9.6.4.2.1.12(BAP - DAMPER-SA APH OUTLET(PGMA 57203)) | 206815169
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 57203 | 1.9.6.4.2.1.12(BAP - DAMPER-SA APH OUTLET(PGMA 57203)) | 206815170
BAP - MTG BKT FOR CL DAMPER AIR CYL(PGMA 57209) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 57209 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815171
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57209 | 1.9.6.4.2.1.13(BAP - MTG BKT FOR CL DAMPER AIR CYL(PGMA 57209)) | 206815172
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57209 | 1.9.6.4.2.1.13(BAP - MTG BKT FOR CL DAMPER AIR CYL(PGMA 57209)) | 206815173
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 57209 | 1.9.6.4.2.1.13(BAP - MTG BKT FOR CL DAMPER AIR CYL(PGMA 57209)) | 206815174
BAP - PLATFORMS AND LADDERS(PGMA 57466) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 57466 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815175
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57466 | 1.9.6.4.2.1.14(BAP - PLATFORMS AND LADDERS(PGMA 57466)) | 206815176
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57466 | 1.9.6.4.2.1.14(BAP - PLATFORMS AND LADDERS(PGMA 57466)) | 206815177
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 57466 | 1.9.6.4.2.1.14(BAP - PLATFORMS AND LADDERS(PGMA 57466)) | 206815178
BAP - ACTUATORS FOR G&D(PGMA 57577) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57577 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815179
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57577 | 1.9.6.4.2.1.15(BAP - ACTUATORS FOR G&D(PGMA 57577)) | 206815180
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57577 | 1.9.6.4.2.1.15(BAP - ACTUATORS FOR G&D(PGMA 57577)) | 206815181
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57577 | 1.9.6.4.2.1.15(BAP - ACTUATORS FOR G&D(PGMA 57577)) | 206815182
BAP - GATE –FGD INLET(PGMA 57560) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57560 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815183
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57560 | 1.9.6.4.2.1.16(BAP - GATE –FGD INLET(PGMA 57560)) | 206815184
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57560 | 1.9.6.4.2.1.16(BAP - GATE –FGD INLET(PGMA 57560)) | 206815185
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57560 | 1.9.6.4.2.1.16(BAP - GATE –FGD INLET(PGMA 57560)) | 206815186
BAP - GATE –FGD OUTLET(PGMA 57C70) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57C70 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815187
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57C70 | 1.9.6.4.2.1.17(BAP - GATE –FGD OUTLET(PGMA 57C70)) | 206815188
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57C70 | 1.9.6.4.2.1.17(BAP - GATE –FGD OUTLET(PGMA 57C70)) | 206815189
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57C70 | 1.9.6.4.2.1.17(BAP - GATE –FGD OUTLET(PGMA 57C70)) | 206815190
BAP - DAMPER –FGD BYPASS(PGMA 57C83) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57C83 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815191
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57C83 | 1.9.6.4.2.1.18(BAP - DAMPER –FGD BYPASS(PGMA 57C83)) | 206815192
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57C83 | 1.9.6.4.2.1.18(BAP - DAMPER –FGD BYPASS(PGMA 57C83)) | 206815193
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57C83 | 1.9.6.4.2.1.18(BAP - DAMPER –FGD BYPASS(PGMA 57C83)) | 206815194
BAP - PLAT FORM AND LADDER –FGD GD(PGMA 57566) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57566 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815195
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57566 | 1.9.6.4.2.1.19(BAP - PLAT FORM AND LADDER –FGD GD(PGMA 57566)) | 206815196
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57566 | 1.9.6.4.2.1.19(BAP - PLAT FORM AND LADDER –FGD GD(PGMA 57566)) | 206815197
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57566 | 1.9.6.4.2.1.19(BAP - PLAT FORM AND LADDER –FGD GD(PGMA 57566)) | 206815198
BAP - GATE WITH CLADDING FOR CO2 TO METHANOL SYSTEM (PGMA 57CX0) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815199
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1.20(BAP - GATE WITH CLADDING FOR CO2 TO METHANOL SYSTEM (PGMA 57CX0)) | 206815200
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1.20(BAP - GATE WITH CLADDING FOR CO2 TO METHANOL SYSTEM (PGMA 57CX0)) | 206815201
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1.20(BAP - GATE WITH CLADDING FOR CO2 TO METHANOL SYSTEM (PGMA 57CX0)) | 206815202
BAP - PLATFORMS AND LADDERS-SCR GD (PGMA 57CX0) | SUP | 2023-07-24 08:00 | 2024-08-06 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815203
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1.21(BAP - PLATFORMS AND LADDERS-SCR GD (PGMA 57CX0)) | 206815204
Manufacturing | MFG | 2023-12-21 08:00 | 2024-06-17 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1.21(BAP - PLATFORMS AND LADDERS-SCR GD (PGMA 57CX0)) | 206815205
Dispatch | DIS | 2024-06-18 08:00 | 2024-08-06 17:00 |  |  |  | 57CX0 | 1.9.6.4.2.1.21(BAP - PLATFORMS AND LADDERS-SCR GD (PGMA 57CX0)) | 206815206
BAP - DAMPER-PA APH INLET(PGMA 57173) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 57173 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815207
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57173 | 1.9.6.4.2.1.22(BAP - DAMPER-PA APH INLET(PGMA 57173)) | 206815208
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57173 | 1.9.6.4.2.1.22(BAP - DAMPER-PA APH INLET(PGMA 57173)) | 206815209
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 57173 | 1.9.6.4.2.1.22(BAP - DAMPER-PA APH INLET(PGMA 57173)) | 206815210
BAP - DAMPER-PA APH OUTLET(PGMA 57223) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 57223 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815211
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57223 | 1.9.6.4.2.1.23(BAP - DAMPER-PA APH OUTLET(PGMA 57223)) | 206815212
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57223 | 1.9.6.4.2.1.23(BAP - DAMPER-PA APH OUTLET(PGMA 57223)) | 206815213
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 57223 | 1.9.6.4.2.1.23(BAP - DAMPER-PA APH OUTLET(PGMA 57223)) | 206815214
BAP - DAMPER-COLD AIR TO MIL(PGMA 57143) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 57143 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815215
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57143 | 1.9.6.4.2.1.24(BAP - DAMPER-COLD AIR TO MIL(PGMA 57143)) | 206815216
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57143 | 1.9.6.4.2.1.24(BAP - DAMPER-COLD AIR TO MIL(PGMA 57143)) | 206815217
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 57143 | 1.9.6.4.2.1.24(BAP - DAMPER-COLD AIR TO MIL(PGMA 57143)) | 206815218
BAP - ELECTRICAL ITEMS FOR GATE,DAMP(PGMA 57578) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 57578 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815219
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57578 | 1.9.6.4.2.1.25(BAP - ELECTRICAL ITEMS FOR GATE,DAMP(PGMA 57578)) | 206815220
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57578 | 1.9.6.4.2.1.25(BAP - ELECTRICAL ITEMS FOR GATE,DAMP(PGMA 57578)) | 206815221
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 57578 | 1.9.6.4.2.1.25(BAP - ELECTRICAL ITEMS FOR GATE,DAMP(PGMA 57578)) | 206815222
BAP - SEAL AIR HAG AND ID FA(PGMA 57141) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 57141 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815223
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 57141 | 1.9.6.4.2.1.26(BAP - SEAL AIR HAG AND ID FA(PGMA 57141)) | 206815224
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 57141 | 1.9.6.4.2.1.26(BAP - SEAL AIR HAG AND ID FA(PGMA 57141)) | 206815225
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 57141 | 1.9.6.4.2.1.26(BAP - SEAL AIR HAG AND ID FA(PGMA 57141)) | 206815226
BAP - DAMPER-PA FAN OUTLET(PGMA 57113) | SUP | 2023-12-21 08:00 | 2024-09-05 17:00 |  |  |  | 57113 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815227
Engineering | ENG | 2023-12-21 08:00 | 2024-01-19 17:00 |  |  |  | 57113 | 1.9.6.4.2.1.27(BAP - DAMPER-PA FAN OUTLET(PGMA 57113)) | 206815228
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-28 17:00 |  |  |  | 57113 | 1.9.6.4.2.1.27(BAP - DAMPER-PA FAN OUTLET(PGMA 57113)) | 206815229
Dispatch | DIS | 2024-04-29 08:00 | 2024-09-05 17:00 |  |  |  | 57113 | 1.9.6.4.2.1.27(BAP - DAMPER-PA FAN OUTLET(PGMA 57113)) | 206815230
BAP - GATE-PA FAN OUTLET(PGMA 57110) | SUP | 2023-12-21 08:00 | 2024-09-05 17:00 |  |  |  | 57110 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815231
Engineering | ENG | 2023-12-21 08:00 | 2024-01-19 17:00 |  |  |  | 57110 | 1.9.6.4.2.1.28(BAP - GATE-PA FAN OUTLET(PGMA 57110)) | 206815232
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-28 17:00 |  |  |  | 57110 | 1.9.6.4.2.1.28(BAP - GATE-PA FAN OUTLET(PGMA 57110)) | 206815233
Dispatch | DIS | 2024-04-29 08:00 | 2024-09-05 17:00 |  |  |  | 57110 | 1.9.6.4.2.1.28(BAP - GATE-PA FAN OUTLET(PGMA 57110)) | 206815234
BAP - BLOWER WITH MOTOR(PGMA 57491) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57491 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815235
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57491 | 1.9.6.4.2.1.29(BAP - BLOWER WITH MOTOR(PGMA 57491)) | 206815236
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57491 | 1.9.6.4.2.1.29(BAP - BLOWER WITH MOTOR(PGMA 57491)) | 206815237
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57491 | 1.9.6.4.2.1.29(BAP - BLOWER WITH MOTOR(PGMA 57491)) | 206815238
BAP - GATE-COLD AIR TO MILLS(PGMA 57160) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57160 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815239
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57160 | 1.9.6.4.2.1.30(BAP - GATE-COLD AIR TO MILLS(PGMA 57160)) | 206815240
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57160 | 1.9.6.4.2.1.30(BAP - GATE-COLD AIR TO MILLS(PGMA 57160)) | 206815241
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57160 | 1.9.6.4.2.1.30(BAP - GATE-COLD AIR TO MILLS(PGMA 57160)) | 206815242
BAP - KNIFE GATE VALVE(PGMA 57497) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57497 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815243
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57497 | 1.9.6.4.2.1.31(BAP - KNIFE GATE VALVE(PGMA 57497)) | 206815244
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57497 | 1.9.6.4.2.1.31(BAP - KNIFE GATE VALVE(PGMA 57497)) | 206815245
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57497 | 1.9.6.4.2.1.31(BAP - KNIFE GATE VALVE(PGMA 57497)) | 206815246
BAP - GATE-HOT AIR TO MILLS(PGMA 57270) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57270 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815247
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57270 | 1.9.6.4.2.1.32(BAP - GATE-HOT AIR TO MILLS(PGMA 57270)) | 206815248
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57270 | 1.9.6.4.2.1.32(BAP - GATE-HOT AIR TO MILLS(PGMA 57270)) | 206815249
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57270 | 1.9.6.4.2.1.32(BAP - GATE-HOT AIR TO MILLS(PGMA 57270)) | 206815250
BAP - DAMPER-HOT AIR TO MILL(PGMA 57273) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57273 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815251
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57273 | 1.9.6.4.2.1.33(BAP - DAMPER-HOT AIR TO MILL(PGMA 57273)) | 206815252
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57273 | 1.9.6.4.2.1.33(BAP - DAMPER-HOT AIR TO MILL(PGMA 57273)) | 206815253
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57273 | 1.9.6.4.2.1.33(BAP - DAMPER-HOT AIR TO MILL(PGMA 57273)) | 206815254
BAP - DAMPER-SA SCAPH BYPASS(PGMA 57083) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57083 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815255
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57083 | 1.9.6.4.2.1.34(BAP - DAMPER-SA SCAPH BYPASS(PGMA 57083)) | 206815256
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57083 | 1.9.6.4.2.1.34(BAP - DAMPER-SA SCAPH BYPASS(PGMA 57083)) | 206815257
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57083 | 1.9.6.4.2.1.34(BAP - DAMPER-SA SCAPH BYPASS(PGMA 57083)) | 206815258
BAP - DUCTS COMMISSIONING SPARES(PGMA 57988) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 57988 | 1.9.6.4.2.1( GATES AND DAMPERS) | 206815259
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 57988 | 1.9.6.4.2.1.35(BAP - DUCTS COMMISSIONING SPARES(PGMA 57988)) | 206815260
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 57988 | 1.9.6.4.2.1.35(BAP - DUCTS COMMISSIONING SPARES(PGMA 57988)) | 206815261
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 57988 | 1.9.6.4.2.1.35(BAP - DUCTS COMMISSIONING SPARES(PGMA 57988)) | 206815262
Erection | ERC | 2024-08-07 08:00 | 2026-05-28 17:00 |  |  |  |  | 1.9.6(Air & Flue Gas System) | 206815263
External Structures ( Supporting Structures for Duct, PG-39 ) | ERC | 2024-08-27 08:00 | 2026-03-16 17:00 |  |  |  | PG39 | 1.9.6.5(Erection) | 206815264
Erection:- Columns/Frames Before ESP (PP) | ERC | 2025-04-21 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815265
Erection:- Columns/Frames Before ESP (SP) | ERC | 2025-04-21 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815266
Erection:- Columns/Frames Near I.D. Fan (PP) | ERC | 2024-08-27 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815267
Erection:- Columns/Frames Near TO Chimney (SP) | ERC | 2024-09-27 08:00 | 2025-05-24 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815268
Erection:- Columns/Frames Between TO Chimney and Chimney | ERC | 2024-11-28 08:00 | 2025-04-26 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815269
Erection:- Platforms External Structure BOF TO ESP | ERC | 2025-06-20 08:00 | 2026-02-14 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815270
Erection:- Platform - External Structure | ERC | 2025-07-20 08:00 | 2026-03-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815271
Erection:- Structure and Platform for Fans | ERC | 2025-12-17 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815272
Erection :- Structure for Motor Hood/Covering | ERC | 2026-01-30 08:00 | 2026-02-13 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815273
Erection:- Fan Handling Structure for FD Fan | ERC | 2025-10-18 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815274
Erection:- Fan Handling Structure for PA Fan | ERC | 2025-09-24 08:00 | 2025-11-22 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815275
Erection:- Fan Handling Structure for ID Fan | ERC | 2025-10-18 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815276
Erection:- Floor Grill | ERC | 2025-07-20 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815277
Erection:- Stairs | ERC | 2025-07-20 08:00 | 2025-11-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815278
Erection:- Hand Rail and Post | ERC | 2025-07-20 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | 206815279
Duct., Dampers and Expn. Joints | ERC | 2024-08-07 08:00 | 2026-05-28 17:00 |  |  |  |  | 1.9.6.5(Erection) | 206815280
AIR DUCTING | ERC | 2024-10-29 08:00 | 2026-01-18 17:00 |  |  |  |  | 1.9.6.5.2(Duct., Dampers and Expn. Joints) | 206815281
FORCED DRAFT AIR | ERC | 2024-10-29 08:00 | 2025-12-22 17:00 |  |  |  |  | 1.9.6.5.2.1( AIR DUCTING) | 206815282
FORCED DRAFT AIR: Pre-assembly of FD duct pieces | ERC | 2024-10-29 08:00 | 2025-03-27 17:00 |  |  |  |  | 1.9.6.5.2.1.1( FORCED DRAFT AIR) | 206815283
FORCED DRAFT AIR: Erection and suspension of ducts on supports | ERC | 2024-12-28 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.9.6.5.2.1.1( FORCED DRAFT AIR) | 206815284
FORCED DRAFT Reresection of gates and actuators | ERC | 2025-05-27 08:00 | 2025-08-24 17:00 |  |  |  |  | 1.9.6.5.2.1.1( FORCED DRAFT AIR) | 206815285
FORCED DRAFT AIR:FD ducting ready after insulation | ERC | 2025-08-25 08:00 | 2025-12-22 17:00 |  |  |  |  | 1.9.6.5.2.1.1( FORCED DRAFT AIR) | 206815286
PRIMARY AIR | ERC | 2025-04-27 08:00 | 2026-01-18 17:00 |  |  |  |  | 1.9.6.5.2.1( AIR DUCTING) | 206815287
PRIMARY AIR: Preassembly of PA duct pieces | ERC | 2025-04-27 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.9.6.5.2.1.2( PRIMARY AIR) | 206815288
PRIMARY AIR: Preassembly and suspension of ducts on supports | ERC | 2025-05-27 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.9.6.5.2.1.2( PRIMARY AIR) | 206815289
PRIMARY AIR: Preassembly of gates and actuators | ERC | 2025-06-03 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.9.6.5.2.1.2( PRIMARY AIR) | 206815290
PRIMARY AIR:PA ducting ready after insulation | ERC | 2025-09-21 08:00 | 2026-01-18 17:00 |  |  |  |  | 1.9.6.5.2.1.2( PRIMARY AIR) | 206815291
FLUE GAS DUCTING | ERC | 2024-08-07 08:00 | 2026-05-28 17:00 |  |  |  |  | 1.9.6.5.2(Duct., Dampers and Expn. Joints) | 206815292
ID TO COMMON DUCT TO Chimney - Priority Pass | ERC | 2024-08-07 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815293
ID-B TO Chimney: Preassembly of duct pieces | ERC | 2024-08-07 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.9.6.5.2.2.1( ID TO COMMON DUCT TO Chimney - Priority Pass) | 206815294
ID-B TO Chimney: Erection and welding of square ducts and expansion pieces | ERC | 2025-04-07 08:00 | 2025-09-03 17:00 |  |  |  |  | 1.9.6.5.2.2.1( ID TO COMMON DUCT TO Chimney - Priority Pass) | 206815295
ID-B TO Chimney: Erection of gates and actuators | ERC | 2025-09-04 08:00 | 2025-10-03 17:00 |  |  |  |  | 1.9.6.5.2.2.1( ID TO COMMON DUCT TO Chimney - Priority Pass) | 206815296
ID-B TO Chimney: Ducting ready after insulation | COM | 2025-10-04 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9.6.5.2.2.1( ID TO COMMON DUCT TO Chimney - Priority Pass) | 206815297
ID to COMMON DUCT TO Chimney - Second Pass | ERC | 2024-12-05 08:00 | 2026-02-22 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815298
ID-A to Chimney: Preassembly of duct pieces | ERC | 2024-12-05 08:00 | 2025-06-02 17:00 |  |  |  |  | 1.9.6.5.2.2.2( ID to COMMON DUCT TO Chimney - Second Pass) | 206815299
ID-A to Chimney: Erection and welding of square ducts and expansion pieces | ERC | 2025-04-29 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.9.6.5.2.2.2( ID to COMMON DUCT TO Chimney - Second Pass) | 206815300
ID-A to Chimney: Erection of gates and actuators | ERC | 2025-09-26 08:00 | 2025-10-25 17:00 |  |  |  |  | 1.9.6.5.2.2.2( ID to COMMON DUCT TO Chimney - Second Pass) | 206815301
ID-A to Chimney: Ducting ready after insulation | COM | 2025-10-26 08:00 | 2026-02-22 17:00 |  |  |  |  | 1.9.6.5.2.2.2( ID to COMMON DUCT TO Chimney - Second Pass) | 206815302
ECO TO APH | ERC | 2025-08-01 08:00 | 2026-01-07 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815303
ECO TO APH: Preassembly of duct pieces | ERC | 2025-08-01 08:00 | 2025-09-14 17:00 |  |  |  |  | 1.9.6.5.2.2.3( ECO TO APH) | 206815304
ECO TO APH: Erection and welding of square ducts and expansion pieces | ERC | 2025-09-15 08:00 | 2025-11-08 17:00 |  |  |  |  | 1.9.6.5.2.2.3( ECO TO APH) | 206815305
ECO TO Perfection of gates and actuators | ERC | 2025-11-09 08:00 | 2025-11-23 17:00 |  |  |  |  | 1.9.6.5.2.2.3( ECO TO APH) | 206815306
ECO TO APH: Ducting ready after insulation | COM | 2025-11-24 08:00 | 2026-01-07 17:00 |  |  |  |  | 1.9.6.5.2.2.3( ECO TO APH) | 206815307
APH TO BOF | ERC | 2025-08-01 08:00 | 2026-01-21 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815308
APH TO BOF: Erection of supports | ERC | 2025-08-01 08:00 | 2025-09-08 17:00 |  |  |  |  | 1.9.6.5.2.2.4( APH TO BOF) | 206815309
APH TO BOF: Preassembly of duct pieces | ERC | 2025-08-01 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.9.6.5.2.2.4( APH TO BOF) | 206815310
APH TO Federation and welding of square ducts and expansion pieces | ERC | 2025-09-07 08:00 | 2025-11-22 17:00 |  |  |  |  | 1.9.6.5.2.2.4( APH TO BOF) | 206815311
APH TO Federation of gates and actuators | ERC | 2025-11-23 08:00 | 2025-12-07 17:00 |  |  |  |  | 1.9.6.5.2.2.4( APH TO BOF) | 206815312
APH TO BOF: Ducting ready after insulation | COM | 2025-12-08 08:00 | 2026-01-21 17:00 |  |  |  |  | 1.9.6.5.2.2.4( APH TO BOF) | 206815313
BOF TO ESP - Priority Pass | ERC | 2025-08-04 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815314
BOF -B TO ESP: Preassembly of duct pieces | ERC | 2025-08-04 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.9.6.5.2.2.5( BOF TO ESP - Priority Pass) | 206815315
BOF -B TO ESP: Erection and welding of square ducts and expansion pieces | ERC | 2025-09-18 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.6.5.2.2.5( BOF TO ESP - Priority Pass) | 206815316
BOF -B TO Superaction of gates and actuators | ERC | 2025-12-17 08:00 | 2025-12-29 17:00 |  |  |  |  | 1.9.6.5.2.2.5( BOF TO ESP - Priority Pass) | 206815317
BOF -B TO ESP: Ducting ready after insulation | COM | 2025-12-30 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.6.5.2.2.5( BOF TO ESP - Priority Pass) | 206815318
BOF TO ESP - Second Pass | ERC | 2025-10-03 08:00 | 2026-05-28 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815319
BOF_ATO Seducing of duct pieces | ERC | 2025-10-03 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.9.6.5.2.2.6( BOF TO ESP - Second Pass) | 206815320
BOF_ATO Seducing and welding of square ducts and expansion pieces | ERC | 2025-12-17 08:00 | 2026-03-16 17:00 |  |  |  |  | 1.9.6.5.2.2.6( BOF TO ESP - Second Pass) | 206815321
BOF_ATO Seducing of gates and actuators | ERC | 2026-03-17 08:00 | 2026-03-29 17:00 |  |  |  |  | 1.9.6.5.2.2.6( BOF TO ESP - Second Pass) | 206815322
BOF_ATO Seducing ready after insulation | COM | 2026-03-30 08:00 | 2026-05-28 17:00 |  |  |  |  | 1.9.6.5.2.2.6( BOF TO ESP - Second Pass) | 206815323
ESP to ID - Priority Pass | ERC | 2025-01-09 08:00 | 2025-12-24 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815324
ESP to ID-A: Preassembly of duct pieces | ERC | 2025-01-09 08:00 | 2025-04-08 17:00 |  |  |  |  | 1.9.6.5.2.2.7( ESP to ID - Priority Pass) | 206815325
ESP to ID-A: Erection and welding of square ducts and expansion pieces | ERC | 2025-04-09 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.9.6.5.2.2.7( ESP to ID - Priority Pass) | 206815326
ESP to Dilaceration of gates and actuators | ERC | 2025-07-28 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.9.6.5.2.2.7( ESP to ID - Priority Pass) | 206815327
ESP to ID-A: Ducting ready after insulation | COM | 2025-09-26 08:00 | 2025-12-24 17:00 |  |  |  |  | 1.9.6.5.2.2.7( ESP to ID - Priority Pass) | 206815328
ESPTO ID - Second Pass | ERC | 2025-04-10 08:00 | 2026-03-25 17:00 |  |  |  |  | 1.9.6.5.2.2( FLUE GAS DUCTING) | 206815329
ESPTO ID-B: Preassembly of duct pieces | ERC | 2025-04-10 08:00 | 2025-07-08 17:00 |  |  |  |  | 1.9.6.5.2.2.8( ESPTO ID - Second Pass) | 206815330
ESPTO ID-B: Erection and welding of square ducts and expansion pieces | ERC | 2025-07-09 08:00 | 2025-10-26 17:00 |  |  |  |  | 1.9.6.5.2.2.8( ESPTO ID - Second Pass) | 206815331
ESPTO ID-B: Preassembly of gates and actuators | ERC | 2025-10-27 08:00 | 2025-12-25 17:00 |  |  |  |  | 1.9.6.5.2.2.8( ESPTO ID - Second Pass) | 206815332
ESPTO ID-B: Ducting ready after insulation | COM | 2025-12-26 08:00 | 2026-03-25 17:00 |  |  |  |  | 1.9.6.5.2.2.8( ESPTO ID - Second Pass) | 206815333
Pulverised Fuel System | OTH | 2022-09-27 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206815334
Civil Work | CIV | 2023-02-24 08:00 | 2025-06-23 17:00 |  |  |  |  | 1.9.7(Pulverised Fuel System) | 206815335
Mills Foundation | CIV | 2023-02-24 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.9.7.1(Civil Work) | 206815336
EXCAVATION | CIV | 2023-02-24 08:00 | 2023-05-09 17:00 |  |  |  |  | 1.9.7.1.1( Mills Foundation) | 206815337
RCC in substructure including PCC | CIV | 2023-05-10 08:00 | 2023-07-13 17:00 |  |  |  |  | 1.9.7.1.1( Mills Foundation) | 206815338
RCC in superstructure | CIV | 2024-05-04 08:00 | 2024-08-07 17:00 |  |  |  |  | 1.9.7.1.1( Mills Foundation) | 206815339
Backfilling | CIV | 2024-08-08 08:00 | 2024-09-01 17:00 |  |  |  |  | 1.9.7.1.1( Mills Foundation) | 206815340
Finishing works | CIV | 2024-09-02 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.9.7.1.1( Mills Foundation) | 206815341
Bunker | ERC | 2024-04-20 08:00 | 2025-06-23 17:00 |  |  |  |  | 1.9.7.1(Civil Work) | 206815342
Pre-Assy of Bunker at Ground | ERC | 2024-04-20 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.9.7.1.2(Bunker) | 206815343
Coal bunker lift up & welding | ERC | 2024-12-16 08:00 | 2025-06-23 17:00 |  |  |  |  | 1.9.7.1.2(Bunker) | 206815344
Supply | SUP | 2022-09-27 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.9.7(Pulverised Fuel System) | 206815345
BHEL TRY | SUP | 2023-04-10 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.9.7.2(Supply) | 206815346
Pulverised Fuel Piping (PG-47) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | PG47 | 1.9.7.2.1(BHEL TRY) | 206815347
Fuel Piping - Sub-delivery (PGMA-47200) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | 47200 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815348
Engineering | ENG | 2023-04-10 08:00 | 2024-02-15 17:00 |  |  |  | 47200 | 1.9.7.2.1.1.1(Fuel Piping - Sub-delivery (PGMA-47200)) | 206815349
Manufacturing | MFG | 2024-02-16 08:00 | 2024-11-26 17:00 |  |  |  | 47200 | 1.9.7.2.1.1.1(Fuel Piping - Sub-delivery (PGMA-47200)) | 206815350
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 47200 | 1.9.7.2.1.1.1(Fuel Piping - Sub-delivery (PGMA-47200)) | 206815351
FUEL PIPE SUPPORTS (PGMA-47261) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | 47261 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815352
Engineering | ENG | 2023-04-10 08:00 | 2024-02-15 17:00 |  |  |  | 47261 | 1.9.7.2.1.1.2(FUEL PIPE SUPPORTS (PGMA-47261)) | 206815353
Manufacturing | MFG | 2024-02-16 08:00 | 2024-11-26 17:00 |  |  |  | 47261 | 1.9.7.2.1.1.2(FUEL PIPE SUPPORTS (PGMA-47261)) | 206815354
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 47261 | 1.9.7.2.1.1.2(FUEL PIPE SUPPORTS (PGMA-47261)) | 206815355
FUEL PIPE COUPLING COLLER & ORIFICE (PGMA-47263) | SUP | 2023-05-18 08:00 | 2024-11-25 17:00 |  |  |  | 47263 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815356
Engineering | ENG | 2023-05-18 08:00 | 2024-02-03 17:00 |  |  |  | 47263 | 1.9.7.2.1.1.3(FUEL PIPE COUPLING COLLER & ORIFICE (PGMA-47263)) | 206815357
Manufacturing | MFG | 2024-02-04 08:00 | 2024-10-26 17:00 |  |  |  | 47263 | 1.9.7.2.1.1.3(FUEL PIPE COUPLING COLLER & ORIFICE (PGMA-47263)) | 206815358
Dispatch | DIS | 2024-10-27 08:00 | 2024-11-25 17:00 |  |  |  | 47263 | 1.9.7.2.1.1.3(FUEL PIPE COUPLING COLLER & ORIFICE (PGMA-47263)) | 206815359
FUEL PIPE ST PIPES FOR MILL G (PGMA-47269) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | 47269 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815360
Engineering | ENG | 2023-04-10 08:00 | 2024-02-15 17:00 |  |  |  | 47269 | 1.9.7.2.1.1.4(FUEL PIPE ST PIPES FOR MILL G (PGMA-47269)) | 206815361
Manufacturing | MFG | 2024-02-16 08:00 | 2024-11-26 17:00 |  |  |  | 47269 | 1.9.7.2.1.1.4(FUEL PIPE ST PIPES FOR MILL G (PGMA-47269)) | 206815362
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 47269 | 1.9.7.2.1.1.4(FUEL PIPE ST PIPES FOR MILL G (PGMA-47269)) | 206815363
Pulverised Fuel Piping - DD items (PGMA-47710) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | 47710 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815364
Engineering | ENG | 2023-04-10 08:00 | 2024-02-15 17:00 |  |  |  | 47710 | 1.9.7.2.1.1.5(Pulverised Fuel Piping - DD items (PGMA-47710)) | 206815365
Manufacturing | MFG | 2024-02-16 08:00 | 2024-11-26 17:00 |  |  |  | 47710 | 1.9.7.2.1.1.5(Pulverised Fuel Piping - DD items (PGMA-47710)) | 206815366
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 47710 | 1.9.7.2.1.1.5(Pulverised Fuel Piping - DD items (PGMA-47710)) | 206815367
Fuel Piping - Shop Items (PGMA-47858) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | 47858 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815368
Engineering | ENG | 2023-04-10 08:00 | 2024-02-15 17:00 |  |  |  | 47858 | 1.9.7.2.1.1.6(Fuel Piping - Shop Items (PGMA-47858)) | 206815369
Manufacturing | MFG | 2024-02-16 08:00 | 2024-11-26 17:00 |  |  |  | 47858 | 1.9.7.2.1.1.6(Fuel Piping - Shop Items (PGMA-47858)) | 206815370
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 47858 | 1.9.7.2.1.1.6(Fuel Piping - Shop Items (PGMA-47858)) | 206815371
COAL PIPING MANDATORY SPARES (PGMA-47997) | SUP | 2023-04-10 08:00 | 2024-12-26 17:00 |  |  |  | 47997 | 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | 206815372
Engineering | ENG | 2023-04-10 08:00 | 2024-02-15 17:00 |  |  |  | 47997 | 1.9.7.2.1.1.7(COAL PIPING MANDATORY SPARES (PGMA-47997)) | 206815373
Manufacturing | MFG | 2024-02-16 08:00 | 2024-11-26 17:00 |  |  |  | 47997 | 1.9.7.2.1.1.7(COAL PIPING MANDATORY SPARES (PGMA-47997)) | 206815374
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 47997 | 1.9.7.2.1.1.7(COAL PIPING MANDATORY SPARES (PGMA-47997)) | 206815375
Coal Feeders (PG-65) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | PG65 | 1.9.7.2.1(BHEL TRY) | 206815376
Coal Feeder- Sub-Delivery (PGMA-65200) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | 65200 | 1.9.7.2.1.2(Coal Feeders (PG-65)) | 206815377
Ordering & Engineering | ENG | 2023-11-29 08:00 | 2024-10-03 17:00 |  |  |  | 65200 | 1.9.7.2.1.2.1(Coal Feeder- Sub-Delivery (PGMA-65200)) | 206815378
Manufacturing | MFG | 2024-10-04 08:00 | 2025-07-28 17:00 |  |  |  | 65200 | 1.9.7.2.1.2.1(Coal Feeder- Sub-Delivery (PGMA-65200)) | 206815379
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 65200 | 1.9.7.2.1.2.1(Coal Feeder- Sub-Delivery (PGMA-65200)) | 206815380
Coal Feeder - DD items (PGMA-65710) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | 65710 | 1.9.7.2.1.2(Coal Feeders (PG-65)) | 206815381
Ordering & Engineering | ENG | 2023-11-29 08:00 | 2024-10-03 17:00 |  |  |  | 65710 | 1.9.7.2.1.2.2(Coal Feeder - DD items (PGMA-65710)) | 206815382
Manufacturing | MFG | 2024-10-04 08:00 | 2025-07-28 17:00 |  |  |  | 65710 | 1.9.7.2.1.2.2(Coal Feeder - DD items (PGMA-65710)) | 206815383
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 65710 | 1.9.7.2.1.2.2(Coal Feeder - DD items (PGMA-65710)) | 206815384
36 INCH GRAVIMETRIC FEEDER (PGMA-65736) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | 65736 | 1.9.7.2.1.2(Coal Feeders (PG-65)) | 206815385
Ordering & Engineering | ENG | 2023-11-29 08:00 | 2024-10-03 17:00 |  |  |  | 65736 | 1.9.7.2.1.2.3(36 INCH GRAVIMETRIC FEEDER (PGMA-65736)) | 206815386
Manufacturing | MFG | 2024-10-04 08:00 | 2025-07-28 17:00 |  |  |  | 65736 | 1.9.7.2.1.2.3(36 INCH GRAVIMETRIC FEEDER (PGMA-65736)) | 206815387
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 65736 | 1.9.7.2.1.2.3(36 INCH GRAVIMETRIC FEEDER (PGMA-65736)) | 206815388
FEEDER MANDATORY SPARE (PGMA-65997) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | 65997 | 1.9.7.2.1.2(Coal Feeders (PG-65)) | 206815389
Ordering & Engineering | ENG | 2023-11-29 08:00 | 2024-10-03 17:00 |  |  |  | 65997 | 1.9.7.2.1.2.4(FEEDER MANDATORY SPARE (PGMA-65997)) | 206815390
Manufacturing | MFG | 2024-10-04 08:00 | 2025-07-28 17:00 |  |  |  | 65997 | 1.9.7.2.1.2.4(FEEDER MANDATORY SPARE (PGMA-65997)) | 206815391
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 65997 | 1.9.7.2.1.2.4(FEEDER MANDATORY SPARE (PGMA-65997)) | 206815392
Coal Valves & Gates (PG-67) | SUP | 2023-11-06 08:00 | 2025-08-27 17:00 |  |  |  | PG67 | 1.9.7.2.1(BHEL TRY) | 206815393
Coal Feeding System- Sub dely. (PGMA-67200) | SUP | 2023-11-21 08:00 | 2025-07-28 17:00 |  |  |  | 67200 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815394
Ordering & Engineering | ENG | 2023-11-21 08:00 | 2024-09-10 17:00 |  |  |  | 67200 | 1.9.7.2.1.3.1(Coal Feeding System- Sub dely. (PGMA-67200)) | 206815395
Manufacturing | MFG | 2024-09-11 08:00 | 2025-06-28 17:00 |  |  |  | 67200 | 1.9.7.2.1.3.1(Coal Feeding System- Sub dely. (PGMA-67200)) | 206815396
Dispatch | DIS | 2025-06-29 08:00 | 2025-07-28 17:00 |  |  |  | 67200 | 1.9.7.2.1.3.1(Coal Feeding System- Sub dely. (PGMA-67200)) | 206815397
RAW COAL GATES NEEDLE TYPE (PGMA-67204) | SUP | 2023-11-21 08:00 | 2025-07-28 17:00 |  |  |  | 67204 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815398
Engineering | ENG | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  | 67204 | 1.9.7.2.1.3.2(RAW COAL GATES NEEDLE TYPE (PGMA-67204)) | 206815399
Manufacturing | MFG | 2024-06-03 08:00 | 2025-06-28 17:00 |  |  |  | 67204 | 1.9.7.2.1.3.2(RAW COAL GATES NEEDLE TYPE (PGMA-67204)) | 206815400
Dispatch | DIS | 2025-06-29 08:00 | 2025-07-28 17:00 |  |  |  | 67204 | 1.9.7.2.1.3.2(RAW COAL GATES NEEDLE TYPE (PGMA-67204)) | 206815401
COAL VALVE-36 INCH MOTOR OPERATED (PGMA-67272) | SUP | 2023-11-21 08:00 | 2025-07-28 17:00 |  |  |  | 67272 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815402
Engineering | ENG | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  | 67272 | 1.9.7.2.1.3.3(COAL VALVE-36 INCH MOTOR OPERATED (PGMA-67272)) | 206815403
Manufacturing | MFG | 2024-06-03 08:00 | 2025-06-28 17:00 |  |  |  | 67272 | 1.9.7.2.1.3.3(COAL VALVE-36 INCH MOTOR OPERATED (PGMA-67272)) | 206815404
Dispatch | DIS | 2025-06-29 08:00 | 2025-07-28 17:00 |  |  |  | 67272 | 1.9.7.2.1.3.3(COAL VALVE-36 INCH MOTOR OPERATED (PGMA-67272)) | 206815405
RAW COAL GATE CHAIN OP 36" CIRCULAR (PGMA-67276) | SUP | 2023-11-21 08:00 | 2025-07-28 17:00 |  |  |  | 67276 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815406
Engineering | ENG | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  | 67276 | 1.9.7.2.1.3.4(RAW COAL GATE CHAIN OP 36" CIRCULAR (PGMA-67276)) | 206815407
Manufacturing | MFG | 2024-06-03 08:00 | 2025-06-28 17:00 |  |  |  | 67276 | 1.9.7.2.1.3.4(RAW COAL GATE CHAIN OP 36" CIRCULAR (PGMA-67276)) | 206815408
Dispatch | DIS | 2025-06-29 08:00 | 2025-07-28 17:00 |  |  |  | 67276 | 1.9.7.2.1.3.4(RAW COAL GATE CHAIN OP 36" CIRCULAR (PGMA-67276)) | 206815409
FEEDER OUTLET ISOLATION GATE (PGMA-67283) | SUP | 2023-11-21 08:00 | 2025-07-28 17:00 |  |  |  | 67283 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815410
Engineering | ENG | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  | 67283 | 1.9.7.2.1.3.5(FEEDER OUTLET ISOLATION GATE (PGMA-67283)) | 206815411
Manufacturing | MFG | 2024-06-03 08:00 | 2025-06-28 17:00 |  |  |  | 67283 | 1.9.7.2.1.3.5(FEEDER OUTLET ISOLATION GATE (PGMA-67283)) | 206815412
Dispatch | DIS | 2025-06-29 08:00 | 2025-07-28 17:00 |  |  |  | 67283 | 1.9.7.2.1.3.5(FEEDER OUTLET ISOLATION GATE (PGMA-67283)) | 206815413
Coal Feeding System - DD items (PGMA-67710) | SUP | 2023-11-21 08:00 | 2025-07-28 17:00 |  |  |  | 67710 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815414
Engineering | ENG | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  | 67710 | 1.9.7.2.1.3.6(Coal Feeding System - DD items (PGMA-67710)) | 206815415
Manufacturing | MFG | 2024-06-03 08:00 | 2025-06-28 17:00 |  |  |  | 67710 | 1.9.7.2.1.3.6(Coal Feeding System - DD items (PGMA-67710)) | 206815416
Dispatch | DIS | 2025-06-29 08:00 | 2025-07-28 17:00 |  |  |  | 67710 | 1.9.7.2.1.3.6(Coal Feeding System - DD items (PGMA-67710)) | 206815417
DOWN SPOUT (PGMA-67801) | SUP | 2023-11-06 08:00 | 2025-06-27 17:00 |  |  |  | 67801 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815418
Engineering | ENG | 2023-11-06 08:00 | 2024-05-05 17:00 |  |  |  | 67801 | 1.9.7.2.1.3.7(DOWN SPOUT (PGMA-67801)) | 206815419
Manufacturing | MFG | 2024-05-06 08:00 | 2025-05-28 17:00 |  |  |  | 67801 | 1.9.7.2.1.3.7(DOWN SPOUT (PGMA-67801)) | 206815420
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 67801 | 1.9.7.2.1.3.7(DOWN SPOUT (PGMA-67801)) | 206815421
BUNKER EMPTYING CHUTE ARRANGEMENT (PGMA-67802) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | 67802 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815422
Engineering | ENG | 2023-11-29 08:00 | 2024-06-25 17:00 |  |  |  | 67802 | 1.9.7.2.1.3.8(BUNKER EMPTYING CHUTE ARRANGEMENT (PGMA-67802)) | 206815423
Manufacturing | MFG | 2024-06-26 08:00 | 2025-07-28 17:00 |  |  |  | 67802 | 1.9.7.2.1.3.8(BUNKER EMPTYING CHUTE ARRANGEMENT (PGMA-67802)) | 206815424
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 67802 | 1.9.7.2.1.3.8(BUNKER EMPTYING CHUTE ARRANGEMENT (PGMA-67802)) | 206815425
FEED PIPE TO MILL (PGMA-67803) | SUP | 2023-11-06 08:00 | 2025-06-27 17:00 |  |  |  | 67803 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815426
Engineering | ENG | 2023-11-06 08:00 | 2024-05-05 17:00 |  |  |  | 67803 | 1.9.7.2.1.3.9(FEED PIPE TO MILL (PGMA-67803)) | 206815427
Manufacturing | MFG | 2024-05-06 08:00 | 2025-05-28 17:00 |  |  |  | 67803 | 1.9.7.2.1.3.9(FEED PIPE TO MILL (PGMA-67803)) | 206815428
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 67803 | 1.9.7.2.1.3.9(FEED PIPE TO MILL (PGMA-67803)) | 206815429
FDR ISOLATION GATE MAND SPARES (PGMA-67997) | SUP | 2023-11-29 08:00 | 2025-08-27 17:00 |  |  |  | 67997 | 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | 206815430
Engineering | ENG | 2023-11-29 08:00 | 2024-10-03 17:00 |  |  |  | 67997 | 1.9.7.2.1.3.10(FDR ISOLATION GATE MAND SPARES (PGMA-67997)) | 206815431
Manufacturing | MFG | 2024-10-04 08:00 | 2025-07-28 17:00 |  |  |  | 67997 | 1.9.7.2.1.3.10(FDR ISOLATION GATE MAND SPARES (PGMA-67997)) | 206815432
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 67997 | 1.9.7.2.1.3.10(FDR ISOLATION GATE MAND SPARES (PGMA-67997)) | 206815433
BHEL HYD | SUP | 2022-09-27 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.9.7.2(Supply) | 206815434
MILL and its Components | SUP | 2022-09-27 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.9.7.2.2(BHEL HYD) | 206815435
MILLS(7 NOS.) | SUP | 2022-09-27 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.9.7.2.2.1(MILL and its Components) | 206815436
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.9.7.2.2.1.1(MILLS(7 NOS.)) | 206815437
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.9.7.2.2.1.1(MILLS(7 NOS.)) | 206815438
ASSEMBLY & TESTING | MFG | 2024-02-09 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.9.7.2.2.1.1(MILLS(7 NOS.)) | 206815439
Dispatch of Major Mill Components ( Bowl Hub, MSL ,PGB, Separator Body ,Separator Top ,KGV ,Journal Head ,Journal Assly) | DIS | 2024-03-05 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.9.7.2.2.1.1(MILLS(7 NOS.)) | 206815440
DISPATCH OF BALANCE MILLS ITEMS & ASOCIATED LOOSE ITEMS | DIS | 2024-07-13 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.9.7.2.2.1.1(MILLS(7 NOS.)) | 206815441
BHEL BPL | SUP | 2023-07-27 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.7.2(Supply) | 206815442
Mill Motor | SUP | 2023-07-27 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.7.2.3( BHEL BPL) | 206815443
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-07-27 08:00 | 2024-05-24 17:00 |  |  |  |  | 1.9.7.2.3.1(Mill Motor) | 206815444
Manufacturing & TESTING | MFG | 2024-05-25 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.9.7.2.3.1(Mill Motor) | 206815445
Dispatch &RECEIPT at site | DIS | 2025-02-22 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.7.2.3.1(Mill Motor) | 206815446
BHEL IP | SUP | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.9.7.2(Supply) | 206815447
Ceralin Lined Pulverised Coal Piping items | SUP | 2023-11-21 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.9.7.2.4( BHEL IP ) | 206815448
Engineering & PROCUREMENT | ENG | 2023-11-21 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.9.7.2.4.1(Ceralin Lined Pulverised Coal Piping items) | 206815449
Manufacturing | MFG | 2024-02-04 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.9.7.2.4.1(Ceralin Lined Pulverised Coal Piping items) | 206815450
Dispatch | DIS | 2024-04-04 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.9.7.2.4.1(Ceralin Lined Pulverised Coal Piping items) | 206815451
Erection | ERC | 2024-09-16 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.9.7(Pulverised Fuel System) | 206815452
Mills | ERC | 2024-09-16 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.9.7.3(Erection) | 206815453
Foundation checking, cleaning & placement of packers | CIV | 2024-09-16 08:00 | 2024-10-10 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815454
Erection, alignment & grouting of sole plate, mounting plate | ERC | 2024-10-11 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815455
Erection of planetary gear box & mill side assy. | ERC | 2024-10-31 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815456
Erection of bullring ASSY, vane wheel ASSY & bowl hub ASSY | ERC | 2024-11-20 08:00 | 2024-12-19 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815457
Erection of separator body and valve outlet | ERC | 2024-12-20 08:00 | 2025-01-18 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815458
Erection of Centre feed pipe | ERC | 2025-01-19 08:00 | 2025-02-03 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815459
Erection of dynamic classifier ASSY | ERC | 2025-02-04 08:00 | 2025-03-20 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815460
Erection of roller journal ASSY | ERC | 2025-03-21 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815461
Erection and alignment of motors | ERC | 2025-05-15 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815462
Erection of seal air piping, MDV headers | ERC | 2025-06-04 08:00 | 2025-08-02 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815463
Lube oil system | ERC | 2025-08-03 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815464
Erection of labyrinth seal upper and lower | ERC | 2025-09-02 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815465
Spring compression and roller gap setting | ERC | 2025-10-02 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.9.7.3.1(Mills) | 206815466
Pulverised Fuel Piping (PG-47) | ERC | 2024-12-27 08:00 | 2025-10-29 17:00 |  |  |  | PG47 | 1.9.7.3(Erection) | 206815467
First 4 Nos Mills | ERC | 2024-12-27 08:00 | 2025-04-25 17:00 |  |  |  |  | 1.9.7.3.2(Pulverised Fuel Piping (PG-47)) | 206815468
Erection: Fuel Piping | ERC | 2024-12-27 08:00 | 2025-04-25 17:00 |  |  |  |  | 1.9.7.3.2.1(First 4 Nos Mills) | 206815469
Erection: FUEL PIPE SUPPORTS | ERC | 2024-12-27 08:00 | 2025-04-25 17:00 |  |  |  |  | 1.9.7.3.2.1(First 4 Nos Mills) | 206815470
Erection: FUEL PIPE COUPLING COLLER & ORIFICE | ERC | 2024-12-27 08:00 | 2025-04-25 17:00 |  |  |  |  | 1.9.7.3.2.1(First 4 Nos Mills) | 206815471
Last 3 Nos Mills | ERC | 2025-07-19 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.9.7.3.2(Pulverised Fuel Piping (PG-47)) | 206815472
Erection: Fuel Piping | ERC | 2025-07-19 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.9.7.3.2.2(Last 3 Nos Mills) | 206815473
Erection: FUEL PIPE SUPPORTS | ERC | 2025-07-19 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.9.7.3.2.2(Last 3 Nos Mills) | 206815474
Erection: FUEL PIPE COUPLING COLLER & ORIFICE | ERC | 2025-07-19 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.9.7.3.2.2(Last 3 Nos Mills) | 206815475
Coal Feeders (PG-65) | ERC | 2025-08-28 08:00 | 2025-11-10 17:00 |  |  |  | PG65 | 1.9.7.3(Erection) | 206815476
Erection: Placement and alignment of feeders (First 4 Nos) | ERC | 2025-08-28 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.9.7.3.3(Coal Feeders (PG-65)) | 206815477
Erection: Placement and alignment of feeders (Last 3 Nos) | ERC | 2025-08-28 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.9.7.3.3(Coal Feeders (PG-65)) | 206815478
Coal Valves & Gates (PG-67) | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  | PG67 | 1.9.7.3(Erection) | 206815479
Mills/Feeders | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4(Coal Valves & Gates (PG-67)) | 206815480
Erection: RAW COAL GATES NEEDLE TYPE | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815481
Erection: COAL VALVE-36 INCH MOTOR OPERATED | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815482
Erection: RAW COAL GATE CHAIN OP 36" CIRCULAR | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815483
Erection: FEEDER OUTLET ISOLATION GATE | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815484
Erection: DOWN SPOUT | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815485
Erection: BUNKER EMPTYING CHUTE ARRANGEMENT | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815486
Erection: FEED PIPE TO MILL | ERC | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.9.7.3.4.1( Mills/Feeders) | 206815487
APH | OTH | 2022-12-26 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206815488
Supply | SUP | 2022-12-26 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.9.8(APH) | 206815489
BHEL RPT | SUP | 2022-12-26 08:00 | 2024-11-04 17:00 |  |  |  | PG52 | 1.9.8.1(Supply) | 206815490
LARG AH-ROTORHOUSING(PGMA-52030) | SUP | 2022-12-26 08:00 | 2023-05-04 17:00 |  |  |  | 52030 | 1.9.8.1.1(BHEL RPT) | 206815491
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 52030 | 1.9.8.1.1.1(LARG AH-ROTORHOUSING(PGMA-52030)) | 206815492
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 52030 | 1.9.8.1.1.1(LARG AH-ROTORHOUSING(PGMA-52030)) | 206815493
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-04 17:00 |  |  |  | 52030 | 1.9.8.1.1.1(LARG AH-ROTORHOUSING(PGMA-52030)) | 206815494
COLD END CONN PLATE(PGMA-52042) | SUP | 2022-12-26 08:00 | 2023-05-14 17:00 |  |  |  | 52042 | 1.9.8.1.1(BHEL RPT) | 206815495
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 52042 | 1.9.8.1.1.2(COLD END CONN PLATE(PGMA-52042)) | 206815496
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 52042 | 1.9.8.1.1.2(COLD END CONN PLATE(PGMA-52042)) | 206815497
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-14 17:00 |  |  |  | 52042 | 1.9.8.1.1.2(COLD END CONN PLATE(PGMA-52042)) | 206815498
HOT END CONN PLATE(PGMA-52041) | SUP | 2022-12-26 08:00 | 2023-06-13 17:00 |  |  |  | 52041 | 1.9.8.1.1(BHEL RPT) | 206815499
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 52041 | 1.9.8.1.1.3(HOT END CONN PLATE(PGMA-52041)) | 206815500
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  | 52041 | 1.9.8.1.1.3(HOT END CONN PLATE(PGMA-52041)) | 206815501
Dispatch | DIS | 2023-03-26 08:00 | 2023-06-13 17:00 |  |  |  | 52041 | 1.9.8.1.1.3(HOT END CONN PLATE(PGMA-52041)) | 206815502
LARG AH-SUPRT BEARNG(PGMA-52262) | SUP | 2023-01-15 08:00 | 2023-07-13 17:00 |  |  |  | 52262 | 1.9.8.1.1(BHEL RPT) | 206815503
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 52262 | 1.9.8.1.1.4(LARG AH-SUPRT BEARNG(PGMA-52262)) | 206815504
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 52262 | 1.9.8.1.1.4(LARG AH-SUPRT BEARNG(PGMA-52262)) | 206815505
Dispatch | DIS | 2023-04-15 08:00 | 2023-07-13 17:00 |  |  |  | 52262 | 1.9.8.1.1.4(LARG AH-SUPRT BEARNG(PGMA-52262)) | 206815506
LARG AH-GUIDE BEARNG(PGMA-52261) | SUP | 2023-01-15 08:00 | 2023-07-13 17:00 |  |  |  | 52261 | 1.9.8.1.1(BHEL RPT) | 206815507
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 52261 | 1.9.8.1.1.5(LARG AH-GUIDE BEARNG(PGMA-52261)) | 206815508
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 52261 | 1.9.8.1.1.5(LARG AH-GUIDE BEARNG(PGMA-52261)) | 206815509
Dispatch | DIS | 2023-04-15 08:00 | 2023-07-13 17:00 |  |  |  | 52261 | 1.9.8.1.1.5(LARG AH-GUIDE BEARNG(PGMA-52261)) | 206815510
LARG AH-ROTOR POST(PGMA-52011) | SUP | 2023-01-15 08:00 | 2023-08-12 17:00 |  |  |  | 52011 | 1.9.8.1.1(BHEL RPT) | 206815511
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 52011 | 1.9.8.1.1.6(LARG AH-ROTOR POST(PGMA-52011)) | 206815512
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-24 17:00 |  |  |  | 52011 | 1.9.8.1.1.6(LARG AH-ROTOR POST(PGMA-52011)) | 206815513
Dispatch | DIS | 2023-04-25 08:00 | 2023-08-12 17:00 |  |  |  | 52011 | 1.9.8.1.1.6(LARG AH-ROTOR POST(PGMA-52011)) | 206815514
LARG AH-ROTOR ASSY(PGMA-52010) | SUP | 2023-01-15 08:00 | 2023-08-12 17:00 |  |  |  | 52010 | 1.9.8.1.1(BHEL RPT) | 206815515
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 52010 | 1.9.8.1.1.7(LARG AH-ROTOR ASSY(PGMA-52010)) | 206815516
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-24 17:00 |  |  |  | 52010 | 1.9.8.1.1.7(LARG AH-ROTOR ASSY(PGMA-52010)) | 206815517
Dispatch | DIS | 2023-04-25 08:00 | 2023-08-12 17:00 |  |  |  | 52010 | 1.9.8.1.1.7(LARG AH-ROTOR ASSY(PGMA-52010)) | 206815518
LARG AH-ROTORPINRACK(PGMA-52012) | SUP | 2023-02-04 08:00 | 2023-09-11 17:00 |  |  |  | 52012 | 1.9.8.1.1(BHEL RPT) | 206815519
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 52012 | 1.9.8.1.1.8(LARG AH-ROTORPINRACK(PGMA-52012)) | 206815520
Manufacturing | MFG | 2023-03-06 08:00 | 2023-05-24 17:00 |  |  |  | 52012 | 1.9.8.1.1.8(LARG AH-ROTORPINRACK(PGMA-52012)) | 206815521
Dispatch | DIS | 2023-05-25 08:00 | 2023-09-11 17:00 |  |  |  | 52012 | 1.9.8.1.1.8(LARG AH-ROTORPINRACK(PGMA-52012)) | 206815522
SPECIAL TOOLS/CONTRA(PGMA-52000) | SUP | 2023-02-04 08:00 | 2023-10-11 17:00 |  |  |  | 52000 | 1.9.8.1.1(BHEL RPT) | 206815523
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 52000 | 1.9.8.1.1.9(SPECIAL TOOLS/CONTRA(PGMA-52000)) | 206815524
Manufacturing | MFG | 2023-03-06 08:00 | 2023-06-13 17:00 |  |  |  | 52000 | 1.9.8.1.1.9(SPECIAL TOOLS/CONTRA(PGMA-52000)) | 206815525
Dispatch | DIS | 2023-06-14 08:00 | 2023-10-11 17:00 |  |  |  | 52000 | 1.9.8.1.1.9(SPECIAL TOOLS/CONTRA(PGMA-52000)) | 206815526
LARGE AH ROTOR DRIVE(PGMA-52100) | SUP | 2023-02-04 08:00 | 2023-10-11 17:00 |  |  |  | 52100 | 1.9.8.1.1(BHEL RPT) | 206815527
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 52100 | 1.9.8.1.1.10(LARGE AH ROTOR DRIVE(PGMA-52100)) | 206815528
Manufacturing | MFG | 2023-03-06 08:00 | 2023-06-13 17:00 |  |  |  | 52100 | 1.9.8.1.1.10(LARGE AH ROTOR DRIVE(PGMA-52100)) | 206815529
Dispatch | DIS | 2023-06-14 08:00 | 2023-10-11 17:00 |  |  |  | 52100 | 1.9.8.1.1.10(LARGE AH ROTOR DRIVE(PGMA-52100)) | 206815530
LARG AH-AUX ROTDRIVE(PGMA-52101) | SUP | 2023-06-24 08:00 | 2023-12-10 17:00 |  |  |  | 52101 | 1.9.8.1.1(BHEL RPT) | 206815531
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  | 52101 | 1.9.8.1.1.11(LARG AH-AUX ROTDRIVE(PGMA-52101)) | 206815532
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  | 52101 | 1.9.8.1.1.11(LARG AH-AUX ROTDRIVE(PGMA-52101)) | 206815533
Dispatch | DIS | 2023-10-22 08:00 | 2023-12-10 17:00 |  |  |  | 52101 | 1.9.8.1.1.11(LARG AH-AUX ROTDRIVE(PGMA-52101)) | 206815534
LARG AH-AXIAL SEAL(PGMA-52054) | SUP | 2023-02-24 08:00 | 2023-11-10 17:00 |  |  |  | 52054 | 1.9.8.1.1(BHEL RPT) | 206815535
Engineering | ENG | 2023-02-24 08:00 | 2023-03-25 17:00 |  |  |  | 52054 | 1.9.8.1.1.12(LARG AH-AXIAL SEAL(PGMA-52054)) | 206815536
Manufacturing | MFG | 2023-03-26 08:00 | 2023-07-03 17:00 |  |  |  | 52054 | 1.9.8.1.1.12(LARG AH-AXIAL SEAL(PGMA-52054)) | 206815537
Dispatch | DIS | 2023-07-04 08:00 | 2023-11-10 17:00 |  |  |  | 52054 | 1.9.8.1.1.12(LARG AH-AXIAL SEAL(PGMA-52054)) | 206815538
LARG AH-BY PASS SEAL(PGMA-52055) | SUP | 2023-02-24 08:00 | 2023-11-10 17:00 |  |  |  | 52055 | 1.9.8.1.1(BHEL RPT) | 206815539
Engineering | ENG | 2023-02-24 08:00 | 2023-03-25 17:00 |  |  |  | 52055 | 1.9.8.1.1.13(LARG AH-BY PASS SEAL(PGMA-52055)) | 206815540
Manufacturing | MFG | 2023-03-26 08:00 | 2023-07-03 17:00 |  |  |  | 52055 | 1.9.8.1.1.13(LARG AH-BY PASS SEAL(PGMA-52055)) | 206815541
Dispatch | DIS | 2023-07-04 08:00 | 2023-11-10 17:00 |  |  |  | 52055 | 1.9.8.1.1.13(LARG AH-BY PASS SEAL(PGMA-52055)) | 206815542
LARG AH-ROTORSEALS(PGMA-52013) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 52013 | 1.9.8.1.1(BHEL RPT) | 206815543
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 52013 | 1.9.8.1.1.14(LARG AH-ROTORSEALS(PGMA-52013)) | 206815544
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 52013 | 1.9.8.1.1.14(LARG AH-ROTORSEALS(PGMA-52013)) | 206815545
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 52013 | 1.9.8.1.1.14(LARG AH-ROTORSEALS(PGMA-52013)) | 206815546
OIL PIPING GUIDE BRG(PGMA-52271) | SUP | 2023-08-13 08:00 | 2024-04-08 17:00 |  |  |  | 52271 | 1.9.8.1.1(BHEL RPT) | 206815547
Engineering | ENG | 2023-08-13 08:00 | 2023-09-11 17:00 |  |  |  | 52271 | 1.9.8.1.1.15(OIL PIPING GUIDE BRG(PGMA-52271)) | 206815548
Manufacturing | MFG | 2023-09-12 08:00 | 2023-12-20 17:00 |  |  |  | 52271 | 1.9.8.1.1.15(OIL PIPING GUIDE BRG(PGMA-52271)) | 206815549
Dispatch | DIS | 2023-12-21 08:00 | 2024-04-08 17:00 |  |  |  | 52271 | 1.9.8.1.1.15(OIL PIPING GUIDE BRG(PGMA-52271)) | 206815550
OIL PIPING SUPRT BRG(PGMA-52272) | SUP | 2023-08-13 08:00 | 2024-04-08 17:00 |  |  |  | 52272 | 1.9.8.1.1(BHEL RPT) | 206815551
Engineering | ENG | 2023-08-13 08:00 | 2023-09-11 17:00 |  |  |  | 52272 | 1.9.8.1.1.16(OIL PIPING SUPRT BRG(PGMA-52272)) | 206815552
Manufacturing | MFG | 2023-09-12 08:00 | 2023-12-20 17:00 |  |  |  | 52272 | 1.9.8.1.1.16(OIL PIPING SUPRT BRG(PGMA-52272)) | 206815553
Dispatch | DIS | 2023-12-21 08:00 | 2024-04-08 17:00 |  |  |  | 52272 | 1.9.8.1.1.16(OIL PIPING SUPRT BRG(PGMA-52272)) | 206815554
LARG AH-GENS DETAILS(PGMA-52220) | SUP | 2023-10-02 08:00 | 2024-07-07 17:00 |  |  |  | 52220 | 1.9.8.1.1(BHEL RPT) | 206815555
Engineering | ENG | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | 52220 | 1.9.8.1.1.17(LARG AH-GENS DETAILS(PGMA-52220)) | 206815556
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-08 17:00 |  |  |  | 52220 | 1.9.8.1.1.17(LARG AH-GENS DETAILS(PGMA-52220)) | 206815557
Dispatch | DIS | 2024-02-09 08:00 | 2024-07-07 17:00 |  |  |  | 52220 | 1.9.8.1.1.17(LARG AH-GENS DETAILS(PGMA-52220)) | 206815558
LUB OIL CIRCULATION UN(PGMA-52274) | SUP | 2023-11-21 08:00 | 2024-08-06 17:00 |  |  |  | 52274 | 1.9.8.1.1(BHEL RPT) | 206815559
Engineering | ENG | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  | 52274 | 1.9.8.1.1.18(LUB OIL CIRCULATION UN(PGMA-52274)) | 206815560
Manufacturing | MFG | 2023-12-21 08:00 | 2024-03-29 17:00 |  |  |  | 52274 | 1.9.8.1.1.18(LUB OIL CIRCULATION UN(PGMA-52274)) | 206815561
Dispatch | DIS | 2024-03-30 08:00 | 2024-08-06 17:00 |  |  |  | 52274 | 1.9.8.1.1.18(LUB OIL CIRCULATION UN(PGMA-52274)) | 206815562
LARGE AIR HEATER-LUBRI(PGMA-52275) | SUP | 2023-11-21 08:00 | 2024-08-06 17:00 |  |  |  | 52275 | 1.9.8.1.1(BHEL RPT) | 206815563
Engineering | ENG | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  | 52275 | 1.9.8.1.1.19(LARGE AIR HEATER-LUBRI(PGMA-52275)) | 206815564
Manufacturing | MFG | 2023-12-21 08:00 | 2024-03-29 17:00 |  |  |  | 52275 | 1.9.8.1.1.19(LARGE AIR HEATER-LUBRI(PGMA-52275)) | 206815565
Dispatch | DIS | 2024-03-30 08:00 | 2024-08-06 17:00 |  |  |  | 52275 | 1.9.8.1.1.19(LARGE AIR HEATER-LUBRI(PGMA-52275)) | 206815566
LARG AH-AIRSEAL PIPE(PGMA-52211) | SUP | 2023-11-21 08:00 | 2024-08-06 17:00 |  |  |  | 52211 | 1.9.8.1.1(BHEL RPT) | 206815567
Engineering | ENG | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  | 52211 | 1.9.8.1.1.20(LARG AH-AIRSEAL PIPE(PGMA-52211)) | 206815568
Manufacturing | MFG | 2023-12-21 08:00 | 2024-03-29 17:00 |  |  |  | 52211 | 1.9.8.1.1.20(LARG AH-AIRSEAL PIPE(PGMA-52211)) | 206815569
Dispatch | DIS | 2024-03-30 08:00 | 2024-08-06 17:00 |  |  |  | 52211 | 1.9.8.1.1.20(LARG AH-AIRSEAL PIPE(PGMA-52211)) | 206815570
WASH MANIFLD GAS INL(PGMA-52301) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 52301 | 1.9.8.1.1(BHEL RPT) | 206815571
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 52301 | 1.9.8.1.1.21(WASH MANIFLD GAS INL(PGMA-52301)) | 206815572
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 52301 | 1.9.8.1.1.21(WASH MANIFLD GAS INL(PGMA-52301)) | 206815573
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 52301 | 1.9.8.1.1.21(WASH MANIFLD GAS INL(PGMA-52301)) | 206815574
WASH MANIFLD GAS OUT(PGMA-52302) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 52302 | 1.9.8.1.1(BHEL RPT) | 206815575
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 52302 | 1.9.8.1.1.22(WASH MANIFLD GAS OUT(PGMA-52302)) | 206815576
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 52302 | 1.9.8.1.1.22(WASH MANIFLD GAS OUT(PGMA-52302)) | 206815577
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 52302 | 1.9.8.1.1.22(WASH MANIFLD GAS OUT(PGMA-52302)) | 206815578
CLEANING DEVICE –RETRACT TYPE (PGMA-52338) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 52338 | 1.9.8.1.1(BHEL RPT) | 206815579
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 52338 | 1.9.8.1.1.23(CLEANING DEVICE –RETRACT TYPE (PGMA-52338)) | 206815580
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 52338 | 1.9.8.1.1.23(CLEANING DEVICE –RETRACT TYPE (PGMA-52338)) | 206815581
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 52338 | 1.9.8.1.1.23(CLEANING DEVICE –RETRACT TYPE (PGMA-52338)) | 206815582
LARGE AH-RETRACT CLNG DEVICE (HE)(PGMA-52339) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.9.8.1.1(BHEL RPT) | 206815583
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 52339 | 1.9.8.1.1.24(LARGE AH-RETRACT CLNG DEVICE (HE)(PGMA-52339)) | 206815584
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 52339 | 1.9.8.1.1.24(LARGE AH-RETRACT CLNG DEVICE (HE)(PGMA-52339)) | 206815585
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 52339 | 1.9.8.1.1.24(LARGE AH-RETRACT CLNG DEVICE (HE)(PGMA-52339)) | 206815586
LARGE AH E,C&I COMPONENETS(PGMA-52600) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 52600 | 1.9.8.1.1(BHEL RPT) | 206815587
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 52600 | 1.9.8.1.1.25(LARGE AH E,C&I COMPONENETS(PGMA-52600)) | 206815588
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 52600 | 1.9.8.1.1.25(LARGE AH E,C&I COMPONENETS(PGMA-52600)) | 206815589
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 52600 | 1.9.8.1.1.25(LARGE AH E,C&I COMPONENETS(PGMA-52600)) | 206815590
LARG AH COMMISSIONING SPARES (PGMA-52988) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 52988 | 1.9.8.1.1(BHEL RPT) | 206815591
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 52988 | 1.9.8.1.1.26(LARG AH COMMISSIONING SPARES (PGMA-52988)) | 206815592
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 52988 | 1.9.8.1.1.26(LARG AH COMMISSIONING SPARES (PGMA-52988)) | 206815593
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 52988 | 1.9.8.1.1.26(LARG AH COMMISSIONING SPARES (PGMA-52988)) | 206815594
STEAM COIL APH (PGMA-50510)- BOI | SUP | 2023-07-24 08:00 | 2024-07-17 17:00 |  |  |  | 50510 | 1.9.8.1.1(BHEL RPT) | 206815595
Engineering & Ordering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 50510 | 1.9.8.1.1.27(STEAM COIL APH (PGMA-50510)- BOI) | 206815596
Manufacturing | MFG | 2023-12-21 08:00 | 2024-05-18 17:00 |  |  |  | 50510 | 1.9.8.1.1.27(STEAM COIL APH (PGMA-50510)- BOI) | 206815597
Dispatch | DIS | 2024-05-19 08:00 | 2024-07-17 17:00 |  |  |  | 50510 | 1.9.8.1.1.27(STEAM COIL APH (PGMA-50510)- BOI) | 206815598
Erection | ERC | 2025-05-21 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9.8(APH) | 206815599
First APH | ERC | 2025-05-21 08:00 | 2025-11-13 17:00 |  |  |  |  | 1.9.8.2(Erection) | 206815600
Preparatory works | ERC | 2025-05-21 08:00 | 2025-05-27 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815601
Main pedestal Erection | ERC | 2025-05-28 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815602
Erection of Connecting plates cold & hot end and rotor ASSY | ERC | 2025-06-05 08:00 | 2025-06-24 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815603
Guide bearings and side panels erection | ERC | 2025-06-25 08:00 | 2025-07-16 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815604
Erection of Module | ERC | 2025-07-17 08:00 | 2025-07-31 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815605
Erection of Rotor drive ASSY-Spacer bar, pin rack and T bar | ERC | 2025-08-01 08:00 | 2025-09-09 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815606
Seal setting - Axial and radial | OTH | 2025-09-10 08:00 | 2025-10-09 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815607
Erection of Lube oil system | ERC | 2025-10-10 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815608
Erection of Support systems cleaning device, sensors, alarms etc | ERC | 2025-10-30 08:00 | 2025-11-13 17:00 |  |  |  |  | 1.9.8.2.1( First APH) | 206815609
Second APH | ERC | 2025-06-27 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9.8.2(Erection) | 206815610
Preparatory works | ERC | 2025-06-27 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815611
Main ASSY | ERC | 2025-07-04 08:00 | 2025-07-11 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815612
Erection of Connecting plates cold & hot end and rotor ASSY | ERC | 2025-07-12 08:00 | 2025-07-31 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815613
Guide bearings and side ASSY | ERC | 2025-08-01 08:00 | 2025-08-22 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815614
Erection of Module | ERC | 2025-08-23 08:00 | 2025-09-06 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815615
Erection of Rotor drive ASSY-Spacer bar, pin rack and T bar | ERC | 2025-09-07 08:00 | 2025-10-21 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815616
Seal setting - Axial and radial | ERC | 2025-10-22 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815617
Erection of Lube oil system | ERC | 2025-11-26 08:00 | 2025-12-17 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815618
Erection of Support systems cleaning device, sensors, alarms etc | ERC | 2025-12-18 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9.8.2.2( Second APH) | 206815619
Various Fans | CIV | 2023-01-15 08:00 | 2026-04-30 17:00 |  |  |  |  | 1.9(Boiler & Auxiliaries) | 206815620
Rel of DWG for FD Fan | PE - RFC | 2023-10-31 17:00 | 2023-10-31 17:00 |  |  |  | PCE-00410 | 1.9.9(Various Fans) | 206815621
Rel of DWG for ID Fan | PE - RFC | 2023-11-10 17:00 | 2023-11-10 17:00 |  |  |  | PCE-00420 | 1.9.9(Various Fans) | 206815622
Rel of DWG for PA Fan | PE - RFC | 2023-07-23 17:00 | 2023-07-23 17:00 |  |  |  | PCE-00430 | 1.9.9(Various Fans) | 206815623
Rel of DWG for SA Fan | PE - RFC | 2023-10-31 17:00 | 2023-10-31 17:00 |  |  |  | PCE-00440 | 1.9.9(Various Fans) | 206815624
Civil Work | CIV | 2023-08-13 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.9.9(Various Fans) | 206815625
First ID Fan foundations | CIV | 2024-01-03 08:00 | 2024-05-27 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815626
Excavation | CIV | 2024-01-03 08:00 | 2024-01-18 17:00 |  |  |  |  | 1.9.9.5.1(First ID Fan foundations) | 206815627
RCC Bottom Raft including PCC | CIV | 2024-01-19 08:00 | 2024-02-12 17:00 |  |  |  |  | 1.9.9.5.1(First ID Fan foundations) | 206815628
RCC wall | CIV | 2024-02-13 08:00 | 2024-03-18 17:00 |  |  |  |  | 1.9.9.5.1(First ID Fan foundations) | 206815629
RCC Top Deck | CIV | 2024-03-19 08:00 | 2024-05-02 17:00 |  |  |  |  | 1.9.9.5.1(First ID Fan foundations) | 206815630
Backfilling | CIV | 2024-05-03 08:00 | 2024-05-17 17:00 |  |  |  |  | 1.9.9.5.1(First ID Fan foundations) | 206815631
Finishing Work | CIV | 2024-05-18 08:00 | 2024-05-27 17:00 |  |  |  |  | 1.9.9.5.1(First ID Fan foundations) | 206815632
Second ID Fan foundation | CIV | 2024-01-30 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815633
Excavation | CIV | 2024-01-30 08:00 | 2024-02-13 17:00 |  |  |  |  | 1.9.9.5.2(Second ID Fan foundation) | 206815634
RCC Bottom Raft including PCC | CIV | 2024-02-14 08:00 | 2024-03-09 17:00 |  |  |  |  | 1.9.9.5.2(Second ID Fan foundation) | 206815635
RCC wall | CIV | 2024-03-10 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.9.9.5.2(Second ID Fan foundation) | 206815636
RCC Top Deck | CIV | 2024-04-14 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.9.9.5.2(Second ID Fan foundation) | 206815637
Backfilling | CIV | 2024-05-29 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.9.9.5.2(Second ID Fan foundation) | 206815638
Finishing Work | CIV | 2024-06-13 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.9.9.5.2(Second ID Fan foundation) | 206815639
First FD Fan Foundation | CIV | 2023-11-21 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815640
Excavation | CIV | 2023-11-21 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.9.9.5.3(First FD Fan Foundation) | 206815641
RCC bottom Raft including PCC | CIV | 2023-12-06 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.9.9.5.3(First FD Fan Foundation) | 206815642
RCC Top Deck | CIV | 2024-08-09 08:00 | 2024-10-02 17:00 |  |  |  |  | 1.9.9.5.3(First FD Fan Foundation) | 206815643
Backfilling | CIV | 2024-10-03 08:00 | 2024-10-12 17:00 |  |  |  |  | 1.9.9.5.3(First FD Fan Foundation) | 206815644
Finishing Work | CIV | 2024-10-13 08:00 | 2024-10-20 17:00 |  |  |  |  | 1.9.9.5.3(First FD Fan Foundation) | 206815645
Second FD Fan Foundation | CIV | 2023-12-26 08:00 | 2025-07-09 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815646
Excavation | CIV | 2023-12-26 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.9.9.5.4(Second FD Fan Foundation) | 206815647
RCC bottom Raft including PCC | CIV | 2024-01-10 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.9.9.5.4(Second FD Fan Foundation) | 206815648
RCC Top Deck | CIV | 2025-05-07 08:00 | 2025-06-25 17:00 |  |  |  |  | 1.9.9.5.4(Second FD Fan Foundation) | 206815649
Backfilling | CIV | 2025-06-26 08:00 | 2025-07-04 17:00 |  |  |  |  | 1.9.9.5.4(Second FD Fan Foundation) | 206815650
Finishing Work | CIV | 2025-07-05 08:00 | 2025-07-09 17:00 |  |  |  |  | 1.9.9.5.4(Second FD Fan Foundation) | 206815651
First PA Fan Foundation | CIV | 2023-08-13 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815652
Excavation | CIV | 2023-08-13 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.9.9.5.5(First PA Fan Foundation) | 206815653
RCC bottom Raft including PCC | CIV | 2023-08-28 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.9.9.5.5(First PA Fan Foundation) | 206815654
RCC Top Deck | CIV | 2024-08-27 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.9.9.5.5(First PA Fan Foundation) | 206815655
Backfilling | CIV | 2024-10-31 08:00 | 2024-11-10 17:00 |  |  |  |  | 1.9.9.5.5(First PA Fan Foundation) | 206815656
Finishing Work | CIV | 2024-11-11 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.9.9.5.5(First PA Fan Foundation) | 206815657
Second PA Fan Foundation | CIV | 2023-09-17 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815658
Excavation | CIV | 2023-09-17 08:00 | 2023-10-01 17:00 |  |  |  |  | 1.9.9.5.6(Second PA Fan Foundation) | 206815659
RCC bottom Raft including PCC | CIV | 2023-10-02 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.9.9.5.6(Second PA Fan Foundation) | 206815660
RCC Top Deck | CIV | 2025-05-04 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.9.9.5.6(Second PA Fan Foundation) | 206815661
Backfilling | CIV | 2025-07-08 08:00 | 2025-07-18 17:00 |  |  |  |  | 1.9.9.5.6(Second PA Fan Foundation) | 206815662
Finishing Work | CIV | 2025-07-19 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.9.9.5.6(Second PA Fan Foundation) | 206815663
SA fan Foundation | CIV | 2025-05-04 08:00 | 2025-07-09 17:00 |  |  |  |  | 1.9.9.5(Civil Work) | 206815664
Excavation | CIV | 2025-05-04 08:00 | 2025-05-11 17:00 |  |  |  |  | 1.9.9.5.7(SA fan Foundation) | 206815665
RCC bottom Raft including PCC | CIV | 2025-05-12 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.9.9.5.7(SA fan Foundation) | 206815666
RCC Top Deck | CIV | 2025-05-27 08:00 | 2025-06-28 17:00 |  |  |  |  | 1.9.9.5.7(SA fan Foundation) | 206815667
Backfilling | CIV | 2025-06-29 08:00 | 2025-07-05 17:00 |  |  |  |  | 1.9.9.5.7(SA fan Foundation) | 206815668
Finishing Work | CIV | 2025-07-06 08:00 | 2025-07-09 17:00 |  |  |  |  | 1.9.9.5.7(SA fan Foundation) | 206815669
Supply | SUP | 2023-01-15 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9(Various Fans) | 206815670
Fans (PG - 55 & 56) - BHEL BAP | SUP | 2023-01-15 08:00 | 2024-12-24 17:00 |  |  |  | PG55/56 | 1.9.9.6(Supply) | 206815671
AXL IDFAN FDN MATL(PGMA-55021) | SUP | 2023-01-15 08:00 | 2023-08-12 17:00 |  |  |  | 55021 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815672
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 55021 | 1.9.9.6.1.1(AXL IDFAN FDN MATL(PGMA-55021)) | 206815673
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-24 17:00 |  |  |  | 55021 | 1.9.9.6.1.1(AXL IDFAN FDN MATL(PGMA-55021)) | 206815674
Dispatch | DIS | 2023-04-25 08:00 | 2023-08-12 17:00 |  |  |  | 55021 | 1.9.9.6.1.1(AXL IDFAN FDN MATL(PGMA-55021)) | 206815675
FD FAN FOUNDATION MATL(PGMA-55011) | SUP | 2023-02-04 08:00 | 2023-09-11 17:00 |  |  |  | 55011 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815676
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 55011 | 1.9.9.6.1.2( FD FAN FOUNDATION MATL(PGMA-55011)) | 206815677
Manufacturing | MFG | 2023-03-06 08:00 | 2023-05-24 17:00 |  |  |  | 55011 | 1.9.9.6.1.2( FD FAN FOUNDATION MATL(PGMA-55011)) | 206815678
Dispatch | DIS | 2023-05-25 08:00 | 2023-09-11 17:00 |  |  |  | 55011 | 1.9.9.6.1.2( FD FAN FOUNDATION MATL(PGMA-55011)) | 206815679
PA FAN FOUNDATION MATL(PGMA-55031) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 55031 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815680
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 55031 | 1.9.9.6.1.3(PA FAN FOUNDATION MATL(PGMA-55031)) | 206815681
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 55031 | 1.9.9.6.1.3(PA FAN FOUNDATION MATL(PGMA-55031)) | 206815682
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 55031 | 1.9.9.6.1.3(PA FAN FOUNDATION MATL(PGMA-55031)) | 206815683
AXIAL IDFAN COUPLING(PGMA-55820) | SUP | 2023-11-21 08:00 | 2024-08-06 17:00 |  |  |  | 55820 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815684
Engineering | ENG | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  | 55820 | 1.9.9.6.1.4(AXIAL IDFAN COUPLING(PGMA-55820)) | 206815685
Manufacturing | MFG | 2023-12-21 08:00 | 2024-03-29 17:00 |  |  |  | 55820 | 1.9.9.6.1.4(AXIAL IDFAN COUPLING(PGMA-55820)) | 206815686
Dispatch | DIS | 2024-03-30 08:00 | 2024-08-06 17:00 |  |  |  | 55820 | 1.9.9.6.1.4(AXIAL IDFAN COUPLING(PGMA-55820)) | 206815687
1 STG ID rotor(PGMA-55216) | SUP | 2023-11-21 08:00 | 2024-08-06 17:00 |  |  |  | 55216 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815688
Engineering | ENG | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  | 55216 | 1.9.9.6.1.5(1 STG ID rotor(PGMA-55216)) | 206815689
Manufacturing | MFG | 2023-12-21 08:00 | 2024-03-29 17:00 |  |  |  | 55216 | 1.9.9.6.1.5(1 STG ID rotor(PGMA-55216)) | 206815690
Dispatch | DIS | 2024-03-30 08:00 | 2024-08-06 17:00 |  |  |  | 55216 | 1.9.9.6.1.5(1 STG ID rotor(PGMA-55216)) | 206815691
2 STG ID ROTOR(PGMA-55327) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 55327 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815692
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55327 | 1.9.9.6.1.6(2 STG ID ROTOR(PGMA-55327)) | 206815693
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55327 | 1.9.9.6.1.6(2 STG ID ROTOR(PGMA-55327)) | 206815694
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 55327 | 1.9.9.6.1.6(2 STG ID ROTOR(PGMA-55327)) | 206815695
SECOND STAGE ID HOUSING(PGMA-55627) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 55627 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815696
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55627 | 1.9.9.6.1.7(SECOND STAGE ID HOUSING(PGMA-55627)) | 206815697
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55627 | 1.9.9.6.1.7(SECOND STAGE ID HOUSING(PGMA-55627)) | 206815698
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 55627 | 1.9.9.6.1.7(SECOND STAGE ID HOUSING(PGMA-55627)) | 206815699
ID SEALING/COOLING FAN(PGMA-55024) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55024 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815700
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55024 | 1.9.9.6.1.8(ID SEALING/COOLING FAN(PGMA-55024)) | 206815701
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55024 | 1.9.9.6.1.8(ID SEALING/COOLING FAN(PGMA-55024)) | 206815702
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55024 | 1.9.9.6.1.8(ID SEALING/COOLING FAN(PGMA-55024)) | 206815703
AXIAL FDFAN COUPLING(PGMA-55810) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55810 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815704
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55810 | 1.9.9.6.1.9(AXIAL FDFAN COUPLING(PGMA-55810)) | 206815705
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55810 | 1.9.9.6.1.9(AXIAL FDFAN COUPLING(PGMA-55810)) | 206815706
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55810 | 1.9.9.6.1.9(AXIAL FDFAN COUPLING(PGMA-55810)) | 206815707
1 STG FD HOUSING (PGMA 55516) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55516 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815708
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55516 | 1.9.9.6.1.10(1 STG FD HOUSING (PGMA 55516)) | 206815709
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55516 | 1.9.9.6.1.10(1 STG FD HOUSING (PGMA 55516)) | 206815710
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55516 | 1.9.9.6.1.10(1 STG FD HOUSING (PGMA 55516)) | 206815711
FD FAN INSUL WOOL (PGMA 55919) | SUP | 2024-05-19 08:00 | 2024-12-24 17:00 |  |  |  | 55919 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815712
Engineering | ENG | 2024-05-19 08:00 | 2024-06-17 17:00 |  |  |  | 55919 | 1.9.9.6.1.11(FD FAN INSUL WOOL (PGMA 55919)) | 206815713
Manufacturing | MFG | 2024-06-18 08:00 | 2024-09-25 17:00 |  |  |  | 55919 | 1.9.9.6.1.11(FD FAN INSUL WOOL (PGMA 55919)) | 206815714
Dispatch | DIS | 2024-09-26 08:00 | 2024-12-24 17:00 |  |  |  | 55919 | 1.9.9.6.1.11(FD FAN INSUL WOOL (PGMA 55919)) | 206815715
FD FAN COUPLING GUARD (PGMA 55015) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55015 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815716
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55015 | 1.9.9.6.1.12(FD FAN COUPLING GUARD (PGMA 55015)) | 206815717
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55015 | 1.9.9.6.1.12(FD FAN COUPLING GUARD (PGMA 55015)) | 206815718
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55015 | 1.9.9.6.1.12(FD FAN COUPLING GUARD (PGMA 55015)) | 206815719
FD SET & INDN SHAFT (PGMA 55410) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55410 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815720
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55410 | 1.9.9.6.1.13(FD SET & INDN SHAFT (PGMA 55410)) | 206815721
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55410 | 1.9.9.6.1.13(FD SET & INDN SHAFT (PGMA 55410)) | 206815722
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55410 | 1.9.9.6.1.13(FD SET & INDN SHAFT (PGMA 55410)) | 206815723
FD FAN EXPN JOINTS (PGMA 55510) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55510 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815724
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55510 | 1.9.9.6.1.14(FD FAN EXPN JOINTS (PGMA 55510)) | 206815725
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55510 | 1.9.9.6.1.14(FD FAN EXPN JOINTS (PGMA 55510)) | 206815726
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55510 | 1.9.9.6.1.14(FD FAN EXPN JOINTS (PGMA 55510)) | 206815727
FD FAN DIFFUSER (PGMA 55816) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55816 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815728
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55816 | 1.9.9.6.1.15(FD FAN DIFFUSER (PGMA 55816)) | 206815729
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55816 | 1.9.9.6.1.15(FD FAN DIFFUSER (PGMA 55816)) | 206815730
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55816 | 1.9.9.6.1.15(FD FAN DIFFUSER (PGMA 55816)) | 206815731
FD FAN SUCTION BOX (PGMA 55716) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55716 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815732
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55716 | 1.9.9.6.1.16(FD FAN SUCTION BOX (PGMA 55716)) | 206815733
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55716 | 1.9.9.6.1.16(FD FAN SUCTION BOX (PGMA 55716)) | 206815734
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55716 | 1.9.9.6.1.16(FD FAN SUCTION BOX (PGMA 55716)) | 206815735
AXIAL FDFAN SILENCER(PGMA-55911) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55911 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815736
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55911 | 1.9.9.6.1.17(AXIAL FDFAN SILENCER(PGMA-55911)) | 206815737
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55911 | 1.9.9.6.1.17(AXIAL FDFAN SILENCER(PGMA-55911)) | 206815738
Dispatch | DIS | 2024-07-08 08:00 | 2024-10-05 17:00 |  |  |  | 55911 | 1.9.9.6.1.17(AXIAL FDFAN SILENCER(PGMA-55911)) | 206815739
ID FAN C&I ITEMS(PGMA-55027) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55027 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815740
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55027 | 1.9.9.6.1.18(ID FAN C&I ITEMS(PGMA-55027)) | 206815741
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55027 | 1.9.9.6.1.18(ID FAN C&I ITEMS(PGMA-55027)) | 206815742
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55027 | 1.9.9.6.1.18(ID FAN C&I ITEMS(PGMA-55027)) | 206815743
ID FAN CPLNG GUARD (PGMA 55025) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55025 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815744
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55025 | 1.9.9.6.1.19(ID FAN CPLNG GUARD (PGMA 55025)) | 206815745
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55025 | 1.9.9.6.1.19(ID FAN CPLNG GUARD (PGMA 55025)) | 206815746
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55025 | 1.9.9.6.1.19(ID FAN CPLNG GUARD (PGMA 55025)) | 206815747
ID SET & INDN SHAFT (PGMA 55420) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55420 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815748
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55420 | 1.9.9.6.1.20(ID SET & INDN SHAFT (PGMA 55420)) | 206815749
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55420 | 1.9.9.6.1.20(ID SET & INDN SHAFT (PGMA 55420)) | 206815750
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55420 | 1.9.9.6.1.20(ID SET & INDN SHAFT (PGMA 55420)) | 206815751
ID FAN EXPN JOINTS (PGMA 55520) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55520 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815752
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55520 | 1.9.9.6.1.21(ID FAN EXPN JOINTS (PGMA 55520)) | 206815753
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55520 | 1.9.9.6.1.21(ID FAN EXPN JOINTS (PGMA 55520)) | 206815754
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55520 | 1.9.9.6.1.21(ID FAN EXPN JOINTS (PGMA 55520)) | 206815755
ID FAN DIFFUSER (PGMA 55827) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55827 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815756
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55827 | 1.9.9.6.1.22(ID FAN DIFFUSER (PGMA 55827)) | 206815757
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55827 | 1.9.9.6.1.22(ID FAN DIFFUSER (PGMA 55827)) | 206815758
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55827 | 1.9.9.6.1.22(ID FAN DIFFUSER (PGMA 55827)) | 206815759
ID FAN SUCTION BOX (PGMA 55727) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55727 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815760
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55727 | 1.9.9.6.1.23(ID FAN SUCTION BOX (PGMA 55727)) | 206815761
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55727 | 1.9.9.6.1.23(ID FAN SUCTION BOX (PGMA 55727)) | 206815762
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55727 | 1.9.9.6.1.23(ID FAN SUCTION BOX (PGMA 55727)) | 206815763
AXIAL ID FAN LUBE OIL(PGMA-55920) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55920 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815764
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55920 | 1.9.9.6.1.24(AXIAL ID FAN LUBE OIL(PGMA-55920)) | 206815765
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55920 | 1.9.9.6.1.24(AXIAL ID FAN LUBE OIL(PGMA-55920)) | 206815766
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55920 | 1.9.9.6.1.24(AXIAL ID FAN LUBE OIL(PGMA-55920)) | 206815767
FD FAN C&I ITEMS(PGMA-55017) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55017 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815768
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55017 | 1.9.9.6.1.25(FD FAN C&I ITEMS(PGMA-55017)) | 206815769
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55017 | 1.9.9.6.1.25(FD FAN C&I ITEMS(PGMA-55017)) | 206815770
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55017 | 1.9.9.6.1.25(FD FAN C&I ITEMS(PGMA-55017)) | 206815771
AXIAL FD FAN LUBE OIL(PGMA-55910) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55910 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815772
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55910 | 1.9.9.6.1.26(AXIAL FD FAN LUBE OIL(PGMA-55910)) | 206815773
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55910 | 1.9.9.6.1.26(AXIAL FD FAN LUBE OIL(PGMA-55910)) | 206815774
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55910 | 1.9.9.6.1.26(AXIAL FD FAN LUBE OIL(PGMA-55910)) | 206815775
2 STG PA ROTOR(PGMA-55335) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55335 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815776
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55335 | 1.9.9.6.1.27(2 STG PA ROTOR(PGMA-55335)) | 206815777
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55335 | 1.9.9.6.1.27(2 STG PA ROTOR(PGMA-55335)) | 206815778
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55335 | 1.9.9.6.1.27(2 STG PA ROTOR(PGMA-55335)) | 206815779
2 STG PA HOUSING (PGMA 55635) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55635 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815780
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55635 | 1.9.9.6.1.28(2 STG PA HOUSING (PGMA 55635)) | 206815781
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55635 | 1.9.9.6.1.28(2 STG PA HOUSING (PGMA 55635)) | 206815782
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55635 | 1.9.9.6.1.28(2 STG PA HOUSING (PGMA 55635)) | 206815783
PA FAN INSUL WOOL (PGMA 55939) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55939 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815784
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55939 | 1.9.9.6.1.29(PA FAN INSUL WOOL (PGMA 55939)) | 206815785
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55939 | 1.9.9.6.1.29(PA FAN INSUL WOOL (PGMA 55939)) | 206815786
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55939 | 1.9.9.6.1.29(PA FAN INSUL WOOL (PGMA 55939)) | 206815787
PA FAN CPLNG GUARD (PGMA 55035) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55035 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815788
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55035 | 1.9.9.6.1.30(PA FAN CPLNG GUARD (PGMA 55035)) | 206815789
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55035 | 1.9.9.6.1.30(PA FAN CPLNG GUARD (PGMA 55035)) | 206815790
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55035 | 1.9.9.6.1.30(PA FAN CPLNG GUARD (PGMA 55035)) | 206815791
PA SET & INDN SHAFT (PGMA 55430) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55430 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815792
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55430 | 1.9.9.6.1.31(PA SET & INDN SHAFT (PGMA 55430)) | 206815793
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55430 | 1.9.9.6.1.31(PA SET & INDN SHAFT (PGMA 55430)) | 206815794
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55430 | 1.9.9.6.1.31(PA SET & INDN SHAFT (PGMA 55430)) | 206815795
PA FAN EXPN JOINTS (PGMA 55530) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55530 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815796
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55530 | 1.9.9.6.1.32(PA FAN EXPN JOINTS (PGMA 55530)) | 206815797
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55530 | 1.9.9.6.1.32(PA FAN EXPN JOINTS (PGMA 55530)) | 206815798
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55530 | 1.9.9.6.1.32(PA FAN EXPN JOINTS (PGMA 55530)) | 206815799
PA FAN DIFFUSER (PGMA 55835) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55835 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815800
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55835 | 1.9.9.6.1.33(PA FAN DIFFUSER (PGMA 55835)) | 206815801
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55835 | 1.9.9.6.1.33(PA FAN DIFFUSER (PGMA 55835)) | 206815802
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55835 | 1.9.9.6.1.33(PA FAN DIFFUSER (PGMA 55835)) | 206815803
PA FAN SUCTION BOX (PGMA 55735) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55735 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815804
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55735 | 1.9.9.6.1.34(PA FAN SUCTION BOX (PGMA 55735)) | 206815805
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55735 | 1.9.9.6.1.34(PA FAN SUCTION BOX (PGMA 55735)) | 206815806
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55735 | 1.9.9.6.1.34(PA FAN SUCTION BOX (PGMA 55735)) | 206815807
RADIAL SEAL AIR FAN ROTOR(PGMA-56173) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56173 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815808
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56173 | 1.9.9.6.1.35(RADIAL SEAL AIR FAN ROTOR(PGMA-56173)) | 206815809
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56173 | 1.9.9.6.1.35(RADIAL SEAL AIR FAN ROTOR(PGMA-56173)) | 206815810
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56173 | 1.9.9.6.1.35(RADIAL SEAL AIR FAN ROTOR(PGMA-56173)) | 206815811
AXL PAFAN COUPLING(PGMA-55830) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55830 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815812
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55830 | 1.9.9.6.1.36(AXL PAFAN COUPLING(PGMA-55830)) | 206815813
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55830 | 1.9.9.6.1.36(AXL PAFAN COUPLING(PGMA-55830)) | 206815814
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55830 | 1.9.9.6.1.36(AXL PAFAN COUPLING(PGMA-55830)) | 206815815
PA FAN SILENCER(PGMA-55931) | SUP | 2023-12-21 08:00 | 2024-09-05 17:00 |  |  |  | 55931 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815816
Engineering | ENG | 2023-12-21 08:00 | 2024-01-19 17:00 |  |  |  | 55931 | 1.9.9.6.1.37(PA FAN SILENCER(PGMA-55931)) | 206815817
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-28 17:00 |  |  |  | 55931 | 1.9.9.6.1.37(PA FAN SILENCER(PGMA-55931)) | 206815818
Dispatch | DIS | 2024-04-29 08:00 | 2024-09-05 17:00 |  |  |  | 55931 | 1.9.9.6.1.37(PA FAN SILENCER(PGMA-55931)) | 206815819
FIRST FILL LUBRICANTS(PGMA-55091) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55091 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815820
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55091 | 1.9.9.6.1.38(FIRST FILL LUBRICANTS(PGMA-55091)) | 206815821
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55091 | 1.9.9.6.1.38(FIRST FILL LUBRICANTS(PGMA-55091)) | 206815822
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55091 | 1.9.9.6.1.38(FIRST FILL LUBRICANTS(PGMA-55091)) | 206815823
RADIAL PENT HOUSE VENT(PGMA-56161) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56161 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815824
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56161 | 1.9.9.6.1.39(RADIAL PENT HOUSE VENT(PGMA-56161)) | 206815825
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56161 | 1.9.9.6.1.39(RADIAL PENT HOUSE VENT(PGMA-56161)) | 206815826
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56161 | 1.9.9.6.1.39(RADIAL PENT HOUSE VENT(PGMA-56161)) | 206815827
RADIAL SEAL AIR FAN BEARINGS (PGMA 56373) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56373 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815828
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56373 | 1.9.9.6.1.40(RADIAL SEAL AIR FAN BEARINGS (PGMA 56373)) | 206815829
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56373 | 1.9.9.6.1.40(RADIAL SEAL AIR FAN BEARINGS (PGMA 56373)) | 206815830
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56373 | 1.9.9.6.1.40(RADIAL SEAL AIR FAN BEARINGS (PGMA 56373)) | 206815831
RADIAL SEAL AIR FAN STATOR (PGMA 56473) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56473 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815832
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56473 | 1.9.9.6.1.41(RADIAL SEAL AIR FAN STATOR (PGMA 56473)) | 206815833
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56473 | 1.9.9.6.1.41(RADIAL SEAL AIR FAN STATOR (PGMA 56473)) | 206815834
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56473 | 1.9.9.6.1.41(RADIAL SEAL AIR FAN STATOR (PGMA 56473)) | 206815835
SA FAN CPLNG GUARD (PGMA 56075) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56075 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815836
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56075 | 1.9.9.6.1.42(SA FAN CPLNG GUARD (PGMA 56075)) | 206815837
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56075 | 1.9.9.6.1.42(SA FAN CPLNG GUARD (PGMA 56075)) | 206815838
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56075 | 1.9.9.6.1.42(SA FAN CPLNG GUARD (PGMA 56075)) | 206815839
SA FAN MTR CANOPY (PGMA 56079) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56079 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815840
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56079 | 1.9.9.6.1.43(SA FAN MTR CANOPY (PGMA 56079)) | 206815841
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56079 | 1.9.9.6.1.43(SA FAN MTR CANOPY (PGMA 56079)) | 206815842
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56079 | 1.9.9.6.1.43(SA FAN MTR CANOPY (PGMA 56079)) | 206815843
SEAL AIR FAN COUPLING((PGMA-56870) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 56870 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815844
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 56870 | 1.9.9.6.1.44(SEAL AIR FAN COUPLING((PGMA-56870)) | 206815845
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 56870 | 1.9.9.6.1.44(SEAL AIR FAN COUPLING((PGMA-56870)) | 206815846
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 56870 | 1.9.9.6.1.44(SEAL AIR FAN COUPLING((PGMA-56870)) | 206815847
AXL FAN TOOL & FIXTU(PGMA-55000) | SUP | 2024-01-10 08:00 | 2024-10-05 17:00 |  |  |  | 55000 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815848
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 55000 | 1.9.9.6.1.45(AXL FAN TOOL & FIXTU(PGMA-55000)) | 206815849
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 55000 | 1.9.9.6.1.45(AXL FAN TOOL & FIXTU(PGMA-55000)) | 206815850
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55000 | 1.9.9.6.1.45(AXL FAN TOOL & FIXTU(PGMA-55000)) | 206815851
PA FAN C&I ITEMS(PGMA-55037) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 55037 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815852
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55037 | 1.9.9.6.1.46(PA FAN C&I ITEMS(PGMA-55037)) | 206815853
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 55037 | 1.9.9.6.1.46(PA FAN C&I ITEMS(PGMA-55037)) | 206815854
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 55037 | 1.9.9.6.1.46(PA FAN C&I ITEMS(PGMA-55037)) | 206815855
SEAL AIR FAN C&I ITEMS(PGMA-56077) | SUP | 2024-05-09 08:00 | 2024-11-14 17:00 |  |  |  | 56077 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815856
Engineering | ENG | 2024-05-09 08:00 | 2024-06-07 17:00 |  |  |  | 56077 | 1.9.9.6.1.47(SEAL AIR FAN C&I ITEMS(PGMA-56077)) | 206815857
Manufacturing | MFG | 2024-06-08 08:00 | 2024-07-27 17:00 |  |  |  | 56077 | 1.9.9.6.1.47(SEAL AIR FAN C&I ITEMS(PGMA-56077)) | 206815858
Dispatch | DIS | 2024-07-28 08:00 | 2024-11-14 17:00 |  |  |  | 56077 | 1.9.9.6.1.47(SEAL AIR FAN C&I ITEMS(PGMA-56077)) | 206815859
RADIAL SEAL AIR FAN MO(PGMA-56670) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 56670 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815860
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 56670 | 1.9.9.6.1.48(RADIAL SEAL AIR FAN MO(PGMA-56670)) | 206815861
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 56670 | 1.9.9.6.1.48(RADIAL SEAL AIR FAN MO(PGMA-56670)) | 206815862
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 56670 | 1.9.9.6.1.48(RADIAL SEAL AIR FAN MO(PGMA-56670)) | 206815863
AXIAL PA FAN LUBE OIL(PGMA-55930) | SUP | 2024-02-29 08:00 | 2024-10-05 17:00 |  |  |  | 55930 | 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | 206815864
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 55930 | 1.9.9.6.1.49(AXIAL PA FAN LUBE OIL(PGMA-55930)) | 206815865
Manufacturing | MFG | 2024-03-30 08:00 | 2024-05-18 17:00 |  |  |  | 55930 | 1.9.9.6.1.49(AXIAL PA FAN LUBE OIL(PGMA-55930)) | 206815866
Dispatch | DIS | 2024-05-19 08:00 | 2024-10-05 17:00 |  |  |  | 55930 | 1.9.9.6.1.49(AXIAL PA FAN LUBE OIL(PGMA-55930)) | 206815867
Fan Motor - BHEL BPL | SUP | 2023-05-27 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6(Supply) | 206815868
ID Fan Motor | SUP | 2023-05-27 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6.2(Fan Motor - BHEL BPL) | 206815869
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-05-27 08:00 | 2024-02-22 17:00 |  |  |  |  | 1.9.9.6.2.1(ID Fan Motor) | 206815870
Manufacturing & TESTING | MFG | 2024-02-23 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.9.9.6.2.1(ID Fan Motor) | 206815871
Dispatch | DIS | 2025-02-22 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.9.6.2.1(ID Fan Motor) | 206815872
RECEIPT AT SITE | REC | 2025-03-24 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6.2.1(ID Fan Motor) | 206815873
FD Fan Motor | SUP | 2023-05-27 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6.2(Fan Motor - BHEL BPL) | 206815874
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-05-27 08:00 | 2024-02-22 17:00 |  |  |  |  | 1.9.9.6.2.2(FD Fan Motor) | 206815875
Manufacturing & TESTING | MFG | 2024-02-23 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.9.9.6.2.2(FD Fan Motor) | 206815876
Dispatch | DIS | 2025-02-22 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.9.6.2.2(FD Fan Motor) | 206815877
RECEIPT AT SITE | REC | 2025-03-24 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6.2.2(FD Fan Motor) | 206815878
PA Fan Motor | SUP | 2023-05-27 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6.2(Fan Motor - BHEL BPL) | 206815879
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-05-27 08:00 | 2024-02-22 17:00 |  |  |  |  | 1.9.9.6.2.3(PA Fan Motor) | 206815880
Manufacturing & TESTING | MFG | 2024-02-23 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.9.9.6.2.3(PA Fan Motor) | 206815881
Dispatch | DIS | 2025-02-22 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.9.6.2.3(PA Fan Motor) | 206815882
RECEIPT AT SITE | REC | 2025-03-24 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.9.9.6.2.3(PA Fan Motor) | 206815883
Erection | ERC | 2024-08-26 08:00 | 2026-04-30 17:00 |  |  |  |  | 1.9.9(Various Fans) | 206815884
First ID FAN | ERC | 2024-08-26 08:00 | 2026-01-30 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815885
Foundation preparation and corrections | CIV | 2024-08-26 08:00 | 2024-09-02 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815886
Blue matching between base plate & fan housing foot | ERC | 2024-09-03 08:00 | 2024-09-20 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815887
Suction chamber pre-assembly and Erection | ERC | 2024-09-21 08:00 | 2024-10-14 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815888
Diffuser pre-assembly undersection | ERC | 2024-10-15 08:00 | 2024-11-07 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815889
Installation of base plate and fan housing bottom | ERC | 2024-11-08 08:00 | 2024-11-25 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815890
Erection of rotor assembly and coupling | ERC | 2024-11-26 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815891
Motor Erection, alignment & grouting | ERC | 2024-12-16 08:00 | 2024-12-27 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815892
Installation of Fan housing upper part | ERC | 2024-12-28 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815893
Erection of dampers and actuators | ERC | 2025-01-15 08:00 | 2025-01-30 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815894
Erection of expansion joints | ERC | 2025-01-31 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815895
Lube oil system Erection | ERC | 2025-02-12 08:00 | 2025-03-13 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815896
Final Alignment | ERC | 2025-09-30 08:00 | 2025-10-06 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815897
Box Up of Fan | ERC | 2025-12-01 08:00 | 2025-12-02 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815898
Insulation | ERC | 2026-01-01 08:00 | 2026-01-30 17:00 |  |  |  |  | 1.9.9.7.1(First ID FAN) | 206815899
Second ID Fan | ERC | 2024-09-26 08:00 | 2026-04-30 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815900
Foundation preparation and corrections | CIV | 2024-09-26 08:00 | 2024-10-03 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815901
Blue matching between base plate & fan housing foot | ERC | 2024-10-04 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815902
Suction chamber pre-assembly Miserection | ERC | 2024-10-22 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815903
Diffuser pre-assembly Miserection | ERC | 2024-11-15 08:00 | 2024-12-08 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815904
Installation of base plate and fan housing bottom | ERC | 2024-12-09 08:00 | 2024-12-26 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815905
Erection of rotor assembly and coupling | ERC | 2024-12-27 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815906
Miserection, alignment & grouting | ERC | 2025-01-16 08:00 | 2025-01-27 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815907
Installation of Fan housing upper part | ERC | 2025-01-28 08:00 | 2025-02-14 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815908
Erection of dampers and actuators | ERC | 2025-02-15 08:00 | 2025-03-02 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815909
Erection of expansion joints | ERC | 2025-03-03 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815910
Lube oil Miserection | ERC | 2025-03-15 08:00 | 2025-04-13 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815911
Final Alignment | ERC | 2025-10-11 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815912
Box Up of Fan | ERC | 2025-12-31 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815913
Insulation | ERC | 2026-04-01 08:00 | 2026-04-30 17:00 |  |  |  |  | 1.9.9.7.2(Second ID Fan) | 206815914
First FD Fan | ERC | 2025-01-19 08:00 | 2026-01-02 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815915
Foundation preparation and correction | CIV | 2025-01-19 08:00 | 2025-01-24 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815916
Blue matching between base plate & fan housing foot | ERC | 2025-01-25 08:00 | 2025-02-09 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815917
Erection of suction chamber & fan housing bottom | ERC | 2025-02-10 08:00 | 2025-02-27 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815918
Erection & Alignment of Diffuser ASSY | ERC | 2025-02-28 08:00 | 2025-03-17 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815919
Silencer preassembly preassembly | ERC | 2025-03-18 08:00 | 2025-04-16 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815920
Erection of rotor ASSY and coupling | ERC | 2025-04-17 08:00 | 2025-04-28 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815921
ASSY, alignment and grouting | ERC | 2025-04-29 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815922
Mounting of blades and blade gap measurement | ERC | 2025-05-09 08:00 | 2025-05-28 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815923
Erection of fan housing upper part | ERC | 2025-05-29 08:00 | 2025-06-09 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815924
Erection of dampers and actuators | ERC | 2025-06-10 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815925
Assembly of expansion joints | ERC | 2025-06-18 08:00 | 2025-06-25 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815926
Lube oil ASSY | ERC | 2025-06-26 08:00 | 2025-07-19 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815927
Final Alignment | ERC | 2025-09-25 08:00 | 2025-09-28 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815928
Box Up of Fan | ERC | 2025-12-06 08:00 | 2025-12-07 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815929
Insulation | ERC | 2025-12-10 08:00 | 2026-01-02 17:00 |  |  |  |  | 1.9.9.7.3(First FD Fan) | 206815930
Second FD Fan | ERC | 2025-07-20 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815931
Foundation preparation and correction | CIV | 2025-07-20 08:00 | 2025-07-25 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815932
Blue matching between base plate & fan housing foot | ERC | 2025-07-26 08:00 | 2025-08-10 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815933
Erection of suction chamber & fan housing bottom | ERC | 2025-08-11 08:00 | 2025-08-26 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815934
Erection & Alignment of Diffuser ASSY | ERC | 2025-08-27 08:00 | 2025-09-11 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815935
Silencer preassembly preassembly | ERC | 2025-09-12 08:00 | 2025-10-07 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815936
Erection of rotor ASSY and coupling | ERC | 2025-10-08 08:00 | 2025-10-19 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815937
ASSY, alignment and grouting | ERC | 2025-10-20 08:00 | 2025-10-27 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815938
Mounting of blades and blade gap measurement | ERC | 2025-10-28 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815939
Erection of fan housing upper part | ERC | 2025-11-15 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815940
Erection of dampers and actuators | ERC | 2025-11-27 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815941
Assembly of expansion joints | ERC | 2025-12-05 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815942
Lube oil ASSY | ERC | 2025-12-13 08:00 | 2025-12-30 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815943
Final Alignment | ERC | 2026-01-17 08:00 | 2026-01-20 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815944
Box Up of Fan | ERC | 2026-01-31 08:00 | 2026-02-01 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815945
Insulation | ERC | 2026-02-04 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.9.9.7.4(Second FD Fan) | 206815946
Second PA Fan | ERC | 2025-02-18 08:00 | 2026-03-30 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815947
Foundation preparation and correction | CIV | 2025-02-18 08:00 | 2025-02-23 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815948
Blue matching between base plate & fan housing foot | ERC | 2025-02-24 08:00 | 2025-03-07 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815949
Erection of suction chamber & fan housing bottom | ERC | 2025-03-08 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815950
Erection & Alignment of Diffuser ASSY | ERC | 2025-03-24 08:00 | 2025-04-08 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815951
Silencer preassembly preassembly | ERC | 2025-04-09 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815952
Erection of rotor ASSY and coupling | ERC | 2025-03-24 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815953
ASSY, alignment and grouting | ERC | 2025-03-24 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815954
Mounting of blades and blade gap measurement | ERC | 2025-04-03 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815955
Erection of fan housing upper part | ERC | 2025-04-21 08:00 | 2025-04-30 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815956
Erection of dampers and actuators | ERC | 2025-05-01 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815957
Assembly of expansion joints | ERC | 2025-05-09 08:00 | 2025-05-16 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815958
Lube oil ASSY | ERC | 2025-05-17 08:00 | 2025-06-09 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815959
Final Alignment | ERC | 2025-09-20 08:00 | 2025-09-23 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815960
Box Up of Fan | ERC | 2026-02-12 08:00 | 2026-02-13 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815961
Insulation | ERC | 2026-03-07 08:00 | 2026-03-30 17:00 |  |  |  |  | 1.9.9.7.5(Second PA Fan) | 206815962
First PA Fan | ERC | 2025-08-22 08:00 | 2026-03-07 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815963
Foundation preparation and correction | CIV | 2025-08-22 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815964
Blue matching between base plate & fan housing foot | ERC | 2025-08-28 08:00 | 2025-09-08 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815965
Erection of suction chamber & fan housing bottom | ERC | 2025-09-09 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815966
Erection & Alignment of Diffuser ASSY | ERC | 2025-09-25 08:00 | 2025-10-10 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815967
Silencer preassembly preassembly | ERC | 2025-09-25 08:00 | 2025-10-24 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815968
Erection of rotor ASSY and coupling | ERC | 2025-09-25 08:00 | 2025-10-06 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815969
ASSY, alignment and grouting | ERC | 2025-10-07 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815970
Mounting of blades and blade gap measurement | ERC | 2025-10-17 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815971
Erection of fan housing upper part | ERC | 2025-11-04 08:00 | 2025-11-13 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815972
Erection of dampers and actuators | ERC | 2025-11-14 08:00 | 2025-11-21 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815973
Assembly of expansion joints | ERC | 2025-11-22 08:00 | 2025-11-29 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815974
Lube oil ASSY | ERC | 2025-11-30 08:00 | 2025-12-23 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815975
Final Alignment | ERC | 2026-01-12 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815976
Box Up of Fan | ERC | 2026-01-28 08:00 | 2026-01-29 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815977
Insulation | ERC | 2026-02-20 08:00 | 2026-03-07 17:00 |  |  |  |  | 1.9.9.7.6(First PA Fan) | 206815978
SA FAN | ERC | 2026-01-20 08:00 | 2026-04-21 17:00 |  |  |  |  | 1.9.9.7(Erection) | 206815979
Foundation preparation and correction | CIV | 2026-01-20 08:00 | 2026-01-31 17:00 |  |  |  |  | 1.9.9.7.7(SA FAN) | 206815980
Blue matching between base plate & fan housing foot | ERC | 2026-02-01 08:00 | 2026-02-20 17:00 |  |  |  |  | 1.9.9.7.7(SA FAN) | 206815981
Erection of fan housing | ERC | 2026-02-21 08:00 | 2026-03-12 17:00 |  |  |  |  | 1.9.9.7.7(SA FAN) | 206815982
Erection of rotor ASSY and coupling | ERC | 2026-03-13 08:00 | 2026-03-22 17:00 |  |  |  |  | 1.9.9.7.7(SA FAN) | 206815983
ASSY, alignment and grouting | ERC | 2026-03-23 08:00 | 2026-04-01 17:00 |  |  |  |  | 1.9.9.7.7(SA FAN) | 206815984
Erection of dampers and actuators | ERC | 2026-04-02 08:00 | 2026-04-21 17:00 |  |  |  |  | 1.9.9.7.7(SA FAN) | 206815985
Electrostatic Precipitator | OTH | 2022-11-16 08:00 | 2025-12-12 17:00 | 2022-11-21 |  |  |  | 1.9(Boiler & Auxiliaries) | 206815986
REL of DWG for ESP Foundation | PE - RFC | 2023-02-26 17:00 | 2023-02-26 17:00 |  |  |  | PCE-00300 | 1.9.10(Electrostatic Precipitator) | 206815987
Civil | CIV | 2023-02-27 08:00 | 2023-12-22 17:00 |  |  |  |  | 1.9.10(Electrostatic Precipitator) | 206815988
ESP Foundations | CIV | 2023-02-27 08:00 | 2023-12-22 17:00 |  |  |  |  | 1.9.10.2(Civil) | 206815989
ESP Foundations- First 3 Pass Foundation | CIV | 2023-02-27 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.9.10.2.1( ESP Foundations) | 206815990
Excavation & PCC of Footing | CIV | 2023-02-27 08:00 | 2023-05-22 17:00 |  |  |  |  | 1.9.10.2.1.1( ESP Foundations- First 3 Pass Foundation) | 206815991
Excavation & PCC of Footings of 1st Pass | CIV | 2023-02-27 08:00 | 2023-04-02 17:00 |  |  |  |  | 1.9.10.2.1.1.1( Excavation & PCC of Footing) | 206815992
Excavation & PCC of Footings of 2nd Pass | CIV | 2023-03-24 08:00 | 2023-04-27 17:00 |  |  |  |  | 1.9.10.2.1.1.1( Excavation & PCC of Footing) | 206815993
Excavation & PCC of Footings of 3rd Pass | CIV | 2023-04-18 08:00 | 2023-05-22 17:00 |  |  |  |  | 1.9.10.2.1.1.1( Excavation & PCC of Footing) | 206815994
Footing Concreting Works | CIV | 2023-03-09 08:00 | 2023-06-26 17:00 |  |  |  |  | 1.9.10.2.1.1( ESP Foundations- First 3 Pass Foundation) | 206815995
Casting of Footings of 1st Pass | CIV | 2023-03-09 08:00 | 2023-05-07 17:00 |  |  |  |  | 1.9.10.2.1.1.2( Footing Concreting Works) | 206815996
Casting of Footings of 2nd Pass | CIV | 2023-04-03 08:00 | 2023-06-01 17:00 |  |  |  |  | 1.9.10.2.1.1.2( Footing Concreting Works) | 206815997
Casting of Footings of 3rd Pass | CIV | 2023-04-28 08:00 | 2023-06-26 17:00 |  |  |  |  | 1.9.10.2.1.1.2( Footing Concreting Works) | 206815998
Pedestal Concreting Works | CIV | 2023-03-29 08:00 | 2023-09-09 17:00 |  |  |  |  | 1.9.10.2.1.1( ESP Foundations- First 3 Pass Foundation) | 206815999
Casting of Pedestals (1st ,2nd & Bolt Lift)-1st Pass | CIV | 2023-03-29 08:00 | 2023-07-21 17:00 |  |  |  |  | 1.9.10.2.1.1.3( Pedestal Concreting Works) | 206816000
Casting of Pedestals (1st ,2nd & Bolt Lift)-Pass B | CIV | 2023-04-23 08:00 | 2023-08-15 17:00 |  |  |  |  | 1.9.10.2.1.1.3( Pedestal Concreting Works) | 206816001
Casting of Pedestals (1st ,2nd & Bolt Lift)-Pass C | CIV | 2023-05-18 08:00 | 2023-09-09 17:00 |  |  |  |  | 1.9.10.2.1.1.3( Pedestal Concreting Works) | 206816002
Backfilling Works | CIV | 2023-05-25 08:00 | 2023-10-07 17:00 |  |  |  |  | 1.9.10.2.1.1( ESP Foundations- First 3 Pass Foundation) | 206816003
Backfilling & Compaction (First Pass) | CIV | 2023-05-25 08:00 | 2023-08-17 17:00 |  |  |  |  | 1.9.10.2.1.1.4( Backfilling Works) | 206816004
Backfilling & Compaction (Second Pass) | CIV | 2023-06-19 08:00 | 2023-09-11 17:00 |  |  |  |  | 1.9.10.2.1.1.4( Backfilling Works) | 206816005
Backfilling & Compaction(Third Pass) | CIV | 2023-07-15 08:00 | 2023-10-07 17:00 |  |  |  |  | 1.9.10.2.1.1.4( Backfilling Works) | 206816006
Grade Slab Concreting Works (Paving Works) | CIV | 2023-06-09 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.9.10.2.1.1( ESP Foundations- First 3 Pass Foundation) | 206816007
Grade slab casting, Fixing of Earthing Mat Work complete in all respects for first Pass | CIV | 2023-06-09 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.9.10.2.1.1.5( Grade Slab Concreting Works (Paving Works)) | 206816008
Grade slab casting, Fixing of Earthing Mat Work complete in all respects for Second Pass | CIV | 2023-07-04 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.9.10.2.1.1.5( Grade Slab Concreting Works (Paving Works)) | 206816009
Grade slab casting, Fixing of Earthing Mat Work complete in all respects for Third Pass | CIV | 2023-07-30 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.9.10.2.1.1.5( Grade Slab Concreting Works (Paving Works)) | 206816010
ESP Foundations- Balance Three Pass | CIV | 2023-04-30 08:00 | 2023-12-22 17:00 |  |  |  |  | 1.9.10.2.1( ESP Foundations) | 206816011
Excavation & PCC of Footings | CIV | 2023-04-30 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.9.10.2.1.2( ESP Foundations- Balance Three Pass) | 206816012
Excavation & PCC of Footings of 4th Pass | CIV | 2023-04-30 08:00 | 2023-06-03 17:00 |  |  |  |  | 1.9.10.2.1.2.1( Excavation & PCC of Footings) | 206816013
Excavation & PCC of Footings of 5th Pass | CIV | 2023-05-25 08:00 | 2023-06-28 17:00 |  |  |  |  | 1.9.10.2.1.2.1( Excavation & PCC of Footings) | 206816014
Excavation & PCC of Footings of 6th Pass | CIV | 2023-06-19 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.9.10.2.1.2.1( Excavation & PCC of Footings) | 206816015
Footing Concreting Works | CIV | 2023-05-10 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.9.10.2.1.2( ESP Foundations- Balance Three Pass) | 206816016
Casting of Footings of 4th Pass | CIV | 2023-05-10 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.9.10.2.1.2.2( Footing Concreting Works) | 206816017
Casting of Footings of 5th Pass | CIV | 2023-06-04 08:00 | 2023-08-02 17:00 |  |  |  |  | 1.9.10.2.1.2.2( Footing Concreting Works) | 206816018
Casting of Footings of 6th Pass | CIV | 2023-06-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.9.10.2.1.2.2( Footing Concreting Works) | 206816019
Pedestal Concreting Works | CIV | 2023-05-30 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.9.10.2.1.2( ESP Foundations- Balance Three Pass) | 206816020
Casting of Pedestals (1st ,2nd & Bolt Lift)- 4th Pass | CIV | 2023-05-30 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.9.10.2.1.2.3( Pedestal Concreting Works) | 206816021
Casting of Pedestals (1st ,2nd & Bolt Lift)- 5th Pass | CIV | 2023-06-24 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.9.10.2.1.2.3( Pedestal Concreting Works) | 206816022
Casting of Pedestals (1st ,2nd & Bolt Lift)- 6th Pass | CIV | 2023-07-19 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.9.10.2.1.2.3( Pedestal Concreting Works) | 206816023
Backfilling Works | CIV | 2023-07-26 08:00 | 2023-12-07 17:00 |  |  |  |  | 1.9.10.2.1.2( ESP Foundations- Balance Three Pass) | 206816024
Backfilling & Compaction (4th Pass) | CIV | 2023-07-26 08:00 | 2023-10-18 17:00 |  |  |  |  | 1.9.10.2.1.2.4( Backfilling Works) | 206816025
Backfilling & Compaction (5th Pass) | CIV | 2023-08-20 08:00 | 2023-11-12 17:00 |  |  |  |  | 1.9.10.2.1.2.4( Backfilling Works) | 206816026
Backfilling & Compaction(6th Pass) | CIV | 2023-09-14 08:00 | 2023-12-07 17:00 |  |  |  |  | 1.9.10.2.1.2.4( Backfilling Works) | 206816027
Grade Slab Concreting Works (Paving Works) | CIV | 2023-08-10 08:00 | 2023-12-22 17:00 |  |  |  |  | 1.9.10.2.1.2( ESP Foundations- Balance Three Pass) | 206816028
Grade slab casting, Fixing of Earthing Mat Work complete in all respects for 4th Pass | CIV | 2023-08-10 08:00 | 2023-11-02 17:00 |  |  |  |  | 1.9.10.2.1.2.5( Grade Slab Concreting Works (Paving Works)) | 206816029
Grade slab casting, Fixing of Earthing Mat Work complete in all respect for 5th Pass | CIV | 2023-09-04 08:00 | 2023-11-27 17:00 |  |  |  |  | 1.9.10.2.1.2.5( Grade Slab Concreting Works (Paving Works)) | 206816030
Grade slab casting, Fixing of Earthing Mat Work complete in all respect for 6th Pass | CIV | 2023-09-29 08:00 | 2023-12-22 17:00 |  |  |  |  | 1.9.10.2.1.2.5( Grade Slab Concreting Works (Paving Works)) | 206816031
Supply | SUP | 2022-11-16 08:00 | 2025-02-02 17:00 | 2022-11-21 |  |  |  | 1.9.10(Electrostatic Precipitator) | 206816032
BAP - Foundation Materials (PGMA 79580) | CIV | 2022-11-16 08:00 | 2023-02-13 17:00 |  |  |  | 79580 | 1.9.10.3(Supply) | 206816033
Engineering | ENG | 2022-11-16 08:00 | 2022-12-15 17:00 |  |  |  | 79580 | 1.9.10.3.1(BAP - Foundation Materials (PGMA 79580)) | 206816034
Manufacturing | MFG | 2022-12-16 08:00 | 2023-01-04 17:00 |  |  |  | 79580 | 1.9.10.3.1(BAP - Foundation Materials (PGMA 79580)) | 206816035
Dispatch | DIS | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79580 | 1.9.10.3.1(BAP - Foundation Materials (PGMA 79580)) | 206816036
BAP - Supporting structure for ESP (PGMA 79581) | OTH | 2022-11-16 08:00 | 2023-02-13 17:00 |  |  |  | 79581 | 1.9.10.3(Supply) | 206816037
Engineering | ENG | 2022-11-16 08:00 | 2022-12-15 17:00 |  |  |  | 79581 | 1.9.10.3.2(BAP - Supporting structure for ESP (PGMA 79581)) | 206816038
Manufacturing | MFG | 2022-12-16 08:00 | 2023-01-04 17:00 |  |  |  | 79581 | 1.9.10.3.2(BAP - Supporting structure for ESP (PGMA 79581)) | 206816039
Dispatch | DIS | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79581 | 1.9.10.3.2(BAP - Supporting structure for ESP (PGMA 79581)) | 206816040
BAP - ROLL/SLIDE SUPPORTS (PGMA 79501) | SUP | 2022-11-16 08:00 | 2023-02-13 17:00 | 2022-12-02 |  |  | 79501 | 1.9.10.3(Supply) | 206816041
Engineering | ENG | 2022-11-16 08:00 | 2022-12-15 17:00 | 2022-12-02 |  |  | 79501 | 1.9.10.3.3(BAP - ROLL/SLIDE SUPPORTS (PGMA 79501)) | 206816042
Manufacturing | MFG | 2022-12-16 08:00 | 2023-01-04 17:00 |  |  |  | 79501 | 1.9.10.3.3(BAP - ROLL/SLIDE SUPPORTS (PGMA 79501)) | 206816043
Dispatch | DIS | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79501 | 1.9.10.3.3(BAP - ROLL/SLIDE SUPPORTS (PGMA 79501)) | 206816044
BAP - CASING STRUCTURE (PGMA 79548) | SUP | 2022-12-06 08:00 | 2023-03-05 17:00 |  |  |  | 79548 | 1.9.10.3(Supply) | 206816045
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 79548 | 1.9.10.3.4(BAP - CASING STRUCTURE (PGMA 79548)) | 206816046
Manufacturing | MFG | 2023-01-05 08:00 | 2023-01-24 17:00 |  |  |  | 79548 | 1.9.10.3.4(BAP - CASING STRUCTURE (PGMA 79548)) | 206816047
Dispatch | DIS | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79548 | 1.9.10.3.4(BAP - CASING STRUCTURE (PGMA 79548)) | 206816048
BAP - ELECTRICAL MISC ITEMS (PGMA 79541) | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  | 79541 | 1.9.10.3(Supply) | 206816049
Engineering | ENG | 2023-12-21 08:00 | 2024-02-18 17:00 |  |  |  | 79541 | 1.9.10.3.5(BAP - ELECTRICAL MISC ITEMS (PGMA 79541)) | 206816050
Manufacturing | MFG | 2024-02-19 08:00 | 2024-10-25 17:00 |  |  |  | 79541 | 1.9.10.3.5(BAP - ELECTRICAL MISC ITEMS (PGMA 79541)) | 206816051
Dispatch | DIS | 2024-05-29 08:00 | 2025-02-02 17:00 |  |  |  | 79541 | 1.9.10.3.5(BAP - ELECTRICAL MISC ITEMS (PGMA 79541)) | 206816052
BAP - HOPPER RIDGES (PGMA 79543) | SUP | 2022-12-06 08:00 | 2023-03-05 17:00 | 2022-12-31 |  |  | 79543 | 1.9.10.3(Supply) | 206816053
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 | 2022-12-31 |  |  | 79543 | 1.9.10.3.6(BAP - HOPPER RIDGES (PGMA 79543)) | 206816054
Manufacturing | MFG | 2023-01-05 08:00 | 2023-01-24 17:00 |  |  |  | 79543 | 1.9.10.3.6(BAP - HOPPER RIDGES (PGMA 79543)) | 206816055
Dispatch | DIS | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79543 | 1.9.10.3.6(BAP - HOPPER RIDGES (PGMA 79543)) | 206816056
BAP - CASING SHELL/PANEL (PGMA 79549) | SUP | 2022-12-06 08:00 | 2023-02-13 17:00 | 2022-12-24 |  |  | 79549 | 1.9.10.3(Supply) | 206816057
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 | 2022-12-24 |  |  | 79549 | 1.9.10.3.7(BAP - CASING SHELL/PANEL (PGMA 79549)) | 206816058
Manufacturing | MFG | 2023-01-05 08:00 | 2023-01-24 17:00 |  |  |  | 79549 | 1.9.10.3.7(BAP - CASING SHELL/PANEL (PGMA 79549)) | 206816059
Dispatch | DIS | 2023-01-25 08:00 | 2023-02-13 17:00 |  |  |  | 79549 | 1.9.10.3.7(BAP - CASING SHELL/PANEL (PGMA 79549)) | 206816060
BAP - EP GALLERIES&STAIRS (PGMA 89610) | SUP | 2022-12-06 08:00 | 2023-03-15 17:00 |  |  |  | 89610 | 1.9.10.3(Supply) | 206816061
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 89610 | 1.9.10.3.8(BAP - EP GALLERIES&STAIRS (PGMA 89610)) | 206816062
Manufacturing | MFG | 2023-01-05 08:00 | 2023-01-24 17:00 |  |  |  | 89610 | 1.9.10.3.8(BAP - EP GALLERIES&STAIRS (PGMA 89610)) | 206816063
Dispatch | SUP | 2023-01-25 08:00 | 2023-03-15 17:00 |  |  |  | 89610 | 1.9.10.3.8(BAP - EP GALLERIES&STAIRS (PGMA 89610)) | 206816064
BAP - FLOOR GRILL AND STEP T (PGMA 89612) | SUP | 2022-12-06 08:00 | 2023-08-22 17:00 |  |  |  | 89612 | 1.9.10.3(Supply) | 206816065
Engineering | ENG | 2022-12-06 08:00 | 2023-04-04 17:00 |  |  |  | 89612 | 1.9.10.3.9(BAP - FLOOR GRILL AND STEP T (PGMA 89612)) | 206816066
Manufacturing | MFG | 2023-04-05 08:00 | 2023-07-03 17:00 |  |  |  | 89612 | 1.9.10.3.9(BAP - FLOOR GRILL AND STEP T (PGMA 89612)) | 206816067
Dispatch | DIS | 2023-07-04 08:00 | 2023-08-22 17:00 |  |  |  | 89612 | 1.9.10.3.9(BAP - FLOOR GRILL AND STEP T (PGMA 89612)) | 206816068
BAP - ESP ROOF BEAM (PGMA 79528) | SUP | 2022-12-06 08:00 | 2023-03-15 17:00 | 2022-12-29 |  |  | 79528 | 1.9.10.3(Supply) | 206816069
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 | 2022-12-29 |  |  | 79528 | 1.9.10.3.10(BAP - ESP ROOF BEAM (PGMA 79528)) | 206816070
Manufacturing | MFG | 2023-01-05 08:00 | 2023-01-24 17:00 |  |  |  | 79528 | 1.9.10.3.10(BAP - ESP ROOF BEAM (PGMA 79528)) | 206816071
Dispatch | DIS | 2023-01-25 08:00 | 2023-03-15 17:00 |  |  |  | 79528 | 1.9.10.3.10(BAP - ESP ROOF BEAM (PGMA 79528)) | 206816072
BAP - COL ELEC SUSPENSION(PGMA 79519) | SUP | 2022-12-06 08:00 | 2023-03-25 17:00 |  |  |  | 79519 | 1.9.10.3(Supply) | 206816073
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 79519 | 1.9.10.3.11(BAP - COL ELEC SUSPENSION(PGMA 79519)) | 206816074
Manufacturing | MFG | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79519 | 1.9.10.3.11(BAP - COL ELEC SUSPENSION(PGMA 79519)) | 206816075
Dispatch | DIS | 2023-02-14 08:00 | 2023-03-25 17:00 |  |  |  | 79519 | 1.9.10.3.11(BAP - COL ELEC SUSPENSION(PGMA 79519)) | 206816076
BAP - EMIT SYST SUSPENSION(PGMA 79513) | SUP | 2022-12-06 08:00 | 2023-04-14 17:00 |  |  |  | 79513 | 1.9.10.3(Supply) | 206816077
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 79513 | 1.9.10.3.12(BAP - EMIT SYST SUSPENSION(PGMA 79513)) | 206816078
Manufacturing | MFG | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79513 | 1.9.10.3.12(BAP - EMIT SYST SUSPENSION(PGMA 79513)) | 206816079
Dispatch | DIS | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 79513 | 1.9.10.3.12(BAP - EMIT SYST SUSPENSION(PGMA 79513)) | 206816080
BAP - INSULATOR SUPP PANEL(PGMA 79546) | SUP | 2022-12-06 08:00 | 2023-04-14 17:00 |  |  |  | 79546 | 1.9.10.3(Supply) | 206816081
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 79546 | 1.9.10.3.13(BAP - INSULATOR SUPP PANEL(PGMA 79546)) | 206816082
Manufacturing | MFG | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79546 | 1.9.10.3.13(BAP - INSULATOR SUPP PANEL(PGMA 79546)) | 206816083
Dispatch | DIS | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 79546 | 1.9.10.3.13(BAP - INSULATOR SUPP PANEL(PGMA 79546)) | 206816084
BAP - EMIT SYS FRAME-TOP(PGMA 79521) | SUP | 2022-12-06 08:00 | 2023-04-14 17:00 |  |  |  | 79521 | 1.9.10.3(Supply) | 206816085
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 79521 | 1.9.10.3.14(BAP - EMIT SYS FRAME-TOP(PGMA 79521)) | 206816086
Manufacturing | MFG | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79521 | 1.9.10.3.14(BAP - EMIT SYS FRAME-TOP(PGMA 79521)) | 206816087
Dispatch | DIS | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 79521 | 1.9.10.3.14(BAP - EMIT SYS FRAME-TOP(PGMA 79521)) | 206816088
BAP - EMIT SYS FRAME-MIDLE(PGMA 79532) | SUP | 2022-12-06 08:00 | 2023-04-14 17:00 |  |  |  | 79532 | 1.9.10.3(Supply) | 206816089
Engineering | ENG | 2022-12-06 08:00 | 2023-01-04 17:00 |  |  |  | 79532 | 1.9.10.3.15(BAP - EMIT SYS FRAME-MIDLE(PGMA 79532)) | 206816090
Manufacturing | MFG | 2023-01-05 08:00 | 2023-02-13 17:00 |  |  |  | 79532 | 1.9.10.3.15(BAP - EMIT SYS FRAME-MIDLE(PGMA 79532)) | 206816091
Dispatch | DIS | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 79532 | 1.9.10.3.15(BAP - EMIT SYS FRAME-MIDLE(PGMA 79532)) | 206816092
BAP - EMIT SYS FRAME BOTOM(PGMA 79522) | SUP | 2022-12-26 08:00 | 2023-05-04 17:00 |  |  |  | 79522 | 1.9.10.3(Supply) | 206816093
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79522 | 1.9.10.3.16(BAP - EMIT SYS FRAME BOTOM(PGMA 79522)) | 206816094
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79522 | 1.9.10.3.16(BAP - EMIT SYS FRAME BOTOM(PGMA 79522)) | 206816095
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-04 17:00 |  |  |  | 79522 | 1.9.10.3.16(BAP - EMIT SYS FRAME BOTOM(PGMA 79522)) | 206816096
BAP - SUPPORT INSULATORS(PGMA 79514) | SUP | 2022-12-26 08:00 | 2023-05-04 17:00 |  |  |  | 79514 | 1.9.10.3(Supply) | 206816097
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79514 | 1.9.10.3.17(BAP - SUPPORT INSULATORS(PGMA 79514)) | 206816098
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79514 | 1.9.10.3.17(BAP - SUPPORT INSULATORS(PGMA 79514)) | 206816099
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-04 17:00 |  |  |  | 79514 | 1.9.10.3.17(BAP - SUPPORT INSULATORS(PGMA 79514)) | 206816100
BAP - COLLECTING ELECTRODE(PGMA 79520) | SUP | 2022-12-26 08:00 | 2023-05-04 17:00 | 2022-11-21 |  |  | 79520 | 1.9.10.3(Supply) | 206816101
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 | 2022-11-21 |  |  | 79520 | 1.9.10.3.18(BAP - COLLECTING ELECTRODE(PGMA 79520)) | 206816102
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79520 | 1.9.10.3.18(BAP - COLLECTING ELECTRODE(PGMA 79520)) | 206816103
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-04 17:00 |  |  |  | 79520 | 1.9.10.3.18(BAP - COLLECTING ELECTRODE(PGMA 79520)) | 206816104
BAP - GAS DIST. ASSY(PGMA 79508) | SUP | 2022-12-26 08:00 | 2023-05-14 17:00 | 2022-12-22 |  |  | 79508 | 1.9.10.3(Supply) | 206816105
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 | 2022-12-22 |  |  | 79508 | 1.9.10.3.19(BAP - GAS DIST. ASSY(PGMA 79508)) | 206816106
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79508 | 1.9.10.3.19(BAP - GAS DIST. ASSY(PGMA 79508)) | 206816107
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-14 17:00 |  |  |  | 79508 | 1.9.10.3.19(BAP - GAS DIST. ASSY(PGMA 79508)) | 206816108
BAP - ROOF PANEL ASSY(PGMA 79547) | SUP | 2022-12-26 08:00 | 2023-05-14 17:00 |  |  |  | 79547 | 1.9.10.3(Supply) | 206816109
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79547 | 1.9.10.3.20(BAP - ROOF PANEL ASSY(PGMA 79547)) | 206816110
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-05 17:00 |  |  |  | 79547 | 1.9.10.3.20(BAP - ROOF PANEL ASSY(PGMA 79547)) | 206816111
Dispatch | DIS | 2023-03-06 08:00 | 2023-05-14 17:00 |  |  |  | 79547 | 1.9.10.3.20(BAP - ROOF PANEL ASSY(PGMA 79547)) | 206816112
BAP - INLET-OUTLET FUNNEL(PGMA 79550) | SUP | 2022-12-26 08:00 | 2023-06-13 17:00 |  |  |  | 79550 | 1.9.10.3(Supply) | 206816113
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79550 | 1.9.10.3.21(BAP - INLET-OUTLET FUNNEL(PGMA 79550)) | 206816114
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  | 79550 | 1.9.10.3.21(BAP - INLET-OUTLET FUNNEL(PGMA 79550)) | 206816115
Dispatch | DIS | 2023-03-26 08:00 | 2023-06-13 17:00 |  |  |  | 79550 | 1.9.10.3.21(BAP - INLET-OUTLET FUNNEL(PGMA 79550)) | 206816116
BAP - SPLITTER&GUIDE VANES(PGMA 79557) | SUP | 2022-12-26 08:00 | 2023-06-13 17:00 |  |  |  | 79557 | 1.9.10.3(Supply) | 206816117
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79557 | 1.9.10.3.22(BAP - SPLITTER&GUIDE VANES(PGMA 79557)) | 206816118
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  | 79557 | 1.9.10.3.22(BAP - SPLITTER&GUIDE VANES(PGMA 79557)) | 206816119
Dispatch | DIS | 2023-03-26 08:00 | 2023-06-13 17:00 |  |  |  | 79557 | 1.9.10.3.22(BAP - SPLITTER&GUIDE VANES(PGMA 79557)) | 206816120
BAP - SHOCK BARS(PGMA 79524) | SUP | 2022-12-26 08:00 | 2023-06-13 17:00 | 2022-12-09 |  |  | 79524 | 1.9.10.3(Supply) | 206816121
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 | 2022-12-09 |  |  | 79524 | 1.9.10.3.23(BAP - SHOCK BARS(PGMA 79524)) | 206816122
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  | 79524 | 1.9.10.3.23(BAP - SHOCK BARS(PGMA 79524)) | 206816123
Dispatch | DIS | 2023-03-26 08:00 | 2023-06-13 17:00 |  |  |  | 79524 | 1.9.10.3.23(BAP - SHOCK BARS(PGMA 79524)) | 206816124
BAP - COLL ELECT RAPP MECH(PGMA 79525) | SUP | 2022-12-26 08:00 | 2023-06-13 17:00 |  |  |  | 79525 | 1.9.10.3(Supply) | 206816125
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79525 | 1.9.10.3.24(BAP - COLL ELECT RAPP MECH(PGMA 79525)) | 206816126
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  | 79525 | 1.9.10.3.24(BAP - COLL ELECT RAPP MECH(PGMA 79525)) | 206816127
Dispatch | DIS | 2023-03-26 08:00 | 2023-06-13 17:00 |  |  |  | 79525 | 1.9.10.3.24(BAP - COLL ELECT RAPP MECH(PGMA 79525)) | 206816128
BAP - GAS SCREEN-EP(PGMA 79511) | SUP | 2022-12-26 08:00 | 2023-06-23 17:00 |  |  |  | 79511 | 1.9.10.3(Supply) | 206816129
Engineering | ENG | 2022-12-26 08:00 | 2023-01-24 17:00 |  |  |  | 79511 | 1.9.10.3.25(BAP - GAS SCREEN-EP(PGMA 79511)) | 206816130
Manufacturing | MFG | 2023-01-25 08:00 | 2023-03-25 17:00 |  |  |  | 79511 | 1.9.10.3.25(BAP - GAS SCREEN-EP(PGMA 79511)) | 206816131
Dispatch | DIS | 2023-03-26 08:00 | 2023-06-23 17:00 |  |  |  | 79511 | 1.9.10.3.25(BAP - GAS SCREEN-EP(PGMA 79511)) | 206816132
BAP - EMITTING ELECTRODES(PGMA 79515) | SUP | 2023-01-15 08:00 | 2023-07-13 17:00 | 2022-11-21 |  |  | 79515 | 1.9.10.3(Supply) | 206816133
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 | 2022-11-21 |  |  | 79515 | 1.9.10.3.26(BAP - EMITTING ELECTRODES(PGMA 79515)) | 206816134
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 79515 | 1.9.10.3.26(BAP - EMITTING ELECTRODES(PGMA 79515)) | 206816135
Dispatch | DIS | 2023-04-15 08:00 | 2023-07-13 17:00 |  |  |  | 79515 | 1.9.10.3.26(BAP - EMITTING ELECTRODES(PGMA 79515)) | 206816136
BAP - OUTER ROOF-EP(PGMA 79542) | SUP | 2023-01-15 08:00 | 2023-07-13 17:00 |  |  |  | 79542 | 1.9.10.3(Supply) | 206816137
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 79542 | 1.9.10.3.27(BAP - OUTER ROOF-EP(PGMA 79542)) | 206816138
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-14 17:00 |  |  |  | 79542 | 1.9.10.3.27(BAP - OUTER ROOF-EP(PGMA 79542)) | 206816139
Dispatch | DIS | 2023-04-15 08:00 | 2023-07-13 17:00 |  |  |  | 79542 | 1.9.10.3.27(BAP - OUTER ROOF-EP(PGMA 79542)) | 206816140
BAP - HOPPER UPPER PART(PGMA 79544) | SUP | 2023-01-15 08:00 | 2023-08-12 17:00 |  |  |  | 79544 | 1.9.10.3(Supply) | 206816141
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 79544 | 1.9.10.3.28(BAP - HOPPER UPPER PART(PGMA 79544)) | 206816142
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-24 17:00 |  |  |  | 79544 | 1.9.10.3.28(BAP - HOPPER UPPER PART(PGMA 79544)) | 206816143
Dispatch | DIS | 2023-04-25 08:00 | 2023-08-12 17:00 |  |  |  | 79544 | 1.9.10.3.28(BAP - HOPPER UPPER PART(PGMA 79544)) | 206816144
BAP - HOP MLD&LOWER PART(PGMA 79545) | SUP | 2023-01-15 08:00 | 2023-08-12 17:00 |  |  |  | 79545 | 1.9.10.3(Supply) | 206816145
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 79545 | 1.9.10.3.29(BAP - HOP MLD&LOWER PART(PGMA 79545)) | 206816146
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-24 17:00 |  |  |  | 79545 | 1.9.10.3.29(BAP - HOP MLD&LOWER PART(PGMA 79545)) | 206816147
Dispatch | DIS | 2023-04-25 08:00 | 2023-08-12 17:00 |  |  |  | 79545 | 1.9.10.3.29(BAP - HOP MLD&LOWER PART(PGMA 79545)) | 206816148
BAP - APP PLATFORM-HOPPER(PGMA 79565) | SUP | 2023-01-15 08:00 | 2023-08-12 17:00 |  |  |  | 79565 | 1.9.10.3(Supply) | 206816149
Engineering | ENG | 2023-01-15 08:00 | 2023-02-13 17:00 |  |  |  | 79565 | 1.9.10.3.30(BAP - APP PLATFORM-HOPPER(PGMA 79565)) | 206816150
Manufacturing | MFG | 2023-02-14 08:00 | 2023-04-24 17:00 |  |  |  | 79565 | 1.9.10.3.30(BAP - APP PLATFORM-HOPPER(PGMA 79565)) | 206816151
Dispatch | DIS | 2023-04-25 08:00 | 2023-08-12 17:00 |  |  |  | 79565 | 1.9.10.3.30(BAP - APP PLATFORM-HOPPER(PGMA 79565)) | 206816152
BAP - EMIT ELECT RAPP MECH(PGMA 79516) | SUP | 2023-02-04 08:00 | 2023-09-11 17:00 |  |  |  | 79516 | 1.9.10.3(Supply) | 206816153
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 79516 | 1.9.10.3.31(BAP - EMIT ELECT RAPP MECH(PGMA 79516)) | 206816154
Manufacturing | MFG | 2023-03-06 08:00 | 2023-05-24 17:00 |  |  |  | 79516 | 1.9.10.3.31(BAP - EMIT ELECT RAPP MECH(PGMA 79516)) | 206816155
Dispatch | DIS | 2023-05-25 08:00 | 2023-09-11 17:00 |  |  |  | 79516 | 1.9.10.3.31(BAP - EMIT ELECT RAPP MECH(PGMA 79516)) | 206816156
BAP - DRIVE ARGT. FOR EMIT.(PGMA 79517) | SUP | 2023-02-04 08:00 | 2023-09-11 17:00 |  |  |  | 79517 | 1.9.10.3(Supply) | 206816157
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 79517 | 1.9.10.3.32(BAP - DRIVE ARGT. FOR EMIT.(PGMA 79517)) | 206816158
Manufacturing | MFG | 2023-03-06 08:00 | 2023-05-24 17:00 |  |  |  | 79517 | 1.9.10.3.32(BAP - DRIVE ARGT. FOR EMIT.(PGMA 79517)) | 206816159
Dispatch | DIS | 2023-05-25 08:00 | 2023-09-11 17:00 |  |  |  | 79517 | 1.9.10.3.32(BAP - DRIVE ARGT. FOR EMIT.(PGMA 79517)) | 206816160
BAP - INSULATOR HOUSING AS(PGMA 79506) | SUP | 2023-02-04 08:00 | 2023-10-11 17:00 |  |  |  | 79506 | 1.9.10.3(Supply) | 206816161
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 79506 | 1.9.10.3.33(BAP - INSULATOR HOUSING AS(PGMA 79506)) | 206816162
Manufacturing | MFG | 2023-03-06 08:00 | 2023-06-13 17:00 |  |  |  | 79506 | 1.9.10.3.33(BAP - INSULATOR HOUSING AS(PGMA 79506)) | 206816163
Dispatch | DIS | 2023-06-14 08:00 | 2023-10-11 17:00 |  |  |  | 79506 | 1.9.10.3.33(BAP - INSULATOR HOUSING AS(PGMA 79506)) | 206816164
BAP - PENT HOUSE FOR E P(PGMA 79555) | SUP | 2023-02-04 08:00 | 2023-10-11 17:00 |  |  |  | 79555 | 1.9.10.3(Supply) | 206816165
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 79555 | 1.9.10.3.34(BAP - PENT HOUSE FOR E P(PGMA 79555)) | 206816166
Manufacturing | MFG | 2023-03-06 08:00 | 2023-06-13 17:00 |  |  |  | 79555 | 1.9.10.3.34(BAP - PENT HOUSE FOR E P(PGMA 79555)) | 206816167
Dispatch | DIS | 2023-06-14 08:00 | 2023-10-11 17:00 |  |  |  | 79555 | 1.9.10.3.34(BAP - PENT HOUSE FOR E P(PGMA 79555)) | 206816168
BAP - PENT HOUSE ROOFING SHE(PGMA 89614) | SUP | 2023-02-04 08:00 | 2023-10-11 17:00 |  |  |  | 89614 | 1.9.10.3(Supply) | 206816169
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 89614 | 1.9.10.3.35(BAP - PENT HOUSE ROOFING SHE(PGMA 89614)) | 206816170
Manufacturing | MFG | 2023-03-06 08:00 | 2023-06-13 17:00 |  |  |  | 89614 | 1.9.10.3.35(BAP - PENT HOUSE ROOFING SHE(PGMA 89614)) | 206816171
Dispatch | DIS | 2023-06-14 08:00 | 2023-10-11 17:00 |  |  |  | 89614 | 1.9.10.3.35(BAP - PENT HOUSE ROOFING SHE(PGMA 89614)) | 206816172
BAP - ESP ROOF HANDRAILS(PGMA 79526) | SUP | 2023-02-04 08:00 | 2023-10-11 17:00 |  |  |  | 79526 | 1.9.10.3(Supply) | 206816173
Engineering | ENG | 2023-02-04 08:00 | 2023-03-05 17:00 |  |  |  | 79526 | 1.9.10.3.36(BAP - ESP ROOF HANDRAILS(PGMA 79526)) | 206816174
Manufacturing | MFG | 2023-03-06 08:00 | 2023-06-13 17:00 |  |  |  | 79526 | 1.9.10.3.36(BAP - ESP ROOF HANDRAILS(PGMA 79526)) | 206816175
Dispatch | DIS | 2023-06-14 08:00 | 2023-10-11 17:00 |  |  |  | 79526 | 1.9.10.3.36(BAP - ESP ROOF HANDRAILS(PGMA 79526)) | 206816176
BAP - COLL ELEC RAPP DRIVE(PGMA 79526) | SUP | 2023-05-05 08:00 | 2024-01-09 17:00 |  |  |  | 79526 | 1.9.10.3(Supply) | 206816177
Engineering | ENG | 2023-05-05 08:00 | 2023-06-03 17:00 |  |  |  | 79526 | 1.9.10.3.37(BAP - COLL ELEC RAPP DRIVE(PGMA 79526)) | 206816178
Manufacturing | MFG | 2023-06-04 08:00 | 2023-09-11 17:00 |  |  |  | 79526 | 1.9.10.3.37(BAP - COLL ELEC RAPP DRIVE(PGMA 79526)) | 206816179
Dispatch | DIS | 2023-09-12 08:00 | 2024-01-09 17:00 |  |  |  | 79526 | 1.9.10.3.37(BAP - COLL ELEC RAPP DRIVE(PGMA 79526)) | 206816180
BAP - GD-RAPPING MECHANISM(PGMA 79509) | SUP | 2023-05-05 08:00 | 2024-01-09 17:00 |  |  |  | 79509 | 1.9.10.3(Supply) | 206816181
Engineering | ENG | 2023-05-05 08:00 | 2023-06-03 17:00 |  |  |  | 79509 | 1.9.10.3.38(BAP - GD-RAPPING MECHANISM(PGMA 79509)) | 206816182
Manufacturing | MFG | 2023-06-04 08:00 | 2023-09-11 17:00 |  |  |  | 79509 | 1.9.10.3.38(BAP - GD-RAPPING MECHANISM(PGMA 79509)) | 206816183
Dispatch | DIS | 2023-09-12 08:00 | 2024-01-09 17:00 |  |  |  | 79509 | 1.9.10.3.38(BAP - GD-RAPPING MECHANISM(PGMA 79509)) | 206816184
BAP - GD_DRIVE ARRANGEMENT(PGMA 79510) | SUP | 2023-05-05 08:00 | 2024-01-09 17:00 |  |  |  | 79510 | 1.9.10.3(Supply) | 206816185
Engineering | ENG | 2023-05-05 08:00 | 2023-06-03 17:00 |  |  |  | 79510 | 1.9.10.3.39(BAP - GD_DRIVE ARRANGEMENT(PGMA 79510)) | 206816186
Manufacturing | MFG | 2023-06-04 08:00 | 2023-09-11 17:00 |  |  |  | 79510 | 1.9.10.3.39(BAP - GD_DRIVE ARRANGEMENT(PGMA 79510)) | 206816187
Dispatch | DIS | 2023-09-12 08:00 | 2024-01-09 17:00 |  |  |  | 79510 | 1.9.10.3.39(BAP - GD_DRIVE ARRANGEMENT(PGMA 79510)) | 206816188
BAP - INSPECTION DOORS(PGMA 79523) | SUP | 2023-05-05 08:00 | 2024-01-09 17:00 | 2022-12-02 |  |  | 79523 | 1.9.10.3(Supply) | 206816189
Engineering | ENG | 2023-05-05 08:00 | 2023-06-03 17:00 | 2022-12-02 |  |  | 79523 | 1.9.10.3.40(BAP - INSPECTION DOORS(PGMA 79523)) | 206816190
Manufacturing | MFG | 2023-06-04 08:00 | 2023-09-11 17:00 |  |  |  | 79523 | 1.9.10.3.40(BAP - INSPECTION DOORS(PGMA 79523)) | 206816191
Dispatch | DIS | 2023-09-12 08:00 | 2024-01-09 17:00 |  |  |  | 79523 | 1.9.10.3.40(BAP - INSPECTION DOORS(PGMA 79523)) | 206816192
BAP - CONTROL ROOM-INSERTS(PGMA 79559) | SUP | 2023-05-05 08:00 | 2024-01-09 17:00 |  |  |  | 79559 | 1.9.10.3(Supply) | 206816193
Engineering | ENG | 2023-05-05 08:00 | 2023-06-03 17:00 |  |  |  | 79559 | 1.9.10.3.41(BAP - CONTROL ROOM-INSERTS(PGMA 79559)) | 206816194
Manufacturing | MFG | 2023-06-04 08:00 | 2023-09-11 17:00 |  |  |  | 79559 | 1.9.10.3.41(BAP - CONTROL ROOM-INSERTS(PGMA 79559)) | 206816195
Dispatch | DIS | 2023-09-12 08:00 | 2024-01-09 17:00 |  |  |  | 79559 | 1.9.10.3.41(BAP - CONTROL ROOM-INSERTS(PGMA 79559)) | 206816196
BAP - GEARED MOTORS FOR RAPP(PGMA 79531) | SUP | 2023-02-24 08:00 | 2023-12-10 17:00 |  |  |  | 79531 | 1.9.10.3(Supply) | 206816197
Engineering | ENG | 2023-02-24 08:00 | 2023-07-23 17:00 |  |  |  | 79531 | 1.9.10.3.42(BAP - GEARED MOTORS FOR RAPP(PGMA 79531)) | 206816198
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  | 79531 | 1.9.10.3.42(BAP - GEARED MOTORS FOR RAPP(PGMA 79531)) | 206816199
Dispatch | DIS | 2023-10-22 08:00 | 2023-12-10 17:00 |  |  |  | 79531 | 1.9.10.3.42(BAP - GEARED MOTORS FOR RAPP(PGMA 79531)) | 206816200
BAP - ESP-SUB-DELIVERY COMPO(PGMA 79505) | SUP | 2023-06-24 08:00 | 2024-03-09 17:00 |  |  |  | 79505 | 1.9.10.3(Supply) | 206816201
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  | 79505 | 1.9.10.3.43(BAP - ESP-SUB-DELIVERY COMPO(PGMA 79505)) | 206816202
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-31 17:00 |  |  |  | 79505 | 1.9.10.3.43(BAP - ESP-SUB-DELIVERY COMPO(PGMA 79505)) | 206816203
Dispatch | DIS | 2023-11-01 08:00 | 2024-03-09 17:00 |  |  |  | 79505 | 1.9.10.3.43(BAP - ESP-SUB-DELIVERY COMPO(PGMA 79505)) | 206816204
BAP - HEATING ELEMENTS(PGMA 79590) | SUP | 2023-10-02 08:00 | 2024-06-07 17:00 |  |  |  | 79590 | 1.9.10.3(Supply) | 206816205
Engineering | ENG | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | 79590 | 1.9.10.3.44(BAP - HEATING ELEMENTS(PGMA 79590)) | 206816206
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-08 17:00 |  |  |  | 79590 | 1.9.10.3.44(BAP - HEATING ELEMENTS(PGMA 79590)) | 206816207
Dispatch | DIS | 2024-02-09 08:00 | 2024-06-07 17:00 |  |  |  | 79590 | 1.9.10.3.44(BAP - HEATING ELEMENTS(PGMA 79590)) | 206816208
BAP - ELECTRICAL SD COMPTS(PGMA 79530) | SUP | 2023-10-02 08:00 | 2024-06-07 17:00 |  |  |  | 79530 | 1.9.10.3(Supply) | 206816209
Engineering | ENG | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | 79530 | 1.9.10.3.45(BAP - ELECTRICAL SD COMPTS(PGMA 79530)) | 206816210
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-08 17:00 |  |  |  | 79530 | 1.9.10.3.45(BAP - ELECTRICAL SD COMPTS(PGMA 79530)) | 206816211
Dispatch | DIS | 2024-02-09 08:00 | 2024-06-07 17:00 |  |  |  | 79530 | 1.9.10.3.45(BAP - ELECTRICAL SD COMPTS(PGMA 79530)) | 206816212
BAP - JUNCTION BOX & PUSH BU(PGMA 79537) | SUP | 2023-10-02 08:00 | 2024-06-07 17:00 |  |  |  | 79537 | 1.9.10.3(Supply) | 206816213
Engineering | ENG | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | 79537 | 1.9.10.3.46(BAP - JUNCTION BOX & PUSH BU(PGMA 79537)) | 206816214
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-08 17:00 |  |  |  | 79537 | 1.9.10.3.46(BAP - JUNCTION BOX & PUSH BU(PGMA 79537)) | 206816215
Dispatch | DIS | 2024-02-09 08:00 | 2024-06-07 17:00 |  |  |  | 79537 | 1.9.10.3.46(BAP - JUNCTION BOX & PUSH BU(PGMA 79537)) | 206816216
BAP - FIXING COMP. FOR ESP I(PGMA 79568) | SUP | 2023-08-13 08:00 | 2024-02-08 17:00 |  |  |  | 79568 | 1.9.10.3(Supply) | 206816217
Engineering | ENG | 2023-08-13 08:00 | 2023-09-11 17:00 |  |  |  | 79568 | 1.9.10.3.47(BAP - FIXING COMP. FOR ESP I(PGMA 79568)) | 206816218
Manufacturing | MFG | 2023-09-12 08:00 | 2023-12-20 17:00 |  |  |  | 79568 | 1.9.10.3.47(BAP - FIXING COMP. FOR ESP I(PGMA 79568)) | 206816219
Dispatch | DIS | 2023-12-21 08:00 | 2024-02-08 17:00 |  |  |  | 79568 | 1.9.10.3.47(BAP - FIXING COMP. FOR ESP I(PGMA 79568)) | 206816220
BAP - WATER WASHING SYSTEM(PGMA 79566) | SUP | 2023-10-02 08:00 | 2024-07-07 17:00 |  |  |  | 79566 | 1.9.10.3(Supply) | 206816221
Engineering | ENG | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | 79566 | 1.9.10.3.48(BAP - WATER WASHING SYSTEM(PGMA 79566)) | 206816222
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-08 17:00 |  |  |  | 79566 | 1.9.10.3.48(BAP - WATER WASHING SYSTEM(PGMA 79566)) | 206816223
Dispatch | DIS | 2024-02-09 08:00 | 2024-07-07 17:00 |  |  |  | 79566 | 1.9.10.3.48(BAP - WATER WASHING SYSTEM(PGMA 79566)) | 206816224
BAP -SUPPORT INSULATORS(PGMA 79514) | SUP | 2023-10-02 08:00 | 2024-07-07 17:00 |  |  |  | 79514 | 1.9.10.3(Supply) | 206816225
Engineering | ENG | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | 79514 | 1.9.10.3.49(BAP -SUPPORT INSULATORS(PGMA 79514)) | 206816226
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-08 17:00 |  |  |  | 79514 | 1.9.10.3.49(BAP -SUPPORT INSULATORS(PGMA 79514)) | 206816227
Dispatch | DIS | 2024-02-09 08:00 | 2024-07-07 17:00 |  |  |  | 79514 | 1.9.10.3.49(BAP -SUPPORT INSULATORS(PGMA 79514)) | 206816228
BAP - BAPCON & ACCESSORIES(PGMA 79578) | SUP | 2024-01-10 08:00 | 2024-09-05 17:00 |  |  |  | 79578 | 1.9.10.3(Supply) | 206816229
Engineering | ENG | 2024-01-10 08:00 | 2024-02-08 17:00 |  |  |  | 79578 | 1.9.10.3.50(BAP - BAPCON & ACCESSORIES(PGMA 79578)) | 206816230
Manufacturing | MFG | 2024-02-09 08:00 | 2024-05-18 17:00 |  |  |  | 79578 | 1.9.10.3.50(BAP - BAPCON & ACCESSORIES(PGMA 79578)) | 206816231
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-05 17:00 |  |  |  | 79578 | 1.9.10.3.50(BAP - BAPCON & ACCESSORIES(PGMA 79578)) | 206816232
BAP - IOS PANEL(PGMA 79595) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 79595 | 1.9.10.3(Supply) | 206816233
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 79595 | 1.9.10.3.51(BAP - IOS PANEL(PGMA 79595)) | 206816234
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 79595 | 1.9.10.3.51(BAP - IOS PANEL(PGMA 79595)) | 206816235
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 79595 | 1.9.10.3.51(BAP - IOS PANEL(PGMA 79595)) | 206816236
BAP - INTERLOCKS(PGMA 79572) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 79572 | 1.9.10.3(Supply) | 206816237
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 79572 | 1.9.10.3.52(BAP - INTERLOCKS(PGMA 79572)) | 206816238
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 79572 | 1.9.10.3.52(BAP - INTERLOCKS(PGMA 79572)) | 206816239
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 79572 | 1.9.10.3.52(BAP - INTERLOCKS(PGMA 79572)) | 206816240
BAP - ELECTRICALLY OPERTD HOIST & ACCESSORIES(PGMA 79573) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 79573 | 1.9.10.3(Supply) | 206816241
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 79573 | 1.9.10.3.53(BAP - ELECTRICALLY OPERTD HOIST & ACCESSORIES(PGMA 79573)) | 206816242
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 79573 | 1.9.10.3.53(BAP - ELECTRICALLY OPERTD HOIST & ACCESSORIES(PGMA 79573)) | 206816243
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 79573 | 1.9.10.3.53(BAP - ELECTRICALLY OPERTD HOIST & ACCESSORIES(PGMA 79573)) | 206816244
BAP - GUIDE VANES /GUIDE PLATES(PGMA 79589) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 79589 | 1.9.10.3(Supply) | 206816245
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 79589 | 1.9.10.3.54(BAP - GUIDE VANES /GUIDE PLATES(PGMA 79589)) | 206816246
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 79589 | 1.9.10.3.54(BAP - GUIDE VANES /GUIDE PLATES(PGMA 79589)) | 206816247
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 79589 | 1.9.10.3.54(BAP - GUIDE VANES /GUIDE PLATES(PGMA 79589)) | 206816248
BAP - COMMISSIONING SPARES(PGMA 79988) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 79988 | 1.9.10.3(Supply) | 206816249
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 79988 | 1.9.10.3.55(BAP - COMMISSIONING SPARES(PGMA 79988)) | 206816250
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 79988 | 1.9.10.3.55(BAP - COMMISSIONING SPARES(PGMA 79988)) | 206816251
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 79988 | 1.9.10.3.55(BAP - COMMISSIONING SPARES(PGMA 79988)) | 206816252
BAP - ESP HAND RAILS(PGMA 89611) | SUP | 2024-02-29 08:00 | 2024-11-04 17:00 |  |  |  | 89611 | 1.9.10.3(Supply) | 206816253
Engineering | ENG | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  | 89611 | 1.9.10.3.56(BAP - ESP HAND RAILS(PGMA 89611)) | 206816254
Manufacturing | MFG | 2024-03-30 08:00 | 2024-07-07 17:00 |  |  |  | 89611 | 1.9.10.3.56(BAP - ESP HAND RAILS(PGMA 89611)) | 206816255
Dispatch | DIS | 2024-07-08 08:00 | 2024-11-04 17:00 |  |  |  | 89611 | 1.9.10.3.56(BAP - ESP HAND RAILS(PGMA 89611)) | 206816256
BAP - HSFG BOLTS(PGMA 89618) | SUP | 2023-03-06 08:00 | 2023-11-10 17:00 |  |  |  | 89618 | 1.9.10.3(Supply) | 206816257
Engineering | ENG | 2023-03-06 08:00 | 2023-04-04 17:00 |  |  |  | 89618 | 1.9.10.3.57(BAP - HSFG BOLTS(PGMA 89618)) | 206816258
Manufacturing | MFG | 2023-04-05 08:00 | 2023-07-13 17:00 |  |  |  | 89618 | 1.9.10.3.57(BAP - HSFG BOLTS(PGMA 89618)) | 206816259
Dispatch | DIS | 2023-07-14 08:00 | 2023-11-10 17:00 |  |  |  | 89618 | 1.9.10.3.57(BAP - HSFG BOLTS(PGMA 89618)) | 206816260
BAP - OPACITY MONITOR & ACCE(PGMA 79574) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 79574 | 1.9.10.3(Supply) | 206816261
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 79574 | 1.9.10.3.58(BAP - OPACITY MONITOR & ACCE(PGMA 79574)) | 206816262
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 79574 | 1.9.10.3.58(BAP - OPACITY MONITOR & ACCE(PGMA 79574)) | 206816263
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 79574 | 1.9.10.3.58(BAP - OPACITY MONITOR & ACCE(PGMA 79574)) | 206816264
BAP - ASH LEVEL INDICATOR(PGMA 79563) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 79563 | 1.9.10.3(Supply) | 206816265
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 79563 | 1.9.10.3.59(BAP - ASH LEVEL INDICATOR(PGMA 79563)) | 206816266
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 79563 | 1.9.10.3.59(BAP - ASH LEVEL INDICATOR(PGMA 79563)) | 206816267
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 79563 | 1.9.10.3.59(BAP - ASH LEVEL INDICATOR(PGMA 79563)) | 206816268
BAP - EP PERF TEST EQUIPT(PGMA 79561) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 79561 | 1.9.10.3(Supply) | 206816269
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 79561 | 1.9.10.3.60(BAP - EP PERF TEST EQUIPT(PGMA 79561)) | 206816270
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 79561 | 1.9.10.3.60(BAP - EP PERF TEST EQUIPT(PGMA 79561)) | 206816271
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 79561 | 1.9.10.3.60(BAP - EP PERF TEST EQUIPT(PGMA 79561)) | 206816272
BAP - TOOLS & TACKLES(PGMA 79996) | SUP | 2023-06-04 08:00 | 2024-02-08 17:00 |  |  |  | 79996 | 1.9.10.3(Supply) | 206816273
Engineering | ENG | 2023-06-04 08:00 | 2023-07-03 17:00 |  |  |  | 79996 | 1.9.10.3.61(BAP - TOOLS & TACKLES(PGMA 79996)) | 206816274
Manufacturing | MFG | 2023-07-04 08:00 | 2023-10-11 17:00 |  |  |  | 79996 | 1.9.10.3.61(BAP - TOOLS & TACKLES(PGMA 79996)) | 206816275
Dispatch | DIS | 2023-10-12 08:00 | 2024-02-08 17:00 |  |  |  | 79996 | 1.9.10.3.61(BAP - TOOLS & TACKLES(PGMA 79996)) | 206816276
BOI Items | SUP | 2022-11-26 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.9.10.3(Supply) | 206816277
BAP - BOI Items: Cable Trays (79562) | SUP | 2023-02-24 08:00 | 2024-01-09 17:00 |  |  |  | 79562 | 1.9.10.3.62(BOI Items) | 206816278
Engineering | ENG | 2023-02-24 08:00 | 2023-08-22 17:00 |  |  |  | 79562 | 1.9.10.3.62.1( BAP - BOI Items: Cable Trays (79562)) | 206816279
Manufacturing | MFG | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  | 79562 | 1.9.10.3.62.1( BAP - BOI Items: Cable Trays (79562)) | 206816280
Dispatch | DIS | 2023-11-21 08:00 | 2024-01-09 17:00 |  |  |  | 79562 | 1.9.10.3.62.1( BAP - BOI Items: Cable Trays (79562)) | 206816281
BAP - BOI Items: Floor Grills (89613) | SUP | 2022-11-26 08:00 | 2023-09-01 17:00 |  |  |  | 89613 | 1.9.10.3.62(BOI Items) | 206816282
Engineering | ENG | 2022-11-26 08:00 | 2023-05-14 17:00 |  |  |  | 89613 | 1.9.10.3.62.2( BAP - BOI Items: Floor Grills (89613)) | 206816283
Manufacturing | MFG | 2023-05-15 08:00 | 2023-07-13 17:00 |  |  |  | 89613 | 1.9.10.3.62.2( BAP - BOI Items: Floor Grills (89613)) | 206816284
Dispatch | DIS | 2023-07-14 08:00 | 2023-09-01 17:00 |  |  |  | 89613 | 1.9.10.3.62.2( BAP - BOI Items: Floor Grills (89613)) | 206816285
BAP - BOI Items: Cable (79560) | SUP | 2023-02-24 08:00 | 2024-01-09 17:00 |  |  |  | 79560 | 1.9.10.3.62(BOI Items) | 206816286
Engineering | ENG | 2023-02-24 08:00 | 2023-08-22 17:00 |  |  |  | 79560 | 1.9.10.3.62.3( BAP - BOI Items: Cable (79560)) | 206816287
Manufacturing | MFG | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  | 79560 | 1.9.10.3.62.3( BAP - BOI Items: Cable (79560)) | 206816288
Dispatch | DIS | 2023-11-21 08:00 | 2024-01-09 17:00 |  |  |  | 79560 | 1.9.10.3.62.3( BAP - BOI Items: Cable (79560)) | 206816289
BAP - BOI Items: Gear Motor (79531) | SUP | 2023-02-24 08:00 | 2023-12-10 17:00 |  |  |  | 79531 | 1.9.10.3.62(BOI Items) | 206816290
Engineering | ENG | 2023-02-24 08:00 | 2023-07-23 17:00 |  |  |  | 79531 | 1.9.10.3.62.4(BAP - BOI Items: Gear Motor (79531)) | 206816291
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  | 79531 | 1.9.10.3.62.4(BAP - BOI Items: Gear Motor (79531)) | 206816292
Dispatch | DIS | 2023-10-22 08:00 | 2023-12-10 17:00 |  |  |  | 79531 | 1.9.10.3.62.4(BAP - BOI Items: Gear Motor (79531)) | 206816293
BAP - BOI Items: Inter Locks (79972) | SUP | 2023-07-24 08:00 | 2024-06-07 17:00 |  |  |  | 79972 | 1.9.10.3.62(BOI Items) | 206816294
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 79972 | 1.9.10.3.62.5(BAP - BOI Items: Inter Locks (79972)) | 206816295
Manufacturing | MFG | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  | 79972 | 1.9.10.3.62.5(BAP - BOI Items: Inter Locks (79972)) | 206816296
Dispatch | DIS | 2024-04-19 08:00 | 2024-06-07 17:00 |  |  |  | 79972 | 1.9.10.3.62.5(BAP - BOI Items: Inter Locks (79972)) | 206816297
BAP - BOI Items: Insulation wool (79567) | SUP | 2023-07-24 08:00 | 2024-06-07 17:00 |  |  |  | 79567 | 1.9.10.3.62(BOI Items) | 206816298
Engineering | ENG | 2023-07-24 08:00 | 2024-01-19 17:00 |  |  |  | 79567 | 1.9.10.3.62.6(BAP - BOI Items: Insulation wool (79567)) | 206816299
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  | 79567 | 1.9.10.3.62.6(BAP - BOI Items: Insulation wool (79567)) | 206816300
Dispatch | DIS | 2024-04-19 08:00 | 2024-06-07 17:00 |  |  |  | 79567 | 1.9.10.3.62.6(BAP - BOI Items: Insulation wool (79567)) | 206816301
BAP - BOI Items: Aluminium Cladding Sheet (89615) | SUP | 2023-01-05 08:00 | 2023-10-11 17:00 |  |  |  | 89615 | 1.9.10.3.62(BOI Items) | 206816302
Engineering | ENG | 2023-01-05 08:00 | 2023-06-23 17:00 |  |  |  | 89615 | 1.9.10.3.62.7(BAP - BOI Items: Aluminium Cladding Sheet (89615)) | 206816303
Manufacturing | MFG | 2023-06-24 08:00 | 2023-08-22 17:00 |  |  |  | 89615 | 1.9.10.3.62.7(BAP - BOI Items: Aluminium Cladding Sheet (89615)) | 206816304
Dispatch | DIS | 2023-08-23 08:00 | 2023-10-11 17:00 |  |  |  | 89615 | 1.9.10.3.62.7(BAP - BOI Items: Aluminium Cladding Sheet (89615)) | 206816305
BAP - BOI Items: PANEL TYPE HOPPER HEATERS & ACCESSORIES (79591) | SUP | 2023-06-04 08:00 | 2024-06-07 17:00 |  |  |  | 79591 | 1.9.10.3.62(BOI Items) | 206816306
Engineering | ENG | 2023-06-04 08:00 | 2023-10-31 17:00 |  |  |  | 79591 | 1.9.10.3.62.8(BAP - BOI Items: PANEL TYPE HOPPER HEATERS & ACCESSORIES (79591)) | 206816307
Manufacturing | MFG | 2023-11-01 08:00 | 2024-04-18 17:00 |  |  |  | 79591 | 1.9.10.3.62.8(BAP - BOI Items: PANEL TYPE HOPPER HEATERS & ACCESSORIES (79591)) | 206816308
Dispatch | DIS | 2024-04-19 08:00 | 2024-06-07 17:00 |  |  |  | 79591 | 1.9.10.3.62.8(BAP - BOI Items: PANEL TYPE HOPPER HEATERS & ACCESSORIES (79591)) | 206816309
BAP - BOI Items: LT SWITCH BOARD (79577) | SUP | 2023-07-24 08:00 | 2024-04-28 17:00 |  |  |  | 79577 | 1.9.10.3.62(BOI Items) | 206816310
Engineering | ENG | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  | 79577 | 1.9.10.3.62.9(BAP - BOI Items: LT SWITCH BOARD (79577)) | 206816311
Manufacturing | MFG | 2023-12-21 08:00 | 2024-03-09 17:00 |  |  |  | 79577 | 1.9.10.3.62.9(BAP - BOI Items: LT SWITCH BOARD (79577)) | 206816312
Dispatch | DIS | 2024-03-10 08:00 | 2024-04-28 17:00 |  |  |  | 79577 | 1.9.10.3.62.9(BAP - BOI Items: LT SWITCH BOARD (79577)) | 206816313
Erection | ERC | 2023-10-23 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.9.10(Electrostatic Precipitator) | 206816314
First 3 Nos Pass | ERC | 2023-10-23 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.9.10.4(Erection) | 206816315
Foundation checking and corrections | CIV | 2023-10-23 08:00 | 2023-10-27 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816316
Erection: Supporting structures | ERC | 2023-10-29 08:00 | 2024-02-05 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816317
Erection: Slide supports & Casing Structure | ERC | 2023-11-28 08:00 | 2024-03-06 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816318
Erection: Casing shell | ERC | 2023-12-28 08:00 | 2024-04-05 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816319
Erection: ESP Galleries & stairs | ERC | 2024-02-06 08:00 | 2024-10-12 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816320
Erection: ESP Roof handrails | ERC | 2024-10-13 08:00 | 2025-01-10 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816321
Erection: Hopper ridges | ERC | 2024-01-17 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816322
Erection: ESP Roof panels | ERC | 2024-02-16 08:00 | 2024-05-15 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816323
Erection: Col & Emitting Ele suspension | ERC | 2024-02-26 08:00 | 2024-05-25 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816324
Erection: Insulator support panel | ERC | 2024-03-27 08:00 | 2024-06-24 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816325
Erection: Emit system frame-top, Middle & Bottom | ERC | 2024-04-26 08:00 | 2024-07-24 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816326
Erection: Gas dist. Assy | ERC | 2024-05-26 08:00 | 2024-08-08 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816327
Erection: Inlet & outlet funnels | ERC | 2024-05-26 08:00 | 2024-08-23 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816328
Erection: Splitters & guide vanes | ERC | 2024-05-26 08:00 | 2024-08-23 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816329
Erection: Col Electrode & Shock Bar | ERC | 2024-06-25 08:00 | 2024-10-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816330
Erection: Roof panel ASSY | ERC | 2024-07-25 08:00 | 2024-10-22 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816331
Erection: Pent house & Outer Roof for ESP | ERC | 2024-09-08 08:00 | 2024-12-06 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816332
Erection: Hopper upperpart | ERC | 2024-10-08 08:00 | 2025-04-05 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816333
Erection: Hopper middle& lower part | ERC | 2024-11-07 08:00 | 2025-05-05 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816334
Erection: Gas screen | ERC | 2025-02-05 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816335
Erection: Hopper App Platform | ERC | 2025-02-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816336
Erection: Insulator housing | ERC | 2025-04-06 08:00 | 2025-07-04 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816337
Erection of Inspection doors | ERC | 2025-06-05 08:00 | 2025-07-04 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816338
Erection of HV Rectifier transformer | ERC | 2025-06-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816339
Erection of Sub-delivery comp | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816340
Erection of Electrically operated hoists | ERC | 2025-06-05 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816341
Erection of Col Rapping Mech | ERC | 2025-03-07 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816342
Erection of Emit Rapping Mech | ERC | 2025-04-06 08:00 | 2025-09-12 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816343
Erection of GD-rapping Mech | ERC | 2025-07-05 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816344
Erection of Col rapping drive | ERC | 2025-07-05 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816345
Erection of Emit rapping drive | ERC | 2025-07-05 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816346
Erection of GD drive arrangement | ERC | 2025-08-19 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816347
Erection of Geared motors for rap | ERC | 2025-07-05 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816348
Erection of Support insulator | ERC | 2025-07-05 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816349
Erection of Emit system suspension | ERC | 2025-07-05 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816350
Erection of Emit electrodes | ERC | 2025-07-05 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816351
Erection of Heating elements | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816352
Erection of Water washing system | ERC | 2025-07-05 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816353
Erection of Interlocks | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816354
Erection of Ash level indicator | ERC | 2025-07-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816355
Erection of ESP Perf test equipments | ERC | 2025-08-04 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816356
Erection of Insulation wool | ERC | 2025-05-06 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.9.10.4.1( First 3 Nos Pass) | 206816357
Last 3 Nos Pass | ERC | 2023-12-23 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.9.10.4(Erection) | 206816358
Foundation checking and corrections | CIV | 2023-12-23 08:00 | 2023-12-27 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816359
Erection of Supporting structures | ERC | 2023-12-29 08:00 | 2024-04-06 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816360
Erection of Slide supports & Casing Structure | ERC | 2024-01-28 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816361
Erection of Casing shell | ERC | 2024-02-27 08:00 | 2024-06-05 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816362
Erection of ESP Galleries & stairs | ERC | 2024-04-07 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816363
Erection of ESP Roof handrails | ERC | 2024-12-13 08:00 | 2025-03-12 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816364
Erection of Hopper ridges | ERC | 2024-03-18 08:00 | 2024-06-15 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816365
Erection of ESP Roof panels | ERC | 2024-04-17 08:00 | 2024-07-15 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816366
Erection of Col Ele suspension | ERC | 2024-04-27 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816367
Erection of Insulator support panel | ERC | 2024-05-27 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816368
Erection of Emit system frame-top, Middle & Bottom | ERC | 2024-06-26 08:00 | 2024-09-23 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816369
Erection of Gas dist. Assy | ERC | 2024-07-26 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816370
Erection of Inlet & outlet funnels | ERC | 2024-07-26 08:00 | 2024-10-23 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816371
Erection of Splitters & guide vanes | ERC | 2024-07-26 08:00 | 2024-10-23 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816372
Erection of Col Electrode & Shock Bar | ERC | 2024-08-25 08:00 | 2024-12-02 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816373
Erection of Roof panel ASSY | ERC | 2024-09-24 08:00 | 2024-12-22 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816374
Erection of Pent house & Outer Roof for ESP | ERC | 2024-11-08 08:00 | 2025-02-05 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816375
Erection of Hopper upperpart | ERC | 2024-12-08 08:00 | 2025-06-05 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816376
Erection of Hopper middle& lower part | ERC | 2025-01-07 08:00 | 2025-07-05 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816377
Erection of Gas screen | ERC | 2025-04-07 08:00 | 2025-06-20 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816378
Erection of Hopper App Platform | ERC | 2025-04-07 08:00 | 2025-10-03 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816379
Erection of Insulator housing | ERC | 2025-06-06 08:00 | 2025-09-03 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816380
Erection of Inspection doors | ERC | 2025-08-05 08:00 | 2025-09-03 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816381
Erection of HV Rectifier transformer | ERC | 2025-08-05 08:00 | 2025-10-03 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816382
Erection of Sub-delivery comp | ERC | 2025-09-04 08:00 | 2025-10-03 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816383
Erection of Electrically operated hoists | ERC | 2025-08-05 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816384
Erection of Col Rapping Mech | ERC | 2025-05-07 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816385
Erection of Emit Rapping Mech | ERC | 2025-06-06 08:00 | 2025-11-12 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816386
Erection of GD-rapping Mech | ERC | 2025-09-04 08:00 | 2025-10-18 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816387
Erection of Col rapping drive | ERC | 2025-09-04 08:00 | 2025-10-18 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816388
Erection of Emit rapping drive | ERC | 2025-09-04 08:00 | 2025-10-18 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816389
Erection of GD drive arrangement | ERC | 2025-10-19 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816390
Erection of Geared motors for rap | ERC | 2025-10-19 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816391
Erection of Support insulator | ERC | 2025-10-14 08:00 | 2025-12-07 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816392
Erection of Emit system suspension | ERC | 2025-10-09 08:00 | 2025-12-02 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816393
Erection of Emit electrodes | ERC | 2025-10-04 08:00 | 2025-11-27 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816394
Erection of Heating elements | ERC | 2025-09-29 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816395
Erection of Water washing system | ERC | 2025-09-29 08:00 | 2025-11-12 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816396
Erection of Interlocks | ERC | 2025-09-29 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816397
Erection of Ash level indicator | ERC | 2025-09-29 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816398
Erection of ESP Perf test equipments | ERC | 2025-10-29 08:00 | 2025-11-12 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816399
Erection of Insulation wool | ERC | 2025-07-06 08:00 | 2025-11-27 17:00 |  |  |  |  | 1.9.10.4.2( Last 3 Nos Pass) | 206816400
Turbo-generator & Auxiliaries | OTH | 2022-09-27 08:00 | 2026-04-20 17:00 | 2022-10-03 |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206816401
Basic engineering | ENG | 2022-10-27 08:00 | 2023-02-23 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816402
PH -Civil / Structural Steel Work | OTH | 2023-05-04 17:00 | 2025-12-08 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816403
REL OF DWG STG Foundation | PE - RFC | 2023-05-04 17:00 | 2023-05-04 17:00 |  |  |  | PCE-00500 | 1.10.2(PH -Civil / Structural Steel Work) | 206816404
Rel of DWG for PH BLDG. PH BLDG.COLS FDN ON ROW A to E | PE - RFC | 2023-06-23 17:00 | 2023-06-23 17:00 |  |  |  | PCE-00600 | 1.10.2(PH -Civil / Structural Steel Work) | 206816405
Rel of DWG for PH BLDG. (AB BAY)- INTERMEDIATE COLS. FDN | PE - RFC | 2023-07-27 17:00 | 2023-07-27 17:00 |  |  |  | PCE-00700 | 1.10.2(PH -Civil / Structural Steel Work) | 206816406
Rel of DWG for PH BLDG.- CEP PIT | PE - RFC | 2023-09-07 17:00 | 2023-09-07 17:00 |  |  |  | PCE-00800 | 1.10.2(PH -Civil / Structural Steel Work) | 206816407
Rel of DWG for PH BLDG-BC BAY INTERMEDIATE COLUMN FOUNDATION | PE - RFC | 2023-09-07 17:00 | 2023-09-07 17:00 |  |  |  | PCE-00900 | 1.10.2(PH -Civil / Structural Steel Work) | 206816408
Rel of DWG for PH BLDG. - OIL CANAL | PE - RFC | 2023-12-28 17:00 | 2023-12-28 17:00 |  |  |  | PCE-01000 | 1.10.2(PH -Civil / Structural Steel Work) | 206816409
Rel of DWG for PH BLDG.-C.W. PIT | PE - RFC | 2024-02-22 17:00 | 2024-02-22 17:00 |  |  |  | PCE-01100 | 1.10.2(PH -Civil / Structural Steel Work) | 206816410
Rel of DWG for PH BLDG.(AB BAY-TG)- FL @EL +8.5M | PE - RFC | 2024-05-02 17:00 | 2024-05-02 17:00 |  |  |  | PCE-01200 | 1.10.2(PH -Civil / Structural Steel Work) | 206816411
Rel of DWG for PH BLDG. (AB BAY-CR)- FL @ EL 17.0M | PE - RFC | 2024-05-02 17:00 | 2024-05-02 17:00 |  |  |  | PCE-01300 | 1.10.2(PH -Civil / Structural Steel Work) | 206816412
Rel of DWG for PH BLDG (AB BAY)- METAL DECK ROOF | PE - RFC | 2024-05-16 17:00 | 2024-05-16 17:00 |  |  |  | PCE-01400 | 1.10.2(PH -Civil / Structural Steel Work) | 206816413
Rel of DWG for PH BLDG.(AB BAY)- FL @EL +3.5M | PE - RFC | 2024-05-16 17:00 | 2024-05-16 17:00 |  |  |  | PCE-01500 | 1.10.2(PH -Civil / Structural Steel Work) | 206816414
Rel of DWG for PH BLDG. (AB BAY-TG)- FL @ EL 17.0M | PE - RFC | 2024-05-16 17:00 | 2024-05-16 17:00 |  |  |  | PCE-01600 | 1.10.2(PH -Civil / Structural Steel Work) | 206816415
Rel of DWG for PH BLDG.(BC BAY-TG) - FL @EL + 25.5M | PE - RFC | 2024-05-23 17:00 | 2024-05-23 17:00 |  |  |  | PCE-01800 | 1.10.2(PH -Civil / Structural Steel Work) | 206816416
Rel of DWG for PH BLDG.(BC BAY-CR) - FL @EL + 34.0M | PE - RFC | 2024-06-06 17:00 | 2024-06-06 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816417
Rel of DWG for PH BLDG.(BC BAY-TG)- EL. +8.50 M | PE - RFC | 2024-06-13 17:00 | 2024-06-13 17:00 |  |  |  | PCE-02000 | 1.10.2(PH -Civil / Structural Steel Work) | 206816418
Rel of DWG for PH BLDG.(BC BAY-TG)- FL @ EL 17.0M | PE - RFC | 2024-06-27 17:00 | 2024-06-27 17:00 |  |  |  | PCE-02100 | 1.10.2(PH -Civil / Structural Steel Work) | 206816419
Rel of DWG for PH BLDG. (AB BAY-CR)- FL @ EL 12M | PE - RFC | 2024-07-11 17:00 | 2024-07-11 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816420
Rel of DWG for PH BLDG.(BC BAY-TG) - FL @EL + 5.0M | PE - RFC | 2024-07-18 17:00 | 2024-07-18 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816421
Rel of DWG for PH BLDG.(AB BAY-CR)- FL @EL +8.5M | PE - RFC | 2024-08-08 17:00 | 2024-08-08 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816422
Rel of DWG for PH BLDG. - FL @ EL + 0.0M | PE - RFC | 2024-08-15 17:00 | 2024-08-15 17:00 |  |  |  | PCE-02700 | 1.10.2(PH -Civil / Structural Steel Work) | 206816423
Rel of DWG for PH BLDG.(BCDEFGH BAY-CR)- FL @ EL 17M | PE - RFC | 2024-08-15 17:00 | 2024-08-15 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816424
Rel of DWG for PH BLDG.(BCDEFGH BAY-CR)- FL @ EL 8.5M | PE - RFC | 2024-08-22 17:00 | 2024-08-22 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816425
Rel of DWG for PH BLDG.(BCDEFGH BAY-CR)- FL @ EL 25.5 M | PE - RFC | 2024-08-22 17:00 | 2024-08-22 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816426
Rel of DWG for PH BLDG.(BCDEFGH BAY-CR)- @ EL 29.5M | PE - RFC | 2024-08-29 17:00 | 2024-08-29 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816427
STG Foundation (TG Raft & Deck) | CIV | 2023-05-05 08:00 | 2024-04-07 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816428
Civil Work | CIV | 2023-05-05 08:00 | 2024-04-07 17:00 |  |  |  |  | 1.10.2.25(STG Foundation (TG Raft & Deck)) | 206816429
EXCAVATION & PCC | CIV | 2023-05-05 08:00 | 2023-05-29 17:00 |  |  |  |  | 1.10.2.25.1(Civil Work) | 206816430
RCC TG RAFT | CIV | 2023-05-30 08:00 | 2023-08-31 17:00 |  |  |  |  | 1.10.2.25.1(Civil Work) | 206816431
COLUMN & DECK CASTING WORK WITH STAGING | CIV | 2023-09-01 08:00 | 2024-04-07 17:00 |  |  |  |  | 1.10.2.25.1(Civil Work) | 206816432
COLUMN CASTING | CIV | 2023-09-01 08:00 | 2024-02-07 17:00 |  |  |  |  | 1.10.2.25.1.3(COLUMN & DECK CASTING WORK WITH STAGING) | 206816433
TG DECK CASTING WORK | CIV | 2024-02-08 08:00 | 2024-04-07 17:00 |  |  |  |  | 1.10.2.25.1.3(COLUMN & DECK CASTING WORK WITH STAGING) | 206816434
PH AB & BC bay civil works | CIV | 2023-06-27 08:00 | 2023-12-04 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816435
Civil Work | CIV | 2023-06-27 08:00 | 2023-12-04 17:00 |  |  |  |  | 1.10.2.26(PH AB & BC bay civil works) | 206816436
Excavation & PCC | CIV | 2023-06-27 08:00 | 2023-09-11 17:00 |  |  |  |  | 1.10.2.26.1(Civil Work) | 206816437
For A row | CIV | 2023-06-27 08:00 | 2023-07-31 17:00 |  |  |  |  | 1.10.2.26.1.1(Excavation & PCC) | 206816438
For B row | CIV | 2023-07-18 08:00 | 2023-08-21 17:00 |  |  |  |  | 1.10.2.26.1.1(Excavation & PCC) | 206816439
For C row | CIV | 2023-08-08 08:00 | 2023-09-11 17:00 |  |  |  |  | 1.10.2.26.1.1(Excavation & PCC) | 206816440
Raft casting | CIV | 2023-07-12 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.10.2.26.1(Civil Work) | 206816441
For A row | CIV | 2023-07-12 08:00 | 2023-08-25 17:00 |  |  |  |  | 1.10.2.26.1.2(Raft casting) | 206816442
For B row | CIV | 2023-08-02 08:00 | 2023-09-15 17:00 |  |  |  |  | 1.10.2.26.1.2(Raft casting) | 206816443
For C row | CIV | 2023-08-23 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.10.2.26.1.2(Raft casting) | 206816444
Pedestals (Till Bolt Lift) | CIV | 2023-08-11 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.10.2.26.1(Civil Work) | 206816445
For A row | CIV | 2023-08-11 08:00 | 2023-10-09 17:00 |  |  |  |  | 1.10.2.26.1.3(Pedestals (Till Bolt Lift)) | 206816446
For B row | CIV | 2023-08-22 08:00 | 2023-10-20 17:00 |  |  |  |  | 1.10.2.26.1.3(Pedestals (Till Bolt Lift)) | 206816447
For C row | CIV | 2023-09-12 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.10.2.26.1.3(Pedestals (Till Bolt Lift)) | 206816448
Backfilling for AB Bay | CIV | 2023-09-25 08:00 | 2023-11-23 17:00 |  |  |  |  | 1.10.2.26.1(Civil Work) | 206816449
Backfilling for BC Bay | CIV | 2023-10-06 08:00 | 2023-12-04 17:00 |  |  |  |  | 1.10.2.26.1(Civil Work) | 206816450
D, E, F bay civil Work | CIV | 2023-08-26 08:00 | 2024-01-02 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816451
Civil Work | CIV | 2023-08-26 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.10.2.27(D, E, F bay civil Work) | 206816452
Excavation & PCC for D row Columns | CIV | 2023-09-12 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.10.2.27.1(Civil Work) | 206816453
Excavation & PCC for E row Columns | CIV | 2023-08-26 08:00 | 2023-09-04 17:00 |  |  |  |  | 1.10.2.27.1(Civil Work) | 206816454
Excavation & PCC for F row Columns | CIV | 2023-08-26 08:00 | 2023-09-04 17:00 |  |  |  |  | 1.10.2.27.1(Civil Work) | 206816455
Foundations | CIV | 2023-09-05 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.10.2.27(D, E, F bay civil Work) | 206816456
Casting of Raft, footings, columns Till Bolt Lift for D Row | CIV | 2023-09-22 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.10.2.27.2(Foundations) | 206816457
Casting of Raft, footings, columns Till Bolt Lift for E Row | CIV | 2023-09-05 08:00 | 2023-10-04 17:00 |  |  |  |  | 1.10.2.27.2(Foundations) | 206816458
Casting of Raft, footings, columns Till Bolt Lift for F Row | CIV | 2023-09-05 08:00 | 2023-10-04 17:00 |  |  |  |  | 1.10.2.27.2(Foundations) | 206816459
Backfilling Works | CIV | 2023-10-05 08:00 | 2024-01-02 17:00 |  |  |  |  | 1.10.2.27(D, E, F bay civil Work) | 206816460
PH - Structural Steel Work(Supply by Trichy) | OTH | 2023-07-02 08:00 | 2025-12-08 17:00 |  |  |  |  | 1.10.2(PH -Civil / Structural Steel Work) | 206816461
Civil Work | OTH | 2023-07-02 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.10.2.28(PH - Structural Steel Work(Supply by Trichy)) | 206816462
Columns Fabrication works | CIV | 2023-07-02 08:00 | 2023-10-29 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816463
Structural steel fabrication A row &Dispatch | DIS | 2023-07-02 08:00 | 2023-08-15 17:00 |  |  |  |  | 1.10.2.28.1.1(Columns Fabrication works) | 206816464
Structural steel fabrication B row &Dispatch | DIS | 2023-07-27 08:00 | 2023-09-09 17:00 |  |  |  |  | 1.10.2.28.1.1(Columns Fabrication works) | 206816465
Structural steel fabrication C row &Dispatch | DIS | 2023-08-21 08:00 | 2023-10-04 17:00 |  |  |  |  | 1.10.2.28.1.1(Columns Fabrication works) | 206816466
Structural steel fabrication Intermediate columns &Dispatch | DIS | 2023-09-15 08:00 | 2023-10-29 17:00 |  |  |  |  | 1.10.2.28.1.1(Columns Fabrication works) | 206816467
Column Erection works | ERC | 2023-10-12 08:00 | 2024-03-09 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816468
Structural steel Erection A row | ERC | 2023-10-12 08:00 | 2023-12-10 17:00 |  |  |  |  | 1.10.2.28.1.2(Column Erection works) | 206816469
Structural selection B row | ERC | 2023-11-06 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.10.2.28.1.2(Column Erection works) | 206816470
Structural selection C row | ERC | 2023-12-01 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.10.2.28.1.2(Column Erection works) | 206816471
Structural selection Intermediate columns | ERC | 2023-12-21 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.10.2.28.1.2(Column Erection works) | 206816472
Grouting works | CIV | 2023-12-11 08:00 | 2024-03-09 17:00 |  |  |  |  | 1.10.2.28.1.2(Column Erection works) | 206816473
FABRICATION of floor beams(Supply-Trichy) | SUP | 2023-10-05 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816474
Fabrication of floor beam & bracings @ EL 3.5 mtr &Dispatch | DIS | 2023-10-05 08:00 | 2023-11-03 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816475
Fabrication of floor beam & bracings @ EL 5.0 mtr &Dispatch | DIS | 2023-10-20 08:00 | 2023-11-18 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816476
Fabrication of floor beam & bracings @ EL 8.5 mtr &Dispatch | DIS | 2023-11-04 08:00 | 2023-12-03 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816477
Fabrication of floor beam & bracings @ EL 12 mtr &Dispatch | DIS | 2023-11-19 08:00 | 2023-12-18 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816478
Fabrication of floor beam & bracings @ EL 17.00 mtr &Dispatch | DIS | 2023-12-04 08:00 | 2024-01-02 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816479
Fabrication of floor beam & bracings @ EL 25.50 mtr &Dispatch | DIS | 2023-12-19 08:00 | 2024-01-17 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816480
Fabrication of floor beam & bracings @ EL 29 mtr &Dispatch | DIS | 2024-02-22 08:00 | 2024-03-22 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816481
Fabrication of floor beam & bracings @ EL 13.5 mtr &Dispatch | DIS | 2024-03-08 08:00 | 2024-04-06 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816482
Fabrication of floor beam & bracings @ EL 34.00 mtr &Dispatch | DIS | 2024-03-23 08:00 | 2024-04-21 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816483
Fabrication of AB bay Roof trusses & Elevation bracings &Dispatch | DIS | 2024-01-03 08:00 | 2024-03-07 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816484
Dispatch of Fabricated beams | DIS | 2023-10-10 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | 206816485
Erection of Floor Beams | ERC | 2023-11-06 08:00 | 2024-06-08 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816486
Erection of floor beam & bracings @ EL 3.5 mtr | ERC | 2023-11-06 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816487
Erection of floor beam & bracings @ EL 5.0 mtr | ERC | 2023-12-06 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816488
Erection of floor beam & bracings @ EL 8.5 mtr | ERC | 2024-01-05 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816489
Erection of floor beam & bracings @ EL 12 mtr | ERC | 2024-02-04 08:00 | 2024-02-15 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816490
Erection of floor beam & bracings @ EL 17.0 mtr | ERC | 2024-02-16 08:00 | 2024-02-27 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816491
Erection of floor beam & bracings @ EL 25.50 mtr | ERC | 2024-02-28 08:00 | 2024-03-10 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816492
Erection of floor beam & bracings @ EL 29 mtr | ERC | 2024-03-11 08:00 | 2024-04-09 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816493
Erection of floor beam & bracings @ EL 13.5 mtr | ERC | 2024-04-10 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816494
Erection of floor beam & bracings @ EL 34.00 mtr | ERC | 2024-05-10 08:00 | 2024-06-08 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816495
Erection of Roof trusses along with elevation Bracing (Grid A, B & C) | ERC | 2024-03-11 08:00 | 2024-03-22 17:00 |  |  |  |  | 1.10.2.28.1.4(Erection of Floor Beams) | 206816496
Cladding along A row | ERC | 2024-04-07 08:00 | 2024-06-15 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816497
Cladding along C row | ERC | 2024-05-17 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816498
Cladding along Gable end | ERC | 2024-07-26 08:00 | 2024-08-24 17:00 |  |  |  |  | 1.10.2.28.1(Civil Work) | 206816499
PH Slab Casting & Roof | CIV | 2024-06-19 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.10.2.28(PH - Structural Steel Work(Supply by Trichy)) | 206816500
RCC slab @ + 3.5 Mtr Level | CIV | 2025-02-14 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816501
RCC slab @ + 5.0 Mtr Level | CIV | 2025-01-15 08:00 | 2025-02-13 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816502
RCC slab @ + 8.5 Mtr Level | CIV | 2024-12-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816503
RCC slab @ + 12.0 Mtr Level | CIV | 2024-11-16 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816504
RCC slab @ + 17.0 Mtr Level | CIV | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816505
RCC slab @ + 34.00 Mtr Level | CIV | 2024-09-17 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816506
RCC slab @ + 25.50 Mtr Level | CIV | 2024-08-18 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816507
RCC slab @ + 13.50 Mtr Level | CIV | 2024-07-19 08:00 | 2024-08-17 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816508
RCC slab @ + 34.00 Mtr Level | CIV | 2024-06-19 08:00 | 2024-07-18 17:00 |  |  |  |  | 1.10.2.28.2(PH Slab Casting & Roof) | 206816509
Grade slab level 0.00 Mtr | CIV | 2024-08-16 08:00 | 2025-12-08 17:00 |  |  |  |  | 1.10.2.28(PH - Structural Steel Work(Supply by Trichy)) | 206816510
RCC Grade Slab AB, BC, CD bay | CIV | 2024-08-16 08:00 | 2024-11-13 17:00 |  |  |  |  | 1.10.2.28.3(Grade slab level 0.00 Mtr) | 206816511
RCC Grade Slab of remaining bays | CIV | 2024-11-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.10.2.28.3(Grade slab level 0.00 Mtr) | 206816512
RCC Misc. Foundation | CIV | 2024-12-14 08:00 | 2025-03-13 17:00 |  |  |  |  | 1.10.2.28.3(Grade slab level 0.00 Mtr) | 206816513
Brickwork | CIV | 2025-03-14 08:00 | 2025-06-11 17:00 |  |  |  |  | 1.10.2.28.3(Grade slab level 0.00 Mtr) | 206816514
Plaster | OTH | 2025-06-12 08:00 | 2025-09-09 17:00 |  |  |  |  | 1.10.2.28.3(Grade slab level 0.00 Mtr) | 206816515
Flooring | CIV | 2025-09-10 08:00 | 2025-12-08 17:00 |  |  |  |  | 1.10.2.28.3(Grade slab level 0.00 Mtr) | 206816516
CW pit | CIV | 2025-03-16 08:00 | 2025-07-24 17:00 |  |  |  |  | 1.10.2.28(PH - Structural Steel Work(Supply by Trichy)) | 206816517
Excavation & PCC | CIV | 2025-03-16 08:00 | 2025-05-09 17:00 |  |  |  |  | 1.10.2.28.4(CW pit) | 206816518
RCC Raft | CIV | 2025-05-10 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.10.2.28.4(CW pit) | 206816519
RCC Pipe Support Pedestal | CIV | 2025-06-05 08:00 | 2025-06-19 17:00 |  |  |  |  | 1.10.2.28.4(CW pit) | 206816520
RCC Wall | CIV | 2025-06-20 08:00 | 2025-07-24 17:00 |  |  |  |  | 1.10.2.28.4(CW pit) | 206816521
Oil Canal | CIV | 2024-03-26 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.10.2.28(PH - Structural Steel Work(Supply by Trichy)) | 206816522
Oil Canal Columns, Beam Erection & welding work | CIV | 2024-03-26 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.10.2.28.5(Oil Canal) | 206816523
Platform for Oil canal trench | CIV | 2024-05-10 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.10.2.28.5(Oil Canal) | 206816524
RCC Trench Slab | CIV | 2024-11-16 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.10.2.28.5(Oil Canal) | 206816525
RCC Trench walls | CIV | 2025-02-14 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.10.2.28.5(Oil Canal) | 206816526
Steam Turbine | OTH | 2022-09-27 08:00 | 2026-04-20 17:00 | 2022-10-03 |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816527
Civil | CIV | 2024-12-31 17:00 | 2025-07-08 17:00 |  |  |  |  | 1.10.3(Steam Turbine) | 206816528
MOT Room | CIV | 2024-12-31 17:00 | 2024-12-31 17:00 |  |  |  |  | 1.10.3.1(Civil) | 206816529
LPBP Foundation | CIV | 2025-06-14 08:00 | 2025-07-08 17:00 |  |  |  |  | 1.10.3.1(Civil) | 206816530
LPBP Hydraulic Unit foundations: RCC | CIV | 2025-06-14 08:00 | 2025-06-28 17:00 |  |  |  |  | 1.10.3.1.2(LPBP Foundation) | 206816531
LPBP Hydraulic Unit foundations: Finishing works | CIV | 2025-06-29 08:00 | 2025-07-08 17:00 |  |  |  |  | 1.10.3.1.2(LPBP Foundation) | 206816532
Supply | SUP | 2022-09-27 08:00 | 2025-09-28 17:00 | 2022-10-03 |  |  |  | 1.10.3(Steam Turbine) | 206816533
TG embedment | SUP | 2022-09-27 08:00 | 2023-12-25 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816534
Engineering | ENG | 2022-09-27 08:00 | 2023-06-13 17:00 | 2022-10-03 | 2023-01-04 |  |  | 1.10.3.2.1(TG embedment) | 206816535
Manufacturing | MFG | 2023-06-14 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.10.3.2.1(TG embedment) | 206816536
Dispatch | DIS | 2023-11-26 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.3.2.1(TG embedment) | 206816537
Base Plate Assembly | SUP | 2022-09-27 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816538
Engineering | ENG | 2022-09-27 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.10.3.2.2( Base Plate Assembly) | 206816539
Manufacturing | MFG | 2023-09-27 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.10.3.2.2( Base Plate Assembly) | 206816540
Dispatch | DIS | 2024-03-30 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.3.2.2( Base Plate Assembly) | 206816541
Bearing Pedestals (Front, HP-IP, IP-LP & LP-Gen.) | SUP | 2022-09-27 08:00 | 2024-05-13 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816542
Engineering | ENG | 2022-09-27 08:00 | 2023-09-26 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.3( Bearing Pedestals (Front, HP-IP, IP-LP & LP-Gen.)) | 206816543
Manufacturing | MFG | 2023-09-27 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.10.3.2.3( Bearing Pedestals (Front, HP-IP, IP-LP & LP-Gen.)) | 206816544
Dispatch | DIS | 2024-03-30 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.3.2.3( Bearing Pedestals (Front, HP-IP, IP-LP & LP-Gen.)) | 206816545
LP Inner Casing | SUP | 2022-09-27 08:00 | 2024-10-12 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816546
Engineering | ENG | 2022-09-27 08:00 | 2023-10-16 17:00 | 2022-10-03 |  |  |  | 1.10.3.2.4( LP Inner Casing) | 206816547
Manufacturing | MFG | 2023-10-17 08:00 | 2024-07-29 17:00 |  |  |  |  | 1.10.3.2.4( LP Inner Casing) | 206816548
Dispatch | DIS | 2024-07-30 08:00 | 2024-10-12 17:00 |  |  |  |  | 1.10.3.2.4( LP Inner Casing) | 206816549
LP Outer Casing | SUP | 2022-09-27 08:00 | 2024-10-12 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816550
Engineering | ENG | 2022-09-27 08:00 | 2023-10-16 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.5( LP Outer Casing) | 206816551
Manufacturing | MFG | 2023-10-17 08:00 | 2024-07-29 17:00 |  |  |  |  | 1.10.3.2.5( LP Outer Casing) | 206816552
Dispatch | DIS | 2024-07-30 08:00 | 2024-10-12 17:00 |  |  |  |  | 1.10.3.2.5( LP Outer Casing) | 206816553
LP Rotor | SUP | 2022-09-27 08:00 | 2024-10-27 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816554
Engineering | ENG | 2022-09-27 08:00 | 2023-11-02 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.6( LP Rotor) | 206816555
Manufacturing | MFG | 2023-11-03 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.10.3.2.6( LP Rotor) | 206816556
Dispatch | DIS | 2024-09-28 08:00 | 2024-10-27 17:00 |  |  |  |  | 1.10.3.2.6( LP Rotor) | 206816557
HP Turbine | SUP | 2022-09-27 08:00 | 2024-12-21 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816558
Engineering | ENG | 2022-09-27 08:00 | 2023-11-10 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.7( HP Turbine) | 206816559
Manufacturing | MFG | 2023-11-11 08:00 | 2024-12-01 17:00 |  |  |  |  | 1.10.3.2.7( HP Turbine) | 206816560
Dispatch | DIS | 2024-12-02 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.10.3.2.7( HP Turbine) | 206816561
IP Turbine | SUP | 2022-09-27 08:00 | 2025-01-07 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816562
Engineering | ENG | 2022-09-27 08:00 | 2023-11-04 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.8( IP Turbine) | 206816563
Manufacturing | MFG | 2023-11-05 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.10.3.2.8( IP Turbine) | 206816564
Dispatch | DIS | 2024-09-28 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.10.3.2.8( IP Turbine) | 206816565
Cross Around Pipe | SUP | 2022-09-27 08:00 | 2024-11-12 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816566
Engineering | ENG | 2022-09-27 08:00 | 2023-11-04 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.9( Cross Around Pipe) | 206816567
Manufacturing | MFG | 2023-11-05 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.10.3.2.9( Cross Around Pipe) | 206816568
Dispatch | DIS | 2024-09-28 08:00 | 2024-11-12 17:00 |  |  |  |  | 1.10.3.2.9( Cross Around Pipe) | 206816569
ESV & CV and Overload Valve | SUP | 2022-09-27 08:00 | 2025-01-12 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816570
Engineering | ENG | 2022-09-27 08:00 | 2023-11-10 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.10(ESV & CV and Overload Valve) | 206816571
Manufacturing | MFG | 2023-11-11 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.10.3.2.10(ESV & CV and Overload Valve) | 206816572
Dispatch | DIS | 2024-11-28 08:00 | 2025-01-12 17:00 |  |  |  |  | 1.10.3.2.10(ESV & CV and Overload Valve) | 206816573
BOI- LP by Pass LPBP(HWR) | SUP | 2023-10-22 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816574
NIT | ENQ | 2023-10-22 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.10.3.2.11(BOI- LP by Pass LPBP(HWR)) | 206816575
Ordering | ORD | 2023-10-23 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.10.3.2.11(BOI- LP by Pass LPBP(HWR)) | 206816576
Manufacturing | MFG | 2024-05-10 08:00 | 2025-03-05 17:00 |  |  |  |  | 1.10.3.2.11(BOI- LP by Pass LPBP(HWR)) | 206816577
Dispatch | DIS | 2025-03-06 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.10.3.2.11(BOI- LP by Pass LPBP(HWR)) | 206816578
BOI- Turbine Integral piping TIP(PC-Chennai) | SUP | 2023-10-22 08:00 | 2025-09-28 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816579
NIT | ENQ | 2023-10-22 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.10.3.2.12(BOI- Turbine Integral piping TIP(PC-Chennai)) | 206816580
Ordering | ORD | 2023-10-23 08:00 | 2024-04-26 17:00 |  |  |  |  | 1.10.3.2.12(BOI- Turbine Integral piping TIP(PC-Chennai)) | 206816581
Manufacturing | MFG | 2024-04-27 08:00 | 2025-05-31 17:00 |  |  |  |  | 1.10.3.2.12(BOI- Turbine Integral piping TIP(PC-Chennai)) | 206816582
Dispatch | DIS | 2025-06-01 08:00 | 2025-09-28 17:00 |  |  |  |  | 1.10.3.2.12(BOI- Turbine Integral piping TIP(PC-Chennai)) | 206816583
BOI- Oil Module(HWR) | SUP | 2023-10-22 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816584
NIT | ENQ | 2023-10-22 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.10.3.2.13(BOI- Oil Module(HWR)) | 206816585
Ordering | ORD | 2023-10-23 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.10.3.2.13(BOI- Oil Module(HWR)) | 206816586
Manufacturing | MFG | 2024-05-10 08:00 | 2025-03-05 17:00 |  |  |  |  | 1.10.3.2.13(BOI- Oil Module(HWR)) | 206816587
Dispatch | DIS | 2025-03-06 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.10.3.2.13(BOI- Oil Module(HWR)) | 206816588
IV & CV | SUP | 2022-09-27 08:00 | 2025-01-22 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816589
Engineering | ENG | 2022-09-27 08:00 | 2023-11-10 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.14(IV & CV) | 206816590
Manufacturing | MFG | 2023-11-11 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.10.3.2.14(IV & CV) | 206816591
Dispatch | DIS | 2024-12-08 08:00 | 2025-01-22 17:00 |  |  |  |  | 1.10.3.2.14(IV & CV) | 206816592
Suspension of LPBP Valves | SUP | 2022-09-27 08:00 | 2025-01-22 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816593
Engineering | ENG | 2022-09-27 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.10.3.2.15(Suspension of LPBP Valves) | 206816594
Manufacturing | MFG | 2024-01-05 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.10.3.2.15(Suspension of LPBP Valves) | 206816595
Dispatch | DIS | 2024-12-08 08:00 | 2025-01-22 17:00 |  |  |  |  | 1.10.3.2.15(Suspension of LPBP Valves) | 206816596
Instruments & JBs | SUP | 2022-09-27 08:00 | 2025-04-13 17:00 | 2022-10-03 |  |  |  | 1.10.3.2(Supply) | 206816597
Engineering | ENG | 2022-09-27 08:00 | 2024-02-13 17:00 | 2022-10-03 | 2022-11-25 |  |  | 1.10.3.2.16(Instruments & JBs) | 206816598
Manufacturing | MFG | 2024-02-14 08:00 | 2025-02-27 17:00 |  |  |  |  | 1.10.3.2.16(Instruments & JBs) | 206816599
Dispatch | DIS | 2025-02-28 08:00 | 2025-04-13 17:00 |  |  |  |  | 1.10.3.2.16(Instruments & JBs) | 206816600
TG C&I Package | SUP | 2022-09-27 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816601
Engineering | ENG | 2022-09-27 08:00 | 2024-02-13 17:00 |  |  |  |  | 1.10.3.2.17(TG C&I Package) | 206816602
Manufacturing | MFG | 2024-02-14 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.10.3.2.17(TG C&I Package) | 206816603
Dispatch | DIS | 2025-02-11 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.10.3.2.17(TG C&I Package) | 206816604
Compensator | SUP | 2022-09-27 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816605
Engineering | ENG | 2022-09-27 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.3.2.18(Compensator) | 206816606
Manufacturing | MFG | 2023-12-06 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.10.3.2.18(Compensator) | 206816607
Dispatch | DIS | 2024-10-29 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.3.2.18(Compensator) | 206816608
Balance BOIs | SUP | 2023-10-22 08:00 | 2025-03-25 17:00 |  |  |  |  | 1.10.3.2(Supply) | 206816609
NIT | ENQ | 2023-10-22 08:00 | 2023-10-22 17:00 |  |  |  |  | 1.10.3.2.19(Balance BOIs) | 206816610
Ordering | ORD | 2023-10-23 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.10.3.2.19(Balance BOIs) | 206816611
Manufacturing | MFG | 2023-10-23 08:00 | 2024-11-25 17:00 |  |  |  |  | 1.10.3.2.19(Balance BOIs) | 206816612
Dispatch | DIS | 2024-11-26 08:00 | 2025-03-25 17:00 |  |  |  |  | 1.10.3.2.19(Balance BOIs) | 206816613
Erection | ERC | 2024-08-07 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.10.3(Steam Turbine) | 206816614
PEDESTAL RELATED WORK | ERC | 2024-08-07 08:00 | 2024-12-05 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816615
Preparation of foundation, making of required Platform & Anchor Plate blue matching | ERC | 2024-08-07 08:00 | 2024-09-14 17:00 |  |  |  |  | 1.10.3.3.1( PEDESTAL RELATED WORK) | 206816616
Cleaning LP bearing Pedestals & LP base Plates, Levelling & Centering | ERC | 2024-09-15 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.10.3.3.1( PEDESTAL RELATED WORK) | 206816617
Cleaning of IP pedestals, assembly and alignment | ERC | 2024-09-28 08:00 | 2024-10-10 17:00 |  |  |  |  | 1.10.3.3.1( PEDESTAL RELATED WORK) | 206816618
Cleaning of HP pedestals, assembly and alignment | ERC | 2024-10-11 08:00 | 2024-10-23 17:00 |  |  |  |  | 1.10.3.3.1( PEDESTAL RELATED WORK) | 206816619
Grouting of all pedestals after final alignment | ERC | 2024-10-24 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.10.3.3.1( PEDESTAL RELATED WORK) | 206816620
Stretching of foundation bolts and locking of nuts | ERC | 2024-12-01 08:00 | 2024-12-05 17:00 |  |  |  |  | 1.10.3.3.1( PEDESTAL RELATED WORK) | 206816621
HP TURBINE | ERC | 2024-12-22 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816622
HP Turbine: Placement of HP module on temp packers | ERC | 2024-12-22 08:00 | 2024-12-27 17:00 |  |  |  |  | 1.10.3.3.2( HP TURBINE) | 206816623
HP Turbine: Clean main and aux HP bearing, prepare of assembly and installation | ERC | 2024-12-28 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.10.3.3.2( HP TURBINE) | 206816624
HP Turbine: Placing HP module in position, levelling & centering | ERC | 2025-01-09 08:00 | 2025-01-26 17:00 |  |  |  |  | 1.10.3.3.2( HP TURBINE) | 206816625
HP Turbine: Alignment of HP turbine casing radially and axially to the HP shaft & Checking and recordings of journal and coupling dimensions and runout | ERC | 2025-01-27 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.10.3.3.2( HP TURBINE) | 206816626
IP TURBINE | ERC | 2025-02-11 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816627
IP TURBINE: Placement of IP turbine on the temp packers | ERC | 2025-02-11 08:00 | 2025-02-16 17:00 |  |  |  |  | 1.10.3.3.3( IP TURBINE) | 206816628
IP TURBINE: clean main and aux IP bearings, preparation for assembly and installation | ERC | 2025-02-17 08:00 | 2025-02-28 17:00 |  |  |  |  | 1.10.3.3.3( IP TURBINE) | 206816629
IP TURBINE: Setting down IP shaft in the bearings and alignment of the shaft | ERC | 2025-03-01 08:00 | 2025-03-20 17:00 |  |  |  |  | 1.10.3.3.3( IP TURBINE) | 206816630
IP TURBINE: Alignment of the IP casing radially and axially to the IP shaft | ERC | 2025-03-21 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.10.3.3.3( IP TURBINE) | 206816631
LP TURBINE | ERC | 2024-11-08 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816632
LP TURBINE: Placement of Longitudinal Girders and levelling, alignment | ERC | 2024-11-08 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816633
LP TURBINE: Placement & alignment of LP end walls | ERC | 2024-11-28 08:00 | 2024-12-17 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816634
LP TURBINE: Fit up and welding of bracing pipes for LP outer casings | ERC | 2024-12-18 08:00 | 2025-01-06 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816635
LP TURBINE: Placement, alignment, fit up and welding of LP inner-outer casing bottom half | ERC | 2025-01-07 08:00 | 2025-02-01 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816636
LP TURBINE: Temporary mounting of expansion joint | ERC | 2025-02-02 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816637
LP TURBINE: Placement and alignment of LP inner-inner casing bottom half | ERC | 2025-02-12 08:00 | 2025-02-26 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816638
LP TURBINE: Erection of LP shaft sealing assembly on the bearing | ERC | 2025-02-27 08:00 | 2025-03-08 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816639
LP TURBINE: Installation of the LP rotor on the main and aux bearings and alignment | ERC | 2025-03-09 08:00 | 2025-03-19 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816640
LP TURBINE: Checking radial and axial clearances of the rotor with the bearing | ERC | 2025-03-20 08:00 | 2025-03-29 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816641
LP TURBINE: Placement of upper half of the shaft sealing assembly | ERC | 2025-03-30 08:00 | 2025-04-11 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816642
LP TURBINE: Mounting of LP top half of guide blade carrier | ERC | 2025-04-12 08:00 | 2025-04-21 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816643
LP TURBINE: Checking of the radial and axial clearances of LP inner casing | ERC | 2025-04-22 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816644
LP TURBINE: Placement and alignment of the LP top halves | ERC | 2025-05-02 08:00 | 2025-05-10 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816645
LP TURBINE: Drilling and reaming of holes in the Joint plane of the LP outer casing | ERC | 2025-05-11 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.10.3.3.4( LP TURBINE) | 206816646
MISCELLANEOUS ACTIVITIES | ERC | 2025-05-20 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816647
TURB. MISCELLANEOUS ACTIVITIES: Alignment of HP,IP,LPT rotors. | ERC | 2025-05-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | 206816648
TURB. MISCELLANEOUS ACTIVITIES: Coupling LP-IP rotor with Aux. Coupling bolts | ERC | 2025-07-04 08:00 | 2025-08-07 17:00 |  |  |  |  | 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | 206816649
TURB. MISCELLANEOUS ACTIVITIES: Coupling IP-HP rotor and recording swing value. | ERC | 2025-07-04 08:00 | 2025-08-07 17:00 |  |  |  |  | 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | 206816650
TURB. MISCELLANEOUS ACTIVITIES: Reaming honing & machining of coupling bolt | ERC | 2025-07-19 08:00 | 2025-09-05 17:00 |  |  |  |  | 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | 206816651
TURB. MISCELLANEOUS ACTIVITIES: Pre-assembly and welding of LP outer casing | ERC | 2025-08-17 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | 206816652
TURB. MISCELLANEOUS ACTIVITIES: Turbine boxed up | ERC | 2025-09-21 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | 206816653
LUBE OIL SYSTEM | ERC | 2025-01-01 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816654
TURB. LUBE OIL SYSTEM: Cleaning SYSTEM: Cleaning of Main Oil tank | ERC | 2025-01-01 08:00 | 2025-01-30 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816655
TURB. LUBE OIL SYSTEM: Placement of Oil Module | ERC | 2025-01-31 08:00 | 2025-02-24 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816656
TURB. LUBE OIL SYSTEM: Placement of motors and couplings | ERC | 2025-02-25 08:00 | 2025-03-30 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816657
TURB. LUBE OIL SYSTEM: Erection of filters, oil cooler, vapor exhauster etc in the Main oil room | ERC | 2025-03-31 08:00 | 2025-04-29 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816658
TURB. LUBE OIL SYSTEM: Lube oil piping, jacking oil & seal oil piping to bearings and recirculation. | ERC | 2025-04-30 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816659
TURB. LUBE OIL SYSTEM:ERECTION OF OIL PURIFICATION UNIT | ERC | 2025-09-27 08:00 | 2025-10-26 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816660
Turbine: Oil flushing | ERC | 2025-09-27 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.10.3.3.6( LUBE OIL SYSTEM) | 206816661
VALVES | ERC | 2025-03-03 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.10.3.3(Erection) | 206816662
LP BYPASS VALVES | ERC | 2025-07-09 08:00 | 2025-08-22 17:00 |  |  |  |  | 1.10.3.3.7( VALVES) | 206816663
TURB. LP BYPASS Valves: Erection of LP bypass valves | ERC | 2025-07-09 08:00 | 2025-08-22 17:00 |  |  |  |  | 1.10.3.3.7.1( LP BYPASS VALVES) | 206816664
EMERGENCY STOP VALVES | ERC | 2025-03-03 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.10.3.3.7( VALVES) | 206816665
TURB. EMERGENCY STOP Vivisection of main steam stop valves | ERC | 2025-03-03 08:00 | 2025-03-17 17:00 |  |  |  |  | 1.10.3.3.7.2( EMERGENCY STOP VALVES) | 206816666
TURB. EMERGENCY STOP VALVES: Assembly of breech nuts with HP casings | ERC | 2025-03-18 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.10.3.3.7.2( EMERGENCY STOP VALVES) | 206816667
IV CONTROL VALVES | ERC | 2025-04-28 08:00 | 2025-05-10 17:00 |  |  |  |  | 1.10.3.3.7( VALVES) | 206816668
TURB. IV CONTROL VALVES: Assembly of RH stop and control valve | ERC | 2025-04-28 08:00 | 2025-05-10 17:00 |  |  |  |  | 1.10.3.3.7.3( IV CONTROL VALVES) | 206816669
HP BYPASS VALVES | ERC | 2026-03-27 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.10.3.3.7( VALVES) | 206816670
HP BYPASS VALVES: Assembly of HP bypass valves | ERC | 2026-03-27 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.10.3.3.7.4(HP BYPASS VALVES) | 206816671
Generator | ERC | 2022-09-27 08:00 | 2026-04-10 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816672
Civil | ERC | 2025-03-14 17:00 | 2025-08-11 17:00 |  |  |  |  | 1.10.4(Generator) | 206816673
Gas Room Readiness | ERC | 2025-08-11 17:00 | 2025-08-11 17:00 |  |  |  |  | 1.10.4.1(Civil) | 206816674
PW Pump & Filter Foundation | CIV | 2025-03-14 17:00 | 2025-03-14 17:00 |  |  |  |  | 1.10.4.1(Civil) | 206816675
PW cooler foundation | OTH | 2025-03-14 17:00 | 2025-03-14 17:00 |  |  |  |  | 1.10.4.1(Civil) | 206816676
Seal oil unit foundation | OTH | 2025-05-03 17:00 | 2025-05-03 17:00 |  |  |  |  | 1.10.4.1(Civil) | 206816677
Supply | SUP | 2022-09-27 08:00 | 2024-12-27 17:00 |  |  |  |  | 1.10.4(Generator) | 206816678
Foundation Accessories | SUP | 2022-09-27 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816679
Engineering | ENG | 2022-09-27 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.10.4.2.1( Foundation Accessories) | 206816680
Manufacturing | MFG | 2023-09-02 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.10.4.2.1( Foundation Accessories) | 206816681
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.10.4.2.1( Foundation Accessories) | 206816682
Generator Stator | SUP | 2022-09-27 08:00 | 2024-10-10 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816683
Engineering | ENG | 2022-09-27 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.10.4.2.2( Generator Stator) | 206816684
Manufacturing | MFG | 2023-10-17 08:00 | 2024-09-10 17:00 |  |  |  |  | 1.10.4.2.2( Generator Stator) | 206816685
Dispatch | DIS | 2024-09-11 08:00 | 2024-10-10 17:00 |  |  |  |  | 1.10.4.2.2( Generator Stator) | 206816686
Generator Rotor | SUP | 2022-09-27 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816687
Engineering | ENG | 2022-09-27 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.10.4.2.3( Generator Rotor ) | 206816688
Manufacturing | MFG | 2023-11-01 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.10.4.2.3( Generator Rotor ) | 206816689
Dispatch | DIS | 2024-09-26 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.10.4.2.3( Generator Rotor ) | 206816690
Brushless Exciter Set & accessories | SUP | 2022-09-27 08:00 | 2024-10-12 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816691
Engineering | ENG | 2022-09-27 08:00 | 2023-11-23 17:00 |  |  |  |  | 1.10.4.2.4(Brushless Exciter Set & accessories) | 206816692
Manufacturing | MFG | 2023-11-24 08:00 | 2024-08-29 17:00 |  |  |  |  | 1.10.4.2.4(Brushless Exciter Set & accessories) | 206816693
Dispatch | DIS | 2024-08-30 08:00 | 2024-10-12 17:00 |  |  |  |  | 1.10.4.2.4(Brushless Exciter Set & accessories) | 206816694
Gen. completing items | SUP | 2022-09-27 08:00 | 2024-10-07 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816695
Engineering | ENG | 2022-09-27 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.10.4.2.5(Gen. completing items) | 206816696
Manufacturing | MFG | 2023-10-17 08:00 | 2024-08-07 17:00 |  |  |  |  | 1.10.4.2.5(Gen. completing items) | 206816697
Dispatch | DIS | 2024-08-08 08:00 | 2024-10-07 17:00 |  |  |  |  | 1.10.4.2.5(Gen. completing items) | 206816698
Gen. Auxiliaries Systems | SUP | 2022-09-27 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816699
Engineering | ENG | 2022-09-27 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.4.2.6(Gen. Auxiliaries Systems) | 206816700
Manufacturing | MFG | 2023-12-06 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.10.4.2.6(Gen. Auxiliaries Systems) | 206816701
Dispatch | DIS | 2024-10-29 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.4.2.6(Gen. Auxiliaries Systems) | 206816702
TG Piping | SUP | 2022-09-27 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816703
Engineering | ENG | 2022-09-27 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.4.2.7(TG Piping) | 206816704
Manufacturing | MFG | 2023-12-06 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.10.4.2.7(TG Piping) | 206816705
Dispatch | DIS | 2024-10-29 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.4.2.7(TG Piping) | 206816706
PW System equipments | SUP | 2022-09-27 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816707
Engineering | ENG | 2022-09-27 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.4.2.8(PW System equipments) | 206816708
Manufacturing | MFG | 2023-12-06 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.10.4.2.8(PW System equipments) | 206816709
Dispatch | DIS | 2024-10-29 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.10.4.2.8(PW System equipments) | 206816710
Loose instruments | SUP | 2022-09-27 08:00 | 2024-12-27 17:00 |  |  |  |  | 1.10.4.2(Supply) | 206816711
Engineering | ENG | 2022-09-27 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.4.2.9(Loose instruments) | 206816712
Manufacturing | MFG | 2023-12-06 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.10.4.2.9(Loose instruments) | 206816713
Dispatch | DIS | 2024-10-29 08:00 | 2024-12-27 17:00 |  |  |  |  | 1.10.4.2.9(Loose instruments) | 206816714
Erection | ERC | 2024-12-06 08:00 | 2026-04-10 17:00 |  |  |  |  | 1.10.4(Generator) | 206816715
MECHANICAL ASSEMBLY STATOR AND ROTOR | ERC | 2024-12-06 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816716
Checking of foundations | CIV | 2024-12-06 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816717
Setting and alignment of machine sole plates | ERC | 2024-12-21 08:00 | 2025-01-09 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816718
Stator lifting and placement on the foundations | ERC | 2025-03-20 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816719
Visual inspection of rotor and stator | ERC | 2025-04-08 08:00 | 2025-04-17 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816720
Mounting of bushing compartment | ERC | 2025-04-18 08:00 | 2025-05-02 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816721
Insertions and removal of Hydrogen coolers | ERC | 2025-05-03 08:00 | 2025-05-12 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816722
Generator rotor insertion | ERC | 2025-05-13 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816723
Alignment of generator | ERC | 2025-05-23 08:00 | 2025-06-11 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816724
Aligning and coupling the brushless exciter rotor | ERC | 2025-06-12 08:00 | 2025-07-01 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816725
Mounting of generator end shields | ERC | 2025-07-02 08:00 | 2025-07-16 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816726
Generator bearing assembly | ERC | 2025-07-17 08:00 | 2025-07-26 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816727
Alignment with LP rotor | ERC | 2025-07-27 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | 206816728
EXCITATION SYSTEM | ERC | 2024-12-21 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816729
Placement and grouting of foundations plates | CIV | 2024-12-21 08:00 | 2024-12-27 17:00 |  |  |  |  | 1.10.4.3.2( EXCITATION SYSTEM) | 206816730
Physical inspection and placement of excitor components and excitation transformer | ERC | 2025-06-12 08:00 | 2025-07-11 17:00 |  |  |  |  | 1.10.4.3.2( EXCITATION SYSTEM) | 206816731
Gen- exciter rotor alignment and correction | OTH | 2025-07-12 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.10.4.3.2( EXCITATION SYSTEM) | 206816732
PW SYSTEM | ERC | 2025-03-15 08:00 | 2025-08-20 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816733
GEN. PW Mounting of PW skid | ERC | 2025-03-15 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.10.4.3.3( PW SYSTEM) | 206816734
GEN. PW Mounting of alkalizer unit | ERC | 2025-03-25 08:00 | 2025-04-03 17:00 |  |  |  |  | 1.10.4.3.3( PW SYSTEM) | 206816735
GEN. PW alkalizer of PW pipings and recirculation line | ERC | 2025-04-04 08:00 | 2025-05-12 17:00 |  |  |  |  | 1.10.4.3.3( PW SYSTEM) | 206816736
GEN. PW recirculation of PW tanks | ERC | 2025-07-17 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.10.4.3.3( PW SYSTEM) | 206816737
GEN. PW SYSTEM:PW line flushing and cleaning | ERC | 2025-08-06 08:00 | 2025-08-20 17:00 |  |  |  |  | 1.10.4.3.3( PW SYSTEM) | 206816738
SEAL OIL SYSTEM | ERC | 2025-05-04 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816739
GEN. SEAL OIL recirculation of Seal oil unit | ERC | 2025-05-04 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.10.4.3.4( SEAL OIL SYSTEM) | 206816740
GEN. SEAL OIL recirculation of seal oil piping | ERC | 2025-05-21 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.10.4.3.4( SEAL OIL SYSTEM) | 206816741
Oil flushing of lube oil and seal oil sys. | ERC | 2025-11-01 08:00 | 2025-12-11 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816742
Box up of exciter | ERC | 2025-12-12 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816743
Air leak test | ERC | 2026-04-01 08:00 | 2026-04-10 17:00 |  |  |  |  | 1.10.4.3(Erection) | 206816744
Condenser & Vacuum system | OTH | 2022-09-27 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816745
Civil | CIV | 2023-05-05 08:00 | 2024-02-23 17:00 |  |  |  |  | 1.10.5(Condenser & Vacuum system) | 206816746
Condenser Foundation | CIV | 2023-05-05 08:00 | 2024-02-23 17:00 |  |  |  |  | 1.10.5.1(Civil) | 206816747
EXCAVATION | CIV | 2023-05-05 08:00 | 2023-06-03 17:00 |  |  |  |  | 1.10.5.1.1(Condenser Foundation) | 206816748
RCC in substructure including PCC | CIV | 2023-06-04 08:00 | 2023-08-12 17:00 |  |  |  |  | 1.10.5.1.1(Condenser Foundation) | 206816749
RCC in superstructure | CIV | 2023-08-13 08:00 | 2023-12-10 17:00 |  |  |  |  | 1.10.5.1.1(Condenser Foundation) | 206816750
Backfilling & Finishing Work | CIV | 2023-12-11 08:00 | 2024-02-23 17:00 |  |  |  |  | 1.10.5.1.1(Condenser Foundation) | 206816751
Supply | SUP | 2022-09-27 08:00 | 2025-06-22 17:00 |  |  |  |  | 1.10.5(Condenser & Vacuum system) | 206816752
Hot Well and bottom plate | SUP | 2022-09-27 08:00 | 2024-02-11 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816753
Engineering | ENG | 2022-09-27 08:00 | 2023-06-28 17:00 |  |  |  |  | 1.10.5.2.1(Hot Well and bottom plate) | 206816754
Manufacturing | MFG | 2023-06-29 08:00 | 2023-12-28 17:00 |  |  |  |  | 1.10.5.2.1(Hot Well and bottom plate) | 206816755
Dispatch | DIS | 2023-12-29 08:00 | 2024-02-11 17:00 |  |  |  |  | 1.10.5.2.1(Hot Well and bottom plate) | 206816756
Condenser Support | SUP | 2022-09-27 08:00 | 2024-02-11 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816757
Engineering | ENG | 2022-09-27 08:00 | 2023-06-28 17:00 |  |  |  |  | 1.10.5.2.2(Condenser Support) | 206816758
Manufacturing | MFG | 2023-06-29 08:00 | 2023-12-28 17:00 |  |  |  |  | 1.10.5.2.2(Condenser Support) | 206816759
Dispatch | DIS | 2023-12-29 08:00 | 2024-02-11 17:00 |  |  |  |  | 1.10.5.2.2(Condenser Support) | 206816760
Side Walls & Internal details | SUP | 2022-09-27 08:00 | 2024-03-12 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816761
Engineering | ENG | 2022-09-27 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.10.5.2.3(Side Walls & Internal details) | 206816762
Manufacturing | MFG | 2023-07-09 08:00 | 2024-01-27 17:00 |  |  |  |  | 1.10.5.2.3(Side Walls & Internal details) | 206816763
Dispatch | DIS | 2024-01-28 08:00 | 2024-03-12 17:00 |  |  |  |  | 1.10.5.2.3(Side Walls & Internal details) | 206816764
Water box & Water chamber | SUP | 2022-09-27 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816765
Engineering | ENG | 2022-09-27 08:00 | 2023-08-12 17:00 |  |  |  |  | 1.10.5.2.4(Water box & Water chamber) | 206816766
Manufacturing | MFG | 2023-08-13 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.10.5.2.4(Water box & Water chamber) | 206816767
Dispatch | DIS | 2024-03-30 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.5.2.4(Water box & Water chamber) | 206816768
Dome Walls & Dome internals | SUP | 2022-09-27 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816769
Engineering | ENG | 2022-09-27 08:00 | 2023-08-12 17:00 |  |  |  |  | 1.10.5.2.5(Dome Walls & Dome internals) | 206816770
Manufacturing | MFG | 2023-08-13 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.10.5.2.5(Dome Walls & Dome internals) | 206816771
Dispatch | DIS | 2024-03-30 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.10.5.2.5(Dome Walls & Dome internals) | 206816772
LPH-1 supports & other Condenser loose items | SUP | 2022-09-27 08:00 | 2024-07-13 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816773
Engineering | ENG | 2022-09-27 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.10.5.2.6(LPH-1 supports & other Condenser loose items ) | 206816774
Manufacturing | MFG | 2023-09-27 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.10.5.2.6(LPH-1 supports & other Condenser loose items ) | 206816775
Dispatch | DIS | 2024-05-30 08:00 | 2024-07-13 17:00 |  |  |  |  | 1.10.5.2.6(LPH-1 supports & other Condenser loose items ) | 206816776
Gland Steam Condenser & LPH-1 | SUP | 2022-09-27 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816777
Engineering | ENG | 2022-09-27 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.10.5.2.7(Gland Steam Condenser & LPH-1) | 206816778
Manufacturing | MFG | 2023-09-27 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.10.5.2.7(Gland Steam Condenser & LPH-1) | 206816779
Dispatch | DIS | 2024-05-30 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.10.5.2.7(Gland Steam Condenser & LPH-1) | 206816780
Loose items of GSC & LPH-1 | SUP | 2022-09-27 08:00 | 2024-08-12 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816781
Engineering | ENG | 2022-09-27 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.10.5.2.8(Loose items of GSC & LPH-1) | 206816782
Manufacturing | MFG | 2023-10-07 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.10.5.2.8(Loose items of GSC & LPH-1) | 206816783
Dispatch | DIS | 2024-06-29 08:00 | 2024-08-12 17:00 |  |  |  |  | 1.10.5.2.8(Loose items of GSC & LPH-1) | 206816784
Condenser Instruments | SUP | 2022-09-27 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816785
Engineering | ENG | 2022-09-27 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.10.5.2.9(Condenser Instruments) | 206816786
Manufacturing | MFG | 2023-09-27 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.10.5.2.9(Condenser Instruments) | 206816787
Dispatch | DIS | 2024-05-30 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.10.5.2.9(Condenser Instruments) | 206816788
BPL - RE Joints | SUP | 2023-08-28 08:00 | 2025-04-12 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816789
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-08-28 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.10.5.2.10(BPL - RE Joints) | 206816790
Manufacturing & TESTING | MFG | 2024-04-14 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.10.5.2.10(BPL - RE Joints) | 206816791
Dispatch | DIS | 2025-02-12 08:00 | 2025-03-13 17:00 |  |  |  |  | 1.10.5.2.10(BPL - RE Joints) | 206816792
RECEIPT AT SITE | REC | 2025-03-14 08:00 | 2025-04-12 17:00 |  |  |  |  | 1.10.5.2.10(BPL - RE Joints) | 206816793
BPL - Flash Tank | SUP | 2023-05-27 08:00 | 2025-06-22 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816794
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-05-27 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.10.5.2.11(BPL - Flash Tank) | 206816795
Manufacturing & TESTING | MFG | 2024-04-24 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.10.5.2.11(BPL - Flash Tank) | 206816796
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.10.5.2.11(BPL - Flash Tank) | 206816797
RECEIPT AT SITE | REC | 2025-05-24 08:00 | 2025-06-22 17:00 |  |  |  |  | 1.10.5.2.11(BPL - Flash Tank) | 206816798
BPL - Misc. Tank | SUP | 2023-05-27 08:00 | 2025-03-11 17:00 |  |  |  |  | 1.10.5.2(Supply) | 206816799
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-05-27 08:00 | 2024-02-25 17:00 |  |  |  |  | 1.10.5.2.12(BPL - Misc. Tank) | 206816800
Manufacturing & TESTING | MFG | 2024-02-26 08:00 | 2025-01-10 17:00 |  |  |  |  | 1.10.5.2.12(BPL - Misc. Tank) | 206816801
Dispatch | DIS | 2025-01-11 08:00 | 2025-02-09 17:00 |  |  |  |  | 1.10.5.2.12(BPL - Misc. Tank) | 206816802
RECEIPT AT SITE | REC | 2025-02-10 08:00 | 2025-03-11 17:00 |  |  |  |  | 1.10.5.2.12(BPL - Misc. Tank) | 206816803
Erection | ERC | 2024-07-29 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.10.5(Condenser & Vacuum system) | 206816804
Condenser: Checking and corrections of foundations | ERC | 2024-07-29 08:00 | 2024-07-31 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816805
Condenser: Prepn. Of foundation. & packer plate grouting. | ERC | 2024-08-01 08:00 | 2024-08-10 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816806
Condenser: Pre-Assy of Bottom plate with hot well & Springs. | ERC | 2024-08-01 08:00 | 2024-08-30 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816807
Condenser: Water Box/water chamber pre-ASSY & welding. | ERC | 2024-08-11 08:00 | 2024-08-30 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816808
Condenser: Pre-Assy of side walls. | ERC | 2024-08-11 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816809
Condenser: Bottom plate Lowering, Levelling & Centering w.r.t LPT . | ERC | 2024-09-02 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816810
Condenser: TSP Hole cleaning | ERC | 2024-09-27 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816811
Condenser: Ern. Of FWC,RWC & side walls and shell formation. | ERC | 2024-10-17 08:00 | 2024-10-31 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816812
Condenser: Lower Dome walls pre - assy. | ERC | 2024-10-17 08:00 | 2024-11-25 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816813
Condenser: Dome stiffening structure (Middle Zone) pre-assembly. | ERC | 2024-10-27 08:00 | 2024-12-05 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816814
Condenser: Erection of TSP's, alignment & Ern. Of shell internals. | ERC | 2024-11-11 08:00 | 2024-12-20 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816815
Condenser: Ern of Lower dome walls (4 sides) & alignment. | ERC | 2024-11-26 08:00 | 2024-12-25 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816816
Condenser: Welding of TSP's and other shell Internals. | ERC | 2024-08-31 08:00 | 2024-10-14 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816817
Condenser: Lower dome walls (4 sides) welding COMPLETION. | ERC | 2024-12-28 08:00 | 2025-02-05 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816818
Condenser: Lowering of dome stiffening structure, levelling & welding. | ERC | 2025-02-06 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816819
Condenser: Cond. Tubing / Tube insertion. | ERC | 2025-02-08 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816820
Condenser: TUBE EXPANSION. | ERC | 2025-02-23 08:00 | 2025-04-08 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816821
Condenser: Pre-assembly of Upper dome walls. | ERC | 2025-02-06 08:00 | 2025-03-02 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816822
Condenser: Ern. Of upper dome wall (front & rear). | ERC | 2025-03-05 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816823
Condenser: Laying Temp. line for filling water in steam space. | ERC | 2025-04-11 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816824
Condenser: LEAK TEST (SHELL SIDE) | ERC | 2025-04-09 08:00 | 2025-04-13 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816825
Condenser: Sand blasting and W. box/W. Chamber painting . | ERC | 2025-04-14 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816826
Condenser: Sand blasting and painting of water chambers. | ERC | 2025-04-24 08:00 | 2025-05-18 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816827
Chamber of water box and tightening of bolts. | ERC | 2025-05-19 08:00 | 2025-06-12 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816828
Condenser: Hydro TEST (C.W.SIDE). | ERC | 2025-06-16 08:00 | 2025-06-25 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816829
Condenser: FLOATING & NECK WELDING. | ERC | 2025-06-28 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816830
Condenser: C.W. Piping (A row to cond.) & R.E Joints. | ERC | 2025-05-09 08:00 | 2025-07-22 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816831
Condenser: Extraction Piping inside Condenser. | ERC | 2025-06-26 08:00 | 2025-08-09 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816832
Condenser: Dome stiffening piping (upper dome) & welding. | ERC | 2025-07-23 08:00 | 2025-08-11 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816833
Condenser: Assy. Of Stand Pipes, all fittings & other instruments. | ERC | 2025-08-12 08:00 | 2025-08-26 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816834
Condenser: C.W. CHARGING. | ERC | 2025-08-30 08:00 | 2025-09-08 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816835
Condenser: Measurement of spring height & grouting. | ERC | 2025-09-09 08:00 | 2025-09-13 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816836
Condenser: Scraps cuttings, grindings. / finishings | ERC | 2025-09-14 08:00 | 2025-09-18 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816837
Erection of Vacuum Pump with associated piping | ERC | 2025-07-23 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816838
Erection of Gland Steam Condenser and associated piping | ERC | 2025-07-23 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816839
Erection of Flash tank, Flash box, drain cooler & G.S.C. | ERC | 2025-08-12 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816840
Other Misc. Piping like Control fluid, Drain & vent piping, Instrument & Service air etc. | ERC | 2025-08-12 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.10.5.3(Erection) | 206816841
Power Cycle Pumps | ERC | 2022-09-27 08:00 | 2026-02-10 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816842
Turbine Driven Boiler Feed Pump & Booster Pump | ERC | 2022-09-27 08:00 | 2026-02-10 17:00 |  |  |  |  | 1.10.6(Power Cycle Pumps) | 206816843
Civil | CIV | 2024-10-17 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.10.6.1(Turbine Driven Boiler Feed Pump & Booster Pump) | 206816844
First TDBFP Foundation | CIV | 2024-10-17 08:00 | 2025-01-12 17:00 |  |  |  |  | 1.10.6.1.1(Civil) | 206816845
Columns & piping, Instrument & Welding Work | ERC | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.10.6.1.1.1(First TDBFP Foundation) | 206816846
Platform For TDBFP Foundation | CIV | 2024-11-16 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.10.6.1.1.1(First TDBFP Foundation) | 206816847
RCC Foundation Casting work | CIV | 2024-12-14 08:00 | 2025-01-12 17:00 |  |  |  |  | 1.10.6.1.1.1(First TDBFP Foundation) | 206816848
Second TDBFP Foundation | CIV | 2024-11-12 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.10.6.1.1(Civil) | 206816849
Columns & piping, Instrument & Welding Work | CIV | 2024-11-12 08:00 | 2024-12-11 17:00 |  |  |  |  | 1.10.6.1.1.2(Second TDBFP Foundation) | 206816850
Platform For TDBFP Foundation | CIV | 2024-12-12 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.10.6.1.1.2(Second TDBFP Foundation) | 206816851
RCC Foundation Casting work | CIV | 2025-01-09 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.10.6.1.1.2(Second TDBFP Foundation) | 206816852
Supply | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1(Turbine Driven Boiler Feed Pump & Booster Pump) | 206816853
HYD- TURBINE DRIVEN BOOSTER PUMP | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2(Supply) | 206816854
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.1.2.1(HYD- TURBINE DRIVEN BOOSTER PUMP) | 206816855
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.1.2.1(HYD- TURBINE DRIVEN BOOSTER PUMP) | 206816856
ASSEMBLY & TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.6.1.2.1(HYD- TURBINE DRIVEN BOOSTER PUMP) | 206816857
Dispatch OF TDBP AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2.1(HYD- TURBINE DRIVEN BOOSTER PUMP) | 206816858
HYD- TURBINE DRIVEN BOILER FEED PUMP | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2(Supply) | 206816859
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.1.2.2(HYD- TURBINE DRIVEN BOILER FEED PUMP) | 206816860
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.1.2.2(HYD- TURBINE DRIVEN BOILER FEED PUMP) | 206816861
ASSEMBLY & TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.6.1.2.2(HYD- TURBINE DRIVEN BOILER FEED PUMP) | 206816862
Dispatch OF TDBFP AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2.2(HYD- TURBINE DRIVEN BOILER FEED PUMP) | 206816863
HYD- BFP DRIVE TURBINE | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2(Supply) | 206816864
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.1.2.3(HYD- BFP DRIVE TURBINE) | 206816865
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.1.2.3(HYD- BFP DRIVE TURBINE) | 206816866
ASSEMBLY & TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.6.1.2.3(HYD- BFP DRIVE TURBINE) | 206816867
Dispatch OF DRIVE TURBINE AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2.3(HYD- BFP DRIVE TURBINE) | 206816868
HYD- BFP DT LUB OIL SYSTEM | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2(Supply) | 206816869
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.1.2.4(HYD- BFP DT LUB OIL SYSTEM) | 206816870
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.1.2.4(HYD- BFP DT LUB OIL SYSTEM) | 206816871
ASSEMBLY & TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.6.1.2.4(HYD- BFP DT LUB OIL SYSTEM) | 206816872
Dispatch OF LUBE OIL SYSTEM AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.1.2.4(HYD- BFP DT LUB OIL SYSTEM) | 206816873
Erection | ERC | 2025-02-10 08:00 | 2026-02-10 17:00 |  |  |  |  | 1.10.6.1(Turbine Driven Boiler Feed Pump & Booster Pump) | 206816874
First TURBINE DRIVEN BFP | ERC | 2025-02-10 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.10.6.1.3(Erection) | 206816875
Foundation checking and correction | CIV | 2025-02-10 08:00 | 2025-02-15 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816876
Placement of sole plates and grouting | ERC | 2025-02-16 08:00 | 2025-02-25 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816877
Placement of turbine assembly on the sole plates and alignment | ERC | 2025-02-26 08:00 | 2025-03-22 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816878
Erection of inlet and exhaust piping | ERC | 2025-03-23 08:00 | 2025-04-03 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816879
Erection of gland sealing system and connecting piping | ERC | 2025-04-04 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816880
Erection and grouting of governing system and control valves | ERC | 2025-04-24 08:00 | 2025-05-13 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816881
Placement and alignment of booster pump and gearbox | ERC | 2025-05-14 08:00 | 2025-05-28 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816882
Placement of BFP | ERC | 2025-05-29 08:00 | 2025-06-12 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816883
Grouting of all equipments | ERC | 2025-06-13 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816884
Erection and fit ups of inlet and exhaust of BP and BFP | ERC | 2025-07-13 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816885
Erection of oil tanks, filters, collars and grouting | ERC | 2025-08-06 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816886
Erection of AOP, JOP, EOP and alignment | ERC | 2025-08-30 08:00 | 2025-09-23 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816887
Lube oil piping and governing oil piping | ERC | 2025-09-24 08:00 | 2025-12-22 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816888
Seal water and cooling water piping | ERC | 2025-12-23 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | 206816889
Second TURBINE DRIVEN BFP | ERC | 2025-03-08 08:00 | 2026-02-10 17:00 |  |  |  |  | 1.10.6.1.3(Erection) | 206816890
Foundation checking and correction | CIV | 2025-03-08 08:00 | 2025-03-13 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816891
Placement of sole plates and grouting | ERC | 2025-03-14 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816892
Placement of turbine assembly on the sole plates and alignment | ERC | 2025-03-24 08:00 | 2025-04-17 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816893
Erection of inlet and exhaust piping | ERC | 2025-04-18 08:00 | 2025-04-29 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816894
Erection of gland sealing system and connecting piping | ERC | 2025-04-30 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816895
Erection and grouting of governing system and control valves | ERC | 2025-05-20 08:00 | 2025-06-08 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816896
Placement and alignment of booster pump and gearbox | ERC | 2025-06-09 08:00 | 2025-06-23 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816897
Placement of BFP | ERC | 2025-06-24 08:00 | 2025-07-08 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816898
Grouting of all equipments | ERC | 2025-07-09 08:00 | 2025-08-07 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816899
Erection and fit ups of inlet and exhaust of BP and BFP | ERC | 2025-08-08 08:00 | 2025-08-31 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816900
Erection of oil tanks, filters, collars and grouting | ERC | 2025-09-01 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816901
Erection of AOP, JOP, EOP and alignment | ERC | 2025-09-25 08:00 | 2025-10-19 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816902
Lube oil piping and governing oil piping | ERC | 2025-10-20 08:00 | 2026-01-17 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816903
Seal water and cooling water piping | ERC | 2026-01-18 08:00 | 2026-02-10 17:00 |  |  |  |  | 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | 206816904
Motor Driven Boiler Feed Pumps and Booster Pumps | ERC | 2022-09-27 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.10.6(Power Cycle Pumps) | 206816905
Civil | CIV | 2024-11-02 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.10.6.2(Motor Driven Boiler Feed Pumps and Booster Pumps) | 206816906
MDBFP Foundation | CIV | 2024-11-02 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.10.6.2.1(Civil) | 206816907
Columns & governing & Welding Work | CIV | 2024-11-02 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.10.6.2.1.1(MDBFP Foundation) | 206816908
Platform For MDBFP Foundation | CIV | 2024-11-17 08:00 | 2024-12-08 17:00 |  |  |  |  | 1.10.6.2.1.1(MDBFP Foundation) | 206816909
RCC Foundation Casting work | CIV | 2024-12-09 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.10.6.2.1.1(MDBFP Foundation) | 206816910
Supply | SUP | 2022-09-27 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.10.6.2(Motor Driven Boiler Feed Pumps and Booster Pumps) | 206816911
HYD - MOTOR DRIVEN BOOSTER PUMP | SUP | 2022-09-27 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.10.6.2.2(Supply) | 206816912
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.2.2.1(HYD - MOTOR DRIVEN BOOSTER PUMP) | 206816913
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.2.2.1(HYD - MOTOR DRIVEN BOOSTER PUMP) | 206816914
ASSEMBLY & TESTING | MFG | 2024-04-15 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.10.6.2.2.1(HYD - MOTOR DRIVEN BOOSTER PUMP) | 206816915
Dispatch OF MDBP AND ALL ASSOCIATED ITEMS | DIS | 2024-08-02 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.10.6.2.2.1(HYD - MOTOR DRIVEN BOOSTER PUMP) | 206816916
HYD - MOTOR DRIVEN BOILER FEED PUMP | SUP | 2022-09-27 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.10.6.2.2(Supply) | 206816917
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.2.2.2(HYD - MOTOR DRIVEN BOILER FEED PUMP) | 206816918
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.2.2.2(HYD - MOTOR DRIVEN BOILER FEED PUMP) | 206816919
ASSEMBLY & TESTING | MFG | 2024-04-15 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.10.6.2.2.2(HYD - MOTOR DRIVEN BOILER FEED PUMP) | 206816920
Dispatch OF MDBFP AND ALL ASSOCIATED ITEMS | DIS | 2024-08-02 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.10.6.2.2.2(HYD - MOTOR DRIVEN BOILER FEED PUMP) | 206816921
BPL - BFP Motor | SUP | 2023-07-27 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.10.6.2.2(Supply) | 206816922
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-07-27 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.10.6.2.2.3(BPL - BFP Motor) | 206816923
Manufacturing & TESTING | MFG | 2024-05-10 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.10.6.2.2.3(BPL - BFP Motor) | 206816924
Dispatch | DIS | 2024-12-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.10.6.2.2.3(BPL - BFP Motor) | 206816925
Erection | ERC | 2025-02-05 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.10.6.2(Motor Driven Boiler Feed Pumps and Booster Pumps) | 206816926
Foundation checking and correction | CIV | 2025-02-05 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816927
Placement and alignment of booster pump and motor | ERC | 2025-02-11 08:00 | 2025-02-16 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816928
Placement and alignment of coupling and BFP | ERC | 2025-02-17 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816929
Bolting of equipments and grouting | ERC | 2025-02-23 08:00 | 2025-03-06 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816930
Erection of oil pumps and grouting | ERC | 2025-03-07 08:00 | 2025-03-22 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816931
Erection of oil tanks and centrifuge | ERC | 2025-03-23 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816932
Erection of LO and WO coolers | ERC | 2025-04-08 08:00 | 2025-04-17 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816933
Lube oil and working oil piping | ERC | 2025-04-18 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816934
Seal water and colling water piping | ERC | 2025-05-04 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816935
Erection of discharge and suction piping and valves | ERC | 2025-05-20 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.10.6.2.3(Erection) | 206816936
Condensate Extraction Pump | ERC | 2022-09-27 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.10.6(Power Cycle Pumps) | 206816937
Civil | CIV | 2023-10-13 08:00 | 2024-08-05 17:00 |  |  |  |  | 1.10.6.3(Condensate Extraction Pump) | 206816938
CEP FOUNDATION: Excavation & PCC | CIV | 2023-10-13 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.10.6.3.1(Civil) | 206816939
CEP FOUNDATION: RCC Raft | CIV | 2023-12-12 08:00 | 2024-02-29 17:00 |  |  |  |  | 1.10.6.3.1(Civil) | 206816940
CEP FOUNDATION: RCC Circular Wall | CIV | 2024-03-08 08:00 | 2024-07-05 17:00 |  |  |  |  | 1.10.6.3.1(Civil) | 206816941
CEP FOUNDATION: Finishing works | CIV | 2024-07-06 08:00 | 2024-08-05 17:00 |  |  |  |  | 1.10.6.3.1(Civil) | 206816942
Supply | SUP | 2022-09-27 08:00 | 2025-03-22 17:00 |  |  |  |  | 1.10.6.3(Condensate Extraction Pump) | 206816943
HYD -Condensate EXTRACT PUMP | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.3.2(Supply) | 206816944
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.3.2.1(HYD -Condensate EXTRACT PUMP) | 206816945
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.3.2.1(HYD -Condensate EXTRACT PUMP) | 206816946
ASSEMBLY & TESTING | OTH | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.6.3.2.1(HYD -Condensate EXTRACT PUMP) | 206816947
Dispatch OF CEP AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.3.2.1(HYD -Condensate EXTRACT PUMP) | 206816948
HYD - DRIP PUMP | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.3.2(Supply) | 206816949
Engineering & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.6.3.2.2(HYD - DRIP PUMP) | 206816950
Manufacturing | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.6.3.2.2(HYD - DRIP PUMP) | 206816951
ASSEMBLY & TESTING | OTH | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.6.3.2.2(HYD - DRIP PUMP) | 206816952
Dispatch OF DRIP PUMP AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.6.3.2.2(HYD - DRIP PUMP) | 206816953
BPL - CEP Motor | SUP | 2023-06-26 08:00 | 2025-03-22 17:00 |  |  |  |  | 1.10.6.3.2(Supply) | 206816954
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-06-26 08:00 | 2024-03-23 17:00 |  |  |  |  | 1.10.6.3.2.3(BPL - CEP Motor) | 206816955
Manufacturing & TESTING | MFG | 2024-03-24 08:00 | 2025-01-21 17:00 |  |  |  |  | 1.10.6.3.2.3(BPL - CEP Motor) | 206816956
Dispatch | DIS | 2025-01-22 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.10.6.3.2.3(BPL - CEP Motor) | 206816957
RECEIPT AT SITE | REC | 2025-02-21 08:00 | 2025-03-22 17:00 |  |  |  |  | 1.10.6.3.2.3(BPL - CEP Motor) | 206816958
Erection | ERC | 2024-08-06 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.10.6.3(Condensate Extraction Pump) | 206816959
Checking and correction of foundations/ pit inspection | ERC | 2024-08-06 08:00 | 2024-08-20 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816960
Placement of frame, cannister | ERC | 2024-11-09 08:00 | 2024-12-23 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816961
Erection and alignment of main pump assembly | ERC | 2024-12-24 08:00 | 2025-02-06 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816962
Maintaining the verticality and alignment of pump with cannister | ERC | 2025-02-07 08:00 | 2025-03-08 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816963
Assembly of bearings and filling oil | ERC | 2025-03-09 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816964
Fit up of the suction and discharge piping pieces | ERC | 2025-04-23 08:00 | 2025-06-06 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816965
releasing the pump on the suction and discharge piping | ERC | 2025-06-07 08:00 | 2025-07-01 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816966
Fixing of coupling and placement of motor | ERC | 2025-07-02 08:00 | 2025-07-26 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816967
Erection of cooling water and seal water piping | ERC | 2025-07-27 08:00 | 2025-09-09 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816968
Mechanical Cleaning of suction and discharge piping | ERC | 2025-09-10 08:00 | 2025-10-09 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816969
piping hangers values calibrated | ERC | 2025-10-10 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.10.6.3.3(Erection) | 206816970
Misc. Horizontal Pump | ERC | 2023-08-03 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206816971
Civil | CIV | 2024-10-06 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.7(Misc. Horizontal Pump) | 206816972
Boiler Fill Pump & Hot well Make up Pump Foundation | CIV | 2024-10-06 08:00 | 2024-12-03 17:00 |  |  |  |  | 1.10.7.1(Civil) | 206816973
Boiler Fill Pump & Hot well Make up Pump Foundation: EXCAVATION | CIV | 2024-10-06 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.10.7.1.1( Boiler Fill Pump & Hot well Make up Pump Foundation) | 206816974
Boiler Fill Pump & Hot well Make up Pump Foundation: RCC in substructure including PCC | CIV | 2024-10-16 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.10.7.1.1( Boiler Fill Pump & Hot well Make up Pump Foundation) | 206816975
Boiler Fill Pump & Hot well Make up Pump Foundation: RCC in superstructure | CIV | 2024-10-31 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.10.7.1.1( Boiler Fill Pump & Hot well Make up Pump Foundation) | 206816976
Boiler Fill Pump & Hot well Make up Pump Foundation: Backfilling | CIV | 2024-11-25 08:00 | 2024-11-30 17:00 |  |  |  |  | 1.10.7.1.1( Boiler Fill Pump & Hot well Make up Pump Foundation) | 206816977
Boiler Fill Pump & Hot well Make up Pump Foundation: Finishing works | CIV | 2024-12-01 08:00 | 2024-12-03 17:00 |  |  |  |  | 1.10.7.1.1( Boiler Fill Pump & Hot well Make up Pump Foundation) | 206816978
SG DMCW Pump foundation | CIV | 2024-12-15 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.10.7.1(Civil) | 206816979
SG DMCW Pump foundation: EXCAVATION | CIV | 2024-12-15 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.10.7.1.2( SG DMCW Pump foundation) | 206816980
SG DMCW Pump foundation: RCC in substructure including PCC | CIV | 2025-01-04 08:00 | 2025-01-28 17:00 |  |  |  |  | 1.10.7.1.2( SG DMCW Pump foundation) | 206816981
SG DMCW Pump foundation: RCC in superstructure | CIV | 2025-01-29 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.10.7.1.2( SG DMCW Pump foundation) | 206816982
SG DMCW Pump foundation: Backfilling | CIV | 2025-03-05 08:00 | 2025-03-11 17:00 |  |  |  |  | 1.10.7.1.2( SG DMCW Pump foundation) | 206816983
SG DMCW Pump foundation: Finishing works | CIV | 2025-03-12 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.10.7.1.2( SG DMCW Pump foundation) | 206816984
TG DMCW Pump foundation: EXCAVATION | CIV | 2024-12-15 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.7.1(Civil) | 206816985
TG DMCW Pump foundation: RCC in substructure including PCC | CIV | 2024-12-15 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.10.7.1.3( TG DMCW Pump foundation: EXCAVATION) | 206816986
TG DMCW Pump foundation: RCC in superstructure | CIV | 2025-01-09 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.10.7.1.3( TG DMCW Pump foundation: EXCAVATION) | 206816987
TG DMCW Pump foundation: Backfilling | CIV | 2025-02-13 08:00 | 2025-02-19 17:00 |  |  |  |  | 1.10.7.1.3( TG DMCW Pump foundation: EXCAVATION) | 206816988
TG DMCW Pump foundation: Finishing works | CIV | 2025-02-20 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.7.1.3( TG DMCW Pump foundation: EXCAVATION) | 206816989
ACW Pump foundation: EXCAVATION | CIV | 2024-12-15 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.7.1(Civil) | 206816990
ACW Pump foundation: RCC in substructure including PCC | CIV | 2024-12-15 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.10.7.1.4( ACW Pump foundation: EXCAVATION) | 206816991
ACW Pump foundation: RCC in superstructure | CIV | 2025-01-09 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.10.7.1.4( ACW Pump foundation: EXCAVATION) | 206816992
ACW Pump foundation: Backfilling | CIV | 2025-02-13 08:00 | 2025-02-19 17:00 |  |  |  |  | 1.10.7.1.4( ACW Pump foundation: EXCAVATION) | 206816993
ACW Pump foundation: Finishing works | CIV | 2025-02-20 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.7.1.4( ACW Pump foundation: EXCAVATION) | 206816994
Supply (BHEL PEM) | SUP | 2023-08-03 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.10.7(Misc. Horizontal Pump) | 206816995
Ordering | ORD | 2023-08-03 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.10.7.2(Supply (BHEL PEM)) | 206816996
Detailed Engineering | ENG | 2023-11-01 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.10.7.2(Supply (BHEL PEM)) | 206816997
Manufacturing | MFG | 2024-03-30 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.10.7.2(Supply (BHEL PEM)) | 206816998
Dispatch | DIS | 2024-08-27 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.10.7.2(Supply (BHEL PEM)) | 206816999
Erection | ERC | 2024-12-04 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.10.7(Misc. Horizontal Pump) | 206817000
Erection of Boiler Fill Pump & Associated piping | ERC | 2024-12-04 08:00 | 2025-02-01 17:00 |  |  |  |  | 1.10.7.3(Erection) | 206817001
Erection of Hotwell make up Pump and Associated Piping | ERC | 2024-12-04 08:00 | 2025-02-01 17:00 |  |  |  |  | 1.10.7.3(Erection) | 206817002
Erection of SG DMCW pump & Associated Piping | ERC | 2025-03-26 08:00 | 2025-08-07 17:00 |  |  |  |  | 1.10.7.3(Erection) | 206817003
Erection of TG DMCW Pump & Associated Piping | ERC | 2025-05-27 08:00 | 2025-09-28 17:00 |  |  |  |  | 1.10.7.3(Erection) | 206817004
Erection of ACW Pump & Associated Piping | ERC | 2025-05-27 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.10.7.3(Erection) | 206817005
HP/LP Heaters & Deaerator | SUP | 2022-09-27 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206817006
HP Heaters | SUP | 2022-09-27 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.10.8(HP/LP Heaters & Deaerator) | 206817007
Civil | CIV | 2025-02-26 08:00 | 2025-03-21 17:00 |  |  |  |  | 1.10.8.1(HP Heaters) | 206817008
HP Heaters Footing: RCC | CIV | 2025-02-26 08:00 | 2025-03-11 17:00 |  |  |  |  | 1.10.8.1.1(Civil) | 206817009
HP Heaters Pedestals with pockets | CIV | 2025-03-12 08:00 | 2025-03-21 17:00 |  |  |  |  | 1.10.8.1.1(Civil) | 206817010
Supply | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.1(HP Heaters) | 206817011
HYD - HP Heaters | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.1.2(Supply) | 206817012
ENGINEERING & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.8.1.2.1(HYD - HP Heaters) | 206817013
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.8.1.2.1(HYD - HP Heaters) | 206817014
ASSEMBLY& TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.8.1.2.1(HYD - HP Heaters) | 206817015
Dispatch OF HP HEATER AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.1.2.1(HYD - HP Heaters) | 206817016
Erection | ERC | 2025-04-12 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.10.8.1(HP Heaters) | 206817017
Placement & alignment of HP Heaters | ERC | 2025-04-12 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.10.8.1.3(Erection) | 206817018
LP Heaters | SUP | 2022-09-27 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.8(HP/LP Heaters & Deaerator) | 206817019
Civil | CIV | 2025-02-12 08:00 | 2025-03-07 17:00 |  |  |  |  | 1.10.8.2(LP Heaters) | 206817020
LP Heaters Footing: RCC | CIV | 2025-02-12 08:00 | 2025-02-25 17:00 |  |  |  |  | 1.10.8.2.1( Civil) | 206817021
LP Heaters Pedestals with pockets | CIV | 2025-02-26 08:00 | 2025-03-07 17:00 |  |  |  |  | 1.10.8.2.1( Civil) | 206817022
Supply | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.2(LP Heaters) | 206817023
HYD - LP Heaters | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.2.2(Supply) | 206817024
ENGINEERING & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.8.2.2.1( HYD - LP Heaters) | 206817025
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.8.2.2.1( HYD - LP Heaters) | 206817026
ASSEMBLY& TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.8.2.2.1( HYD - LP Heaters) | 206817027
Dispatch OF LP HEATER AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.2.2.1( HYD - LP Heaters) | 206817028
Erection | ERC | 2025-05-02 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.8.2(LP Heaters) | 206817029
Placement & alignment of LP Heaters | ERC | 2025-05-02 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.10.8.2.3(Erection) | 206817030
Deaerator | SUP | 2022-09-27 08:00 | 2024-12-28 17:00 |  |  |  |  | 1.10.8(HP/LP Heaters & Deaerator) | 206817031
Civil | CIV | 2024-08-16 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.10.8.3(Deaerator) | 206817032
Deaerator Footing: RCC | CIV | 2024-08-16 08:00 | 2024-08-30 17:00 |  |  |  |  | 1.10.8.3.1( Civil) | 206817033
Deaerator Pedestals with pockets & insert | CIV | 2024-08-31 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.10.8.3.1( Civil) | 206817034
Supply | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.3(Deaerator) | 206817035
HYD - Deaerator | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.3.2(Supply) | 206817036
ENGINEERING & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.8.3.2.1( HYD - Deaerator) | 206817037
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.8.3.2.1( HYD - Deaerator) | 206817038
ASSEMBLY& TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.8.3.2.1( HYD - Deaerator) | 206817039
Dispatch OF DEAERATOR AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.3.2.1( HYD - Deaerator) | 206817040
HYD - Drain Cooler | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.3.2(Supply) | 206817041
ENGINEERING & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.10.8.3.2.2( HYD - Drain Cooler) | 206817042
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.10.8.3.2.2( HYD - Drain Cooler) | 206817043
ASSEMBLY& TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.10.8.3.2.2( HYD - Drain Cooler) | 206817044
Dispatch OF DRAIN COOLER AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.10.8.3.2.2( HYD - Drain Cooler) | 206817045
Erection | ERC | 2024-10-20 08:00 | 2024-12-28 17:00 |  |  |  |  | 1.10.8.3(Deaerator) | 206817046
Lifting and placement of De-aerator and Feed Storage Tank with fittings and associated platform | ERC | 2024-10-20 08:00 | 2024-11-03 17:00 |  |  |  |  | 1.10.8.3.3(Erection) | 206817047
Welding of FST shells | ERC | 2024-11-04 08:00 | 2024-12-18 17:00 |  |  |  |  | 1.10.8.3.3(Erection) | 206817048
Erection of drain cooler | ERC | 2024-12-19 08:00 | 2024-12-28 17:00 |  |  |  |  | 1.10.8.3.3(Erection) | 206817049
Dosing System | SUP | 2023-08-23 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206817050
Chemical Dosing System | SUP | 2023-08-23 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.10.9(Dosing System) | 206817051
Civil | CIV | 2025-03-07 08:00 | 2025-04-10 17:00 |  |  |  |  | 1.10.9.1(Chemical Dosing System) | 206817052
EXCAVATION | CIV | 2025-03-07 08:00 | 2025-03-11 17:00 |  |  |  |  | 1.10.9.1.1(Civil) | 206817053
RCC in substructure including PCC | CIV | 2025-03-12 08:00 | 2025-03-21 17:00 |  |  |  |  | 1.10.9.1.1(Civil) | 206817054
RCC in superstructure | CIV | 2025-03-22 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.10.9.1.1(Civil) | 206817055
Backfilling | CIV | 2025-04-01 08:00 | 2025-04-05 17:00 |  |  |  |  | 1.10.9.1.1(Civil) | 206817056
Finishing works | CIV | 2025-04-06 08:00 | 2025-04-10 17:00 |  |  |  |  | 1.10.9.1.1(Civil) | 206817057
Supply (BHEL PEM) | SUP | 2023-08-23 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.10.9.1(Chemical Dosing System) | 206817058
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.10.9.1.2(Supply (BHEL PEM)) | 206817059
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.10.9.1.2(Supply (BHEL PEM)) | 206817060
Manufacturing | MFG | 2024-04-19 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.10.9.1.2(Supply (BHEL PEM)) | 206817061
Dispatch | DIS | 2024-10-06 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.10.9.1.2(Supply (BHEL PEM)) | 206817062
Erection | ERC | 2025-05-01 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.10.9.1(Chemical Dosing System) | 206817063
Erection of Chemical Dosing Skids & Associated Piping | ERC | 2025-05-01 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.10.9.1.3(Erection) | 206817064
Electrical , C&I and Commissioning | COM | 2025-09-28 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.10.9.1.3(Erection) | 206817065
Oxygen Dosing System | SUP | 2023-08-23 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.10.9(Dosing System) | 206817066
Civil | CIV | 2025-04-16 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.10.9.2(Oxygen Dosing System) | 206817067
EXCAVATION | CIV | 2025-04-16 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.10.9.2.1(Civil) | 206817068
RCC in substructure including PCC | CIV | 2025-04-21 08:00 | 2025-04-30 17:00 |  |  |  |  | 1.10.9.2.1(Civil) | 206817069
RCC in superstructure | CIV | 2025-05-01 08:00 | 2025-05-10 17:00 |  |  |  |  | 1.10.9.2.1(Civil) | 206817070
Backfilling | CIV | 2025-05-11 08:00 | 2025-05-15 17:00 |  |  |  |  | 1.10.9.2.1(Civil) | 206817071
Finishing works | CIV | 2025-05-16 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.10.9.2.1(Civil) | 206817072
Supply (BHEL PEM) | SUP | 2023-08-23 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.10.9.2(Oxygen Dosing System) | 206817073
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.10.9.2.2(Supply (BHEL PEM)) | 206817074
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.10.9.2.2(Supply (BHEL PEM)) | 206817075
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.10.9.2.2(Supply (BHEL PEM)) | 206817076
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.10.9.2.2(Supply (BHEL PEM)) | 206817077
Erection | ERC | 2025-06-10 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.10.9.2(Oxygen Dosing System) | 206817078
Erection of Oxygen Dosing Skids & Associated Piping | ERC | 2025-06-10 08:00 | 2025-11-06 17:00 |  |  |  |  | 1.10.9.2.3(Erection) | 206817079
Electrical , C&I and Commissioning | COM | 2025-11-07 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.10.9.2.3(Erection) | 206817080
PLATE HEAT EXCHANGERS | SUP | 2023-10-12 08:00 | 2025-03-29 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206817081
Civil | CIV | 2024-12-04 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.10.10(PLATE HEAT EXCHANGERS) | 206817082
SG PHE foundation | CIV | 2024-12-04 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.10.10.1(Civil) | 206817083
RCC Pedestal | CIV | 2024-12-04 08:00 | 2025-01-02 17:00 |  |  |  |  | 1.10.10.1.1( SG PHE foundation) | 206817084
Finishing works | CIV | 2025-01-03 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.10.10.1.1( SG PHE foundation) | 206817085
TG PHE foundation: | CIV | 2025-01-08 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.10.10.1(Civil) | 206817086
RCC Pedestal | CIV | 2025-01-08 08:00 | 2025-02-06 17:00 |  |  |  |  | 1.10.10.1.2( TG PHE foundation:) | 206817087
Finishing works | CIV | 2025-02-07 08:00 | 2025-02-11 17:00 |  |  |  |  | 1.10.10.1.2( TG PHE foundation:) | 206817088
Supply (BHEL PEM) | SUP | 2023-10-12 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.10.10(PLATE HEAT EXCHANGERS) | 206817089
Ordering | ORD | 2023-10-12 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.10.10.2(Supply (BHEL PEM)) | 206817090
Detailed Engineering | ENG | 2024-01-10 08:00 | 2024-05-08 17:00 |  |  |  |  | 1.10.10.2(Supply (BHEL PEM)) | 206817091
Manufacturing | MFG | 2024-05-09 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.10.10.2(Supply (BHEL PEM)) | 206817092
Dispatch | DIS | 2024-09-06 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.10.10.2(Supply (BHEL PEM)) | 206817093
Erection | ERC | 2025-01-29 08:00 | 2025-03-29 17:00 |  |  |  |  | 1.10.10(PLATE HEAT EXCHANGERS) | 206817094
SG PHE Erection | ERC | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  |  | 1.10.10.3(Erection) | 206817095
TG Perfection | ERC | 2025-02-28 08:00 | 2025-03-29 17:00 |  |  |  |  | 1.10.10.3(Erection) | 206817096
Auxiliary PRDS | OTH | 2023-10-12 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206817097
Supply BOI-PEM | SUP | 2023-10-12 08:00 | 2024-12-19 17:00 |  |  |  |  | 1.10.11(Auxiliary PRDS) | 206817098
Ordering | ORD | 2023-10-12 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.10.11.1(Supply BOI-PEM) | 206817099
Detailed Engineering | ENG | 2024-01-10 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.10.11.1(Supply BOI-PEM) | 206817100
Manufacturing | MFG | 2024-06-08 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.10.11.1(Supply BOI-PEM) | 206817101
Dispatch | DIS | 2024-11-05 08:00 | 2024-12-19 17:00 |  |  |  |  | 1.10.11.1(Supply BOI-PEM) | 206817102
Erection | ERC | 2025-03-20 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.10.11(Auxiliary PRDS) | 206817103
Erection of Aux PRDS | ERC | 2025-03-20 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.10.11.2(Erection) | 206817104
Online Condenser Tube Cleaning System | ORD | 2024-04-25 08:00 | 2026-02-20 17:00 |  |  |  |  | 1.10(Turbo-generator & Auxiliaries) | 206817105
Supply, BHEL PEM | SUP | 2024-04-25 08:00 | 2025-04-04 09:00 |  |  |  |  | 1.10.12(Online Condenser Tube Cleaning System) | 206817106
COLTCS | SUP | 2024-04-25 08:00 | 2025-04-04 09:00 |  |  |  |  | 1.10.12.1(Supply, BHEL PEM) | 206817107
Ordering | ORD | 2024-04-25 08:00 | 2024-07-23 17:00 |  |  |  |  | 1.10.12.1.1( COLTCS ) | 206817108
Detailed Engineering | ENG | 2024-07-24 08:00 | 2024-11-20 17:00 |  |  |  |  | 1.10.12.1.1( COLTCS ) | 206817109
Manufacturing | MFG | 2024-10-26 09:00 | 2024-10-27 09:00 |  |  |  |  | 1.10.12.1.1( COLTCS ) | 206817110
Dispatch | DIS | 2025-03-05 09:00 | 2025-04-04 09:00 |  |  |  |  | 1.10.12.1.1( COLTCS ) | 206817111
Erection | ERC | 2025-06-26 08:00 | 2026-02-20 17:00 |  |  |  |  | 1.10.12(Online Condenser Tube Cleaning System) | 206817112
Erection of COLTCS | ERC | 2025-06-26 08:00 | 2025-11-22 17:00 |  |  |  |  | 1.10.12.2(Erection) | 206817113
Erection of Conical strainer | ERC | 2025-07-26 08:00 | 2025-12-22 17:00 |  |  |  |  | 1.10.12.2(Erection) | 206817114
Electrical , C&I work and Commissioning | COM | 2025-12-23 08:00 | 2026-02-20 17:00 |  |  |  |  | 1.10.12.2(Erection) | 206817115
Piping & Valves | SUP | 2022-09-27 08:00 | 2026-02-02 17:00 |  |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206817116
Supply | SUP | 2022-09-27 08:00 | 2025-05-30 17:00 |  |  |  |  | 1.11(Piping & Valves) | 206817117
BHEL PC (PG 80 & 81) | SUP | 2022-09-27 08:00 | 2025-05-30 17:00 |  |  |  | PG 80 & 81 | 1.11.1(Supply) | 206817118
For Non Drainable HT | SUP | 2023-01-25 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.11.1.1(BHEL PC (PG 80 & 81)) | 206817119
Engineering COMPLETION | ENG | 2023-01-25 08:00 | 2023-06-03 17:00 |  |  |  |  | 1.11.1.1.1(For Non Drainable HT) | 206817120
COMPLETION OF DDR | ENG | 2023-06-04 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.11.1.1.1(For Non Drainable HT) | 206817121
MS FROM SUPERHEATER TO BOILER STOP VALVE (PGMA-80300) | SUP | 2023-08-23 08:00 | 2024-11-27 17:00 |  |  |  | 80300 | 1.11.1.1.1(For Non Drainable HT) | 206817122
Manufacturing | MFG | 2023-08-23 08:00 | 2024-10-13 17:00 |  |  |  | 80300 | 1.11.1.1.1.3(MS FROM SUPERHEATER TO BOILER STOP VALVE (PGMA-80300)) | 206817123
Dispatch | DIS | 2024-10-14 08:00 | 2024-11-27 17:00 |  |  |  | 80300 | 1.11.1.1.1.3(MS FROM SUPERHEATER TO BOILER STOP VALVE (PGMA-80300)) | 206817124
H AND S FOR Hydro TEST - (PGMA 80920) | SUP | 2023-08-23 08:00 | 2024-11-27 17:00 |  |  |  | 80920 | 1.11.1.1.1(For Non Drainable HT) | 206817125
Manufacturing | MFG | 2023-08-23 08:00 | 2024-10-13 17:00 |  |  |  | 80920 | 1.11.1.1.1.4(H AND S FOR Hydro TEST - (PGMA 80920)) | 206817126
Dispatch | DIS | 2024-10-14 08:00 | 2024-11-27 17:00 |  |  |  | 80920 | 1.11.1.1.1.4(H AND S FOR Hydro TEST - (PGMA 80920)) | 206817127
IMPORTED ELECTRODES- (PGMA -80-992) | SUP | 2023-08-23 08:00 | 2024-11-27 17:00 |  |  |  | 80992 | 1.11.1.1.1(For Non Drainable HT) | 206817128
Manufacturing | MFG | 2023-08-23 08:00 | 2024-10-13 17:00 |  |  |  | 80992 | 1.11.1.1.1.5(IMPORTED ELECTRODES- (PGMA -80-992)) | 206817129
Dispatch | DIS | 2024-10-14 08:00 | 2024-11-27 17:00 |  |  |  | 80992 | 1.11.1.1.1.5(IMPORTED ELECTRODES- (PGMA -80-992)) | 206817130
Misc. Erection MATLS- (PGMA -80-993) | SUP | 2023-08-23 08:00 | 2024-11-27 17:00 |  |  |  | 80993 | 1.11.1.1.1(For Non Drainable HT) | 206817131
Manufacturing | MFG | 2023-08-23 08:00 | 2024-10-13 17:00 |  |  |  | 80993 | 1.11.1.1.1.6(Misc. Erection MATLS- (PGMA -80-993)) | 206817132
Dispatch | DIS | 2024-10-14 08:00 | 2024-11-27 17:00 |  |  |  | 80993 | 1.11.1.1.1.6(Misc. Erection MATLS- (PGMA -80-993)) | 206817133
For BLU | SUP | 2022-09-27 08:00 | 2025-01-30 17:00 |  |  |  |  | 1.11.1.1(BHEL PC (PG 80 & 81)) | 206817134
Engineering | ENG | 2022-09-27 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.11.1.1.2(For BLU) | 206817135
COMPLETION of DDR | ENG | 2023-03-11 08:00 | 2023-10-24 17:00 |  |  |  |  | 1.11.1.1.2(For BLU) | 206817136
AUX STEAM HEADER- (PGMA -80-340) | OTH | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80340 | 1.11.1.1.2(For BLU) | 206817137
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80340 | 1.11.1.1.2.3(AUX STEAM HEADER- (PGMA -80-340)) | 206817138
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80340 | 1.11.1.1.2.3(AUX STEAM HEADER- (PGMA -80-340)) | 206817139
80341 AUX STEAM HEADER INTERCONN. BET UNITS | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80341 | 1.11.1.1.2(For BLU) | 206817140
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80341 | 1.11.1.1.2.4(80341 AUX STEAM HEADER INTERCONN. BET UNITS) | 206817141
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80341 | 1.11.1.1.2.4(80341 AUX STEAM HEADER INTERCONN. BET UNITS) | 206817142
NON DDR - FLOW NOZZLE- (PGMA -80-326) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80326 | 1.11.1.1.2(For BLU) | 206817143
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80326 | 1.11.1.1.2.5( NON DDR - FLOW NOZZLE- (PGMA -80-326)) | 206817144
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80326 | 1.11.1.1.2.5( NON DDR - FLOW NOZZLE- (PGMA -80-326)) | 206817145
AUX STEAM TO SCAPH- (PGMA -80-342) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80342 | 1.11.1.1.2(For BLU) | 206817146
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80342 | 1.11.1.1.2.6(AUX STEAM TO SCAPH- (PGMA -80-342)) | 206817147
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80342 | 1.11.1.1.2.6(AUX STEAM TO SCAPH- (PGMA -80-342)) | 206817148
AUX STEAM TO AH SOOT BLOWERS- (PGMA -80-343) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80343 | 1.11.1.1.2(For BLU) | 206817149
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80343 | 1.11.1.1.2.7(AUX STEAM TO AH SOOT BLOWERS- (PGMA -80-343)) | 206817150
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80343 | 1.11.1.1.2.7(AUX STEAM TO AH SOOT BLOWERS- (PGMA -80-343)) | 206817151
AUX STEAM TO DEAERATING HEATER- (PGMA -80-345) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80345 | 1.11.1.1.2(For BLU) | 206817152
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80345 | 1.11.1.1.2.8(AUX STEAM TO DEAERATING HEATER- (PGMA -80-345)) | 206817153
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80345 | 1.11.1.1.2.8(AUX STEAM TO DEAERATING HEATER- (PGMA -80-345)) | 206817154
AUX STEAM HEADER SV EXHAUST- (PGMA -80-373) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80373 | 1.11.1.1.2(For BLU) | 206817155
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80373 | 1.11.1.1.2.9(AUX STEAM HEADER SV EXHAUST- (PGMA -80-373)) | 206817156
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80373 | 1.11.1.1.2.9(AUX STEAM HEADER SV EXHAUST- (PGMA -80-373)) | 206817157
CONDENSATE SUCTION- (PGMA -80-400) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80400 | 1.11.1.1.2(For BLU) | 206817158
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80400 | 1.11.1.1.2.10(CONDENSATE SUCTION- (PGMA -80-400)) | 206817159
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80400 | 1.11.1.1.2.10(CONDENSATE SUCTION- (PGMA -80-400)) | 206817160
CD FROM PUMP TO LPH1/DC INLET TEE AND RE- (PGMA -80-401) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80401 | 1.11.1.1.2(For BLU) | 206817161
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80401 | 1.11.1.1.2.11(CD FROM PUMP TO LPH1/DC INLET TEE AND RE- (PGMA -80-401)) | 206817162
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80401 | 1.11.1.1.2.11(CD FROM PUMP TO LPH1/DC INLET TEE AND RE- (PGMA -80-401)) | 206817163
CD FROM LPH1/DC INLET TEE TO TG TP- (PGMA -80-402) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80402 | 1.11.1.1.2(For BLU) | 206817164
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80402 | 1.11.1.1.2.12(CD FROM LPH1/DC INLET TEE TO TG TP- (PGMA -80-402)) | 206817165
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80402 | 1.11.1.1.2.12(CD FROM LPH1/DC INLET TEE TO TG TP- (PGMA -80-402)) | 206817166
CD FROM TG TP TO DEAERATING HEATER- (PGMA -80-403) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80403 | 1.11.1.1.2(For BLU) | 206817167
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80403 | 1.11.1.1.2.13(CD FROM TG TP TO DEAERATING HEATER- (PGMA -80-403)) | 206817168
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80403 | 1.11.1.1.2.13(CD FROM TG TP TO DEAERATING HEATER- (PGMA -80-403)) | 206817169
CONDENSATE FOR SEALING OF VACUUM- (PGMA -80-407) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80407 | 1.11.1.1.2(For BLU) | 206817170
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80407 | 1.11.1.1.2.14(CONDENSATE FOR SEALING OF VACUUM- (PGMA -80-407)) | 206817171
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80407 | 1.11.1.1.2.14(CONDENSATE FOR SEALING OF VACUUM- (PGMA -80-407)) | 206817172
CONDENSATE DUMP FROM HEADER- (PGMA -80-408) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80408 | 1.11.1.1.2(For BLU) | 206817173
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80408 | 1.11.1.1.2.15(CONDENSATE DUMP FROM HEADER- (PGMA -80-408)) | 206817174
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80408 | 1.11.1.1.2.15(CONDENSATE DUMP FROM HEADER- (PGMA -80-408)) | 206817175
CONDENSATE TRANSFER- (PGMA -80-412) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80412 | 1.11.1.1.2(For BLU) | 206817176
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80412 | 1.11.1.1.2.16(CONDENSATE TRANSFER- (PGMA -80-412)) | 206817177
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80412 | 1.11.1.1.2.16(CONDENSATE TRANSFER- (PGMA -80-412)) | 206817178
ERECTION MATERIALS FOR INSTRUMENTS- (PGMA -80-418) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80418 | 1.11.1.1.2(For BLU) | 206817179
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80418 | 1.11.1.1.2.17(ERECTION MATERIALS FOR INSTRUMENTS- (PGMA -80-418)) | 206817180
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80418 | 1.11.1.1.2.17(ERECTION MATERIALS FOR INSTRUMENTS- (PGMA -80-418)) | 206817181
DEAERATOR SAFETY VALVE EXHAUST TO ATM- (PGMA -80-419) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80419 | 1.11.1.1.2(For BLU) | 206817182
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80419 | 1.11.1.1.2.18(DEAERATOR SAFETY VALVE EXHAUST TO ATM- (PGMA -80-419)) | 206817183
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80419 | 1.11.1.1.2.18(DEAERATOR SAFETY VALVE EXHAUST TO ATM- (PGMA -80-419)) | 206817184
BOILER FEED PUMP SUCTION- (PGMA -80-420) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80420 | 1.11.1.1.2(For BLU) | 206817185
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80420 | 1.11.1.1.2.19(BOILER FEED PUMP SUCTION- (PGMA -80-420)) | 206817186
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80420 | 1.11.1.1.2.19(BOILER FEED PUMP SUCTION- (PGMA -80-420)) | 206817187
BOILER FEED PUMP RECIRCULATION- (PGMA -80-421) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80421 | 1.11.1.1.2(For BLU) | 206817188
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80421 | 1.11.1.1.2.20(BOILER FEED PUMP RECIRCULATION- (PGMA -80-421)) | 206817189
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80421 | 1.11.1.1.2.20(BOILER FEED PUMP RECIRCULATION- (PGMA -80-421)) | 206817190
BOILER FEED PUMP TO HPH INCLUDING BYPASS- (PGMA -80-423) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80423 | 1.11.1.1.2(For BLU) | 206817191
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80423 | 1.11.1.1.2.21(BOILER FEED PUMP TO HPH INCLUDING BYPASS- (PGMA -80-423)) | 206817192
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80423 | 1.11.1.1.2.21(BOILER FEED PUMP TO HPH INCLUDING BYPASS- (PGMA -80-423)) | 206817193
BFD BETWEEN HTRS AND GROUP PROTECTION- (PGMA -80-424) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80424 | 1.11.1.1.2(For BLU) | 206817194
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80424 | 1.11.1.1.2.22(BFD BETWEEN HTRS AND GROUP PROTECTION- (PGMA -80-424)) | 206817195
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80424 | 1.11.1.1.2.22(BFD BETWEEN HTRS AND GROUP PROTECTION- (PGMA -80-424)) | 206817196
BFD FROM FINAL HPH TO SG TP- (PGMA -80-425) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80425 | 1.11.1.1.2(For BLU) | 206817197
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80425 | 1.11.1.1.2.23(BFD FROM FINAL HPH TO SG TP- (PGMA -80-425)) | 206817198
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80425 | 1.11.1.1.2.23(BFD FROM FINAL HPH TO SG TP- (PGMA -80-425)) | 206817199
SPRAY WATER TO HPBP- (PGMA -80-430) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80430 | 1.11.1.1.2(For BLU) | 206817200
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80430 | 1.11.1.1.2.24(SPRAY WATER TO HPBP- (PGMA -80-430)) | 206817201
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80430 | 1.11.1.1.2.24(SPRAY WATER TO HPBP- (PGMA -80-430)) | 206817202
UNLISTED SPRAY WATER - SG SCOPE- (PGMA -80-434) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80434 | 1.11.1.1.2(For BLU) | 206817203
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80434 | 1.11.1.1.2.25(UNLISTED SPRAY WATER - SG SCOPE- (PGMA -80-434)) | 206817204
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80434 | 1.11.1.1.2.25(UNLISTED SPRAY WATER - SG SCOPE- (PGMA -80-434)) | 206817205
SPRAY WATER FROM BFP INTERSTAGE- (PGMA -80-433) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80433 | 1.11.1.1.2(For BLU) | 206817206
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80433 | 1.11.1.1.2.26(SPRAY WATER FROM BFP INTERSTAGE- (PGMA -80-433)) | 206817207
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80433 | 1.11.1.1.2.26(SPRAY WATER FROM BFP INTERSTAGE- (PGMA -80-433)) | 206817208
DEAERATING HEATER OVER FLOW AND DRAIN- (PGMA -80-446) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80446 | 1.11.1.1.2(For BLU) | 206817209
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80446 | 1.11.1.1.2.27(DEAERATING HEATER OVER FLOW AND DRAIN- (PGMA -80-446)) | 206817210
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80446 | 1.11.1.1.2.27(DEAERATING HEATER OVER FLOW AND DRAIN- (PGMA -80-446)) | 206817211
BOILER INTEGRAL PIPING DRAINS- (PGMA -80-451) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80451 | 1.11.1.1.2(For BLU) | 206817212
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80451 | 1.11.1.1.2.28(BOILER INTEGRAL PIPING DRAINS- (PGMA -80-451)) | 206817213
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80451 | 1.11.1.1.2.28(BOILER INTEGRAL PIPING DRAINS- (PGMA -80-451)) | 206817214
HP PIPING DRAINS - SG SCOPE- (PGMA -80-452) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80452 | 1.11.1.1.2(For BLU) | 206817215
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80452 | 1.11.1.1.2.29(HP PIPING DRAINS - SG SCOPE- (PGMA -80-452)) | 206817216
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80452 | 1.11.1.1.2.29(HP PIPING DRAINS - SG SCOPE- (PGMA -80-452)) | 206817217
LP PIPING DRAINS - SG SCOPE- (PGMA -80-453) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80453 | 1.11.1.1.2(For BLU) | 206817218
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80453 | 1.11.1.1.2.30(LP PIPING DRAINS - SG SCOPE- (PGMA -80-453)) | 206817219
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80453 | 1.11.1.1.2.30(LP PIPING DRAINS - SG SCOPE- (PGMA -80-453)) | 206817220
SCAPH DRAINS- (PGMA -80-454) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80454 | 1.11.1.1.2(For BLU) | 206817221
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80454 | 1.11.1.1.2.31(SCAPH DRAINS- (PGMA -80-454)) | 206817222
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80454 | 1.11.1.1.2.31(SCAPH DRAINS- (PGMA -80-454)) | 206817223
DRAIN FROM UNLISTED EQPT/VESSEL-SG SCOPE- (PGMA -80-455) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80455 | 1.11.1.1.2(For BLU) | 206817224
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80455 | 1.11.1.1.2.32(DRAIN FROM UNLISTED EQPT/VESSEL-SG SCOPE- (PGMA -80-455)) | 206817225
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80455 | 1.11.1.1.2.32(DRAIN FROM UNLISTED EQPT/VESSEL-SG SCOPE- (PGMA -80-455)) | 206817226
SG AUX COOLING WATER UNIT SYSTEM- (PGMA -80-460) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80460 | 1.11.1.1.2(For BLU) | 206817227
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80460 | 1.11.1.1.2.33(SG AUX COOLING WATER UNIT SYSTEM- (PGMA -80-460)) | 206817228
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80460 | 1.11.1.1.2.33(SG AUX COOLING WATER UNIT SYSTEM- (PGMA -80-460)) | 206817229
PC - TG AUX COOLING WATER- (PGMA -80-463) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80463 | 1.11.1.1.2(For BLU) | 206817230
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80463 | 1.11.1.1.2.34(PC - TG AUX COOLING WATER- (PGMA -80-463)) | 206817231
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80463 | 1.11.1.1.2.34(PC - TG AUX COOLING WATER- (PGMA -80-463)) | 206817232
PC - MAIN CIRCULATION WATER PIPING- (PGMA -80-468) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80468 | 1.11.1.1.2(For BLU) | 206817233
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80468 | 1.11.1.1.2.35(PC - MAIN CIRCULATION WATER PIPING- (PGMA -80-468)) | 206817234
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80468 | 1.11.1.1.2.35(PC - MAIN CIRCULATION WATER PIPING- (PGMA -80-468)) | 206817235
PC - MISCELLANEOUS COOLING WATER (PGMA - 80 - 469) | SUP | 2023-04-28 08:00 | 2024-08-30 17:00 |  |  |  | 80 469 | 1.11.1.1.2(For BLU) | 206817236
Manufacturing | MFG | 2023-04-28 08:00 | 2024-07-16 17:00 |  |  |  | 80 469 | 1.11.1.1.2.36(PC - MISCELLANEOUS COOLING WATER (PGMA - 80 - 469)) | 206817237
Dispatch | DIS | 2024-07-17 08:00 | 2024-08-30 17:00 |  |  |  | 80 469 | 1.11.1.1.2.36(PC - MISCELLANEOUS COOLING WATER (PGMA - 80 - 469)) | 206817238
PC - BOILER WATER WASH TO AND FROM UNIT- (PGMA -80-471) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80471 | 1.11.1.1.2(For BLU) | 206817239
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80471 | 1.11.1.1.2.37(PC - BOILER WATER WASH TO AND FROM UNIT- (PGMA -80-471)) | 206817240
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80471 | 1.11.1.1.2.37(PC - BOILER WATER WASH TO AND FROM UNIT- (PGMA -80-471)) | 206817241
PC - DEMINERALISED WATER SYSTEM- (PGMA -80-473) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80473 | 1.11.1.1.2(For BLU) | 206817242
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80473 | 1.11.1.1.2.38(PC - DEMINERALISED WATER SYSTEM- (PGMA -80-473)) | 206817243
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80473 | 1.11.1.1.2.38(PC - DEMINERALISED WATER SYSTEM- (PGMA -80-473)) | 206817244
PC - SERVICE WATER PIPING- (PGMA -80-477) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80477 | 1.11.1.1.2(For BLU) | 206817245
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80477 | 1.11.1.1.2.39(PC - SERVICE WATER PIPING- (PGMA -80-477)) | 206817246
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80477 | 1.11.1.1.2.39(PC - SERVICE WATER PIPING- (PGMA -80-477)) | 206817247
PC - FIRE WATER-OTHER AREAS- (PGMA -80-480) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80480 | 1.11.1.1.2(For BLU) | 206817248
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80480 | 1.11.1.1.2.40(PC - FIRE WATER-OTHER AREAS- (PGMA -80-480)) | 206817249
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80480 | 1.11.1.1.2.40(PC - FIRE WATER-OTHER AREAS- (PGMA -80-480)) | 206817250
PC - CONTROL OIL PIPING (PGMA -80-484) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80484 | 1.11.1.1.2(For BLU) | 206817251
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80484 | 1.11.1.1.2.41(PC - CONTROL OIL PIPING (PGMA -80-484)) | 206817252
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80484 | 1.11.1.1.2.41(PC - CONTROL OIL PIPING (PGMA -80-484)) | 206817253
PC - LOW PRESSURE DOSING PIPING- (PGMA -80-601) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80601 | 1.11.1.1.2(For BLU) | 206817254
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80601 | 1.11.1.1.2.42(PC - LOW PRESSURE DOSING PIPING- (PGMA -80-601)) | 206817255
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80601 | 1.11.1.1.2.42(PC - LOW PRESSURE DOSING PIPING- (PGMA -80-601)) | 206817256
PC - ACID CLEANING PIPING-TEMPORARY (PGMA - 80-604) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80604 | 1.11.1.1.2(For BLU) | 206817257
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80604 | 1.11.1.1.2.43(PC - ACID CLEANING PIPING-TEMPORARY (PGMA - 80-604)) | 206817258
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80604 | 1.11.1.1.2.43(PC - ACID CLEANING PIPING-TEMPORARY (PGMA - 80-604)) | 206817259
PC - SERVICE AIR-COMP SUCT AND DIS TO RECEI- (PGMA -80-610) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80610 | 1.11.1.1.2(For BLU) | 206817260
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80610 | 1.11.1.1.2.44(PC - SERVICE AIR-COMP SUCT AND DIS TO RECEI- (PGMA -80-610)) | 206817261
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80610 | 1.11.1.1.2.44(PC - SERVICE AIR-COMP SUCT AND DIS TO RECEI- (PGMA -80-610)) | 206817262
PC - SERVICE AIR FOR INDIVIDUAL UNITS- (PGMA -80-612) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80612 | 1.11.1.1.2(For BLU) | 206817263
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80612 | 1.11.1.1.2.45(PC - SERVICE AIR FOR INDIVIDUAL UNITS- (PGMA -80-612)) | 206817264
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80612 | 1.11.1.1.2.45(PC - SERVICE AIR FOR INDIVIDUAL UNITS- (PGMA -80-612)) | 206817265
PC - INST AIR COMP SUC AND DIS TO RECEIVER- (PGMA -80-614) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80614 | 1.11.1.1.2(For BLU) | 206817266
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80614 | 1.11.1.1.2.46(PC - INST AIR COMP SUC AND DIS TO RECEIVER- (PGMA -80-614)) | 206817267
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80614 | 1.11.1.1.2.46(PC - INST AIR COMP SUC AND DIS TO RECEIVER- (PGMA -80-614)) | 206817268
PC - INSTRUMENT AIR FOR INDIVIDUAL UNIT- (PGMA -80-616) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80616 | 1.11.1.1.2(For BLU) | 206817269
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80616 | 1.11.1.1.2.47(PC - INSTRUMENT AIR FOR INDIVIDUAL UNIT- (PGMA -80-616)) | 206817270
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80616 | 1.11.1.1.2.47(PC - INSTRUMENT AIR FOR INDIVIDUAL UNIT- (PGMA -80-616)) | 206817271
PC - FUEL OIL Supply AND RETURN PIPING- (PGMA -80-650) | SUP | 2023-04-28 08:00 | 2024-09-29 17:00 |  |  |  | 80650 | 1.11.1.1.2(For BLU) | 206817272
Manufacturing | MFG | 2023-04-28 08:00 | 2024-08-15 17:00 |  |  |  | 80650 | 1.11.1.1.2.48(PC - FUEL OIL Supply AND RETURN PIPING- (PGMA -80-650)) | 206817273
Dispatch | DIS | 2024-08-16 08:00 | 2024-09-29 17:00 |  |  |  | 80650 | 1.11.1.1.2.48(PC - FUEL OIL Supply AND RETURN PIPING- (PGMA -80-650)) | 206817274
PC - H AND S FOR LP PIPING- (PGMA -80-933) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80933 | 1.11.1.1.2(For BLU) | 206817275
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80933 | 1.11.1.1.2.49(PC - H AND S FOR LP PIPING- (PGMA -80-933)) | 206817276
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80933 | 1.11.1.1.2.49(PC - H AND S FOR LP PIPING- (PGMA -80-933)) | 206817277
PC - SUB DELIVERY VALVES FOR LIGHT UP- (PGMA -80-901) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80901 | 1.11.1.1.2(For BLU) | 206817278
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80901 | 1.11.1.1.2.50(PC - SUB DELIVERY VALVES FOR LIGHT UP- (PGMA -80-901)) | 206817279
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80901 | 1.11.1.1.2.50(PC - SUB DELIVERY VALVES FOR LIGHT UP- (PGMA -80-901)) | 206817280
PC - H AND S FOR LIGHT UP STEAM LINE- (PGMA -80-921) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80921 | 1.11.1.1.2(For BLU) | 206817281
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80921 | 1.11.1.1.2.51(PC - H AND S FOR LIGHT UP STEAM LINE- (PGMA -80-921)) | 206817282
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80921 | 1.11.1.1.2.51(PC - H AND S FOR LIGHT UP STEAM LINE- (PGMA -80-921)) | 206817283
PC - H&S FOR TEMPORARY PIPING ACID AND ALKALI (PGMA -80-926) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80926 | 1.11.1.1.2(For BLU) | 206817284
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80926 | 1.11.1.1.2.52(PC - H&S FOR TEMPORARY PIPING ACID AND ALKALI (PGMA -80-926)) | 206817285
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80926 | 1.11.1.1.2.52(PC - H&S FOR TEMPORARY PIPING ACID AND ALKALI (PGMA -80-926)) | 206817286
PC - H&S FOR TEMPORARY PIPING - STEAM BLOWING (PGMA -80-927) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80927 | 1.11.1.1.2(For BLU) | 206817287
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80927 | 1.11.1.1.2.53(PC - H&S FOR TEMPORARY PIPING - STEAM BLOWING (PGMA -80-927)) | 206817288
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80927 | 1.11.1.1.2.53(PC - H&S FOR TEMPORARY PIPING - STEAM BLOWING (PGMA -80-927)) | 206817289
PC - H AND S FOR BOILER LIGHT UP - TG- (PGMA -80-928) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 80928 | 1.11.1.1.2(For BLU) | 206817290
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 80928 | 1.11.1.1.2.54(PC - H AND S FOR BOILER LIGHT UP - TG- (PGMA -80-928)) | 206817291
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 80928 | 1.11.1.1.2.54(PC - H AND S FOR BOILER LIGHT UP - TG- (PGMA -80-928)) | 206817292
PC - CW STORAGE TANK 16-25 CUM- (PGMA -81-036) | SUP | 2023-04-28 08:00 | 2024-06-30 17:00 |  |  |  | 81036 | 1.11.1.1.2(For BLU) | 206817293
Manufacturing | MFG | 2023-04-28 08:00 | 2024-05-16 17:00 |  |  |  | 81036 | 1.11.1.1.2.55(PC - CW STORAGE TANK 16-25 CUM- (PGMA -81-036)) | 206817294
Dispatch | DIS | 2024-05-17 08:00 | 2024-06-30 17:00 |  |  |  | 81036 | 1.11.1.1.2.55(PC - CW STORAGE TANK 16-25 CUM- (PGMA -81-036)) | 206817295
PC - SPECIAL TANKS AND VESSELS- (PGMA -81-060) | SUP | 2023-04-28 08:00 | 2024-06-30 17:00 |  |  |  | 81060 | 1.11.1.1.2(For BLU) | 206817296
Manufacturing | MFG | 2023-04-28 08:00 | 2024-05-16 17:00 |  |  |  | 81060 | 1.11.1.1.2.56(PC - SPECIAL TANKS AND VESSELS- (PGMA -81-060)) | 206817297
Dispatch | DIS | 2024-05-17 08:00 | 2024-06-30 17:00 |  |  |  | 81060 | 1.11.1.1.2.56(PC - SPECIAL TANKS AND VESSELS- (PGMA -81-060)) | 206817298
PC - COOLING WATER PUMP- (PGMA -81-110) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81110 | 1.11.1.1.2(For BLU) | 206817299
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81110 | 1.11.1.1.2.57(PC - COOLING WATER PUMP- (PGMA -81-110)) | 206817300
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81110 | 1.11.1.1.2.57(PC - COOLING WATER PUMP- (PGMA -81-110)) | 206817301
PC - FIX COM FOR MISCELLANEOUS PPG INSULATION- (PGMA -81-318) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81318 | 1.11.1.1.2(For BLU) | 206817302
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81318 | 1.11.1.1.2.58(PC - FIX COM FOR MISCELLANEOUS PPG INSULATION- (PGMA -81-318)) | 206817303
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81318 | 1.11.1.1.2.58(PC - FIX COM FOR MISCELLANEOUS PPG INSULATION- (PGMA -81-318)) | 206817304
PC - MINERAL WOOL MATTRESS- (PGMA -81-325) | SUP | 2023-04-28 08:00 | 2025-01-30 17:00 |  |  |  | 81325 | 1.11.1.1.2(For BLU) | 206817305
Manufacturing | MFG | 2023-04-28 08:00 | 2024-12-16 17:00 |  |  |  | 81325 | 1.11.1.1.2.59(PC - MINERAL WOOL MATTRESS- (PGMA -81-325)) | 206817306
Dispatch | DIS | 2024-12-17 08:00 | 2025-01-30 17:00 |  |  |  | 81325 | 1.11.1.1.2.59(PC - MINERAL WOOL MATTRESS- (PGMA -81-325)) | 206817307
PC - SEALING COMPOUND FOR INSL- (PGMA -81-341) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81341 | 1.11.1.1.2(For BLU) | 206817308
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81341 | 1.11.1.1.2.60(PC - SEALING COMPOUND FOR INSL- (PGMA -81-341)) | 206817309
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81341 | 1.11.1.1.2.60(PC - SEALING COMPOUND FOR INSL- (PGMA -81-341)) | 206817310
PC - ALUMINIUM CLADDING FOR INSULATION- (PGMA -81-350) | SUP | 2023-04-28 08:00 | 2025-01-30 17:00 |  |  |  | 81350 | 1.11.1.1.2(For BLU) | 206817311
Manufacturing | MFG | 2023-04-28 08:00 | 2024-12-16 17:00 |  |  |  | 81350 | 1.11.1.1.2.61(PC - ALUMINIUM CLADDING FOR INSULATION- (PGMA -81-350)) | 206817312
Dispatch | DIS | 2024-12-17 08:00 | 2025-01-30 17:00 |  |  |  | 81350 | 1.11.1.1.2.61(PC - ALUMINIUM CLADDING FOR INSULATION- (PGMA -81-350)) | 206817313
PC - DIRECT GAUGES FOR STEAM LINES- (PGMA -81-411) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81411 | 1.11.1.1.2(For BLU) | 206817314
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81411 | 1.11.1.1.2.62(PC - DIRECT GAUGES FOR STEAM LINES- (PGMA -81-411)) | 206817315
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81411 | 1.11.1.1.2.62(PC - DIRECT GAUGES FOR STEAM LINES- (PGMA -81-411)) | 206817316
PC - DIRECT GAUGES FOR NON-STEAM LINES- (PGMA -81-412) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81412 | 1.11.1.1.2(For BLU) | 206817317
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81412 | 1.11.1.1.2.63(PC - DIRECT GAUGES FOR NON-STEAM LINES- (PGMA -81-412)) | 206817318
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81412 | 1.11.1.1.2.63(PC - DIRECT GAUGES FOR NON-STEAM LINES- (PGMA -81-412)) | 206817319
PC - LOCAL CONTROL EQPT FOR NON-STEAM LINES- (PGMA -81-414) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81414 | 1.11.1.1.2(For BLU) | 206817320
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81414 | 1.11.1.1.2.64(PC - LOCAL CONTROL EQPT FOR NON-STEAM LINES- (PGMA -81-414)) | 206817321
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81414 | 1.11.1.1.2.64(PC - LOCAL CONTROL EQPT FOR NON-STEAM LINES- (PGMA -81-414)) | 206817322
PC - TEST THERMOWELLS- (PGMA -81-415) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81415 | 1.11.1.1.2(For BLU) | 206817323
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81415 | 1.11.1.1.2.65(PC - TEST THERMOWELLS- (PGMA -81-415)) | 206817324
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81415 | 1.11.1.1.2.65(PC - TEST THERMOWELLS- (PGMA -81-415)) | 206817325
PC - INSTRUMENTATION FOR STARTUP SYSTEM- (PGMA -81-417) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81417 | 1.11.1.1.2(For BLU) | 206817326
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81417 | 1.11.1.1.2.66(PC - INSTRUMENTATION FOR STARTUP SYSTEM- (PGMA -81-417)) | 206817327
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81417 | 1.11.1.1.2.66(PC - INSTRUMENTATION FOR STARTUP SYSTEM- (PGMA -81-417)) | 206817328
For SB | SUP | 2022-09-27 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.11.1.1(BHEL PC (PG 80 & 81)) | 206817329
Engineering COMPLETION | ENG | 2022-09-27 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.11.1.1.3(For SB) | 206817330
COMPLETION of DDR | ENG | 2023-03-11 08:00 | 2023-10-24 17:00 |  |  |  |  | 1.11.1.1.3(For SB) | 206817331
PC - MS FROM BOILER STOP VALVE TO ESV- (PGMA -80-301) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80301 | 1.11.1.1.3(For SB) | 206817332
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80301 | 1.11.1.1.3.3(PC - MS FROM BOILER STOP VALVE TO ESV- (PGMA -80-301)) | 206817333
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80301 | 1.11.1.1.3.3(PC - MS FROM BOILER STOP VALVE TO ESV- (PGMA -80-301)) | 206817334
PC - MS FROM ESV TO TURBINE (PGMA - 80-302) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80302 | 1.11.1.1.3(For SB) | 206817335
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80302 | 1.11.1.1.3.4(PC - MS FROM ESV TO TURBINE (PGMA - 80-302)) | 206817336
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80302 | 1.11.1.1.3.4(PC - MS FROM ESV TO TURBINE (PGMA - 80-302)) | 206817337
PC - MS HEADER TO AUX PRDS- (PGMA -80-303) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80303 | 1.11.1.1.3(For SB) | 206817338
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80303 | 1.11.1.1.3.5(PC - MS HEADER TO AUX PRDS- (PGMA -80-303)) | 206817339
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80303 | 1.11.1.1.3.5(PC - MS HEADER TO AUX PRDS- (PGMA -80-303)) | 206817340
PC - MS HEADER TO HPBP VALVE- (PGMA -80-304) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80304 | 1.11.1.1.3(For SB) | 206817341
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80304 | 1.11.1.1.3.6(PC - MS HEADER TO HPBP VALVE- (PGMA -80-304)) | 206817342
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80304 | 1.11.1.1.3.6(PC - MS HEADER TO HPBP VALVE- (PGMA -80-304)) | 206817343
PC - HRH FROM REHEATER TO INTERCEPTOR VALVE- (PGMA -80-310) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80310 | 1.11.1.1.3(For SB) | 206817344
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80310 | 1.11.1.1.3.7(PC - HRH FROM REHEATER TO INTERCEPTOR VALVE- (PGMA -80-310)) | 206817345
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80310 | 1.11.1.1.3.7(PC - HRH FROM REHEATER TO INTERCEPTOR VALVE- (PGMA -80-310)) | 206817346
PC - LPBP VALVE UPSTREAM AND DOWNSTREAM- (PGMA -80-312) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80312 | 1.11.1.1.3(For SB) | 206817347
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80312 | 1.11.1.1.3.8(PC - LPBP VALVE UPSTREAM AND DOWNSTREAM- (PGMA -80-312)) | 206817348
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80312 | 1.11.1.1.3.8(PC - LPBP VALVE UPSTREAM AND DOWNSTREAM- (PGMA -80-312)) | 206817349
PC - PERMANENT STEAM BLOWING (PGMA - 80-319) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80319 | 1.11.1.1.3(For SB) | 206817350
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80319 | 1.11.1.1.3.9(PC - PERMANENT STEAM BLOWING (PGMA - 80-319)) | 206817351
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80319 | 1.11.1.1.3.9(PC - PERMANENT STEAM BLOWING (PGMA - 80-319)) | 206817352
PC - CRH FROM TURBINE TO REHEATER- (PGMA -80-320) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80320 | 1.11.1.1.3(For SB) | 206817353
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80320 | 1.11.1.1.3.10(PC - CRH FROM TURBINE TO REHEATER- (PGMA -80-320)) | 206817354
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80320 | 1.11.1.1.3.10(PC - CRH FROM TURBINE TO REHEATER- (PGMA -80-320)) | 206817355
PC - HPBP VALVE TO CRH PIPING- (PGMA -80-321) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80321 | 1.11.1.1.3(For SB) | 206817356
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80321 | 1.11.1.1.3.11(PC - HPBP VALVE TO CRH PIPING- (PGMA -80-321)) | 206817357
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80321 | 1.11.1.1.3.11(PC - HPBP VALVE TO CRH PIPING- (PGMA -80-321)) | 206817358
PC - STEAM TO BFP DRIVE TURBINE- (PGMA -80-323) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80323 | 1.11.1.1.3(For SB) | 206817359
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80323 | 1.11.1.1.3.12(PC - STEAM TO BFP DRIVE TURBINE- (PGMA -80-323)) | 206817360
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80323 | 1.11.1.1.3.12(PC - STEAM TO BFP DRIVE TURBINE- (PGMA -80-323)) | 206817361
PC - CRH HEADER TO AUX.PRDS- (PGMA -80-324) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80324 | 1.11.1.1.3(For SB) | 206817362
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80324 | 1.11.1.1.3.13(PC - CRH HEADER TO AUX.PRDS- (PGMA -80-324)) | 206817363
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80324 | 1.11.1.1.3.13(PC - CRH HEADER TO AUX.PRDS- (PGMA -80-324)) | 206817364
PC - H AND S FOR CRITICAL PPG(BLR & TG AREA)- (PGMA -80-830) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.11.1.1.3(For SB) | 206817365
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80830 | 1.11.1.1.3.14(PC - H AND S FOR CRITICAL PPG(BLR & TG AREA)- (PGMA -80-830)) | 206817366
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80830 | 1.11.1.1.3.14(PC - H AND S FOR CRITICAL PPG(BLR & TG AREA)- (PGMA -80-830)) | 206817367
PC - AUX STRUCTURE FOR CRITICAL PIPING-SG- (PGMA -80-940) | SUP | 2023-04-28 08:00 | 2025-04-01 17:00 |  |  |  | 80940 | 1.11.1.1.3(For SB) | 206817368
Manufacturing | MFG | 2023-04-28 08:00 | 2025-02-15 17:00 |  |  |  | 80940 | 1.11.1.1.3.15(PC - AUX STRUCTURE FOR CRITICAL PIPING-SG- (PGMA -80-940)) | 206817369
Dispatch | DIS | 2025-02-16 08:00 | 2025-04-01 17:00 |  |  |  | 80940 | 1.11.1.1.3.15(PC - AUX STRUCTURE FOR CRITICAL PIPING-SG- (PGMA -80-940)) | 206817370
For SYN | SUP | 2022-09-27 08:00 | 2025-05-30 17:00 |  |  |  |  | 1.11.1.1(BHEL PC (PG 80 & 81)) | 206817371
Engineering COMPLETION | ENG | 2022-09-27 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817372
COMPLETION of DDR | ENG | 2023-03-11 08:00 | 2023-10-24 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817373
PC - HP AND LP BYPASS WARM UP- (PGMA -80-307) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80307 | 1.11.1.1.4(For SYN) | 206817374
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80307 | 1.11.1.1.4.3(PC - HP AND LP BYPASS WARM UP- (PGMA -80-307)) | 206817375
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80307 | 1.11.1.1.4.3(PC - HP AND LP BYPASS WARM UP- (PGMA -80-307)) | 206817376
PC - CRH PIPING TO DEAERATING HEATER- (PGMA -80-322) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80322 | 1.11.1.1.4(For SYN) | 206817377
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80322 | 1.11.1.1.4.4(PC - CRH PIPING TO DEAERATING HEATER- (PGMA -80-322)) | 206817378
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80322 | 1.11.1.1.4.4(PC - CRH PIPING TO DEAERATING HEATER- (PGMA -80-322)) | 206817379
PC - EXTRACTION STEAM TO BFP DRIVE TURBINE- (PGMA -80-329) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80329 | 1.11.1.1.4(For SYN) | 206817380
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80329 | 1.11.1.1.4.5(PC - EXTRACTION STEAM TO BFP DRIVE TURBINE- (PGMA -80-329)) | 206817381
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80329 | 1.11.1.1.4.5(PC - EXTRACTION STEAM TO BFP DRIVE TURBINE- (PGMA -80-329)) | 206817382
PC - EXTRACTION STEAM TO LP HEATER-2- (PGMA -80-331) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80331 | 1.11.1.1.4(For SYN) | 206817383
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80331 | 1.11.1.1.4.6(PC - EXTRACTION STEAM TO LP HEATER-2- (PGMA -80-331)) | 206817384
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80331 | 1.11.1.1.4.6(PC - EXTRACTION STEAM TO LP HEATER-2- (PGMA -80-331)) | 206817385
PC - EXTRACTION STEAM TO LP HEATER-3- (PGMA -80-332) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80332 | 1.11.1.1.4(For SYN) | 206817386
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80332 | 1.11.1.1.4.7(PC - EXTRACTION STEAM TO LP HEATER-3- (PGMA -80-332)) | 206817387
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80332 | 1.11.1.1.4.7(PC - EXTRACTION STEAM TO LP HEATER-3- (PGMA -80-332)) | 206817388
PC - EXTRACTION STEAM TO LP HEATER-4- (PGMA -80-333) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80333 | 1.11.1.1.4(For SYN) | 206817389
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80333 | 1.11.1.1.4.8(PC - EXTRACTION STEAM TO LP HEATER-4- (PGMA -80-333)) | 206817390
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80333 | 1.11.1.1.4.8(PC - EXTRACTION STEAM TO LP HEATER-4- (PGMA -80-333)) | 206817391
PC - EXTRACTION STEAM TO LP HEATER-5 (PGMA - 80334) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80334 | 1.11.1.1.4(For SYN) | 206817392
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80334 | 1.11.1.1.4.9(PC - EXTRACTION STEAM TO LP HEATER-5 (PGMA - 80334)) | 206817393
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80334 | 1.11.1.1.4.9(PC - EXTRACTION STEAM TO LP HEATER-5 (PGMA - 80334)) | 206817394
PC - EXTRACTION STEAM TO DEAERATING HEATER- (PGMA -80-335) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80335 | 1.11.1.1.4(For SYN) | 206817395
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80335 | 1.11.1.1.4.10(PC - EXTRACTION STEAM TO DEAERATING HEATER- (PGMA -80-335)) | 206817396
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80335 | 1.11.1.1.4.10(PC - EXTRACTION STEAM TO DEAERATING HEATER- (PGMA -80-335)) | 206817397
PC - EXTRACTION STEAM TO HP HEATER NO.1- (PGMA -80-336) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80336 | 1.11.1.1.4(For SYN) | 206817398
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80336 | 1.11.1.1.4.11(PC - EXTRACTION STEAM TO HP HEATER NO.1- (PGMA -80-336)) | 206817399
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80336 | 1.11.1.1.4.11(PC - EXTRACTION STEAM TO HP HEATER NO.1- (PGMA -80-336)) | 206817400
PC - EXTRACTION STEAM TO HP HEATER-2- (PGMA -80-337) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80337 | 1.11.1.1.4(For SYN) | 206817401
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80337 | 1.11.1.1.4.12(PC - EXTRACTION STEAM TO HP HEATER-2- (PGMA -80-337)) | 206817402
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80337 | 1.11.1.1.4.12(PC - EXTRACTION STEAM TO HP HEATER-2- (PGMA -80-337)) | 206817403
PC - EXTRACTION STEAM TO HP HEATER-3- (PGMA -80-338) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80338 | 1.11.1.1.4(For SYN) | 206817404
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80338 | 1.11.1.1.4.13(PC - EXTRACTION STEAM TO HP HEATER-3- (PGMA -80-338)) | 206817405
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80338 | 1.11.1.1.4.13(PC - EXTRACTION STEAM TO HP HEATER-3- (PGMA -80-338)) | 206817406
PC - AUX STEAM TO BFD TURBINE- (PGMA -80-339) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80339 | 1.11.1.1.4(For SYN) | 206817407
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80339 | 1.11.1.1.4.14(PC - AUX STEAM TO BFD TURBINE- (PGMA -80-339)) | 206817408
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80339 | 1.11.1.1.4.14(PC - AUX STEAM TO BFD TURBINE- (PGMA -80-339)) | 206817409
PC - AUX STEAM TO GLAND SEALS - TG SCOPE- (PGMA -80-349) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80349 | 1.11.1.1.4(For SYN) | 206817410
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80349 | 1.11.1.1.4.15(PC - AUX STEAM TO GLAND SEALS - TG SCOPE- (PGMA -80-349)) | 206817411
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80349 | 1.11.1.1.4.15(PC - AUX STEAM TO GLAND SEALS - TG SCOPE- (PGMA -80-349)) | 206817412
PC - AUX STEAM TO UNLISTED USERS - SG SCOPE- (PGMA -80-351) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80351 | 1.11.1.1.4(For SYN) | 206817413
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80351 | 1.11.1.1.4.16(PC - AUX STEAM TO UNLISTED USERS - SG SCOPE- (PGMA -80-351)) | 206817414
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80351 | 1.11.1.1.4.16(PC - AUX STEAM TO UNLISTED USERS - SG SCOPE- (PGMA -80-351)) | 206817415
PC - EXHAUST STEAM FROM PRIME MOVERS-TG SCOPE- (PGMA -80-363) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80363 | 1.11.1.1.4(For SYN) | 206817416
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80363 | 1.11.1.1.4.17(PC - EXHAUST STEAM FROM PRIME MOVERS-TG SCOPE- (PGMA -80-363)) | 206817417
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80363 | 1.11.1.1.4.17(PC - EXHAUST STEAM FROM PRIME MOVERS-TG SCOPE- (PGMA -80-363)) | 206817418
PC - HP DRAIN FLASH TANK VENT TO ATMOSPHERE- (PGMA -80-370) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80370 | 1.11.1.1.4(For SYN) | 206817419
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80370 | 1.11.1.1.4.18(PC - HP DRAIN FLASH TANK VENT TO ATMOSPHERE- (PGMA -80-370)) | 206817420
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80370 | 1.11.1.1.4.18(PC - HP DRAIN FLASH TANK VENT TO ATMOSPHERE- (PGMA -80-370)) | 206817421
PC - DRAIN FLASH TANK VENT TO CONDENSER- (PGMA -80-371) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80371 | 1.11.1.1.4(For SYN) | 206817422
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80371 | 1.11.1.1.4.19(PC - DRAIN FLASH TANK VENT TO CONDENSER- (PGMA -80-371)) | 206817423
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80371 | 1.11.1.1.4.19(PC - DRAIN FLASH TANK VENT TO CONDENSER- (PGMA -80-371)) | 206817424
PC - UNLISTED SV EXHAUSTS - TG SCOPE- (PGMA -80-375) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80375 | 1.11.1.1.4(For SYN) | 206817425
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80375 | 1.11.1.1.4.20(PC - UNLISTED SV EXHAUSTS - TG SCOPE- (PGMA -80-375)) | 206817426
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80375 | 1.11.1.1.4.20(PC - UNLISTED SV EXHAUSTS - TG SCOPE- (PGMA -80-375)) | 206817427
PC - HPH SV EXHAUST TO FLASH TANK- (PGMA -80-379) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80379 | 1.11.1.1.4(For SYN) | 206817428
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80379 | 1.11.1.1.4.21( PC - HPH SV EXHAUST TO FLASH TANK- (PGMA -80-379)) | 206817429
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80379 | 1.11.1.1.4.21( PC - HPH SV EXHAUST TO FLASH TANK- (PGMA -80-379)) | 206817430
PC - HP HEATER VENTS - TG SCOPE- (PGMA -80-381) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80381 | 1.11.1.1.4(For SYN) | 206817431
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80381 | 1.11.1.1.4.22(PC - HP HEATER VENTS - TG SCOPE- (PGMA -80-381)) | 206817432
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80381 | 1.11.1.1.4.22(PC - HP HEATER VENTS - TG SCOPE- (PGMA -80-381)) | 206817433
PC - LP HEATER VENTS- (PGMA -80-382) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80382 | 1.11.1.1.4(For SYN) | 206817434
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80382 | 1.11.1.1.4.23(PC - LP HEATER VENTS- (PGMA -80-382)) | 206817435
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80382 | 1.11.1.1.4.23(PC - LP HEATER VENTS- (PGMA -80-382)) | 206817436
PC - VENT FROM UNLISTED PPG/EQPT TO COND- (PGMA -80-385) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80385 | 1.11.1.1.4(For SYN) | 206817437
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80385 | 1.11.1.1.4.24(PC - VENT FROM UNLISTED PPG/EQPT TO COND- (PGMA -80-385)) | 206817438
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80385 | 1.11.1.1.4.24(PC - VENT FROM UNLISTED PPG/EQPT TO COND- (PGMA -80-385)) | 206817439
STEAM BLOWING PIPING-TEMPORARY (PGMA - 80-399) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80399 | 1.11.1.1.4(For SYN) | 206817440
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80399 | 1.11.1.1.4.25(STEAM BLOWING PIPING-TEMPORARY (PGMA - 80-399)) | 206817441
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80399 | 1.11.1.1.4.25(STEAM BLOWING PIPING-TEMPORARY (PGMA - 80-399)) | 206817442
PC - UNLISTED SPRAY WATER - TG SCOPE- (PGMA -80-435) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80435 | 1.11.1.1.4(For SYN) | 206817443
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80435 | 1.11.1.1.4.26(PC - UNLISTED SPRAY WATER - TG SCOPE- (PGMA -80-435)) | 206817444
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80435 | 1.11.1.1.4.26(PC - UNLISTED SPRAY WATER - TG SCOPE- (PGMA -80-435)) | 206817445
PC - CONTROL OIL PIPING ESV & IV- (PGMA -80-482) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80482 | 1.11.1.1.4(For SYN) | 206817446
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80482 | 1.11.1.1.4.27(PC - CONTROL OIL PIPING ESV & IV- (PGMA -80-482)) | 206817447
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80482 | 1.11.1.1.4.27(PC - CONTROL OIL PIPING ESV & IV- (PGMA -80-482)) | 206817448
PC - GLAND STEAM COOLER DRAINS- (PGMA -80-442) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80442 | 1.11.1.1.4(For SYN) | 206817449
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80442 | 1.11.1.1.4.28(PC - GLAND STEAM COOLER DRAINS- (PGMA -80-442)) | 206817450
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80442 | 1.11.1.1.4.28(PC - GLAND STEAM COOLER DRAINS- (PGMA -80-442)) | 206817451
PC - LP HEATER-1 TO CONDENSER- (PGMA -80-443) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80443 | 1.11.1.1.4(For SYN) | 206817452
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80443 | 1.11.1.1.4.29(PC - LP HEATER-1 TO CONDENSER- (PGMA -80-443)) | 206817453
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80443 | 1.11.1.1.4.29(PC - LP HEATER-1 TO CONDENSER- (PGMA -80-443)) | 206817454
PC - LP HEATER-2/3/4/5 DRAINS AND DRIP PUMP I- (PGMA -80-444) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80444 | 1.11.1.1.4(For SYN) | 206817455
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80444 | 1.11.1.1.4.30(PC - LP HEATER-2/3/4/5 DRAINS AND DRIP PUMP I- (PGMA -80-444)) | 206817456
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80444 | 1.11.1.1.4.30(PC - LP HEATER-2/3/4/5 DRAINS AND DRIP PUMP I- (PGMA -80-444)) | 206817457
PC - HP HEATER DRAINS- (PGMA -80-447) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80447 | 1.11.1.1.4(For SYN) | 206817458
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80447 | 1.11.1.1.4.31(PC - HP HEATER DRAINS- (PGMA -80-447)) | 206817459
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80447 | 1.11.1.1.4.31(PC - HP HEATER DRAINS- (PGMA -80-447)) | 206817460
PC - DRAIN FROM UNLISTED EQPT/VESSEL-TG SCOPE- (PGMA -80-448) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80448 | 1.11.1.1.4(For SYN) | 206817461
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80448 | 1.11.1.1.4.32(PC - DRAIN FROM UNLISTED EQPT/VESSEL-TG SCOPE- (PGMA -80-448)) | 206817462
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80448 | 1.11.1.1.4.32(PC - DRAIN FROM UNLISTED EQPT/VESSEL-TG SCOPE- (PGMA -80-448)) | 206817463
PC - TG CYCLE PIPING DRAINS AND VENTS- (PGMA -80-449) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80449 | 1.11.1.1.4(For SYN) | 206817464
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80449 | 1.11.1.1.4.33(PC - TG CYCLE PIPING DRAINS AND VENTS- (PGMA -80-449)) | 206817465
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80449 | 1.11.1.1.4.33(PC - TG CYCLE PIPING DRAINS AND VENTS- (PGMA -80-449)) | 206817466
PC - MANIFOLDS FOR HP FLASH BOX AND CONDENS- (PGMA -80-457) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80457 | 1.11.1.1.4(For SYN) | 206817467
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80457 | 1.11.1.1.4.34(PC - MANIFOLDS FOR HP FLASH BOX AND CONDENS- (PGMA -80-457)) | 206817468
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80457 | 1.11.1.1.4.34(PC - MANIFOLDS FOR HP FLASH BOX AND CONDENS- (PGMA -80-457)) | 206817469
PC - HP FLASH TANK DRAIN TO CONDENSER- (PGMA -80-459) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80459 | 1.11.1.1.4(For SYN) | 206817470
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80459 | 1.11.1.1.4.35(PC - HP FLASH TANK DRAIN TO CONDENSER- (PGMA -80-459)) | 206817471
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80459 | 1.11.1.1.4.35(PC - HP FLASH TANK DRAIN TO CONDENSER- (PGMA -80-459)) | 206817472
PC - DRINKING WATER PIPING- (PGMA -80-478) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80478 | 1.11.1.1.4(For SYN) | 206817473
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80478 | 1.11.1.1.4.36(PC - DRINKING WATER PIPING- (PGMA -80-478)) | 206817474
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80478 | 1.11.1.1.4.36(PC - DRINKING WATER PIPING- (PGMA -80-478)) | 206817475
PC - HP FLASH TANK VENT TO CONDENSER- (PGMA -80-493) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80493 | 1.11.1.1.4(For SYN) | 206817476
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80493 | 1.11.1.1.4.37(PC - HP FLASH TANK VENT TO CONDENSER- (PGMA -80-493)) | 206817477
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80493 | 1.11.1.1.4.37(PC - HP FLASH TANK VENT TO CONDENSER- (PGMA -80-493)) | 206817478
PC - LP FLASH TANK VENT TO CONDENSER- (PGMA -80-494) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80494 | 1.11.1.1.4(For SYN) | 206817479
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80494 | 1.11.1.1.4.38(PC - LP FLASH TANK VENT TO CONDENSER- (PGMA -80-494)) | 206817480
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80494 | 1.11.1.1.4.38(PC - LP FLASH TANK VENT TO CONDENSER- (PGMA -80-494)) | 206817481
PC - LP FLASH TANK DRAIN TO COND- (PGMA -80-495) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80495 | 1.11.1.1.4(For SYN) | 206817482
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80495 | 1.11.1.1.4.39(PC - LP FLASH TANK DRAIN TO COND- (PGMA -80-495)) | 206817483
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80495 | 1.11.1.1.4.39(PC - LP FLASH TANK DRAIN TO COND- (PGMA -80-495)) | 206817484
PC - LP Condensate PIPING WITHIN TG HALL FOR- (PGMA -80-545) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80545 | 1.11.1.1.4(For SYN) | 206817485
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80545 | 1.11.1.1.4.40(PC - LP Condensate PIPING WITHIN TG HALL FOR- (PGMA -80-545)) | 206817486
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80545 | 1.11.1.1.4.40(PC - LP Condensate PIPING WITHIN TG HALL FOR- (PGMA -80-545)) | 206817487
PC - LUB OIL FLUSHING & PR TESTING (PGMA - 80-673) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80673 | 1.11.1.1.4(For SYN) | 206817488
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80673 | 1.11.1.1.4.41(PC - LUB OIL FLUSHING & PR TESTING (PGMA - 80-673)) | 206817489
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80673 | 1.11.1.1.4.41(PC - LUB OIL FLUSHING & PR TESTING (PGMA - 80-673)) | 206817490
PC - H AND S FOR SYNCHRONISATION - TG- (PGMA -80-930) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 80930 | 1.11.1.1.4(For SYN) | 206817491
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 80930 | 1.11.1.1.4.42(PC - H AND S FOR SYNCHRONISATION - TG- (PGMA -80-930)) | 206817492
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 80930 | 1.11.1.1.4.42(PC - H AND S FOR SYNCHRONISATION - TG- (PGMA -80-930)) | 206817493
PC - CLEAN DRAIN FLASH TANK - DIA 1500 MM- (PGMA -81-012) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 81012 | 1.11.1.1.4(For SYN) | 206817494
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 81012 | 1.11.1.1.4.43(PC - CLEAN DRAIN FLASH TANK - DIA 1500 MM- (PGMA -81-012)) | 206817495
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 81012 | 1.11.1.1.4.43(PC - CLEAN DRAIN FLASH TANK - DIA 1500 MM- (PGMA -81-012)) | 206817496
PC -Condensate TRANSFER PUMP- (PGMA -81-100) | SUP | 2023-04-28 08:00 | 2024-11-30 17:00 |  |  |  | 81100 | 1.11.1.1.4(For SYN) | 206817497
Manufacturing | MFG | 2023-04-28 08:00 | 2024-10-16 17:00 |  |  |  | 81100 | 1.11.1.1.4.44(PC -Condensate TRANSFER PUMP- (PGMA -81-100)) | 206817498
Dispatch | DIS | 2024-10-17 08:00 | 2024-11-30 17:00 |  |  |  | 81100 | 1.11.1.1.4.44(PC -Condensate TRANSFER PUMP- (PGMA -81-100)) | 206817499
PC - PERFORMANCE GUARANTEE TEST MATERIALS- (PGMA -81-416) | SUP | 2023-04-28 08:00 | 2025-05-30 17:00 |  |  |  | 81416 | 1.11.1.1.4(For SYN) | 206817500
Manufacturing | MFG | 2023-04-28 08:00 | 2025-04-15 17:00 |  |  |  | 81416 | 1.11.1.1.4.45(PC - PERFORMANCE GUARANTEE TEST MATERIALS- (PGMA -81-416)) | 206817501
Dispatch | DIS | 2025-04-16 08:00 | 2025-05-30 17:00 |  |  |  | 81416 | 1.11.1.1.4.45(PC - PERFORMANCE GUARANTEE TEST MATERIALS- (PGMA -81-416)) | 206817502
BOI-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN | SUP | 2024-01-20 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817503
Ordering | ORD | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.11.1.1.4.46(BOI-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN ) | 206817504
Detailed Engineering | ENG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.11.1.1.4.46(BOI-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN ) | 206817505
Manufacturing | MFG | 2024-09-16 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.11.1.1.4.46(BOI-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN ) | 206817506
Dispatch | DIS | 2025-02-13 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.11.1.1.4.46(BOI-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN ) | 206817507
BOI-PEM - THERMAL INSULATION -ANCILLARY MATERIAL | SUP | 2023-12-01 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817508
Ordering | ORD | 2023-12-01 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.11.1.1.4.47(BOI-PEM - THERMAL INSULATION -ANCILLARY MATERIAL ) | 206817509
Detailed Engineering | ENG | 2024-02-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.11.1.1.4.47(BOI-PEM - THERMAL INSULATION -ANCILLARY MATERIAL ) | 206817510
Manufacturing | MFG | 2024-07-28 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.11.1.1.4.47(BOI-PEM - THERMAL INSULATION -ANCILLARY MATERIAL ) | 206817511
Dispatch | DIS | 2024-12-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.11.1.1.4.47(BOI-PEM - THERMAL INSULATION -ANCILLARY MATERIAL ) | 206817512
BOI-PEM - ALUMINIUM SHEETS/COILS | SUP | 2024-04-04 08:00 | 2025-05-28 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817513
Ordering | ORD | 2024-04-04 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.11.1.1.4.48(BOI-PEM - ALUMINIUM SHEETS/COILS) | 206817514
Detailed Engineering | ENG | 2024-07-03 08:00 | 2024-11-29 17:00 |  |  |  |  | 1.11.1.1.4.48(BOI-PEM - ALUMINIUM SHEETS/COILS) | 206817515
Manufacturing | MFG | 2024-11-30 08:00 | 2025-04-28 17:00 |  |  |  |  | 1.11.1.1.4.48(BOI-PEM - ALUMINIUM SHEETS/COILS) | 206817516
Dispatch | DIS | 2025-04-29 08:00 | 2025-05-28 17:00 |  |  |  |  | 1.11.1.1.4.48(BOI-PEM - ALUMINIUM SHEETS/COILS) | 206817517
BOI- PEM - AIR TRAPS | SUP | 2023-11-21 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817518
Ordering | ORD | 2023-11-21 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.11.1.1.4.49( BOI- PEM - AIR TRAPS ) | 206817519
Detailed Engineering | ENG | 2024-02-19 08:00 | 2024-07-17 17:00 |  |  |  |  | 1.11.1.1.4.49( BOI- PEM - AIR TRAPS ) | 206817520
Manufacturing | MFG | 2024-07-18 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.11.1.1.4.49( BOI- PEM - AIR TRAPS ) | 206817521
Dispatch | DIS | 2024-12-15 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.11.1.1.4.49( BOI- PEM - AIR TRAPS ) | 206817522
PEM - STEAM TRAPS | SUP | 2023-12-01 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.11.1.1.4(For SYN) | 206817523
Ordering | ORD | 2023-12-01 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.11.1.1.4.50(PEM - STEAM TRAPS ) | 206817524
Detailed Engineering | ENG | 2024-02-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.11.1.1.4.50(PEM - STEAM TRAPS ) | 206817525
Manufacturing | MFG | 2024-07-28 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.11.1.1.4.50(PEM - STEAM TRAPS ) | 206817526
Dispatch | DIS | 2024-12-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.11.1.1.4.50(PEM - STEAM TRAPS ) | 206817527
Valves | SUP | 2022-09-27 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.11.1(Supply) | 206817528
Supply | SUP | 2022-09-27 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.11.1.2(Valves) | 206817529
TRYV - Power Cycle Piping, DM. Water & Lube Oil System Valves ( PGMA - 80913) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80913 | 1.11.1.2.1(Supply) | 206817530
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80913 | 1.11.1.2.1.1(TRYV - Power Cycle Piping, DM. Water & Lube Oil System Valves ( PGMA - 80913)) | 206817531
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80913 | 1.11.1.2.1.1(TRYV - Power Cycle Piping, DM. Water & Lube Oil System Valves ( PGMA - 80913)) | 206817532
TRYV - Turbine Integral Piping system Valves( PGMA - 80919) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80919 | 1.11.1.2.1(Supply) | 206817533
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80919 | 1.11.1.2.1.2(TRYV - Turbine Integral Piping system Valves( PGMA - 80919)) | 206817534
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80919 | 1.11.1.2.1.2(TRYV - Turbine Integral Piping system Valves( PGMA - 80919)) | 206817535
TRYV - Extraction Line QCNRVs( PGMA - 80918) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80918 | 1.11.1.2.1(Supply) | 206817536
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80918 | 1.11.1.2.1.3(TRYV - Extraction Line QCNRVs( PGMA - 80918)) | 206817537
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80918 | 1.11.1.2.1.3(TRYV - Extraction Line QCNRVs( PGMA - 80918)) | 206817538
TRYV - HP Bypass System - Oil Supply System Valves( PGMA - 22100) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22100 | 1.11.1.2.1(Supply) | 206817539
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22100 | 1.11.1.2.1.4(TRYV - HP Bypass System - Oil Supply System Valves( PGMA - 22100)) | 206817540
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22100 | 1.11.1.2.1.4(TRYV - HP Bypass System - Oil Supply System Valves( PGMA - 22100)) | 206817541
TRYV - HP Bypass System - HP Bypass valve ASSY valves( PGMA - 22101) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22101 | 1.11.1.2.1(Supply) | 206817542
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22101 | 1.11.1.2.1.5(TRYV - HP Bypass System - HP Bypass valve ASSY valves( PGMA - 22101)) | 206817543
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22101 | 1.11.1.2.1.5(TRYV - HP Bypass System - HP Bypass valve ASSY valves( PGMA - 22101)) | 206817544
TRYV - HP Bypass System - Oil Piping HP Bypass Valves( PGMA - 22600) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22600 | 1.11.1.2.1(Supply) | 206817545
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22600 | 1.11.1.2.1.6(TRYV - HP Bypass System - Oil Piping HP Bypass Valves( PGMA - 22600)) | 206817546
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22600 | 1.11.1.2.1.6(TRYV - HP Bypass System - Oil Piping HP Bypass Valves( PGMA - 22600)) | 206817547
TRYV - HP Bypass System - Common HP Oil Piping Valves( PGMA - 22601) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22601 | 1.11.1.2.1(Supply) | 206817548
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22601 | 1.11.1.2.1.7(TRYV - HP Bypass System - Common HP Oil Piping Valves( PGMA - 22601)) | 206817549
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22601 | 1.11.1.2.1.7(TRYV - HP Bypass System - Common HP Oil Piping Valves( PGMA - 22601)) | 206817550
TRYV - HP Bypass System - Hand Tools( PGMA - 22701) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22701 | 1.11.1.2.1(Supply) | 206817551
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22701 | 1.11.1.2.1.8(TRYV - HP Bypass System - Hand Tools( PGMA - 22701)) | 206817552
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22701 | 1.11.1.2.1.8(TRYV - HP Bypass System - Hand Tools( PGMA - 22701)) | 206817553
TRYV - HP Bypass System - Special Equipments( PGMA - 22889) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22889 | 1.11.1.2.1(Supply) | 206817554
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22889 | 1.11.1.2.1.9(TRYV - HP Bypass System - Special Equipments( PGMA - 22889)) | 206817555
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22889 | 1.11.1.2.1.9(TRYV - HP Bypass System - Special Equipments( PGMA - 22889)) | 206817556
TRYV - HP Bypass System - Common Spares( PGMA - 22988) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 22988 | 1.11.1.2.1(Supply) | 206817557
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 22988 | 1.11.1.2.1.10(TRYV - HP Bypass System - Common Spares( PGMA - 22988)) | 206817558
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 22988 | 1.11.1.2.1.10(TRYV - HP Bypass System - Common Spares( PGMA - 22988)) | 206817559
TRYV - Root Valves (Normal Measurement+PG Test) ( PGMA - 80914) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80914 | 1.11.1.2.1(Supply) | 206817560
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80914 | 1.11.1.2.1.11(TRYV - Root Valves (Normal Measurement+PG Test) ( PGMA - 80914)) | 206817561
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80914 | 1.11.1.2.1.11(TRYV - Root Valves (Normal Measurement+PG Test) ( PGMA - 80914)) | 206817562
TRYV - SG Integral Piping Valves ( PGMA - 80905) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80905 | 1.11.1.2.1(Supply) | 206817563
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80905 | 1.11.1.2.1.12(TRYV - SG Integral Piping Valves ( PGMA - 80905)) | 206817564
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80905 | 1.11.1.2.1.12(TRYV - SG Integral Piping Valves ( PGMA - 80905)) | 206817565
TRYV - Low Pressure piping valves ( PGMA - 80277) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80277 | 1.11.1.2.1(Supply) | 206817566
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80277 | 1.11.1.2.1.13(TRYV - Low Pressure piping valves ( PGMA - 80277)) | 206817567
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80277 | 1.11.1.2.1.13(TRYV - Low Pressure piping valves ( PGMA - 80277)) | 206817568
TRYV - Heat Exchanger and Fabrication Water Expansion Relief Valves (WERV)( PGMA - 80278) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80278 | 1.11.1.2.1(Supply) | 206817569
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80278 | 1.11.1.2.1.14(TRYV - Heat Exchanger and Fabrication Water Expansion Relief Valves (WERV)( PGMA - 80278)) | 206817570
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80278 | 1.11.1.2.1.14(TRYV - Heat Exchanger and Fabrication Water Expansion Relief Valves (WERV)( PGMA - 80278)) | 206817571
TRYV - BFP Drive Turbine Valves including SRV and QCNRV's ( PGMA - 80279) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80279 | 1.11.1.2.1(Supply) | 206817572
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80279 | 1.11.1.2.1.15(TRYV - BFP Drive Turbine Valves including SRV and QCNRV's ( PGMA - 80279)) | 206817573
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80279 | 1.11.1.2.1.15(TRYV - BFP Drive Turbine Valves including SRV and QCNRV's ( PGMA - 80279)) | 206817574
TRYV - Acid Cleaning Valves ( PGMA - 80917) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80917 | 1.11.1.2.1(Supply) | 206817575
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80917 | 1.11.1.2.1.16(TRYV - Acid Cleaning Valves ( PGMA - 80917)) | 206817576
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80917 | 1.11.1.2.1.16(TRYV - Acid Cleaning Valves ( PGMA - 80917)) | 206817577
TRYV - Steam Blowing Valves ( PGMA - 80918) | SUP | 2024-05-28 08:00 | 2025-02-11 17:00 |  |  |  | 80918 | 1.11.1.2.1(Supply) | 206817578
Manufacturing | MFG | 2024-05-28 08:00 | 2024-11-27 17:00 |  |  |  | 80918 | 1.11.1.2.1.17(TRYV - Steam Blowing Valves ( PGMA - 80918)) | 206817579
Dispatch | DIS | 2024-08-28 08:00 | 2025-02-11 17:00 |  |  |  | 80918 | 1.11.1.2.1.17(TRYV - Steam Blowing Valves ( PGMA - 80918)) | 206817580
BOI-PEM - BUTTERFLY VALVES (STEAM SERVICE) | SUP | 2022-09-27 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.11.1.2.1(Supply) | 206817581
Ordering | ORD | 2023-10-19 08:00 | 2024-01-16 17:00 |  |  |  |  | 1.11.1.2.1.18(BOI-PEM - BUTTERFLY VALVES (STEAM SERVICE) ) | 206817582
Detailed Engineering | ENG | 2024-01-17 08:00 | 2024-06-14 17:00 |  |  |  |  | 1.11.1.2.1.18(BOI-PEM - BUTTERFLY VALVES (STEAM SERVICE) ) | 206817583
Manufacturing | MFG | 2022-09-27 08:00 | 2023-02-23 17:00 |  |  |  |  | 1.11.1.2.1.18(BOI-PEM - BUTTERFLY VALVES (STEAM SERVICE) ) | 206817584
Dispatch | DIS | 2024-06-15 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.11.1.2.1.18(BOI-PEM - BUTTERFLY VALVES (STEAM SERVICE) ) | 206817585
BOI-PEM - BALL VALVES | SUP | 2023-10-19 08:00 | 2024-12-11 17:00 |  |  |  |  | 1.11.1.2.1(Supply) | 206817586
Ordering | ORD | 2023-10-19 08:00 | 2024-01-16 17:00 |  |  |  |  | 1.11.1.2.1.19(BOI-PEM - BALL VALVES ) | 206817587
Detailed Engineering | ENG | 2024-01-17 08:00 | 2024-06-14 17:00 |  |  |  |  | 1.11.1.2.1.19(BOI-PEM - BALL VALVES ) | 206817588
Manufacturing | MFG | 2024-06-15 08:00 | 2024-11-11 17:00 |  |  |  |  | 1.11.1.2.1.19(BOI-PEM - BALL VALVES ) | 206817589
Dispatch | DIS | 2024-11-12 08:00 | 2024-12-11 17:00 |  |  |  |  | 1.11.1.2.1.19(BOI-PEM - BALL VALVES ) | 206817590
BOI-PEM - AIR RELEASE VALVES | SUP | 2023-08-23 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.11.1.2.1(Supply) | 206817591
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.11.1.2.1.20(BOI-PEM - AIR RELEASE VALVES ) | 206817592
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.11.1.2.1.20(BOI-PEM - AIR RELEASE VALVES ) | 206817593
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.11.1.2.1.20(BOI-PEM - AIR RELEASE VALVES ) | 206817594
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.11.1.2.1.20(BOI-PEM - AIR RELEASE VALVES ) | 206817595
Dispatch | DIS | 2024-10-16 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.11.1.2.1.20(BOI-PEM - AIR RELEASE VALVES ) | 206817596
BOI-PEM - LUBE OIL TRANSFER PUMPS | SUP | 2024-01-30 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.11.1.2.1(Supply) | 206817597
Ordering | ORD | 2024-01-30 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.11.1.2.1.21(BOI-PEM - LUBE OIL TRANSFER PUMPS) | 206817598
Detailed Engineering | ENG | 2024-04-29 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.11.1.2.1.21(BOI-PEM - LUBE OIL TRANSFER PUMPS) | 206817599
Manufacturing | MFG | 2024-09-26 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.11.1.2.1.21(BOI-PEM - LUBE OIL TRANSFER PUMPS) | 206817600
Dispatch | DIS | 2025-02-23 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.11.1.2.1.21(BOI-PEM - LUBE OIL TRANSFER PUMPS) | 206817601
BOI-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS | SUP | 2023-11-01 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.11.1.2.1(Supply) | 206817602
Ordering | ORD | 2023-11-01 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.11.1.2.1.22(BOI-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS) | 206817603
Detailed Engineering | ENG | 2024-01-30 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.11.1.2.1.22(BOI-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS) | 206817604
Manufacturing | MFG | 2024-06-28 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.11.1.2.1.22(BOI-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS) | 206817605
Dispatch | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.11.1.2.1.22(BOI-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS) | 206817606
BPL - Butterfly Valve | SUP | 2023-04-26 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.11.1.2.1(Supply) | 206817607
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-04-26 08:00 | 2024-03-23 17:00 |  |  |  |  | 1.11.1.2.1.23(BPL - Butterfly Valve) | 206817608
Manufacturing & TESTING | MFG | 2024-03-24 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.11.1.2.1.23(BPL - Butterfly Valve) | 206817609
Dispatch | DIS | 2025-03-24 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.11.1.2.1.23(BPL - Butterfly Valve) | 206817610
RECEIPT AT SITE | REC | 2025-04-23 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.11.1.2.1.23(BPL - Butterfly Valve) | 206817611
Erection | ERC | 2024-11-28 08:00 | 2026-02-02 17:00 |  |  |  |  | 1.11(Piping & Valves) | 206817612
DRIP LINES AND DRAINS | ERC | 2025-09-14 08:00 | 2025-12-31 17:00 |  |  |  |  | 1.11.2(Erection) | 206817613
Erection, welding and supports for drip and drain lines & valves | ERC | 2025-09-14 08:00 | 2025-12-25 17:00 |  |  |  |  | 1.11.2.1( DRIP LINES AND DRAINS) | 206817614
Hydro test of drip and drain lines | ERC | 2025-12-26 08:00 | 2025-12-31 17:00 |  |  |  |  | 1.11.2.1( DRIP LINES AND DRAINS) | 206817615
HRH PIPING | ERC | 2025-05-02 08:00 | 2025-11-28 17:00 |  |  |  |  | 1.11.2(Erection) | 206817616
Preassembly, Erection and align of HRH Pipe to IV | ERC | 2025-05-02 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.11.2.2( HRH PIPING) | 206817617
P-91 welding of HRH Pipe up to IV | ERC | 2025-05-02 08:00 | 2025-09-28 17:00 |  |  |  |  | 1.11.2.2( HRH PIPING) | 206817618
Erection of hangers of HRH up to IV | ERC | 2025-06-01 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.11.2.2( HRH PIPING) | 206817619
erection and align HRH line from IV to turbine | ERC | 2025-10-29 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.11.2.2( HRH PIPING) | 206817620
P-91 welding of HRH upto turbine | ERC | 2025-11-11 08:00 | 2025-11-19 17:00 |  |  |  |  | 1.11.2.2( HRH PIPING) | 206817621
Erection of supports up to turbine | ERC | 2025-11-20 08:00 | 2025-11-28 17:00 |  |  |  |  | 1.11.2.2( HRH PIPING) | 206817622
LP AND HP BYPASS PIPING | ERC | 2025-08-23 08:00 | 2026-01-25 17:00 |  |  |  |  | 1.11.2(Erection) | 206817623
Erection of LP BP upstream and downstream | ERC | 2025-08-23 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817624
Erection of LP warm up piping | ERC | 2025-09-16 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817625
P-91 welding on LPBP piping | ERC | 2025-09-28 08:00 | 2025-10-21 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817626
Erection of hangers of LPBP piping | ERC | 2025-10-22 08:00 | 2025-11-08 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817627
Erection of HP Bp upstream and downstream | ERC | 2025-11-09 08:00 | 2025-12-02 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817628
Erection of HP warm up piping | ERC | 2025-12-03 08:00 | 2025-12-14 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817629
P-91 welding on HPBP piping | ERC | 2025-12-15 08:00 | 2026-01-07 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817630
Erection of hangers of HPBP | ERC | 2026-01-08 08:00 | 2026-01-25 17:00 |  |  |  |  | 1.11.2.3( LP AND HP BYPASS PIPING) | 206817631
Condensate PIPING | ERC | 2025-03-09 08:00 | 2025-09-04 17:00 |  |  |  |  | 1.11.2(Erection) | 206817632
Erection, welding, valves and supports for Condensate line | ERC | 2025-03-09 08:00 | 2025-09-04 17:00 |  |  |  |  | 1.11.2.4(Condensate PIPING) | 206817633
BOILER FEED LINE PIPING | ERC | 2025-02-17 08:00 | 2025-10-11 17:00 |  |  |  |  | 1.11.2(Erection) | 206817634
Erection, welding, valves and supports for BFD and suction lines | ERC | 2025-02-17 08:00 | 2025-08-15 17:00 |  |  |  |  | 1.11.2.5( BOILER FEED LINE PIPING) | 206817635
Hydro test of BFD lines | ERC | 2025-08-16 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.11.2.5( BOILER FEED LINE PIPING) | 206817636
Thermal insulation | ERC | 2025-08-22 08:00 | 2025-10-11 17:00 |  |  |  |  | 1.11.2.5( BOILER FEED LINE PIPING) | 206817637
MAIN STEAM PIPING | ERC | 2024-11-28 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.11.2(Erection) | 206817638
for Condensate and align MS Pipe from SH header to BSV | ERC | 2024-11-28 08:00 | 2025-01-26 17:00 |  |  |  |  | 1.11.2.6( MAIN STEAM PIPING) | 206817639
P-91 welding and SR of MS Pipe from SH header to BSV | ERC | 2024-11-28 08:00 | 2025-02-25 17:00 |  |  |  |  | 1.11.2.6( MAIN STEAM PIPING) | 206817640
Erection of hangers from SH header to BSV | ERC | 2024-12-28 08:00 | 2025-03-27 17:00 |  |  |  |  | 1.11.2.6( MAIN STEAM PIPING) | 206817641
for Condensate and align of MS Pipe from BSV to ESV | ERC | 2025-04-02 08:00 | 2025-06-30 17:00 |  |  |  |  | 1.11.2.6( MAIN STEAM PIPING) | 206817642
P-91 welding and SR of MS Pipe from BSV to ESV | ERC | 2025-04-02 08:00 | 2025-07-30 17:00 |  |  |  |  | 1.11.2.6( MAIN STEAM PIPING) | 206817643
Erection of hangers of MS Pipe from BSV to ESV | ERC | 2025-05-02 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.11.2.6( MAIN STEAM PIPING) | 206817644
EXTRACTION PIPING | ERC | 2025-08-10 08:00 | 2025-12-29 17:00 |  |  |  |  | 1.11.2(Erection) | 206817645
Extraction piping to LPH-1, 2, 3 | ERC | 2025-08-10 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.11.2.7( EXTRACTION PIPING) | 206817646
Extraction piping to Deaerator | ERC | 2025-09-03 08:00 | 2025-09-14 17:00 |  |  |  |  | 1.11.2.7( EXTRACTION PIPING) | 206817647
Extraction piping to HPH 6, 7 | ERC | 2025-09-15 08:00 | 2025-10-02 17:00 |  |  |  |  | 1.11.2.7( EXTRACTION PIPING) | 206817648
Erection piping to TDBFP | ERC | 2025-10-03 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.11.2.7( EXTRACTION PIPING) | 206817649
HP welding on ext. lines | ERC | 2025-10-29 08:00 | 2025-12-03 17:00 |  |  |  |  | 1.11.2.7( EXTRACTION PIPING) | 206817650
Erection of hangers | ERC | 2025-12-04 08:00 | 2025-12-29 17:00 |  |  |  |  | 1.11.2.7( EXTRACTION PIPING) | 206817651
CRH PIPING | ERC | 2025-04-02 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.11.2(Erection) | 206817652
ext. and align of CRH Pipe from Turbine to RH header | ERC | 2025-04-02 08:00 | 2025-06-30 17:00 |  |  |  |  | 1.11.2.8( CRH PIPING) | 206817653
P-91 welding and SR in main CRH Pipe from Turbine to RH header | ERC | 2025-04-02 08:00 | 2025-07-30 17:00 |  |  |  |  | 1.11.2.8( CRH PIPING) | 206817654
Erection of tap off to TDBFP, Aux PRDS and Deaerator | ERC | 2025-07-01 08:00 | 2025-07-30 17:00 |  |  |  |  | 1.11.2.8( CRH PIPING) | 206817655
HP welding and testing on Tap Off piping from CRH Pipe | ERC | 2025-07-16 08:00 | 2025-08-14 17:00 |  |  |  |  | 1.11.2.8( CRH PIPING) | 206817656
Erection of hangers | ERC | 2025-05-02 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.11.2.8( CRH PIPING) | 206817657
MISC HP & LP PIPING WITH VALVES & SUPPORTS | ERC | 2025-06-16 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.11.2(Erection) | 206817658
Hydro test of MS piping | ERC | 2025-08-30 08:00 | 2025-09-05 17:00 |  |  |  |  | 1.11.2(Erection) | 206817659
Insulation of MS and HPBP upstream piping | ERC | 2025-09-06 08:00 | 2026-01-03 17:00 |  |  |  |  | 1.11.2(Erection) | 206817660
Hydro test of HRH piping | ERC | 2025-10-29 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.11.2(Erection) | 206817661
Insulation of HRH and LPBP piping | ERC | 2025-11-05 08:00 | 2026-02-02 17:00 |  |  |  |  | 1.11.2(Erection) | 206817662
Hydro test of CRH piping | ERC | 2025-08-30 08:00 | 2025-09-05 17:00 |  |  |  |  | 1.11.2(Erection) | 206817663
Insulation of CRH & HPBP downstream piping | ERC | 2025-09-06 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.11.2(Erection) | 206817664
Electrical | OTH | 2022-09-27 08:00 | 2026-05-07 17:00 |  |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206817665
Rel of DGW for Service power Transformer, Aux Transformer, Misc. transformer | PE - RFC | 2023-04-29 08:00 | 2024-02-22 17:00 |  |  |  |  | 1.12(Electrical) | 206817666
Rel of DGW for ST | PE - RFC | 2024-02-23 08:00 | 2024-02-23 17:00 |  |  |  | PCE-03900 | 1.12(Electrical) | 206817667
Rel of DGW for ESP/FGD control room | PE - RFC | 2023-04-15 08:00 | 2023-04-15 17:00 |  |  |  | PCE-04000 | 1.12(Electrical) | 206817668
Civil | CIV | 2023-05-16 08:00 | 2025-08-06 17:00 |  |  |  |  | 1.12(Electrical) | 206817669
TRANSFORMER YARD | CIV | 2024-02-23 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.12.4(Civil) | 206817670
GENERATOR TRANSFORMER FOUNDATION | CIV | 2024-02-23 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817671
foundation readiness for Erection | CIV | 2024-02-23 08:00 | 2024-06-21 17:00 |  |  |  |  | 1.12.4.1.1(GENERATOR TRANSFORMER FOUNDATION) | 206817672
Rail fixing & final stage casting | CIV | 2024-06-22 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.12.4.1.1(GENERATOR TRANSFORMER FOUNDATION) | 206817673
STATION TRANSFORMER FOUNDATION | CIV | 2024-02-24 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817674
foundation readiness correction | CIV | 2024-02-24 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.12.4.1.2(STATION TRANSFORMER FOUNDATION) | 206817675
Rail fixing & final stage casting | CIV | 2024-07-03 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.12.4.1.2(STATION TRANSFORMER FOUNDATION) | 206817676
Service power transformer | CIV | 2024-08-25 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817677
foundation readiness correction | CIV | 2024-08-25 08:00 | 2025-01-01 17:00 |  |  |  |  | 1.12.4.1.3(Service power transformer) | 206817678
Rail fixing & final stage casting | CIV | 2025-01-02 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.12.4.1.3(Service power transformer) | 206817679
Unit Aux Transformer | CIV | 2024-08-25 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817680
foundation readiness correction | CIV | 2024-08-25 08:00 | 2025-01-01 17:00 |  |  |  |  | 1.12.4.1.4(Unit Aux Transformer) | 206817681
Rail fixing & final stage casting | CIV | 2025-01-02 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.12.4.1.4(Unit Aux Transformer) | 206817682
Misc. Service Transformer | CIV | 2024-08-25 08:00 | 2025-01-01 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817683
foundation readiness Misc. | CIV | 2024-08-25 08:00 | 2025-01-01 17:00 |  |  |  |  | 1.12.4.1.5(Misc. Service Transformer) | 206817684
UNIT TRANSFORMER FOUNDATION | CIV | 2024-06-28 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817685
foundation readiness Misc. | CIV | 2024-06-28 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.4.1.6(UNIT TRANSFORMER FOUNDATION) | 206817686
Rail fixing & final stage casting | CIV | 2024-11-05 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.12.4.1.6(UNIT TRANSFORMER FOUNDATION) | 206817687
STATION AUXILLARY TRANSFORMER FOUNDATION | CIV | 2024-07-08 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.4.1(TRANSFORMER YARD) | 206817688
foundation readiness Misc. | CIV | 2024-07-08 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.12.4.1.7(STATION AUXILLARY TRANSFORMER FOUNDATION) | 206817689
Rail fixing & final stage casting | CIV | 2024-11-15 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.4.1.7(STATION AUXILLARY TRANSFORMER FOUNDATION) | 206817690
Fire Wall, Fencing, BPI , LA & other Misc. Works | CIV | 2024-11-15 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.12.4(Civil) | 206817691
SPBD Pedestals FOUNDATION | CIV | 2025-01-02 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.12.4(Civil) | 206817692
Excavation | CIV | 2025-01-02 08:00 | 2025-01-21 17:00 |  |  |  |  | 1.12.4.3(SPBD Pedestals FOUNDATION) | 206817693
RCC foundation | CIV | 2025-01-12 08:00 | 2025-03-07 17:00 |  |  |  |  | 1.12.4.3(SPBD Pedestals FOUNDATION) | 206817694
RCC pedestal | CIV | 2025-02-16 08:00 | 2025-04-16 17:00 |  |  |  |  | 1.12.4.3(SPBD Pedestals FOUNDATION) | 206817695
Backfilling & Finishing Work | CIV | 2025-04-13 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.12.4.3(SPBD Pedestals FOUNDATION) | 206817696
MV SwitchGear Room | CIV | 2025-03-16 08:00 | 2025-08-06 17:00 |  |  |  |  | 1.12.4(Civil) | 206817697
RCC in column encasing works | CIV | 2025-03-16 08:00 | 2025-03-30 17:00 |  |  |  |  | 1.12.4.4(MV SwitchGear Room) | 206817698
Brick Work & Plastering | CIV | 2025-05-07 08:00 | 2025-06-20 17:00 |  |  |  |  | 1.12.4.4(MV SwitchGear Room) | 206817699
Flooring | CIV | 2025-06-21 08:00 | 2025-06-27 17:00 |  |  |  |  | 1.12.4.4(MV SwitchGear Room) | 206817700
Door ,Window- glass ,aluminium fixing works | CIV | 2025-06-28 08:00 | 2025-07-22 17:00 |  |  |  |  | 1.12.4.4(MV SwitchGear Room) | 206817701
Finishing works | CIV | 2025-07-23 08:00 | 2025-08-06 17:00 |  |  |  |  | 1.12.4.4(MV SwitchGear Room) | 206817702
LT SwitchGear Room | CIV | 2025-01-15 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.12.4(Civil) | 206817703
RCC in column encasing works | CIV | 2025-01-15 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.12.4.5(LT SwitchGear Room) | 206817704
Brick Work & Plastering | CIV | 2025-01-30 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.12.4.5(LT SwitchGear Room) | 206817705
Flooring | CIV | 2025-03-16 08:00 | 2025-03-22 17:00 |  |  |  |  | 1.12.4.5(LT SwitchGear Room) | 206817706
Door ,Window- glass ,aluminium fixing works | CIV | 2025-03-23 08:00 | 2025-04-16 17:00 |  |  |  |  | 1.12.4.5(LT SwitchGear Room) | 206817707
Finishing works | CIV | 2025-04-17 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.12.4.5(LT SwitchGear Room) | 206817708
UPS & Battery Room | CIV | 2024-12-16 08:00 | 2025-05-16 17:00 |  |  |  |  | 1.12.4(Civil) | 206817709
RCC in column encasing works | CIV | 2024-12-16 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.12.4.6(UPS & Battery Room) | 206817710
Brick Work & Plastering | CIV | 2024-12-31 08:00 | 2025-02-13 17:00 |  |  |  |  | 1.12.4.6(UPS & Battery Room) | 206817711
Flooring | CIV | 2025-02-14 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.12.4.6(UPS & Battery Room) | 206817712
false ceiling & insulation works | CIV | 2025-02-21 08:00 | 2025-04-06 17:00 |  |  |  |  | 1.12.4.6(UPS & Battery Room) | 206817713
Door ,Window- glass ,aluminium fixing works | CIV | 2025-04-07 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.12.4.6(UPS & Battery Room) | 206817714
Finishing works | CIV | 2025-05-02 08:00 | 2025-05-16 17:00 |  |  |  |  | 1.12.4.6(UPS & Battery Room) | 206817715
IPBD Pedestals FOUNDATION | CIV | 2024-10-26 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.12.4(Civil) | 206817716
Excavation | CIV | 2024-10-26 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.12.4.7(IPBD Pedestals FOUNDATION) | 206817717
RCC foundation | CIV | 2024-11-10 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.4.7(IPBD Pedestals FOUNDATION) | 206817718
RCC pedestal | CIV | 2024-12-14 08:00 | 2025-02-16 17:00 |  |  |  |  | 1.12.4.7(IPBD Pedestals FOUNDATION) | 206817719
Backfilling & Finishing Work | CIV | 2025-02-13 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.12.4.7(IPBD Pedestals FOUNDATION) | 206817720
ESP/FGD Control Room | CIV | 2023-05-16 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.12.4(Civil) | 206817721
Up to Plinth Level | CIV | 2023-05-16 08:00 | 2023-10-12 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817722
EXCAVATION | CIV | 2023-05-16 08:00 | 2023-05-30 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817723
PCC | CIV | 2023-05-31 08:00 | 2023-06-09 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817724
Reinforcement cutting & Bending of Footings & columns (1st,2nd,3rd) | CIV | 2023-06-10 08:00 | 2023-06-29 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817725
Footing Casting work | CIV | 2023-06-30 08:00 | 2023-07-24 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817726
Pedestal 1st,2nd, Final lift- Till Plinth Beam Level | CIV | 2023-07-25 08:00 | 2023-09-17 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817727
Backfilling | CIV | 2023-09-18 08:00 | 2023-09-27 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817728
Plinth Beam Concreting Work | CIV | 2023-09-28 08:00 | 2023-10-12 17:00 |  |  |  |  | 1.12.4.8.1(Up to Plinth Level) | 206817729
up to First Floor | CIV | 2023-10-03 08:00 | 2023-12-21 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817730
Fabrication of Column & Bracings | ERC | 2023-10-03 08:00 | 2023-11-01 17:00 |  |  |  |  | 1.12.4.8.2(up to First Floor) | 206817731
Erection of Column & Bracings | ERC | 2023-10-23 08:00 | 2023-11-06 17:00 |  |  |  |  | 1.12.4.8.2(up to First Floor) | 206817732
Fabrication of First Floor Beams | ERC | 2023-10-28 08:00 | 2023-11-26 17:00 |  |  |  |  | 1.12.4.8.2(up to First Floor) | 206817733
Erection of First Floor Beams | ERC | 2023-11-17 08:00 | 2023-12-01 17:00 |  |  |  |  | 1.12.4.8.2(up to First Floor) | 206817734
Slab Casting of First Floor | CIV | 2023-12-02 08:00 | 2023-12-21 17:00 |  |  |  |  | 1.12.4.8.2(up to First Floor) | 206817735
Up to 2nd Floor | CIV | 2023-12-02 08:00 | 2024-01-25 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817736
Fabrication of Second Floor Beams | ERC | 2023-12-02 08:00 | 2023-12-31 17:00 |  |  |  |  | 1.12.4.8.3(Up to 2nd Floor) | 206817737
Erection of Second Floor Beams | ERC | 2023-12-22 08:00 | 2024-01-05 17:00 |  |  |  |  | 1.12.4.8.3(Up to 2nd Floor) | 206817738
Slab Casting of Second Floor | CIV | 2024-01-06 08:00 | 2024-01-25 17:00 |  |  |  |  | 1.12.4.8.3(Up to 2nd Floor) | 206817739
Up to Third Floor & Roof | CIV | 2024-01-06 08:00 | 2024-04-09 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817740
Fabrication of Third Floor Beams | ERC | 2024-01-06 08:00 | 2024-02-04 17:00 |  |  |  |  | 1.12.4.8.4(Up to Third Floor & Roof) | 206817741
Erection of Third Floor Beams | ERC | 2024-01-26 08:00 | 2024-02-09 17:00 |  |  |  |  | 1.12.4.8.4(Up to Third Floor & Roof) | 206817742
Slab Casting of Third Floor | CIV | 2024-02-10 08:00 | 2024-02-29 17:00 |  |  |  |  | 1.12.4.8.4(Up to Third Floor & Roof) | 206817743
Parapet wall of Roof | CIV | 2024-03-01 08:00 | 2024-03-10 17:00 |  |  |  |  | 1.12.4.8.4(Up to Third Floor & Roof) | 206817744
Water Proofing of Roof | CIV | 2024-03-11 08:00 | 2024-04-09 17:00 |  |  |  |  | 1.12.4.8.4(Up to Third Floor & Roof) | 206817745
Brickwork | CIV | 2024-01-11 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817746
Plaster Exterior & Interior | CIV | 2024-02-10 08:00 | 2024-06-08 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817747
Painting | CIV | 2024-05-20 08:00 | 2024-07-18 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817748
Flooring | CIV | 2024-06-19 08:00 | 2024-08-17 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817749
Finishing Works | CIV | 2024-07-19 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817750
Transformer Foundations & adjoining wall | CIV | 2024-04-10 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.12.4.8(ESP/FGD Control Room) | 206817751
Supply | SUP | 2022-09-27 08:00 | 2025-12-17 17:00 |  |  |  |  | 1.12(Electrical) | 206817752
JHS - 25 MVA Service Power Transformer | SUP | 2023-04-05 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.12.5(Supply) | 206817753
Engineering | ENG | 2023-04-05 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.12.5.1(JHS - 25 MVA Service Power Transformer) | 206817754
Manufacturing & testing | MFG | 2023-08-03 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.12.5.1(JHS - 25 MVA Service Power Transformer) | 206817755
Packing, Dispatch | DIS | 2024-07-20 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.12.5.1(JHS - 25 MVA Service Power Transformer) | 206817756
JHS - 16 MVA Unit Aux Transformer | SUP | 2023-04-05 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.12.5(Supply) | 206817757
Engineering | ENG | 2023-04-05 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.12.5.2(JHS - 16 MVA Unit Aux Transformer) | 206817758
Manufacturing & testing | MFG | 2023-08-03 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.12.5.2(JHS - 16 MVA Unit Aux Transformer) | 206817759
Packing, Dispatch | DIS | 2024-07-20 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.12.5.2(JHS - 16 MVA Unit Aux Transformer) | 206817760
JHS - 7.5 MVA Misc. Service Transformer | SUP | 2022-09-27 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.12.5(Supply) | 206817761
Engineering | ENG | 2022-09-27 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.12.5.3(JHS - 7.5 MVA Misc. Service Transformer) | 206817762
Manufacturing & testing | MFG | 2023-01-25 08:00 | 2024-05-10 17:00 |  |  |  |  | 1.12.5.3(JHS - 7.5 MVA Misc. Service Transformer) | 206817763
Packing, Dispatch | DIS | 2024-01-12 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.12.5.3(JHS - 7.5 MVA Misc. Service Transformer) | 206817764
JHS - UNIT TRANSFORMER | SUP | 2023-07-04 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.12.5(Supply) | 206817765
Engineering | ENG | 2023-07-04 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.12.5.4(JHS - UNIT TRANSFORMER) | 206817766
Manufacturing & testing | MFG | 2023-11-01 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.12.5.4(JHS - UNIT TRANSFORMER) | 206817767
Dispatch | DIS | 2024-06-28 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.12.5.4(JHS - UNIT TRANSFORMER) | 206817768
RECEIPT | SUP | 2024-09-26 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.12.5.4(JHS - UNIT TRANSFORMER) | 206817769
JHS - Dry Type Transformer (DTT) | SUP | 2023-08-03 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.12.5(Supply) | 206817770
Engineering | ENG | 2023-08-03 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.12.5.5(JHS - Dry Type Transformer (DTT)) | 206817771
Manufacturing & testing | MFG | 2023-11-01 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.12.5.5(JHS - Dry Type Transformer (DTT)) | 206817772
Dispatch | DIS | 2024-04-29 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.12.5.5(JHS - Dry Type Transformer (DTT)) | 206817773
RECEIPT | REC | 2024-07-28 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.12.5.5(JHS - Dry Type Transformer (DTT)) | 206817774
JHS - HVR | SUP | 2023-10-02 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.12.5(Supply) | 206817775
Engineering | ENG | 2023-10-02 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.12.5.6(JHS - HVR) | 206817776
Manufacturing & testing | MFG | 2023-12-31 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.12.5.6(JHS - HVR) | 206817777
Dispatch | DIS | 2024-04-29 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.12.5.6(JHS - HVR) | 206817778
RECEIPT | REC | 2024-05-29 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.12.5.6(JHS - HVR) | 206817779
BPL - Generator Transformer | SUP | 2023-03-11 08:00 | 2025-03-19 17:00 |  |  |  |  | 1.12.5(Supply) | 206817780
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-03-11 08:00 | 2024-02-13 17:00 |  |  |  |  | 1.12.5.7(BPL - Generator Transformer) | 206817781
Manufacturing & TESTING | MFG | 2024-02-14 08:00 | 2025-01-18 17:00 |  |  |  |  | 1.12.5.7(BPL - Generator Transformer) | 206817782
Dispatch | DIS | 2025-01-19 08:00 | 2025-02-17 17:00 |  |  |  |  | 1.12.5.7(BPL - Generator Transformer) | 206817783
RECEIPT AT SITE | REC | 2025-02-18 08:00 | 2025-03-19 17:00 |  |  |  |  | 1.12.5.7(BPL - Generator Transformer) | 206817784
BPL - HT Switchgear | SUP | 2024-09-25 08:00 | 2025-09-21 17:00 |  |  |  |  | 1.12.5(Supply) | 206817785
Engineering, INDENTING AND PROCUREMENT | ENG | 2024-09-25 08:00 | 2025-04-24 17:00 |  |  |  |  | 1.12.5.8(BPL - HT Switchgear) | 206817786
Manufacturing & TESTING | MFG | 2025-04-25 08:00 | 2025-07-23 17:00 |  |  |  |  | 1.12.5.8(BPL - HT Switchgear) | 206817787
Dispatch | DIS | 2025-07-24 08:00 | 2025-08-22 17:00 |  |  |  |  | 1.12.5.8(BPL - HT Switchgear) | 206817788
RECEIPT AT SITE | REC | 2025-08-23 08:00 | 2025-09-21 17:00 |  |  |  |  | 1.12.5.8(BPL - HT Switchgear) | 206817789
BPL - Station Transformer | SUP | 2023-04-05 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.12.5(Supply) | 206817790
Engineering | ENG | 2023-04-05 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.12.5.9(BPL - Station Transformer) | 206817791
Manufacturing & testing | MFG | 2023-08-03 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.12.5.9(BPL - Station Transformer) | 206817792
Packing, Dispatch | DIS | 2024-07-20 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.12.5.9(BPL - Station Transformer) | 206817793
BPL - GRP | SUP | 2023-12-31 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.12.5(Supply) | 206817794
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-12-31 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.12.5.10( BPL - GRP) | 206817795
Manufacturing & TESTING | MFG | 2024-12-30 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.12.5.10( BPL - GRP) | 206817796
Dispatch | DIS | 2025-06-18 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.12.5.10( BPL - GRP) | 206817797
RECEIPT AT SITE | REC | 2025-07-18 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.12.5.10( BPL - GRP) | 206817798
RUDR - SPBD | SUP | 2023-11-21 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.12.5(Supply) | 206817799
Main Supply | SUP | 2023-11-21 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.12.5.11(RUDR - SPBD) | 206817800
Engineering & PROCUREMENT | ENG | 2023-11-21 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.12.5.11.1(Main Supply) | 206817801
Manufacturing | MFG | 2024-10-21 08:00 | 2025-04-18 17:00 |  |  |  |  | 1.12.5.11.1(Main Supply) | 206817802
Dispatch | DIS | 2025-02-18 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.12.5.11.1(Main Supply) | 206817803
RECEIPT AT SITE | REC | 2025-03-10 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.12.5.11.1(Main Supply) | 206817804
BOIs-SPBD | SUP | 2023-11-21 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.12.5.11(RUDR - SPBD) | 206817805
Engineering & PROCUREMENT | ENG | 2023-11-21 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.12.5.11.2(BOIs-SPBD) | 206817806
Manufacturing | MFG | 2024-10-21 08:00 | 2025-04-18 17:00 |  |  |  |  | 1.12.5.11.2(BOIs-SPBD) | 206817807
Dispatch | DIS | 2025-02-18 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.12.5.11.2(BOIs-SPBD) | 206817808
RECEIPT AT SITE | REC | 2025-03-10 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.12.5.11.2(BOIs-SPBD) | 206817809
RUDR - IPBD | SUP | 2023-12-31 08:00 | 2025-08-26 17:00 |  |  |  |  | 1.12.5(Supply) | 206817810
Main Supply | SUP | 2023-12-31 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.12.5.12(RUDR - IPBD) | 206817811
Engineering & PROCUREMENT | ENG | 2023-12-31 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.12.5.12.1(Main Supply) | 206817812
Manufacturing | MFG | 2024-11-30 08:00 | 2025-05-28 17:00 |  |  |  |  | 1.12.5.12.1(Main Supply) | 206817813
Dispatch | DIS | 2025-03-30 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.12.5.12.1(Main Supply) | 206817814
RECEIPT AT SITE | REC | 2025-04-19 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.12.5.12.1(Main Supply) | 206817815
BOIs-IPBD | SUP | 2024-01-10 08:00 | 2025-08-26 17:00 |  |  |  |  | 1.12.5.12(RUDR - IPBD) | 206817816
Engineering & PROCUREMENT | ENG | 2024-01-10 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.12.5.12.2(BOIs-IPBD) | 206817817
Manufacturing | MFG | 2024-12-10 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.12.5.12.2(BOIs-IPBD) | 206817818
Dispatch | DIS | 2025-04-09 08:00 | 2025-08-06 17:00 |  |  |  |  | 1.12.5.12.2(BOIs-IPBD) | 206817819
RECEIPT AT SITE | REC | 2025-04-29 08:00 | 2025-08-26 17:00 |  |  |  |  | 1.12.5.12.2(BOIs-IPBD) | 206817820
SBU - LV Switchgear & L V Bus Duct | SUP | 2023-08-23 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.12.5(Supply) | 206817821
Engineering & PROCUREMENT | ENG | 2023-08-23 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.12.5.13(SBU - LV Switchgear & L V Bus Duct) | 206817822
Manufacturing | MFG | 2023-12-06 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.13(SBU - LV Switchgear & L V Bus Duct) | 206817823
Dispatch | DIS | 2023-12-21 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.12.5.13(SBU - LV Switchgear & L V Bus Duct) | 206817824
RECEIPT AT SITE | REC | 2024-01-10 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.12.5.13(SBU - LV Switchgear & L V Bus Duct) | 206817825
BOI- PEM - DC BATTERY CHARGER | SUP | 2023-09-02 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.5(Supply) | 206817826
Ordering | ORD | 2023-09-02 08:00 | 2023-11-30 17:00 |  |  |  |  | 1.12.5.14(BOI- PEM - DC BATTERY CHARGER ) | 206817827
Detailed Engineering | ENG | 2023-12-01 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.14(BOI- PEM - DC BATTERY CHARGER ) | 206817828
Manufacturing | MFG | 2024-04-19 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.12.5.14(BOI- PEM - DC BATTERY CHARGER ) | 206817829
Dispatch | DIS | 2024-10-06 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.5.14(BOI- PEM - DC BATTERY CHARGER ) | 206817830
BOI-PEM - CABLE TRAYS & ACC. | SUP | 2023-08-23 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5(Supply) | 206817831
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.12.5.15(BOI-PEM - CABLE TRAYS & ACC. ) | 206817832
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.15(BOI-PEM - CABLE TRAYS & ACC. ) | 206817833
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.12.5.15(BOI-PEM - CABLE TRAYS & ACC. ) | 206817834
Dispatch | DIS | 2024-08-17 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.15(BOI-PEM - CABLE TRAYS & ACC. ) | 206817835
BOI-PEM - ABOVE GROUND EARTHING MATERIALS EXCEPT CHP, AHP & SWITCHYARD | SUP | 2023-09-22 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5(Supply) | 206817836
Ordering | ORD | 2023-09-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.12.5.16(BOI-PEM - ABOVE GROUND EARTHING MATERIALS EXCEPT CHP, AHP & SWITCHYARD) | 206817837
Detailed Engineering | ENG | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.16(BOI-PEM - ABOVE GROUND EARTHING MATERIALS EXCEPT CHP, AHP & SWITCHYARD) | 206817838
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.12.5.16(BOI-PEM - ABOVE GROUND EARTHING MATERIALS EXCEPT CHP, AHP & SWITCHYARD) | 206817839
Dispatch | DIS | 2024-08-17 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.16(BOI-PEM - ABOVE GROUND EARTHING MATERIALS EXCEPT CHP, AHP & SWITCHYARD) | 206817840
BOI-PEM - CABLE TERM.& JOINT KITS | SUP | 2023-09-22 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5(Supply) | 206817841
Ordering | ORD | 2023-09-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.12.5.17(BOI-PEM - CABLE TERM.& JOINT KITS ) | 206817842
Detailed Engineering | ENG | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.17(BOI-PEM - CABLE TERM.& JOINT KITS ) | 206817843
Manufacturing | MFG | 2024-04-19 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.17(BOI-PEM - CABLE TERM.& JOINT KITS ) | 206817844
Dispatch | DIS | 2024-12-05 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5.17(BOI-PEM - CABLE TERM.& JOINT KITS ) | 206817845
BOI-PEM - TREFOIL CLAMPS | SUP | 2023-09-22 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5(Supply) | 206817846
Ordering | ORD | 2023-09-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.12.5.18(BOI-PEM - TREFOIL CLAMPS ) | 206817847
Detailed Engineering | ENG | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.18(BOI-PEM - TREFOIL CLAMPS ) | 206817848
Manufacturing | MFG | 2024-04-19 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.18(BOI-PEM - TREFOIL CLAMPS ) | 206817849
Dispatch | DIS | 2024-12-05 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5.18(BOI-PEM - TREFOIL CLAMPS ) | 206817850
BOI- PEM - LT PVC CONTROL CABLE | SUP | 2023-09-22 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5(Supply) | 206817851
Ordering | ORD | 2023-09-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.12.5.19(BOI- PEM - LT PVC CONTROL CABLE) | 206817852
Detailed Engineering | ENG | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.19(BOI- PEM - LT PVC CONTROL CABLE) | 206817853
Manufacturing | MFG | 2024-04-19 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.19(BOI- PEM - LT PVC CONTROL CABLE) | 206817854
Dispatch | DIS | 2024-12-05 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5.19(BOI- PEM - LT PVC CONTROL CABLE) | 206817855
BOI-PEM - DC Lead Acid/Nicad Battery | SUP | 2023-12-01 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.12.5(Supply) | 206817856
Ordering | ORD | 2023-12-01 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.12.5.20(BOI-PEM - DC Lead Acid/Nicad Battery) | 206817857
Detailed Engineering | ENG | 2024-02-29 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.12.5.20(BOI-PEM - DC Lead Acid/Nicad Battery) | 206817858
Manufacturing | MFG | 2024-06-28 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.12.5.20(BOI-PEM - DC Lead Acid/Nicad Battery) | 206817859
Dispatch | DIS | 2024-10-26 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.12.5.20(BOI-PEM - DC Lead Acid/Nicad Battery) | 206817860
BOI-PEM - Electrical Lab (Calibration and diagnostics) | SUP | 2023-09-22 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5(Supply) | 206817861
Ordering | ORD | 2023-09-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.12.5.21(BOI-PEM - Electrical Lab (Calibration and diagnostics)) | 206817862
Detailed Engineering | ENG | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.21(BOI-PEM - Electrical Lab (Calibration and diagnostics)) | 206817863
Manufacturing | MFG | 2024-04-19 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.21(BOI-PEM - Electrical Lab (Calibration and diagnostics)) | 206817864
Dispatch | DIS | 2024-12-05 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.12.5.21(BOI-PEM - Electrical Lab (Calibration and diagnostics)) | 206817865
BOI-PEM - Electrical Lab (Metering and testing) | SUP | 2024-03-10 08:00 | 2025-08-01 17:00 |  |  |  |  | 1.12.5(Supply) | 206817866
Ordering | ORD | 2024-03-10 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.12.5.22(BOI-PEM - Electrical Lab (Metering and testing)) | 206817867
Detailed Engineering | ENG | 2024-06-28 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.12.5.22(BOI-PEM - Electrical Lab (Metering and testing)) | 206817868
Manufacturing | MFG | 2025-02-03 08:00 | 2025-07-02 17:00 |  |  |  |  | 1.12.5.22(BOI-PEM - Electrical Lab (Metering and testing)) | 206817869
Dispatch | DIS | 2025-07-03 08:00 | 2025-08-01 17:00 |  |  |  |  | 1.12.5.22(BOI-PEM - Electrical Lab (Metering and testing)) | 206817870
BOI-PEM - FIRE SEALING SYSTEM | SUP | 2024-10-24 08:00 | 2025-12-17 17:00 |  |  |  |  | 1.12.5(Supply) | 206817871
Ordering | ORD | 2024-10-24 08:00 | 2025-01-21 17:00 |  |  |  |  | 1.12.5.23(BOI-PEM - FIRE SEALING SYSTEM ) | 206817872
Detailed Engineering | ENG | 2025-01-22 08:00 | 2025-06-20 17:00 |  |  |  |  | 1.12.5.23(BOI-PEM - FIRE SEALING SYSTEM ) | 206817873
Manufacturing | MFG | 2025-06-21 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.12.5.23(BOI-PEM - FIRE SEALING SYSTEM ) | 206817874
Dispatch | DIS | 2025-11-18 08:00 | 2025-12-17 17:00 |  |  |  |  | 1.12.5.23(BOI-PEM - FIRE SEALING SYSTEM ) | 206817875
BOI-PEM - CABLE TRAY SUPPORT SYSTEM - BOLTABLE | SUP | 2023-11-01 08:00 | 2025-03-09 17:00 |  |  |  |  | 1.12.5(Supply) | 206817876
Ordering | ORD | 2023-11-01 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.12.5.24(BOI-PEM - CABLE TRAY SUPPORT SYSTEM - BOLTABLE) | 206817877
Detailed Engineering | ENG | 2024-01-30 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.12.5.24(BOI-PEM - CABLE TRAY SUPPORT SYSTEM - BOLTABLE) | 206817878
Manufacturing | MFG | 2024-06-28 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.12.5.24(BOI-PEM - CABLE TRAY SUPPORT SYSTEM - BOLTABLE) | 206817879
Dispatch | DIS | 2025-02-08 08:00 | 2025-03-09 17:00 |  |  |  |  | 1.12.5.24(BOI-PEM - CABLE TRAY SUPPORT SYSTEM - BOLTABLE) | 206817880
BOI-PEM - HT XLPE CABLES | SUP | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5(Supply) | 206817881
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.12.5.25(BOI-PEM - HT XLPE CABLES ) | 206817882
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.25(BOI-PEM - HT XLPE CABLES ) | 206817883
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.25(BOI-PEM - HT XLPE CABLES ) | 206817884
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.25(BOI-PEM - HT XLPE CABLES ) | 206817885
BOI- PEM - LT XLPE POWER CABLE | SUP | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5(Supply) | 206817886
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.12.5.26(BOI- PEM - LT XLPE POWER CABLE ) | 206817887
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.26(BOI- PEM - LT XLPE POWER CABLE ) | 206817888
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.26(BOI- PEM - LT XLPE POWER CABLE ) | 206817889
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.26(BOI- PEM - LT XLPE POWER CABLE ) | 206817890
BOI-PEM - SCREENED CONTROL CABLES | SUP | 2023-10-12 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5(Supply) | 206817891
Ordering | ORD | 2023-10-12 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.12.5.27(BOI-PEM - SCREENED CONTROL CABLES ) | 206817892
Detailed Engineering | ENG | 2024-01-10 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.12.5.27(BOI-PEM - SCREENED CONTROL CABLES ) | 206817893
Manufacturing | MFG | 2024-06-08 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.5.27(BOI-PEM - SCREENED CONTROL CABLES ) | 206817894
Dispatch | DIS | 2024-11-05 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.27(BOI-PEM - SCREENED CONTROL CABLES ) | 206817895
BOI-PEM - MS ROD FOR BELOW GROUND EARTHING | SUP | 2023-10-12 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5(Supply) | 206817896
Ordering | ORD | 2023-10-12 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.12.5.28(BOI-PEM - MS ROD FOR BELOW GROUND EARTHING ) | 206817897
Detailed Engineering | ENG | 2024-01-10 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.12.5.28(BOI-PEM - MS ROD FOR BELOW GROUND EARTHING ) | 206817898
Manufacturing | MFG | 2024-06-08 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.5.28(BOI-PEM - MS ROD FOR BELOW GROUND EARTHING ) | 206817899
Dispatch | DIS | 2024-11-05 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.28(BOI-PEM - MS ROD FOR BELOW GROUND EARTHING ) | 206817900
BOI-PEM - NEUTRAL GROUNDING RESISTOR | SUP | 2023-09-14 08:00 | 2024-11-06 17:00 |  |  |  |  | 1.12.5(Supply) | 206817901
Ordering | ORD | 2023-09-14 08:00 | 2023-12-12 17:00 |  |  |  |  | 1.12.5.29(BOI-PEM - NEUTRAL GROUNDING RESISTOR ) | 206817902
Detailed Engineering | ENG | 2023-12-13 08:00 | 2024-05-10 17:00 |  |  |  |  | 1.12.5.29(BOI-PEM - NEUTRAL GROUNDING RESISTOR ) | 206817903
Manufacturing | MFG | 2024-05-11 08:00 | 2024-10-07 17:00 |  |  |  |  | 1.12.5.29(BOI-PEM - NEUTRAL GROUNDING RESISTOR ) | 206817904
Dispatch | DIS | 2024-10-08 08:00 | 2024-11-06 17:00 |  |  |  |  | 1.12.5.29(BOI-PEM - NEUTRAL GROUNDING RESISTOR ) | 206817905
BOI-PEM - OIL FILLED SERVICE TRANSFORMER | SUP | 2023-09-22 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.12.5(Supply) | 206817906
Ordering | ORD | 2023-09-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.12.5.30(BOI-PEM - OIL FILLED SERVICE TRANSFORMER ) | 206817907
Detailed Engineering | ENG | 2023-12-21 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.12.5.30(BOI-PEM - OIL FILLED SERVICE TRANSFORMER ) | 206817908
Manufacturing | MFG | 2024-05-19 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.30(BOI-PEM - OIL FILLED SERVICE TRANSFORMER ) | 206817909
Dispatch | DIS | 2024-10-16 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.12.5.30(BOI-PEM - OIL FILLED SERVICE TRANSFORMER ) | 206817910
BOI-PEM - STATION LIGHTING SYSTEM | SUP | 2023-08-23 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5(Supply) | 206817911
Lighting Poles and Masts, | ORD | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.31(BOI-PEM - STATION LIGHTING SYSTEM ) | 206817912
Ordering | OTH | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.12.5.31.1(Lighting Poles and Masts,) | 206817913
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.31.1(Lighting Poles and Masts,) | 206817914
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.31.1(Lighting Poles and Masts,) | 206817915
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.31.1(Lighting Poles and Masts,) | 206817916
Lighting Distribution Boards | SUP | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.31(BOI-PEM - STATION LIGHTING SYSTEM ) | 206817917
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.12.5.31.2(Lighting Distribution Boards) | 206817918
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.31.2(Lighting Distribution Boards) | 206817919
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.31.2(Lighting Distribution Boards) | 206817920
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.31.2(Lighting Distribution Boards) | 206817921
Lighting Fixtures, Lamps & Misc. Items. | SUP | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.31(BOI-PEM - STATION LIGHTING SYSTEM ) | 206817922
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.12.5.31.3(Lighting Fixtures, Lamps & Misc. Items.) | 206817923
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.12.5.31.3(Lighting Fixtures, Lamps & Misc. Items.) | 206817924
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.12.5.31.3(Lighting Fixtures, Lamps & Misc. Items.) | 206817925
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.12.5.31.3(Lighting Fixtures, Lamps & Misc. Items.) | 206817926
Lighting PVC wires | SUP | 2023-10-12 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.31(BOI-PEM - STATION LIGHTING SYSTEM ) | 206817927
Ordering | ORD | 2023-10-12 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.12.5.31.4(Lighting PVC wires) | 206817928
Detailed Engineering | ENG | 2024-01-10 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.12.5.31.4(Lighting PVC wires) | 206817929
Manufacturing | MFG | 2024-06-08 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.5.31.4(Lighting PVC wires) | 206817930
Dispatch | DIS | 2024-11-05 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.31.4(Lighting PVC wires) | 206817931
Lighting Rigid Steel Conduits | SUP | 2023-10-12 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.31(BOI-PEM - STATION LIGHTING SYSTEM ) | 206817932
Ordering | ORD | 2023-10-12 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.12.5.31.5(Lighting Rigid Steel Conduits) | 206817933
Detailed Engineering | ENG | 2024-01-10 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.12.5.31.5(Lighting Rigid Steel Conduits) | 206817934
Manufacturing | MFG | 2024-06-08 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.12.5.31.5(Lighting Rigid Steel Conduits) | 206817935
Dispatch | DIS | 2024-11-05 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.12.5.31.5(Lighting Rigid Steel Conduits) | 206817936
Erection | ERC | 2023-04-10 08:00 | 2026-05-07 17:00 |  |  |  |  | 1.12(Electrical) | 206817937
Station Transformer, Service power transformer, Unit Transformer & Misc. Service Transformer | ERC | 2025-02-21 08:00 | 2025-06-19 17:00 |  |  |  |  | 1.12.6(Erection) | 206817938
Placement of Main tank, erection of headers pipes, radiator bank, conservator | ERC | 2025-02-21 08:00 | 2025-04-11 17:00 |  |  |  |  | 1.12.6.1(Station Transformer, Service power transformer, Unit Transformer & Misc. Service Transformer) | 206817939
Pre-commissioning/Protection tests and Relays Testing. | COM | 2025-05-02 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.12.6.1(Station Transformer, Service power transformer, Unit Transformer & Misc. Service Transformer) | 206817940
Statutory Clearance. | ERC | 2025-05-23 08:00 | 2025-05-24 17:00 |  |  |  |  | 1.12.6.1(Station Transformer, Service power transformer, Unit Transformer & Misc. Service Transformer) | 206817941
Transformer Charging. | ERC | 2025-06-19 08:00 | 2025-06-19 17:00 |  |  |  |  | 1.12.6.1(Station Transformer, Service power transformer, Unit Transformer & Misc. Service Transformer) | 206817942
SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB) | ERC | 2025-04-23 08:00 | 2025-06-18 17:00 |  |  |  |  | 1.12.6(Erection) | 206817943
Erection of support structure | ERC | 2025-04-23 08:00 | 2025-05-07 17:00 |  |  |  |  | 1.12.6.2(SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB)) | 206817944
Erection of SPBD from ST Transformer to Station Boards 11kV Boards (0BA&0BB) | ERC | 2025-05-08 08:00 | 2025-06-02 17:00 |  |  |  |  | 1.12.6.2(SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB)) | 206817945
Tie from Station Boards to Unit Boards (11 KV) (6BA & 6BB) and to Station Boards (11 KV) (0CC& 0CD) | ERC | 2025-06-03 08:00 | 2025-06-10 17:00 |  |  |  |  | 1.12.6.2(SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB)) | 206817946
Hi-pot & CRM of Bus duct | ERC | 2025-06-11 08:00 | 2025-06-14 17:00 |  |  |  |  | 1.12.6.2(SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB)) | 206817947
SBD of Station and Related TIE's ready for charging | ERC | 2025-06-15 08:00 | 2025-06-18 17:00 |  |  |  |  | 1.12.6.2(SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB)) | 206817948
HT SWITCH GEARS (Station and Unit Boards) | ERC | 2025-04-07 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.12.6(Erection) | 206817949
Placement of panels, coupling, bus bar joints and released for cabling | ERC | 2025-04-07 08:00 | 2025-05-06 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817950
Control bus, interpanel wiring | ERC | 2025-05-07 08:00 | 2025-05-24 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817951
contact resistance tests for bus bar joints | ERC | 2025-05-25 08:00 | 2025-06-05 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817952
HV test of power bus | ERC | 2025-06-06 08:00 | 2025-06-09 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817953
CT/PT/Relay testing | ERC | 2025-06-10 08:00 | 2025-07-14 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817954
Breaker commissioning checks | COM | 2025-07-15 08:00 | 2025-08-13 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817955
Switchgear Charging | ERC | 2025-08-14 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | 206817956
SERVICE & UNIT AUXILLARY TRANSFORMERS | ERC | 2025-05-12 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.12.6(Erection) | 206817957
Placement of Main intercanal of headers pipes, radiator bank, conservator | ERC | 2025-05-12 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817958
Installation of turret, bushing | ERC | 2025-05-20 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817959
Vacuum Pulling and N2 Filling. | ERC | 2025-05-24 08:00 | 2025-05-27 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817960
Oil filteration, filling and dry out | ERC | 2025-05-28 08:00 | 2025-06-02 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817961
Power and control cabling ,cabling between marshalling box and transformer/fans | ERC | 2025-06-03 08:00 | 2025-06-08 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817962
LV Testing of transformer. | ERC | 2025-08-19 08:00 | 2025-08-20 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817963
Pre-commissioning/Protection tests and Relays Testing. | COM | 2025-08-21 08:00 | 2025-08-23 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817964
Statutory Clearance. | ERC | 2025-08-24 08:00 | 2025-08-25 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817965
Transformer Charging. | ERC | 2025-08-26 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | 206817966
HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL | ERC | 2025-04-07 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.12.6(Erection) | 206817967
Placement of panels, coupling, bus bar joints and released for cabling | ERC | 2025-04-07 08:00 | 2025-04-16 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817968
Control bus, interpanel wiring | ERC | 2025-04-17 08:00 | 2025-04-24 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817969
contact resistance tests for bus bar joints | ERC | 2025-04-25 08:00 | 2025-04-28 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817970
HV test of power bus | ERC | 2025-04-29 08:00 | 2025-04-30 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817971
CT/PT/Relay testing . | ERC | 2025-05-01 08:00 | 2025-05-10 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817972
Breaker commissioning checks | COM | 2025-05-11 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817973
Switchgear Charging. | ERC | 2025-08-28 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | 206817974
LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts. | ERC | 2025-03-31 08:00 | 2025-11-08 17:00 |  |  |  |  | 1.12.6(Erection) | 206817975
Erection of Boiler MCC,LT Transformers ,LT Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-03-31 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817976
Erection of Turbine MCC,LT Transformers ,LT Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-04-20 08:00 | 2025-05-09 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817977
Erection of Station Switch Gear PMCC/MCC,LT Transformers, LT Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-05-10 08:00 | 2025-05-29 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817978
Erection of Unit Switch Gear PMCC/MCC,LT Transformers Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-05-30 08:00 | 2025-06-18 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817979
Erection of Boiler Valve MCC,LT Transformers Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-06-19 08:00 | 2025-07-08 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817980
Erection of Turbine Valve MCC,LT Transformers Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-07-09 08:00 | 2025-07-28 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817981
Erection of FOPH MCC,LT Transformers Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-07-29 08:00 | 2025-08-17 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817982
Erection of CWPH MCC,LT Transformers ,LT Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-08-18 08:00 | 2025-09-06 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817983
Erection of Emergency MCC,LT Transformers ,LT Bus Ducts and LV Testing of Transformer and CT/PT/Relays Testing. | ERC | 2025-09-07 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817984
Erection of Soot Blower MCC,LT Transformers Bus Ducts and LV Testing of Transformer and CT/PT/Relays/breaker Testing. | ERC | 2025-09-27 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817985
Other MCC | ERC | 2025-09-27 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817986
IR checking and Interlock Trials of Swgrs. | ERC | 2025-10-17 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817987
LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts:LT Switchgear Charging. | ERC | 2025-10-29 08:00 | 2025-11-08 17:00 |  |  |  |  | 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | 206817988
220 V MAIN PLANT DC BATTERY SYSTEM | ERC | 2025-03-13 08:00 | 2025-09-21 17:00 |  |  |  |  | 1.12.6(Erection) | 206817989
Placement of batteries | ERC | 2025-03-13 08:00 | 2025-04-26 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817990
Placement of Battery Charger Panel & its DCDB | ERC | 2025-04-27 08:00 | 2025-05-06 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817991
Cabling and connections | ERC | 2025-05-07 08:00 | 2025-05-16 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817992
Connections with the DC main bus | ERC | 2025-05-17 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817993
Charging and Dis-Charging. | ERC | 2025-08-30 08:00 | 2025-09-08 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817994
Main plant battery system ready for Re-Charging | ERC | 2025-09-09 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817995
Battery system commissioned | COM | 2025-09-21 08:00 | 2025-09-21 17:00 |  |  |  |  | 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | 206817996
HT/LT Cabling and Associated Tray Work for BLU | ERC | 2025-09-14 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.12.6(Erection) | 206817997
Power and Control Cabling for Valves and Dampers for BLU | ERC | 2025-09-14 08:00 | 2025-12-12 17:00 |  |  |  |  | 1.12.6(Erection) | 206817998
Unit AUX Transformer | ERC | 2025-04-22 08:00 | 2025-08-02 17:00 |  |  |  |  | 1.12.6(Erection) | 206817999
Placement of Main Ducts' of headers pipes, radiator bank, conservator | ERC | 2025-04-22 08:00 | 2025-05-11 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818000
Installation of turret, bushing | ERC | 2025-05-12 08:00 | 2025-05-18 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818001
Vacuum Pulling and N2 Filling. | ERC | 2025-05-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818002
Oil Vacuum and dry out | ERC | 2025-05-24 08:00 | 2025-06-01 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818003
Power and control cabling ,cabling between marshalling box and transformer/fans | ERC | 2025-06-02 08:00 | 2025-06-10 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818004
LV Testing of transformer, SFRA, Tan Delta, OLTC, NGR etc. | ERC | 2025-06-11 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818005
Pre-commissioning/Protection tests and Relays Testing. | COM | 2025-07-08 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818006
Statutory Clearance. | ERC | 2025-07-28 08:00 | 2025-08-01 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818007
Transformer Charging. | ERC | 2025-08-02 08:00 | 2025-08-02 17:00 |  |  |  |  | 1.12.6.10(Unit AUX Transformer) | 206818008
GENERATOR TRANSFORME (R/Y/B) | ERC | 2025-04-19 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.12.6(Erection) | 206818009
Placement of Main tank ,Erection of headers pipes, radiator bank, conservator | ERC | 2025-04-19 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818010
Installation of turret, bushing etc | ERC | 2025-07-23 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818011
Vacuum Pulling and N2 Filling. | ERC | 2025-08-29 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818012
Oil filtration, filling and dry out | ERC | 2025-10-03 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818013
Cabling between marshalling box and transformer/fans& Pumps | ERC | 2025-11-07 08:00 | 2025-11-21 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818014
LV Testing of transformer, SFRA, Tan Delta etc. | ERC | 2025-11-22 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818015
Pre-commissioning/Protection tests and Relays Testing. | COM | 2026-01-16 08:00 | 2026-03-16 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818016
Statutory Clearance. | ERC | 2026-03-17 08:00 | 2026-04-05 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818017
Transformer Ready for charging | ERC | 2026-04-06 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | 206818018
UNIT TRANSFORMERS | ERC | 2024-12-25 08:00 | 2026-04-24 17:00 |  |  |  |  | 1.12.6(Erection) | 206818019
Placement of Main tank ,Erection of headers pipes, radiator bank, conservator | ERC | 2024-12-25 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818020
Installation of turret, bushing etc | ERC | 2025-01-08 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818021
Vacuum Pulling and N2 Filling. | ERC | 2025-10-03 08:00 | 2025-10-08 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818022
Oil filtration, filling and dry out | ERC | 2025-11-07 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818023
Power and control cabling ,cabling between marshalling box and transformer/fans | ERC | 2025-11-15 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818024
LV Testing of transformer, OLTC, NGR etc. | ERC | 2025-11-21 08:00 | 2025-11-24 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818025
Pre-commissioning/Protection tests and Relays Testing. | COM | 2025-11-25 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818026
BTS readiness | ERC | 2025-11-25 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818027
Statutory Clearance. | ERC | 2026-04-06 08:00 | 2026-04-08 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818028
Readiness for Transformer charging | ERC | 2026-04-24 08:00 | 2026-04-24 17:00 |  |  |  |  | 1.12.6.12(UNIT TRANSFORMERS) | 206818029
STATION TRANSFORMERS | ERC | 2024-12-17 08:00 | 2025-04-27 17:00 |  |  |  |  | 1.12.6(Erection) | 206818030
Placement of Main tank ,Erection of headers pipes, radiator bank, conservator | ERC | 2024-12-17 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818031
Installation of turret, bushing etc | ERC | 2024-12-31 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818032
Vacuum Pulling and N2 Filling. | ERC | 2025-01-08 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818033
Oil filtration, filling and dry out | ERC | 2025-01-14 08:00 | 2025-01-21 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818034
Power and control cabling ,cabling between marshalling box and transformer/fans | ERC | 2025-01-22 08:00 | 2025-01-27 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818035
LV Testing of transformer, OLTC, NGR etc. | ERC | 2025-01-28 08:00 | 2025-01-31 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818036
Pre-commissioning/Protection tests and Relays Testing. | COM | 2025-02-01 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818037
BTS readiness | ERC | 2025-02-01 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818038
Statutory Clearance. | ERC | 2025-02-11 08:00 | 2025-02-13 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818039
Readiness for Transformer charging | ERC | 2025-04-27 08:00 | 2025-04-27 17:00 |  |  |  |  | 1.12.6.13(STATION TRANSFORMERS) | 206818040
SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S | ERC | 2025-05-03 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.12.6(Erection) | 206818041
Erection of support structure, | ERC | 2025-05-03 08:00 | 2025-05-12 17:00 |  |  |  |  | 1.12.6.14(SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S) | 206818042
Erection of SPBD from UT Transformer to Unit Boards11 kV Boards | ERC | 2025-05-13 08:00 | 2025-05-28 17:00 |  |  |  |  | 1.12.6.14(SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S) | 206818043
Connection of Tie from Station Boards to Unit Boards (11kV). | ERC | 2025-05-29 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.12.6.14(SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S) | 206818044
Hi-pot & CRM of Bus duct | ERC | 2025-06-04 08:00 | 2025-06-05 17:00 |  |  |  |  | 1.12.6.14(SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S) | 206818045
SPBD of Unit and Related TIE's ready for charging | ERC | 2025-06-06 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.12.6.14(SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S) | 206818046
IP BUS DUCTS | ERC | 2025-07-18 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.12.6(Erection) | 206818047
IP BUS DUCTS: erection and foundation parts and supports for ducts | ERC | 2025-07-18 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818048
IP BUS DUCTS: Erection & Welding of conductor and duct enclosures for the main run | ERC | 2025-08-17 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818049
IP BUS Clearance & Welding of conductor and duct enclosures for the tap off run | ERC | 2025-10-16 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818050
IP BUS Clearance of NGT and LAVT . | ERC | 2025-11-05 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818051
IP BUS DUCTS: Testing of NGT, LAVT. | ERC | 2025-11-15 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818052
IP BUS DUCTS: Hi-Pot test & CRM of IPBD | ERC | 2025-11-21 08:00 | 2025-11-22 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818053
IP BUS DUCTS:IPBD ready for charging | ERC | 2025-11-23 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.12.6.15(IP BUS DUCTS) | 206818054
HT/LT Cabling & associated Tray, other Works for Rolling and Synchronisation. | ERC | 2025-12-13 08:00 | 2026-04-11 17:00 |  |  |  |  | 1.12.6(Erection) | 206818055
ESP Charging | ERC | 2024-08-18 08:00 | 2025-12-20 17:00 |  |  |  |  | 1.12.6(Erection) | 206818056
Erection and alignment of EC Panels and LTMSB and ACP Panels | ERC | 2024-08-18 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818057
Checking of control bus, interpanel wiring | ERC | 2024-09-17 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818058
Contact resistance tests for bus bar joints | ERC | 2024-09-27 08:00 | 2024-10-04 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818059
HT SWITCH GEARS:CT/PT/Relay testing after readiness of DC Supply | ERC | 2024-10-05 08:00 | 2024-10-24 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818060
Testing of HVR's of ESP | ERC | 2025-10-04 08:00 | 2025-10-19 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818061
Cable Laying and Termination of Cables for ESP | ERC | 2025-10-20 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818062
Charging of LTMSB,ACP and EC Panels | ERC | 2025-10-30 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818063
Dummy Load , SCC and OCC of Panels | ERC | 2025-11-05 08:00 | 2025-11-18 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818064
Field Charging and Charging of heaters and operation or CERM and EERM. | ERC | 2025-12-13 08:00 | 2025-12-20 17:00 |  |  |  |  | 1.12.6.17(ESP Charging) | 206818065
HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers. | ERC | 2025-01-30 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.12.6(Erection) | 206818066
Placement of panels, coupling, bus bar joints and released for cabling | ERC | 2025-01-30 08:00 | 2025-03-03 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818067
control bus, interpanel wiring | ERC | 2025-03-04 08:00 | 2025-03-24 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818068
contact resistance tests for bus bar joints | ERC | 2025-03-25 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818069
HV test of power bus | ERC | 2025-04-03 08:00 | 2025-04-08 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818070
CT/PT/ Relay testing and LV Testing of Transformers. | ERC | 2025-04-09 08:00 | 2025-04-29 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818071
Breaker commissioning checks and Readiness of Transformers. | COM | 2025-04-30 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818072
Switchgear energized | ERC | 2025-08-03 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | 206818073
Readiness of STRP | ERC | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.12.6(Erection) | 206818074
Erection and Commissioning of GRP, ECP, DATA concentrator panel & DAVR | COM | 2025-08-17 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.12.6(Erection) | 206818075
Erection and Commissioning of DAVR | COM | 2025-10-02 08:00 | 2026-04-19 17:00 |  |  |  |  | 1.12.6(Erection) | 206818076
HT/LT Cabling & associated Tray , other Works for Coal Firing and AHP & CHP | ERC | 2025-08-06 08:00 | 2026-05-07 17:00 |  |  |  |  | 1.12.6(Erection) | 206818077
Completion of BOP Packages viz LT SWGRS,FIRE SYSTEMS AND FIRE SEALING. | ERC | 2025-12-18 08:00 | 2026-03-01 17:00 |  |  |  |  | 1.12.6(Erection) | 206818078
Erection of Below Ground earthing | ERC | 2023-04-10 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.12.6(Erection) | 206818079
Erection Above Ground earthing | ERC | 2025-03-23 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.12.6(Erection) | 206818080
Readiness of Trial Run COMPLETION including EMS | ERC | 2026-03-02 08:00 | 2026-03-11 17:00 |  |  |  |  | 1.12.6(Erection) | 206818081
Completion of Station Lighting Package | ERC | 2024-04-19 08:00 | 2024-12-25 17:00 |  |  |  |  | 1.12.6(Erection) | 206818082
Control & Instrumentation | ERC | 2023-04-15 08:00 | 2026-05-15 17:00 |  |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206818083
Civil | CIV | 2024-11-16 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.13(Control & Instrumentation) | 206818084
Main Control Room | CIV | 2024-11-16 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.13.1(Civil) | 206818085
RCC in column encasing works | CIV | 2024-11-16 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.13.1.1(Main Control Room) | 206818086
Brick Work & Plastering | CIV | 2024-12-31 08:00 | 2025-02-18 17:00 |  |  |  |  | 1.13.1.1(Main Control Room) | 206818087
Flooring | CIV | 2025-02-19 08:00 | 2025-03-30 17:00 |  |  |  |  | 1.13.1.1(Main Control Room) | 206818088
false ceiling & insulation works | CIV | 2025-03-11 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.13.1.1(Main Control Room) | 206818089
Door ,Window- glass ,aluminium fixing works | CIV | 2025-06-04 08:00 | 2025-07-18 17:00 |  |  |  |  | 1.13.1.1(Main Control Room) | 206818090
Finishing works | CIV | 2025-07-19 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.13.1.1(Main Control Room) | 206818091
Supply | SUP | 2023-04-15 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.13(Control & Instrumentation) | 206818092
BHEL EDN | SUP | 2023-04-15 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2(Supply) | 206818093
DAVR PACKAGE | SUP | 2023-04-15 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818094
Engineering | ENG | 2023-04-15 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.13.2.1.1(DAVR PACKAGE) | 206818095
Manufacturing | MFG | 2024-06-08 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.13.2.1.1(DAVR PACKAGE) | 206818096
Dispatch | DIS | 2024-08-07 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.13.2.1.1(DAVR PACKAGE) | 206818097
RECEIPT at Site | REC | 2024-08-27 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.13.2.1.1(DAVR PACKAGE) | 206818098
SG C&I PACKAGE | SUP | 2023-04-15 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818099
Engineering | ENG | 2023-04-15 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.13.2.1.2(SG C&I PACKAGE ) | 206818100
Manufacturing | MFG | 2024-03-20 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.2(SG C&I PACKAGE ) | 206818101
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.1.2(SG C&I PACKAGE ) | 206818102
RECEIPT at Site | REC | 2024-06-08 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1.2(SG C&I PACKAGE ) | 206818103
TG C&I PACKAGE | SUP | 2023-08-13 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818104
Engineering | ENG | 2023-08-13 08:00 | 2024-07-17 17:00 |  |  |  |  | 1.13.2.1.3(TG C&I PACKAGE ) | 206818105
Manufacturing | MFG | 2024-07-18 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.3(TG C&I PACKAGE ) | 206818106
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.3(TG C&I PACKAGE ) | 206818107
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.3(TG C&I PACKAGE ) | 206818108
HMI | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818109
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.4(HMI) | 206818110
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.4(HMI) | 206818111
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.4(HMI) | 206818112
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.4(HMI) | 206818113
Station C&I | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818114
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.5(Station C&I) | 206818115
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.5(Station C&I) | 206818116
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.5(Station C&I) | 206818117
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.5(Station C&I) | 206818118
Offsite C&I | OTH | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818119
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.6(Offsite C&I) | 206818120
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.6(Offsite C&I) | 206818121
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.6(Offsite C&I) | 206818122
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.6(Offsite C&I) | 206818123
FIELD INSTRUMENTS and erection MATERIALS | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818124
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.7(FIELD INSTRUMENTS and erection MATERIALS) | 206818125
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.7(FIELD INSTRUMENTS and erection MATERIALS) | 206818126
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.7(FIELD INSTRUMENTS and erection MATERIALS) | 206818127
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.7(FIELD INSTRUMENTS and erection MATERIALS) | 206818128
CABLES AND CABLE TRAY | SUP | 2023-08-23 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818129
Engineering | ENG | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.13.2.1.8(CABLES AND CABLE TRAY) | 206818130
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.8(CABLES AND CABLE TRAY) | 206818131
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.1.8(CABLES AND CABLE TRAY) | 206818132
RECEIPT at Site | REC | 2024-06-08 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1.8(CABLES AND CABLE TRAY) | 206818133
CCTV | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818134
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.9(CCTV) | 206818135
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.9(CCTV) | 206818136
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.9(CCTV) | 206818137
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.9(CCTV) | 206818138
LVS | SUP | 2023-08-23 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818139
Engineering | ENG | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.13.2.1.10(LVS) | 206818140
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.10(LVS) | 206818141
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.1.10(LVS) | 206818142
RECEIPT at Site | REC | 2024-06-08 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1.10(LVS) | 206818143
UPS & ACDB | SUP | 2023-08-23 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818144
Engineering | ENG | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.13.2.1.11(UPS & ACDB) | 206818145
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.11(UPS & ACDB) | 206818146
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.1.11(UPS & ACDB) | 206818147
RECEIPT at Site | REC | 2024-06-08 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1.11(UPS & ACDB) | 206818148
UPS BATTERY | SUP | 2023-08-23 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818149
Engineering | ENG | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.13.2.1.12(UPS BATTERY) | 206818150
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.12(UPS BATTERY) | 206818151
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.1.12(UPS BATTERY) | 206818152
RECEIPT at Site | REC | 2024-06-08 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1.12(UPS BATTERY) | 206818153
CHARGER FOR BATTERY | SUP | 2023-08-23 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818154
Engineering | ENG | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.13.2.1.13(CHARGER FOR BATTERY) | 206818155
Manufacturing | MFG | 2024-04-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.13(CHARGER FOR BATTERY) | 206818156
Dispatch | DIS | 2024-05-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.1.13(CHARGER FOR BATTERY) | 206818157
RECEIPT at Site | REC | 2024-06-08 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.13.2.1.13(CHARGER FOR BATTERY) | 206818158
MASTER SLAVE CLOCK | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818159
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.14(MASTER SLAVE CLOCK) | 206818160
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.14(MASTER SLAVE CLOCK) | 206818161
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.14(MASTER SLAVE CLOCK) | 206818162
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.14(MASTER SLAVE CLOCK) | 206818163
HART MANAGEMENT SYSTEM | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818164
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.15(HART MANAGEMENT SYSTEM) | 206818165
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.15(HART MANAGEMENT SYSTEM) | 206818166
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.15(HART MANAGEMENT SYSTEM) | 206818167
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.15(HART MANAGEMENT SYSTEM) | 206818168
TURBINE SUPERVISORY SSTEM | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818169
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.16(TURBINE SUPERVISORY SSTEM) | 206818170
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.16(TURBINE SUPERVISORY SSTEM) | 206818171
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.16(TURBINE SUPERVISORY SSTEM) | 206818172
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.16(TURBINE SUPERVISORY SSTEM) | 206818173
ANALYZERS AND MEASURING INSTRUMENTS INCLUDING SOx , NOx | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818174
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.17(ANALYZERS AND MEASURING INSTRUMENTS INCLUDING SOx , NOx ) | 206818175
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.17(ANALYZERS AND MEASURING INSTRUMENTS INCLUDING SOx , NOx ) | 206818176
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.17(ANALYZERS AND MEASURING INSTRUMENTS INCLUDING SOx , NOx ) | 206818177
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.17(ANALYZERS AND MEASURING INSTRUMENTS INCLUDING SOx , NOx ) | 206818178
HMI BOIs AND DIGITAL TECHNOLOGIES | SUP | 2023-12-21 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1(BHEL EDN) | 206818179
Engineering | ENG | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.13.2.1.18(HMI BOIs AND DIGITAL TECHNOLOGIES) | 206818180
Manufacturing | MFG | 2024-08-17 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.13.2.1.18(HMI BOIs AND DIGITAL TECHNOLOGIES) | 206818181
Dispatch | DIS | 2024-09-16 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.13.2.1.18(HMI BOIs AND DIGITAL TECHNOLOGIES) | 206818182
RECEIPT at Site | REC | 2024-10-06 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.13.2.1.18(HMI BOIs AND DIGITAL TECHNOLOGIES) | 206818183
BOI- PEM | SUP | 2023-08-23 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2(Supply) | 206818184
BOI-PEM CONTROL VALVE | SUP | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.13.2.2(BOI- PEM) | 206818185
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.13.2.2.1(BOI-PEM CONTROL VALVE ) | 206818186
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.13.2.2.1(BOI-PEM CONTROL VALVE ) | 206818187
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.13.2.2.1(BOI-PEM CONTROL VALVE ) | 206818188
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.13.2.2.1(BOI-PEM CONTROL VALVE ) | 206818189
BOI- PEM-FLOW ELEMENT - NOZZLE | SUP | 2023-12-07 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2(BOI- PEM) | 206818190
Ordering | ORD | 2023-12-07 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.13.2.2.2(BOI- PEM-FLOW ELEMENT - NOZZLE ) | 206818191
Detailed Engineering | ENG | 2024-03-06 08:00 | 2024-08-02 17:00 |  |  |  |  | 1.13.2.2.2(BOI- PEM-FLOW ELEMENT - NOZZLE ) | 206818192
Manufacturing | MFG | 2024-08-03 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.13.2.2.2(BOI- PEM-FLOW ELEMENT - NOZZLE ) | 206818193
Dispatch | DIS | 2024-12-31 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2.2(BOI- PEM-FLOW ELEMENT - NOZZLE ) | 206818194
BOI-PEM-FLOW ELEMENT - ORIFICE | SUP | 2023-12-07 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2(BOI- PEM) | 206818195
Ordering | ORD | 2023-12-07 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.13.2.2.3(BOI-PEM-FLOW ELEMENT - ORIFICE ) | 206818196
Detailed Engineering | ENG | 2024-03-06 08:00 | 2024-08-02 17:00 |  |  |  |  | 1.13.2.2.3(BOI-PEM-FLOW ELEMENT - ORIFICE ) | 206818197
Manufacturing | MFG | 2024-08-03 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.13.2.2.3(BOI-PEM-FLOW ELEMENT - ORIFICE ) | 206818198
Dispatch | DIS | 2024-12-31 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2.3(BOI-PEM-FLOW ELEMENT - ORIFICE ) | 206818199
BOI-PEM-ULTRASONIC FLOW METER | SUP | 2023-12-07 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2(BOI- PEM) | 206818200
Ordering | ORD | 2023-12-07 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.13.2.2.4(BOI-PEM-ULTRASONIC FLOW METER) | 206818201
Detailed Engineering | ENG | 2024-03-06 08:00 | 2024-08-02 17:00 |  |  |  |  | 1.13.2.2.4(BOI-PEM-ULTRASONIC FLOW METER) | 206818202
Manufacturing | MFG | 2024-08-03 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.13.2.2.4(BOI-PEM-ULTRASONIC FLOW METER) | 206818203
Dispatch | DIS | 2024-12-31 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2.4(BOI-PEM-ULTRASONIC FLOW METER) | 206818204
BOI-PEM-ELECTROMAGNETIC FLOW METER | SUP | 2023-12-07 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2(BOI- PEM) | 206818205
Ordering | ORD | 2023-12-07 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.13.2.2.5(BOI-PEM-ELECTROMAGNETIC FLOW METER) | 206818206
Detailed Engineering | ENG | 2024-03-06 08:00 | 2024-08-02 17:00 |  |  |  |  | 1.13.2.2.5(BOI-PEM-ELECTROMAGNETIC FLOW METER) | 206818207
Manufacturing | MFG | 2024-08-03 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.13.2.2.5(BOI-PEM-ELECTROMAGNETIC FLOW METER) | 206818208
Dispatch | DIS | 2024-12-31 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.13.2.2.5(BOI-PEM-ELECTROMAGNETIC FLOW METER) | 206818209
BOI-PEM-ROTAMETER | SUP | 2023-12-01 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.13.2.2(BOI- PEM) | 206818210
Ordering | ORD | 2023-12-01 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.13.2.2.6(BOI-PEM-ROTAMETER ) | 206818211
Detailed Engineering | ENG | 2024-02-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.13.2.2.6(BOI-PEM-ROTAMETER ) | 206818212
Manufacturing | MFG | 2024-07-28 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.13.2.2.6(BOI-PEM-ROTAMETER ) | 206818213
Dispatch | DIS | 2024-12-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.13.2.2.6(BOI-PEM-ROTAMETER ) | 206818214
BHEL TRY | SUP | 2023-06-20 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.13.2(Supply) | 206818215
Blr. Control and Instrumentation | SUP | 2023-06-20 08:00 | 2025-09-26 17:00 |  |  |  |  | 1.13.2.3(BHEL TRY) | 206818216
Boiler Fuel Firing Controls (PG-95) | SUP | 2023-07-23 08:00 | 2025-09-26 17:00 |  |  |  | PG95 | 1.13.2.3.1(Blr. Control and Instrumentation) | 206818217
FSSS FLAME SCANNER (PGMA-95088) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 95088 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818218
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 95088 | 1.13.2.3.1.1.1(FSSS FLAME SCANNER (PGMA-95088)) | 206818219
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 95088 | 1.13.2.3.1.1.1(FSSS FLAME SCANNER (PGMA-95088)) | 206818220
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 95088 | 1.13.2.3.1.1.1(FSSS FLAME SCANNER (PGMA-95088)) | 206818221
FSSS FLAME SCANNER (PGMA-95088) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 95088 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818222
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 95088 | 1.13.2.3.1.1.2(FSSS FLAME SCANNER (PGMA-95088)) | 206818223
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 95088 | 1.13.2.3.1.1.2(FSSS FLAME SCANNER (PGMA-95088)) | 206818224
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 95088 | 1.13.2.3.1.1.2(FSSS FLAME SCANNER (PGMA-95088)) | 206818225
FSSS FIELD INTERCONNECTING EQUIPMENTS (PGMA-95091) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 95091 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818226
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 95091 | 1.13.2.3.1.1.3(FSSS FIELD INTERCONNECTING EQUIPMENTS (PGMA-95091)) | 206818227
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 95091 | 1.13.2.3.1.1.3(FSSS FIELD INTERCONNECTING EQUIPMENTS (PGMA-95091)) | 206818228
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 95091 | 1.13.2.3.1.1.3(FSSS FIELD INTERCONNECTING EQUIPMENTS (PGMA-95091)) | 206818229
GRAVIMETRIC FEEDER REMOTE POWER CABINET (PGMA-95485) | SUP | 2023-10-21 08:00 | 2025-08-27 17:00 |  |  |  | 95485 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818230
Engineering | ENG | 2023-10-21 08:00 | 2024-07-17 17:00 |  |  |  | 95485 | 1.13.2.3.1.1.4(GRAVIMETRIC FEEDER REMOTE POWER CABINET (PGMA-95485)) | 206818231
Manufacturing | MFG | 2024-07-18 08:00 | 2025-07-28 17:00 |  |  |  | 95485 | 1.13.2.3.1.1.4(GRAVIMETRIC FEEDER REMOTE POWER CABINET (PGMA-95485)) | 206818232
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 95485 | 1.13.2.3.1.1.4(GRAVIMETRIC FEEDER REMOTE POWER CABINET (PGMA-95485)) | 206818233
UCB MOUNTED INSTS & CALIBRATION KIT (PGMA-95487) | SUP | 2023-10-21 08:00 | 2025-08-27 17:00 |  |  |  | 95487 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818234
Engineering | ENG | 2023-10-21 08:00 | 2024-07-17 17:00 |  |  |  | 95487 | 1.13.2.3.1.1.5(UCB MOUNTED INSTS & CALIBRATION KIT (PGMA-95487)) | 206818235
Manufacturing | MFG | 2024-07-18 08:00 | 2025-07-28 17:00 |  |  |  | 95487 | 1.13.2.3.1.1.5(UCB MOUNTED INSTS & CALIBRATION KIT (PGMA-95487)) | 206818236
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 95487 | 1.13.2.3.1.1.5(UCB MOUNTED INSTS & CALIBRATION KIT (PGMA-95487)) | 206818237
FEEDER MOUNTED C&I EQUIPMENTS (PGMA-95488) | SUP | 2023-10-21 08:00 | 2025-08-27 17:00 |  |  |  | 95488 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818238
Engineering | ENG | 2023-10-21 08:00 | 2024-07-17 17:00 |  |  |  | 95488 | 1.13.2.3.1.1.6(FEEDER MOUNTED C&I EQUIPMENTS (PGMA-95488)) | 206818239
Manufacturing | MFG | 2024-07-18 08:00 | 2025-07-28 17:00 |  |  |  | 95488 | 1.13.2.3.1.1.6(FEEDER MOUNTED C&I EQUIPMENTS (PGMA-95488)) | 206818240
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 95488 | 1.13.2.3.1.1.6(FEEDER MOUNTED C&I EQUIPMENTS (PGMA-95488)) | 206818241
COAL FLOW MONITER (PGMA-95489) | SUP | 2023-10-21 08:00 | 2025-08-27 17:00 |  |  |  | 95489 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818242
Engineering | ENG | 2023-10-21 08:00 | 2024-07-17 17:00 |  |  |  | 95489 | 1.13.2.3.1.1.7(COAL FLOW MONITER (PGMA-95489)) | 206818243
Manufacturing | MFG | 2024-07-18 08:00 | 2025-07-28 17:00 |  |  |  | 95489 | 1.13.2.3.1.1.7(COAL FLOW MONITER (PGMA-95489)) | 206818244
Dispatch | DIS | 2025-07-29 08:00 | 2025-08-27 17:00 |  |  |  | 95489 | 1.13.2.3.1.1.7(COAL FLOW MONITER (PGMA-95489)) | 206818245
FUEL FIRING CONTROL COMMISSIONING SPARE (PGMA-95988) | SUP | 2023-10-21 08:00 | 2025-09-26 17:00 |  |  |  | 95988 | 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | 206818246
Engineering | ENG | 2023-10-21 08:00 | 2024-07-17 17:00 |  |  |  | 95988 | 1.13.2.3.1.1.8(FUEL FIRING CONTROL COMMISSIONING SPARE (PGMA-95988)) | 206818247
Manufacturing | MFG | 2024-07-18 08:00 | 2025-08-27 17:00 |  |  |  | 95988 | 1.13.2.3.1.1.8(FUEL FIRING CONTROL COMMISSIONING SPARE (PGMA-95988)) | 206818248
Dispatch | DIS | 2025-08-28 08:00 | 2025-09-26 17:00 |  |  |  | 95988 | 1.13.2.3.1.1.8(FUEL FIRING CONTROL COMMISSIONING SPARE (PGMA-95988)) | 206818249
Boiler House Auxiliaries Control (PG-96) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | PG96 | 1.13.2.3.1(Blr. Control and Instrumentation) | 206818250
SOOT BLOWER MOTOR CONTROL CENTRE (PGMA-96186) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 96186 | 1.13.2.3.1.2(Boiler House Auxiliaries Control (PG-96)) | 206818251
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 96186 | 1.13.2.3.1.2.1(SOOT BLOWER MOTOR CONTROL CENTRE (PGMA-96186)) | 206818252
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 96186 | 1.13.2.3.1.2.1(SOOT BLOWER MOTOR CONTROL CENTRE (PGMA-96186)) | 206818253
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 96186 | 1.13.2.3.1.2.1(SOOT BLOWER MOTOR CONTROL CENTRE (PGMA-96186)) | 206818254
FURNACE TEMPARATURE PROBE STARTER BOX (PGMA-96188) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 96188 | 1.13.2.3.1.2(Boiler House Auxiliaries Control (PG-96)) | 206818255
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 96188 | 1.13.2.3.1.2.2(FURNACE TEMPARATURE PROBE STARTER BOX (PGMA-96188)) | 206818256
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 96188 | 1.13.2.3.1.2.2(FURNACE TEMPARATURE PROBE STARTER BOX (PGMA-96188)) | 206818257
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 96188 | 1.13.2.3.1.2.2(FURNACE TEMPARATURE PROBE STARTER BOX (PGMA-96188)) | 206818258
MISCELLANEOUS STARTER BOX (PGMA-96193) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 96193 | 1.13.2.3.1.2(Boiler House Auxiliaries Control (PG-96)) | 206818259
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 96193 | 1.13.2.3.1.2.3(MISCELLANEOUS STARTER BOX (PGMA-96193)) | 206818260
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 96193 | 1.13.2.3.1.2.3(MISCELLANEOUS STARTER BOX (PGMA-96193)) | 206818261
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 96193 | 1.13.2.3.1.2.3(MISCELLANEOUS STARTER BOX (PGMA-96193)) | 206818262
Boiler Instruments and Misc. Controls (PG-97) | SUP | 2023-06-20 08:00 | 2025-06-27 17:00 |  |  |  | PG97 | 1.13.2.3.1(Blr. Control and Instrumentation) | 206818263
INSTRUMENTATION FIELD TRANSMITTERS (PGMA-97097) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 97097 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818264
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 97097 | 1.13.2.3.1.3.1(INSTRUMENTATION FIELD TRANSMITTERS (PGMA-97097)) | 206818265
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 97097 | 1.13.2.3.1.3.1(INSTRUMENTATION FIELD TRANSMITTERS (PGMA-97097)) | 206818266
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 97097 | 1.13.2.3.1.3.1(INSTRUMENTATION FIELD TRANSMITTERS (PGMA-97097)) | 206818267
BOI-LU-FLOWMETERS (PGMA-97282) | SUP | 2023-12-01 08:00 | 2025-05-24 17:00 |  |  |  | 97282 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818268
NIT | ENQ | 2023-12-01 08:00 | 2023-12-01 17:00 |  |  |  | 97282 | 1.13.2.3.1.3.2(BOI-LU-FLOWMETERS (PGMA-97282)) | 206818269
Ordering | ORD | 2023-12-02 08:00 | 2024-06-18 17:00 |  |  |  | 97282 | 1.13.2.3.1.3.2(BOI-LU-FLOWMETERS (PGMA-97282)) | 206818270
Manufacturing | MFG | 2024-06-19 08:00 | 2025-04-24 17:00 |  |  |  | 97282 | 1.13.2.3.1.3.2(BOI-LU-FLOWMETERS (PGMA-97282)) | 206818271
Dispatch | DIS | 2025-04-25 08:00 | 2025-05-24 17:00 |  |  |  | 97282 | 1.13.2.3.1.3.2(BOI-LU-FLOWMETERS (PGMA-97282)) | 206818272
FIELD GAUGES (PGMA-97284) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97284 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818273
Engineering | ENG | 2023-10-21 08:00 | 2024-08-15 17:00 |  |  |  | 97284 | 1.13.2.3.1.3.3(FIELD GAUGES (PGMA-97284)) | 206818274
Manufacturing | MFG | 2024-08-16 08:00 | 2025-05-28 17:00 |  |  |  | 97284 | 1.13.2.3.1.3.3(FIELD GAUGES (PGMA-97284)) | 206818275
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97284 | 1.13.2.3.1.3.3(FIELD GAUGES (PGMA-97284)) | 206818276
FIELD SWITCHES (PGMA-97285) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97285 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818277
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 97285 | 1.13.2.3.1.3.4(FIELD SWITCHES (PGMA-97285)) | 206818278
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 97285 | 1.13.2.3.1.3.4(FIELD SWITCHES (PGMA-97285)) | 206818279
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97285 | 1.13.2.3.1.3.4(FIELD SWITCHES (PGMA-97285)) | 206818280
INST & ACC IN STEAM,WATER,SB SYSTEM (PGMA-97287) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97287 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818281
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 97287 | 1.13.2.3.1.3.5(INST & ACC IN STEAM,WATER,SB SYSTEM (PGMA-97287)) | 206818282
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 97287 | 1.13.2.3.1.3.5(INST & ACC IN STEAM,WATER,SB SYSTEM (PGMA-97287)) | 206818283
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97287 | 1.13.2.3.1.3.5(INST & ACC IN STEAM,WATER,SB SYSTEM (PGMA-97287)) | 206818284
MTM CLAMPS AND PADS (PGMA-97297) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 97297 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818285
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 97297 | 1.13.2.3.1.3.6(MTM CLAMPS AND PADS (PGMA-97297)) | 206818286
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 97297 | 1.13.2.3.1.3.6(MTM CLAMPS AND PADS (PGMA-97297)) | 206818287
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 97297 | 1.13.2.3.1.3.6(MTM CLAMPS AND PADS (PGMA-97297)) | 206818288
MTM THERMO COUPLES & JUNCTION BOXES (PGMA-97298) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 97298 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818289
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 97298 | 1.13.2.3.1.3.7(MTM THERMO COUPLES & JUNCTION BOXES (PGMA-97298)) | 206818290
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 97298 | 1.13.2.3.1.3.7(MTM THERMO COUPLES & JUNCTION BOXES (PGMA-97298)) | 206818291
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 97298 | 1.13.2.3.1.3.7(MTM THERMO COUPLES & JUNCTION BOXES (PGMA-97298)) | 206818292
ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97585 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818293
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 97585 | 1.13.2.3.1.3.8(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | 206818294
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 97585 | 1.13.2.3.1.3.8(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | 206818295
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97585 | 1.13.2.3.1.3.8(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | 206818296
ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97585 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818297
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 97585 | 1.13.2.3.1.3.9(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | 206818298
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 97585 | 1.13.2.3.1.3.9(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | 206818299
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97585 | 1.13.2.3.1.3.9(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | 206818300
ERECTION MATERIALS (PGMA-97590) | SUP | 2023-06-20 08:00 | 2025-01-25 17:00 |  |  |  | 97590 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818301
Engineering | ENG | 2023-06-20 08:00 | 2024-03-15 17:00 |  |  |  | 97590 | 1.13.2.3.1.3.10(ERECTION MATERIALS (PGMA-97590)) | 206818302
Manufacturing | MFG | 2024-03-16 08:00 | 2024-12-26 17:00 |  |  |  | 97590 | 1.13.2.3.1.3.10(ERECTION MATERIALS (PGMA-97590)) | 206818303
Dispatch | DIS | 2024-12-27 08:00 | 2025-01-25 17:00 |  |  |  | 97590 | 1.13.2.3.1.3.10(ERECTION MATERIALS (PGMA-97590)) | 206818304
MISCELLANEOUS ITEMS (PGMA-97591) | SUP | 2023-07-23 08:00 | 2025-03-29 17:00 |  |  |  | 97591 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818305
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 97591 | 1.13.2.3.1.3.11(MISCELLANEOUS ITEMS (PGMA-97591)) | 206818306
Manufacturing | MFG | 2024-04-18 08:00 | 2025-02-27 17:00 |  |  |  | 97591 | 1.13.2.3.1.3.11(MISCELLANEOUS ITEMS (PGMA-97591)) | 206818307
Dispatch | DIS | 2025-02-28 08:00 | 2025-03-29 17:00 |  |  |  | 97591 | 1.13.2.3.1.3.11(MISCELLANEOUS ITEMS (PGMA-97591)) | 206818308
PNEUMATIC TUBINGS & FITTINGS,AIRSET (PGMA-97592) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 97592 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818309
Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 97592 | 1.13.2.3.1.3.12(PNEUMATIC TUBINGS & FITTINGS,AIRSET (PGMA-97592)) | 206818310
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 97592 | 1.13.2.3.1.3.12(PNEUMATIC TUBINGS & FITTINGS,AIRSET (PGMA-97592)) | 206818311
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 97592 | 1.13.2.3.1.3.12(PNEUMATIC TUBINGS & FITTINGS,AIRSET (PGMA-97592)) | 206818312
CLOSED CIRCUIT TELEVISION SYSTEM (PGMA-97596) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97596 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818313
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 97596 | 1.13.2.3.1.3.13(CLOSED CIRCUIT TELEVISION SYSTEM (PGMA-97596)) | 206818314
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 97596 | 1.13.2.3.1.3.13(CLOSED CIRCUIT TELEVISION SYSTEM (PGMA-97596)) | 206818315
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97596 | 1.13.2.3.1.3.13(CLOSED CIRCUIT TELEVISION SYSTEM (PGMA-97596)) | 206818316
PNEUMATIC ACTUATOR IN AIR&FLUE GAS SYS (PGMA-97599) | SUP | 2023-10-21 08:00 | 2025-06-27 17:00 |  |  |  | 97599 | 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | 206818317
Engineering | ENG | 2023-10-21 08:00 | 2024-07-16 17:00 |  |  |  | 97599 | 1.13.2.3.1.3.14(PNEUMATIC ACTUATOR IN AIR&FLUE GAS SYS (PGMA-97599)) | 206818318
Manufacturing | MFG | 2024-07-17 08:00 | 2025-05-28 17:00 |  |  |  | 97599 | 1.13.2.3.1.3.14(PNEUMATIC ACTUATOR IN AIR&FLUE GAS SYS (PGMA-97599)) | 206818319
Dispatch | DIS | 2025-05-29 08:00 | 2025-06-27 17:00 |  |  |  | 97599 | 1.13.2.3.1.3.14(PNEUMATIC ACTUATOR IN AIR&FLUE GAS SYS (PGMA-97599)) | 206818320
Erection | ERC | 2024-09-14 08:00 | 2026-05-15 17:00 |  |  |  |  | 1.13(Control & Instrumentation) | 206818321
Civil clearance for Control Room for C&I Work | CIV | 2025-07-19 08:00 | 2025-07-19 17:00 |  |  |  |  | 1.13.3(Erection) | 206818322
MAIN CONTROL ROOM | ERC | 2025-07-20 08:00 | 2025-10-27 17:00 |  |  |  |  | 1.13.3(Erection) | 206818323
24 V DC Battery Charger, DCDB & its Battery Bank -E&C | ERC | 2025-07-20 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818324
DCS Panels installation in CER | ERC | 2025-07-20 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818325
Power Supply & earthing - cabling to DCS Panels | ERC | 2025-08-09 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818326
Control Desk & Human Machine Interface (HMI) -E&C | ERC | 2025-07-20 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818327
Network cabling | ERC | 2025-08-09 08:00 | 2025-10-22 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818328
Interpanel Cabling | ERC | 2025-10-03 08:00 | 2025-10-22 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818329
DCS Panels Charging | ERC | 2025-10-23 08:00 | 2025-10-27 17:00 |  |  |  |  | 1.13.3.2(MAIN CONTROL ROOM) | 206818330
BOILER OPERATING FLOOR (AB Elevation) | ERC | 2025-10-05 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.13.3(Erection) | 206818331
Copper Tubing for LOTV/Corner Valves/Control Valves | ERC | 2025-10-05 08:00 | 2025-10-08 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818332
Erection of JB Frames and JBs for AB Elevation | ERC | 2025-10-09 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818333
Healthiness checking of Limit Switches & Adjusting the same | ERC | 2025-10-16 08:00 | 2025-10-21 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818334
Cabling for Valves & Limit Switches of AB Elevation | ERC | 2025-10-22 08:00 | 2025-10-28 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818335
Stroking of Corner Skid Valves | ERC | 2025-10-29 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818336
Stroking of LOTV & LOCV | ERC | 2025-11-02 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818337
HEA Igniters, flame scanners, cabling and commissioning | COM | 2025-12-10 08:00 | 2025-12-17 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818338
Firing Floor Instrumentation - PS, TS, PT, Flow TXR, etc | ERC | 2025-12-10 08:00 | 2025-12-17 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818339
Gun Trial | COM | 2025-12-18 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | 206818340
SADC | ERC | 2024-09-14 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3(Erection) | 206818341
Erection of SADC I/P, Press. SW & AFR station after calibration | ERC | 2024-09-14 08:00 | 2024-09-28 17:00 |  |  |  |  | 1.13.3.4(SADC) | 206818342
Calibration of SADC Power Cylinders | ERC | 2024-09-29 08:00 | 2024-10-13 17:00 |  |  |  |  | 1.13.3.4(SADC) | 206818343
Erection of Trays for Cu Tubing | ERC | 2024-10-14 08:00 | 2024-10-23 17:00 |  |  |  |  | 1.13.3.4(SADC) | 206818344
Erection of Cu Tubing. & flexible hoses | ERC | 2024-10-24 08:00 | 2024-11-12 17:00 |  |  |  |  | 1.13.3.4(SADC) | 206818345
Cabling of SADC system | ERC | 2024-11-13 08:00 | 2024-11-22 17:00 |  |  |  |  | 1.13.3.4(SADC) | 206818346
Commissioning of SADC System | COM | 2025-11-01 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3.4(SADC) | 206818347
FD FAN | ERC | 2025-07-20 08:00 | 2026-02-03 17:00 |  |  |  |  | 1.13.3(Erection) | 206818348
First FD Fan | ERC | 2025-07-20 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.13.3.5(FD FAN) | 206818349
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-07-20 08:00 | 2025-07-25 17:00 |  |  |  |  | 1.13.3.5.1(First FD Fan) | 206818350
Motor Decoupled Trial Run | ERC | 2025-09-24 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.13.3.5.1(First FD Fan) | 206818351
Remote operation of drives like LOPs, Motor, Blade Pitch, Gates, etc | ERC | 2025-11-14 08:00 | 2025-11-21 17:00 |  |  |  |  | 1.13.3.5.1(First FD Fan) | 206818352
FDF Instrumentation | ERC | 2025-11-22 08:00 | 2025-12-05 17:00 |  |  |  |  | 1.13.3.5.1(First FD Fan) | 206818353
Lube Oil flushing | ERC | 2025-08-14 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.13.3.5.1(First FD Fan) | 206818354
FDF Protection checking & Fan Trial | COM | 2025-12-08 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.13.3.5.1(First FD Fan) | 206818355
Second FD Fan | ERC | 2025-12-31 08:00 | 2026-02-03 17:00 |  |  |  |  | 1.13.3.5(FD FAN) | 206818356
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-12-31 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.13.3.5.2(Second FD Fan) | 206818357
Motor Decoupled Trial Run | COM | 2026-01-06 08:00 | 2026-01-06 17:00 |  |  |  |  | 1.13.3.5.2(Second FD Fan) | 206818358
Remote operation of drives like LOPs, Motor, Blade Pitch, Gates, etc | ERC | 2026-01-07 08:00 | 2026-01-14 17:00 |  |  |  |  | 1.13.3.5.2(Second FD Fan) | 206818359
FDF Instrumentation | ERC | 2026-01-21 08:00 | 2026-01-30 17:00 |  |  |  |  | 1.13.3.5.2(Second FD Fan) | 206818360
Lube Oil flushing | ERC | 2026-01-03 08:00 | 2026-01-16 17:00 |  |  |  |  | 1.13.3.5.2(Second FD Fan) | 206818361
FDF Protection checking & Fan Trial | COM | 2026-02-02 08:00 | 2026-02-03 17:00 |  |  |  |  | 1.13.3.5.2(Second FD Fan) | 206818362
ID FAN | ERC | 2025-03-14 08:00 | 2026-03-31 17:00 |  |  |  |  | 1.13.3(Erection) | 206818363
First ID Fan | ERC | 2025-03-14 08:00 | 2025-12-31 17:00 |  |  |  |  | 1.13.3.6(ID FAN) | 206818364
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-03-14 08:00 | 2025-03-19 17:00 |  |  |  |  | 1.13.3.6.1(First ID Fan) | 206818365
Motor Decoupled Trial | COM | 2025-09-19 08:00 | 2025-09-19 17:00 |  |  |  |  | 1.13.3.6.1(First ID Fan) | 206818366
Remote operation of drives like LOPs, Motor, IGV, Scoop, Gates, etc | ERC | 2025-11-09 08:00 | 2025-11-18 17:00 |  |  |  |  | 1.13.3.6.1(First ID Fan) | 206818367
IDF Instrumentation | ERC | 2025-11-19 08:00 | 2025-11-30 17:00 |  |  |  |  | 1.13.3.6.1(First ID Fan) | 206818368
Lube Oil flushing | ERC | 2025-03-14 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.13.3.6.1(First ID Fan) | 206818369
IDF Protection checking & Fan Trial | COM | 2025-12-30 08:00 | 2025-12-31 17:00 |  |  |  |  | 1.13.3.6.1(First ID Fan) | 206818370
Second ID Fan | ERC | 2025-04-14 08:00 | 2026-03-31 17:00 |  |  |  |  | 1.13.3.6(ID FAN) | 206818371
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-04-14 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.13.3.6.2(Second ID Fan) | 206818372
Motor Decoupled Trial | COM | 2025-09-30 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.13.3.6.2(Second ID Fan) | 206818373
Remote operation of drives like LOPs, Motor, IGV, Scoop, Gates, etc | ERC | 2025-12-09 08:00 | 2025-12-18 17:00 |  |  |  |  | 1.13.3.6.2(Second ID Fan) | 206818374
IDF Instrumentation | ERC | 2025-12-19 08:00 | 2025-12-30 17:00 |  |  |  |  | 1.13.3.6.2(Second ID Fan) | 206818375
Lube Oil flushing | ERC | 2025-04-14 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.13.3.6.2(Second ID Fan) | 206818376
IDF Protection checking & Fan Trial | COM | 2026-03-30 08:00 | 2026-03-31 17:00 |  |  |  |  | 1.13.3.6.2(Second ID Fan) | 206818377
APH | ERC | 2025-10-30 08:00 | 2026-02-01 17:00 |  |  |  |  | 1.13.3(Erection) | 206818378
First APH | ERC | 2025-10-30 08:00 | 2025-11-29 17:00 |  |  |  |  | 1.13.3.7(APH) | 206818379
APH Instrumentation like Brg RTD, Fire Sensing T/C, GO Switch, etc. | ERC | 2025-10-30 08:00 | 2025-11-13 17:00 |  |  |  |  | 1.13.3.7.1(First APH) | 206818380
Remote operation of drives like LOPs, Electric Motor, Air Motor, etc | ERC | 2025-11-14 08:00 | 2025-11-19 17:00 |  |  |  |  | 1.13.3.7.1(First APH) | 206818381
Oil Flushing | ERC | 2025-11-20 08:00 | 2025-11-27 17:00 |  |  |  |  | 1.13.3.7.1(First APH) | 206818382
APH Protection checking & Motor / Fan Trial | COM | 2025-11-28 08:00 | 2025-11-29 17:00 |  |  |  |  | 1.13.3.7.1(First APH) | 206818383
Second APH | ERC | 2026-01-02 08:00 | 2026-02-01 17:00 |  |  |  |  | 1.13.3.7(APH) | 206818384
APH Instrumentation like Brg RTD, Fire Sensing T/C, GO Switch, etc. | ERC | 2026-01-02 08:00 | 2026-01-16 17:00 |  |  |  |  | 1.13.3.7.2(Second APH) | 206818385
Remote operation of drives like LOPs, Electric Motor, Air Motor, etc | ERC | 2026-01-17 08:00 | 2026-01-22 17:00 |  |  |  |  | 1.13.3.7.2(Second APH) | 206818386
Oil Flushing | ERC | 2026-01-23 08:00 | 2026-01-30 17:00 |  |  |  |  | 1.13.3.7.2(Second APH) | 206818387
SAPH Protection checking & Motor / Fan Trial | COM | 2026-01-31 08:00 | 2026-02-01 17:00 |  |  |  |  | 1.13.3.7.2(Second APH) | 206818388
SCANNER FAN | ERC | 2025-10-16 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.13.3(Erection) | 206818389
DC Scanner Air Fan Starter Panel Erection & Cabling | ERC | 2025-10-16 08:00 | 2025-10-25 17:00 |  |  |  |  | 1.13.3.8(SCANNER FAN) | 206818390
Protection Checking & Motor & Fan Trial | COM | 2025-10-26 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.13.3.8(SCANNER FAN) | 206818391
Commissioning of O/L Dampers & Scanner Air Parameters | COM | 2025-10-30 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.13.3.8(SCANNER FAN) | 206818392
INSTRUMENTATION FOR BLU | ERC | 2025-08-08 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.13.3(Erection) | 206818393
Boiler MTM Thermo-couple erection | ERC | 2025-10-09 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818394
ACW Pump Instrumentation & Commissioning | COM | 2025-10-24 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818395
SG DMCW Pump Instrumentation & Commissioning | COM | 2025-08-08 08:00 | 2025-08-19 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818396
TG DMCW Pump Instrumentation & Commissioning | COM | 2025-09-29 08:00 | 2025-10-10 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818397
Air & Flue Gas Path Instrumentation | ERC | 2025-12-17 08:00 | 2025-12-28 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818398
Remote operation of drives like Boiler Drains & Vents, FG Path Gates & Dampers | ERC | 2025-12-27 08:00 | 2025-12-29 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818399
Furnace Parameters readiness like Furnace Pressure Secondary Air Flow, Flue Gas Pressures & Temperatures, etc. | ERC | 2025-12-21 08:00 | 2025-12-30 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818400
Boiler Protection Trial | COM | 2025-12-31 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.13.3.9(INSTRUMENTATION FOR BLU) | 206818401
C&I Readiness for BOILER LIGHT-UP | ERC | 2026-01-02 08:00 | 2026-01-02 17:00 |  |  |  |  | 1.13.3(Erection) | 206818402
BOILER OPERATING FLOOR (CD Elevation) | ERC | 2025-10-12 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3(Erection) | 206818403
Copper Tubing for HOTV/Corner Valves/Control Valves | ERC | 2025-10-12 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818404
Erection of JB Frames and JBs for CD Elevation | ERC | 2025-10-16 08:00 | 2025-10-23 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818405
Healthiness checking of Limit Switches & Adjusting the same | ERC | 2025-10-24 08:00 | 2025-10-29 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818406
Cabling for Valves & Limit Switches of CD Elevation | ERC | 2025-10-30 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818407
Stroking of Corner Skid Valves | ERC | 2025-11-05 08:00 | 2025-11-08 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818408
Stroking of HOTV & HOFCV | ERC | 2025-11-09 08:00 | 2025-11-10 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818409
Installation of HEA Igniters, flame scanners and its cabling and commissioning | COM | 2025-11-11 08:00 | 2025-11-18 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818410
Firing Floor Instrumentation - PS, TS, PT, Flow TXR, etc | ERC | 2025-11-11 08:00 | 2025-11-18 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818411
Gun Trial | COM | 2025-11-19 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | 206818412
Readiness for BOILER CHEMICAL CLEANING | ERC | 2025-11-21 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.13.3(Erection) | 206818413
BOILER OPERATING FLOOR (EF Elevation) | ERC | 2025-11-26 08:00 | 2026-01-13 17:00 |  |  |  |  | 1.13.3(Erection) | 206818414
Copper Tubing for Corner Valves | ERC | 2025-11-26 08:00 | 2025-12-03 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818415
Erection of JB Frames and JBs for CD Elevation | ERC | 2025-12-04 08:00 | 2025-12-11 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818416
Healthiness checking of Limit Switches & Adjusting the same | ERC | 2025-12-12 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818417
Cabling for Valves & Limit Switches of EF Elevation | ERC | 2025-12-20 08:00 | 2025-12-27 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818418
Stroking of Corner Skid Valves | ERC | 2025-12-28 08:00 | 2026-01-01 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818419
Installation of HEA Igniters, flame scanners and its cabling and commissioning | COM | 2026-01-02 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818420
Gun Trial | COM | 2026-01-12 08:00 | 2026-01-13 17:00 |  |  |  |  | 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | 206818421
MDBFP | ERC | 2025-06-05 08:00 | 2025-09-18 17:00 |  |  |  |  | 1.13.3(Erection) | 206818422
Motor Winding/Brg RTD hookup to DCS & HT Breaker cabling & remote operation from DCS | ERC | 2025-06-05 08:00 | 2025-06-14 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818423
LGB & LIR Erection & Cabling | ERC | 2025-06-15 08:00 | 2025-06-24 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818424
Impulse Piping of LO LGB, Seal Wtr LGB, FW LIR-HYD/EDN, BP/BFP Suction Strainer DPT, Suction Flow Txr, PT, etc. | ERC | 2025-06-25 08:00 | 2025-07-09 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818425
MDBFP Motor Trial | COM | 2025-08-19 08:00 | 2025-08-19 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818426
Hydraulic Coupling Instrumentation - LS, Speed Probe, PT | ERC | 2025-08-20 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818427
Commissioning of scoop controller, Speed Measurement, etc | COM | 2025-08-30 08:00 | 2025-09-03 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818428
MDBFP Motor+Hydraulic Coupling Trial | COM | 2025-09-04 08:00 | 2025-09-04 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818429
FW System Instrumentation | ERC | 2025-09-05 08:00 | 2025-09-14 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818430
Copper tubing & commissioning of BFP Re-circulation valve | COM | 2025-09-15 08:00 | 2025-09-16 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818431
Discharge MOV commissioning | COM | 2025-09-17 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818432
MDBFP Coupled Trial | COM | 2025-09-18 08:00 | 2025-09-18 17:00 |  |  |  |  | 1.13.3.14(MDBFP) | 206818433
Readiness for STEAM BLOWING | ERC | 2025-12-01 08:00 | 2025-12-25 17:00 |  |  |  |  | 1.13.3(Erection) | 206818434
Boiler C&I Required for Synchronisation | ERC | 2025-09-16 08:00 | 2026-04-28 17:00 |  |  |  |  | 1.13.3(Erection) | 206818435
Instrumentation - Air and Flue Gas Path | ERC | 2026-03-25 08:00 | 2026-04-03 17:00 |  |  |  |  | 1.13.3.16(Boiler C&I Required for Synchronisation) | 206818436
Instrumentation - Steam and Water Cycle | ERC | 2026-01-26 08:00 | 2026-02-04 17:00 |  |  |  |  | 1.13.3.16(Boiler C&I Required for Synchronisation) | 206818437
EWLI commissioning | COM | 2026-02-05 08:00 | 2026-02-12 17:00 |  |  |  |  | 1.13.3.16(Boiler C&I Required for Synchronisation) | 206818438
APRDS Instrumentation & Commissioning | COM | 2025-09-16 08:00 | 2025-10-10 17:00 |  |  |  |  | 1.13.3.16(Boiler C&I Required for Synchronisation) | 206818439
HPBP Instrumentation & Commissioning | COM | 2026-04-21 08:00 | 2026-04-28 17:00 |  |  |  |  | 1.13.3.16(Boiler C&I Required for Synchronisation) | 206818440
TG C&I READINESS FOR BARRING GEAR | ERC | 2025-08-19 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.13.3(Erection) | 206818441
LO System Instrumentation | ERC | 2025-10-07 08:00 | 2025-10-21 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818442
LO System Drives - Cabling Commissioning | COM | 2025-10-22 08:00 | 2025-10-31 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818443
LO Temp. CV commissioning | COM | 2025-10-27 08:00 | 2025-10-31 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818444
Seal Oil System Instrumentation & Drives Commissioning | COM | 2025-08-19 08:00 | 2025-08-30 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818445
Turbine/Generator Bearing Temperature Measurement Instrumentation | ERC | 2025-12-12 08:00 | 2025-12-15 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818446
Turbine Supervisory Instrumentation | ERC | 2025-12-16 08:00 | 2025-12-20 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818447
LO System Interlocks & Protection Trial | ERC | 2025-12-16 08:00 | 2025-12-28 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818448
Barring Gear | ERC | 2026-01-26 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | 206818449
TG C&I READINESS FOR SYNCHRONISATION | ERC | 2025-08-21 08:00 | 2026-04-27 17:00 |  |  |  |  | 1.13.3(Erection) | 206818450
Gland Steam System Instrumentation | ERC | 2025-11-10 08:00 | 2025-11-24 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818451
Vacuum System Instrumentation | ERC | 2025-11-10 08:00 | 2025-11-23 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818452
Vacuum Breaker Commissioning | COM | 2025-11-24 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818453
Commissioning of Vacuum Pumps | COM | 2025-11-27 08:00 | 2025-12-02 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818454
Primary Water Instrumentation | ERC | 2025-08-21 08:00 | 2025-09-09 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818455
Generator Instrumentation | ERC | 2026-04-11 08:00 | 2026-04-25 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818456
MAL Valves commissioning | COM | 2025-11-20 08:00 | 2025-12-01 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818457
Turbine Integral Drain Valves commissioning | COM | 2025-11-25 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818458
Condensate System Instrumentation | ERC | 2025-09-05 08:00 | 2025-09-19 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818459
Hotwell Instrumentation | ERC | 2025-09-20 08:00 | 2025-09-29 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818460
CEP Instrumentation & Commissioning | COM | 2025-11-04 08:00 | 2025-11-18 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818461
Control Valve Commissioning | COM | 2025-11-04 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818462
LP Bypass System Instrumentation - Commissioning | COM | 2026-04-06 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818463
Steam line instrumentation | ERC | 2025-09-09 08:00 | 2025-09-23 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818464
Governing System Commissioning | COM | 2026-04-06 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818465
Stop Valve/Control Valve Position F/B Commissioning | COM | 2026-04-21 08:00 | 2026-04-24 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818466
Turbine Protection checking | COM | 2026-04-25 08:00 | 2026-04-27 17:00 |  |  |  |  | 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | 206818467
C&I READINESS FOR COAL FIRING | ERC | 2025-06-03 08:00 | 2026-05-05 17:00 |  |  |  |  | 1.13.3(Erection) | 206818468
PA FAN | ERC | 2025-06-10 08:00 | 2026-03-06 17:00 |  |  |  |  | 1.13.3.19(C&I READINESS FOR COAL FIRING) | 206818469
Second PA Fan | ERC | 2025-06-10 08:00 | 2026-03-06 17:00 |  |  |  |  | 1.13.3.19.1(PA FAN) | 206818470
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-06-10 08:00 | 2025-06-15 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818471
Motor Decoupled trial run | ERC | 2025-09-14 08:00 | 2025-09-14 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818472
Remote operation of drives like LOPs, Motor, etc | ERC | 2026-01-15 08:00 | 2026-01-22 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818473
Lube Oil flushing | ERC | 2025-07-10 08:00 | 2025-07-23 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818474
PA FAN - Instrumentation | ERC | 2026-02-02 08:00 | 2026-02-11 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818475
Outlet Gate & Blade Pitch Commissioning | COM | 2026-02-12 08:00 | 2026-02-17 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818476
Hot PA Header Instrumentation | ERC | 2026-02-18 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818477
Protection Check & Fan Trial run | COM | 2026-03-05 08:00 | 2026-03-06 17:00 |  |  |  |  | 1.13.3.19.1.1(Second PA Fan) | 206818478
First PA Fan: | ERC | 2025-12-24 08:00 | 2026-02-19 17:00 |  |  |  |  | 1.13.3.19.1(PA FAN) | 206818479
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-12-24 08:00 | 2025-12-29 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818480
Motor Decoupled trial run | COM | 2025-12-30 08:00 | 2025-12-30 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818481
Remote operation of drives like LOPs, Motor, etc | COM | 2025-12-31 08:00 | 2026-01-07 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818482
Lube Oil flushing | ERC | 2025-12-29 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818483
PA FAN - Instrumentation | ERC | 2026-01-18 08:00 | 2026-01-27 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818484
Outlet Gate & Blade Pitch Commissioning | COM | 2026-01-28 08:00 | 2026-02-02 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818485
Hot PA Header Instrumentation | ERC | 2026-02-03 08:00 | 2026-02-12 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818486
Protection Check & Fan Trial run | COM | 2026-02-18 08:00 | 2026-02-19 17:00 |  |  |  |  | 1.13.3.19.1.2(First PA Fan:) | 206818487
MILLS | ERC | 2025-09-02 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3.19(C&I READINESS FOR COAL FIRING) | 206818488
Mills | ERC | 2025-09-02 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3.19.2(MILLS) | 206818489
Motor Winding & Bearing Temperature signals hookup to DCS | ERC | 2025-09-02 08:00 | 2025-09-11 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818490
Remote operation of drives like LOPs, Motor, etc | COM | 2025-09-12 08:00 | 2025-09-21 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818491
Oil Flushing | ERC | 2025-09-22 08:00 | 2025-10-16 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818492
Mill Instrumentation | ERC | 2025-10-17 08:00 | 2025-11-05 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818493
Protection checking & Motor / Mill Trial | COM | 2025-11-06 08:00 | 2025-11-15 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818494
Cabling, commissioning & calibration of Feeders | COM | 2025-11-11 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818495
Drives like I/L gates, O/L gates, HAD/G, CAD/G, etc commissioning | COM | 2025-11-18 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.13.3.19.2.1(Mills) | 206818496
SEAL AIR FAN | ERC | 2026-04-22 08:00 | 2026-05-05 17:00 |  |  |  |  | 1.13.3.19(C&I READINESS FOR COAL FIRING) | 206818497
Seal Air System Instrumentation | ERC | 2026-04-22 08:00 | 2026-05-01 17:00 |  |  |  |  | 1.13.3.19.3(SEAL AIR FAN) | 206818498
Protection Checking & Motor & Fan Trial | COM | 2026-05-02 08:00 | 2026-05-05 17:00 |  |  |  |  | 1.13.3.19.3(SEAL AIR FAN) | 206818499
Boiler C&I Required for Coal Firing | ERC | 2025-06-03 08:00 | 2026-04-25 17:00 |  |  |  |  | 1.13.3.19(C&I READINESS FOR COAL FIRING) | 206818500
SH & RH Spray System | ERC | 2026-03-27 08:00 | 2026-04-10 17:00 |  |  |  |  | 1.13.3.19.4(Boiler C&I Required for Coal Firing) | 206818501
Burner Tilt Commissioning | COM | 2026-04-06 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.13.3.19.4(Boiler C&I Required for Coal Firing) | 206818502
Erection & Commissioning of O2 Analysers | COM | 2025-06-03 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.13.3.19.4(Boiler C&I Required for Coal Firing) | 206818503
ERV commissioning | COM | 2026-04-06 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.13.3.19.4(Boiler C&I Required for Coal Firing) | 206818504
Soot Blower System Instrumentation & commissioning of MOVs/CVs/SOVs | COM | 2025-07-30 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.13.3.19.4(Boiler C&I Required for Coal Firing) | 206818505
SWAS -Erection & Commissioning | COM | 2026-04-06 08:00 | 2026-04-25 17:00 |  |  |  |  | 1.13.3.19.4(Boiler C&I Required for Coal Firing) | 206818506
TDBFP | ERC | 2026-02-11 08:00 | 2026-04-18 17:00 |  |  |  |  | 1.13.3.19(C&I READINESS FOR COAL FIRING) | 206818507
L.O. System Instrumentation | ERC | 2026-02-11 08:00 | 2026-02-20 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818508
LGB & Commissioning & Cabling | COM | 2026-02-11 08:00 | 2026-02-20 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818509
Impulse piping of LO LGB, Seal Wtr LGB, FW LIR-HYD, BP/BFP Suction Strainer DPT, etc. | ERC | 2026-02-21 08:00 | 2026-03-04 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818510
LO Drives commissioning | COM | 2026-03-05 08:00 | 2026-03-09 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818511
TSI & Speed Probes Installation | ERC | 2026-03-10 08:00 | 2026-03-19 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818512
Barring Gear | ERC | 2026-03-20 08:00 | 2026-03-20 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818513
Stm Line, GS line, Exhaust - Instrumentation & CV commissioning | COM | 2026-03-21 08:00 | 2026-03-28 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818514
Governing System Commissioning | COM | 2026-03-29 08:00 | 2026-04-01 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818515
TDBFP Solo Run | COM | 2026-04-02 08:00 | 2026-04-02 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818516
Gearbox Instrumentation | ERC | 2026-04-03 08:00 | 2026-04-04 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818517
FW System Instrumentation | ERC | 2026-04-05 08:00 | 2026-04-14 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818518
Copper tubing & commissioning of BFP Re-circulation valve | COM | 2026-04-15 08:00 | 2026-04-16 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818519
Discharge MOV commissioning | COM | 2026-04-17 08:00 | 2026-04-17 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818520
TDBFP Coupled Trial | ERC | 2026-04-18 08:00 | 2026-04-18 17:00 |  |  |  |  | 1.13.3.19.5(TDBFP) | 206818521
E&C of EPABX (Telephone) system | ERC | 2025-07-27 08:00 | 2026-04-17 17:00 |  |  |  |  | 1.13.3(Erection) | 206818522
E&C of AAQMS | ERC | 2026-04-16 08:00 | 2026-05-15 17:00 |  |  |  |  | 1.13.3(Erection) | 206818523
BOP Systems | OTH | 2022-09-27 08:00 | 2026-08-05 17:00 | 2022-09-27 |  |  |  | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 206818524
Chimney | OTH | 2023-07-13 17:00 | 2025-11-30 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818525
Chimney- Detailed Engineering & RELEASE OF DRAWING | PE - RFC | 2023-07-13 17:00 | 2023-07-13 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818526
Chimney- Readiness for BLU | COM | 2025-09-01 17:00 | 2025-09-01 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818527
Chimney- Complete Readiness | COM | 2025-11-30 17:00 | 2025-11-30 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818528
Chimney- CIVIL Work | CIV | 2023-07-14 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818529
Chimney- Excavation & PCC | CIV | 2023-07-14 08:00 | 2023-08-17 17:00 |  |  |  |  | 1.14.1.4(Chimney- CIVIL Work) | 206818530
Chimney- Reinforcement fixing & Raft segment casting | CIV | 2023-08-03 08:00 | 2024-01-02 17:00 |  |  |  |  | 1.14.1.4(Chimney- CIVIL Work) | 206818531
Chimney- Reinforcement cutting & Bending Works | CIV | 2023-08-03 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.1.4.2(Chimney- Reinforcement fixing & Raft segment casting) | 206818532
Chimney- Raft | CIV | 2023-08-23 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.1.4.2(Chimney- Reinforcement fixing & Raft segment casting) | 206818533
Chimney- Starter Block for slipform work | CIV | 2023-12-31 08:00 | 2024-01-02 17:00 |  |  |  |  | 1.14.1.4.2(Chimney- Reinforcement fixing & Raft segment casting) | 206818534
Chimney- Backfilling Works | CIV | 2023-12-26 08:00 | 2024-01-24 17:00 |  |  |  |  | 1.14.1.4(Chimney- CIVIL Work) | 206818535
Chimney- Slipform apparatus arrival @ site | CIV | 2023-12-20 17:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.1.4(Chimney- CIVIL Work) | 206818536
Chimney- Slipform Erection to start at site | CIV | 2024-01-08 08:00 | 2024-03-02 17:00 |  |  |  |  | 1.14.1.4(Chimney- CIVIL Work) | 206818537
Chimney- Shell Casting includes platforms & door openings | CIV | 2024-03-13 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.14.1.4(Chimney- CIVIL Work) | 206818538
Chimney- Shell Casting includes platforms at 45 mtr height | CIV | 2024-03-13 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | 206818539
Chimney- Shell Casting includes platforms at 90 mtr height | CIV | 2024-05-14 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | 206818540
Chimney- Shell Casting includes platforms at 135 mtr height | CIV | 2024-07-05 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | 206818541
Chimney- Shell Casting includes platforms at 180 mtr height | CIV | 2024-08-21 08:00 | 2024-09-24 17:00 |  |  |  |  | 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | 206818542
Chimney- Shell Casting includes platforms at 225 mtr height | CIV | 2024-10-02 08:00 | 2024-10-31 17:00 |  |  |  |  | 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | 206818543
Chimney- Shell Casting includes platforms at 270 mtr height | CIV | 2024-11-08 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | 206818544
Chimney- Preassembly of Main beams & Supporting Beams of Inner Support Structure | CIV | 2024-06-01 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818545
Chimney- Preassembly of Steel Flue | CIV | 2024-06-01 08:00 | 2024-11-27 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818546
Chimney- Inner supporting structure Erection , alignment & fixing in position | CIV | 2024-12-13 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818547
Chimney-Erection & alignment at 270 Mtr height | CIV | 2024-12-13 08:00 | 2025-01-11 17:00 |  |  |  |  | 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | 206818548
Chimney-Erection & alignment at 225 Mtr height | CIV | 2025-01-17 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | 206818549
Chimney-Erection & alignment at 180 Mtr height | CIV | 2025-02-16 08:00 | 2025-03-07 17:00 |  |  |  |  | 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | 206818550
Chimney-Erection & alignment at 135 Mtr height | CIV | 2025-03-13 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | 206818551
Chimney-Erection & alignment at 90 Mtr height | CIV | 2025-04-07 08:00 | 2025-04-21 17:00 |  |  |  |  | 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | 206818552
Chimney-Erection & alignment at 45 mtr height | CIV | 2025-04-22 08:00 | 2025-05-01 17:00 |  |  |  |  | 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | 206818553
Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining | CIV | 2025-05-07 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818554
Chimney-Erection from 275 Mtr to 225 Mtr height | CIV | 2025-05-07 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | 206818555
Chimney-Erection 225 Mtr to 180 Mtr height | CIV | 2025-06-01 08:00 | 2025-06-18 17:00 |  |  |  |  | 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | 206818556
Chimney-Erection from 180 mtr to 135 Mtr height | CIV | 2025-06-24 08:00 | 2025-07-09 17:00 |  |  |  |  | 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | 206818557
Chimney-Erection from 135 mtr to 90 Mtr height | CIV | 2025-07-15 08:00 | 2025-07-30 17:00 |  |  |  |  | 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | 206818558
Chimney-Erection from 90 mtr to 45 Mtr height | CIV | 2025-08-05 08:00 | 2025-08-17 17:00 |  |  |  |  | 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | 206818559
Chimney-Erection from 45 Mtr to 0.00 mtr height | CIV | 2025-08-23 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | 206818560
Chimney- Painting of Outer shell structure | CIV | 2025-09-05 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818561
Chimney- Painting upto platforms at 45 mtr height | CIV | 2025-09-05 08:00 | 2025-09-14 17:00 |  |  |  |  | 1.14.1.9(Chimney- Painting of Outer shell structure) | 206818562
Chimney- Painting upto platform at 90 mtr height | CIV | 2025-09-15 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.14.1.9(Chimney- Painting of Outer shell structure) | 206818563
Chimney- Painting upto platform at 135 mtr height | CIV | 2025-09-25 08:00 | 2025-10-04 17:00 |  |  |  |  | 1.14.1.9(Chimney- Painting of Outer shell structure) | 206818564
Chimney- Painting upto platform at 180 mtr height | CIV | 2025-10-05 08:00 | 2025-10-14 17:00 |  |  |  |  | 1.14.1.9(Chimney- Painting of Outer shell structure) | 206818565
Chimney- Painting upto platform at 225 mtr height | CIV | 2025-10-15 08:00 | 2025-10-24 17:00 |  |  |  |  | 1.14.1.9(Chimney- Painting of Outer shell structure) | 206818566
Chimney- Painting upto platforms at 270 mtr height | CIV | 2025-10-25 08:00 | 2025-11-03 17:00 |  |  |  |  | 1.14.1.9(Chimney- Painting of Outer shell structure) | 206818567
Chimney- Grade slab Casting & earthing rod installation | CIV | 2025-09-22 08:00 | 2025-11-20 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818568
Chimney-Supply & Fixing of aviation lights, lightening arrestor, Chimney Lift &COMPLETION of other Electrical Works | CIV | 2025-09-02 08:00 | 2025-11-30 17:00 |  |  |  |  | 1.14.1(Chimney) | 206818569
NDCT cooling Tower | CIV | 2023-05-19 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818570
NDCT Execution Agency(Ordering by PEM) | CIV | 2023-05-19 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.2(NDCT cooling Tower) | 206818571
Enquiry | ENQ | 2023-05-19 08:00 | 2023-05-19 17:00 |  |  |  |  | 1.14.2.1( NDCT Execution Agency(Ordering by PEM)) | 206818572
PO Placement | ORD | 2023-05-20 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.2.1( NDCT Execution Agency(Ordering by PEM)) | 206818573
Submission of Basic Engineering Design/Drgs | ENG | 2023-10-17 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.2.1( NDCT Execution Agency(Ordering by PEM)) | 206818574
Supply for Cooling Tower | SUP | 2024-12-25 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.2(NDCT cooling Tower) | 206818575
Cooling Tower- Dispatch: Fill | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818576
Cooling Tower- Dispatch: Distribution Pipe | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818577
Cooling Tower- Dispatch: Nozzles | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818578
Cooling Tower- Dispatch: Butterfly Valve | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818579
Cooling Tower- Dispatch: Pumps/ Motors and connecting pipes and valves | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818580
Cooling Tower- Dispatch: AW Lights and other lights and fittings | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818581
Cooling Tower- Dispatch: Cable, Tray and distribution board | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818582
Cooling Tower- Dispatch: Lighting protection equipment | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818583
Cooling Tower- Dispatch: Earthing | DIS | 2024-12-25 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818584
Cooling Tower- Dispatch: Miscellaneous items - Gates, Sluice valve, Thermowell etc | DIS | 2024-12-25 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.2.2(Supply for Cooling Tower) | 206818585
Cooling Tower Civil Work | CIV | 2023-12-16 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14.2(NDCT cooling Tower) | 206818586
Cooling Tower Civil : Excavation | CIV | 2023-12-16 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818587
Cooling Tower Civil : PCC Under Foundation | CIV | 2023-12-31 08:00 | 2024-02-13 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818588
Cooling Tower Civil : Raft/Footing Casting | CIV | 2024-01-15 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818589
Cooling Tower Civil : Pedestal Casting | CIV | 2024-02-19 08:00 | 2024-03-31 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818590
Cooling Tower Civil : Racker Column Casting | CIV | 2024-03-02 08:00 | 2024-07-29 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818591
Cooling Tower Civil : Tower Crane Erection | ERC | 2024-02-19 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818592
Cooling Tower Civil : Ring Beam Casting | CIV | 2024-05-01 08:00 | 2024-08-28 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818593
Cooling Tower Civil : PCC for Pound | CIV | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818594
Cooling Tower Civil : RCC for pound floor | CIV | 2024-03-30 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818595
Cooling Tower Civil : Pound wall RCC | CIV | 2024-04-14 08:00 | 2024-08-11 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818596
Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift) | CIV | 2024-06-15 08:00 | 2025-07-02 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818597
Cooling Tower Civil : Shell casting Initial manual lifts | CIV | 2024-09-01 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818598
Cooling Tower Civil : Jump form erection | CIV | 2024-06-15 08:00 | 2024-09-22 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818599
Cooling Tower Civil : Shell casting- next 27 nos lifts | CIV | 2024-10-26 08:00 | 2024-12-19 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818600
Cooling Tower Civil : Shell casting - next 23 nos lifts | CIV | 2024-12-20 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818601
Cooling Tower Civil : shell casting - next 23 nos lifts | CIV | 2025-02-03 08:00 | 2025-03-19 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818602
Cooling Tower Civil : shell casting- next 25 nos lift | CIV | 2025-03-20 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818603
Cooling Tower Civil : shell casting COMPLETION including top platform | CIV | 2025-05-09 08:00 | 2025-07-02 17:00 |  |  |  |  | 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | 206818604
Inner Grillage columns casting | CIV | 2024-06-01 08:00 | 2025-11-12 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818605
Cooling Tower Civil : Grillage columns 1st lift | CIV | 2024-06-01 08:00 | 2024-10-03 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818606
Cooling Tower Civil : Grillage columns 2nd lift | CIV | 2024-09-04 08:00 | 2025-01-06 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818607
Cooling Tower Civil : Bottom connecting beam | CIV | 2024-12-08 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818608
Cooling Tower Civil : Top connecting beam | CIV | 2025-03-03 08:00 | 2025-06-25 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818609
Cooling Tower Civil : Auxiliary /secondary connecting bottom beams | CIV | 2025-05-27 08:00 | 2025-09-03 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818610
Cooling Tower Civil : Auxiliary /secondary connecting top beams | CIV | 2025-08-05 08:00 | 2025-11-12 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818611
Cooling Tower Civil : Precast Auxiliary 1st tier | CIV | 2025-04-02 08:00 | 2025-06-30 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818612
Cooling Tower Civil : Precast Auxiliary 2nd tier | CIV | 2025-07-01 08:00 | 2025-09-28 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818613
Cooling Tower Civil :Erection of duct columns 1st lift | ERC | 2025-04-02 08:00 | 2025-06-30 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818614
Cooling Tower Civil :Erection of duct columns 2nd lift | ERC | 2025-05-02 08:00 | 2025-07-30 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818615
Cooling Tower Civil :Erection of grillage bracket 1st lift | ERC | 2025-05-02 08:00 | 2025-07-30 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818616
Cooling Tower Civil :Erection of grillage bracket 2nd lift | ERC | 2025-06-01 08:00 | 2025-08-29 17:00 |  |  |  |  | 1.14.2.3.12(Inner Grillage columns casting) | 206818617
Cooling Tower Civil : Stair case & Ladders | CIV | 2025-06-03 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818618
Cooling Tower Civil :COMPLETION of work | CIV | 2025-11-13 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14.2.3( Cooling Tower Civil Work) | 206818619
Cooling Tower E&C | ERC | 2025-01-04 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.2(NDCT cooling Tower) | 206818620
Cooling Tower E&C :Erection of Fill, Distribution pipe & Nozzle | ERC | 2025-06-18 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818621
Cooling Tower E&C :Erection of Pump, connecting pipes and Valve | ERC | 2025-08-17 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818622
Cooling Tower E&C : Fabrication Tower E&C of Hot water piping | ERC | 2025-01-04 08:00 | 2025-06-02 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818623
Cooling Tower E&C :Erection of Cable Tray, AW Lights and other lights and fittings | ERC | 2025-06-03 08:00 | 2025-09-10 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818624
Cooling Tower E&C :Erection of Lighting protection equipment | ERC | 2025-06-03 08:00 | 2025-09-10 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818625
Cooling Tower E&C :Erection of Miscellaneous items - Gates, Sluice valve , Thermowell etc | ERC | 2025-09-11 08:00 | 2025-10-10 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818626
Cooling Tower E&C : Commissioning | COM | 2025-11-13 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.2.4( Cooling Tower E&C ) | 206818627
Air Conditioning System | ERC | 2023-10-27 08:00 | 2026-01-19 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818628
Rel of Dwg for Air conditioning system | PE - RFC | 2024-06-18 08:00 | 2024-06-18 17:00 |  |  |  |  | 1.14.3(Air Conditioning System) | 206818629
Air conditioning system Execution Agency | PRC | 2023-10-27 08:00 | 2024-03-26 17:00 |  |  |  |  | 1.14.3(Air Conditioning System) | 206818630
Enquiry | ENQ | 2023-10-27 08:00 | 2023-10-27 17:00 |  |  |  |  | 1.14.3.2( Air conditioning system Execution Agency) | 206818631
PO Placement | ORD | 2024-03-26 08:00 | 2024-03-26 17:00 |  |  |  |  | 1.14.3.2( Air conditioning system Execution Agency) | 206818632
Air Conditioning System-Dispatch | DIS | 2024-10-23 08:00 | 2025-01-20 17:00 |  |  |  |  | 1.14.3(Air Conditioning System) | 206818633
Air Conditioning System-Dispatch: Screw Chiller Unit | DIS | 2024-10-23 08:00 | 2024-11-21 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818634
Air Conditioning System-Dispatch: Cooling Water Pumps | DIS | 2024-10-23 08:00 | 2024-11-21 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818635
Air Conditioning System-Dispatch: Chilled Water Pumps | DIS | 2024-10-23 08:00 | 2024-11-21 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818636
Air Conditioning System-Dispatch: Pipe & Fittings | DIS | 2024-11-22 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818637
Air Conditioning System-Dispatch: AHU | DIS | 2024-12-22 08:00 | 2025-01-20 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818638
Air Conditioning System-Dispatch: Duct & Dampers | DIS | 2024-12-22 08:00 | 2025-01-20 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818639
Air Conditioning System-Dispatch: Cable & Cable Tray | DIS | 2024-12-22 08:00 | 2025-01-20 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818640
Air Conditioning System-Dispatch: Valves | DIS | 2024-11-22 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818641
Air Conditioning System-Dispatch: Misc. Items | DIS | 2024-12-22 08:00 | 2025-01-20 17:00 |  |  |  |  | 1.14.3.3( Air Conditioning System-Dispatch) | 206818642
E&C for AIR CONDITIONING SYSTEM | ERC | 2024-11-22 08:00 | 2026-01-19 17:00 |  |  |  |  | 1.14.3(Air Conditioning System) | 206818643
AIR CONDITIONING SYSTEM E&C:Water cooled screw chiller unit | ERC | 2024-11-22 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818644
AIR CONDITIONING SYSTEM E&C:Condenser cooling water pumps | ERC | 2024-12-22 08:00 | 2025-02-04 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818645
AIR CONDITIONING SYSTEM E&C:Chilled Water circulating Pumps | ERC | 2025-02-05 08:00 | 2025-03-21 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818646
AIR CONDITIONING SYSTEM E&C:Cooling Tower | ERC | 2025-03-22 08:00 | 2025-07-19 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818647
AIR CONDITIONING SYSTEM E&C:Interconnecting piping | ERC | 2025-05-21 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818648
AIR CONDITIONING SYSTEM E&C:Air Handling Units | ERC | 2025-06-20 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818649
AIR CONDITIONING SYSTEM E&C:Ducting / Dampers / Hangers / Supports / Fire dampers | ERC | 2025-07-20 08:00 | 2025-12-16 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818650
AIR CONDITIONING SYSTEM E&C:Electrical & C&I, Misc. item | ERC | 2025-08-19 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818651
AIR CONDITIONING SYSTEME&C:AC SYSTEM Commissioning | COM | 2026-01-06 08:00 | 2026-01-19 17:00 |  |  |  |  | 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | 206818652
Air Compressor System | ERC | 2023-08-23 08:00 | 2025-12-21 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818653
Rel of Dwg for Air compressor house | PE - RFC | 2024-06-04 08:00 | 2024-06-04 17:00 |  |  |  | PCE-04400 | 1.14.4(Air Compressor System) | 206818654
Air compressor system Execution Agency | PRC | 2023-08-23 08:00 | 2024-01-20 17:00 |  |  |  |  | 1.14.4(Air Compressor System) | 206818655
Enquiry | ENQ | 2023-08-23 08:00 | 2023-08-23 17:00 |  |  |  |  | 1.14.4.2( Air compressor system Execution Agency) | 206818656
PO Placement | ORD | 2023-08-24 08:00 | 2024-01-20 17:00 |  |  |  |  | 1.14.4.2( Air compressor system Execution Agency) | 206818657
Civil | CIV | 2024-06-05 08:00 | 2025-12-21 17:00 |  |  |  |  | 1.14.4(Air Compressor System) | 206818658
Air Compressor Building: Foundation | CIV | 2024-06-05 08:00 | 2024-12-01 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818659
Air Compressor Building: Structure Erection | ERC | 2024-12-02 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818660
Air Compressor Building: Grade Slab | CIV | 2025-04-01 08:00 | 2025-04-30 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818661
Air Compressor Building: Cladding & Sheeting | CIV | 2025-04-01 08:00 | 2025-04-30 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818662
Air Compressor Building: EOT Erection | ERC | 2025-04-01 08:00 | 2025-07-29 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818663
Air Compressor Building: Brick Work & Plastering | CIV | 2025-07-30 08:00 | 2025-10-27 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818664
Air Compressor Building: Flooring | CIV | 2025-10-28 08:00 | 2025-11-21 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818665
Air Compressor Building: Finishing works | CIV | 2025-11-22 08:00 | 2025-12-21 17:00 |  |  |  |  | 1.14.4.3( Civil) | 206818666
Supply-PEM | SUP | 2024-09-07 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.4(Air Compressor System) | 206818667
Dispatch of COMPRESSED AIR SYSTEM: Instrument & Service air Compressors | DIS | 2024-09-07 08:00 | 2024-10-06 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818668
Dispatch of COMPRESSED AIR SYSTEM: Air Dryer | DIS | 2024-09-07 08:00 | 2024-10-06 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818669
Dispatch of COMPRESSED AIR SYSTEM: Air receiver tank | DIS | 2024-09-07 08:00 | 2024-10-06 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818670
Dispatch of COMPRESSED AIR SYSTEM: Pipe & Fittings | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818671
Dispatch of COMPRESSED AIR SYSTEM: Valves | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818672
Dispatch of COMPRESSED AIR SYSTEM: Cables and cable tray and other electrical & C&I items | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818673
Dispatch of COMPRESSED AIR SYSTEM: PLC | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818674
Dispatch of COMPRESSED AIR SYSTEM: Misc. Items | DIS | 2024-09-22 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.4.4(Supply-PEM) | 206818675
Erection | ERC | 2025-05-01 08:00 | 2025-10-24 17:00 |  |  |  |  | 1.14.4(Air Compressor System) | 206818676
E&C for compressed air system: ERECTION OF DRYER FOR INSTRUMENT AIR COMPRESSOR | ERC | 2025-05-01 08:00 | 2025-05-07 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818677
E&C for compressed air Misc. OF RECEIVER TANK FOR INSTRUMENT AIR COMPRESSOR | ERC | 2025-05-08 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818678
E&C for compressed air system: PLACEMENT OF INSTRUMENT AIR COMPRESSOR ON ON FOUNDATION | ERC | 2025-05-15 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818679
E&C for compressed air system: PLACEMENT OF DRYER FOR SERVICE AIR COMPRESSOR | ERC | 2025-06-04 08:00 | 2025-06-10 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818680
E&C for compressed air system: PLACEMENT OF RECEIVER TANK FOR SERVICE AIR COMPRESSOR | ERC | 2025-06-11 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818681
E&C for compressed air system: PLACEMENT OF SERVICE AIR COMPRESSOR ON ON FOUNDATION | ERC | 2025-06-18 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818682
E&C for compressed air system: PLACEMENT OF PIPES AND FITTINGS | ERC | 2025-07-08 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818683
E&C for compressed air system: PLACEMENT OF VALVES | ERC | 2025-08-22 08:00 | 2025-09-08 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818684
E&C for compressed air system: PLACEMENT OF PLC, Electrical , C&I and misc. items FOR COMRESSED AIR SYSTEM | ERC | 2025-09-09 08:00 | 2025-10-08 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818685
E&C for compressed air system: Commissioning of compressed air system | COM | 2025-10-09 08:00 | 2025-10-24 17:00 |  |  |  |  | 1.14.4.5(Erection) | 206818686
Water Treatment system | CIV | 2023-06-04 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818687
Raw Water Storage Reservoir & Pump house | CIV | 2023-07-14 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.5(Water Treatment system ) | 206818688
Civil | CIV | 2023-07-14 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.5.1(Raw Water Storage Reservoir & Pump house) | 206818689
Rel of DWG for Raw water storage tank | PE - RFC | 2023-09-27 08:00 | 2023-09-27 17:00 |  |  |  | PCE-05700 | 1.14.5.1.1(Civil) | 206818690
Rel of DWG for Raw water PH | PE - RFC | 2023-12-26 08:00 | 2023-12-26 17:00 |  |  |  | PCE-05800 | 1.14.5.1.1(Civil) | 206818691
RAW WATER RESERVOIR | CIV | 2023-10-28 08:00 | 2024-04-09 17:00 |  |  |  |  | 1.14.5.1.1(Civil) | 206818692
EXCAVATION | CIV | 2023-10-28 08:00 | 2023-11-21 17:00 |  |  |  |  | 1.14.5.1.1.3(RAW WATER RESERVOIR) | 206818693
PCC | CIV | 2023-11-22 08:00 | 2023-12-06 17:00 |  |  |  |  | 1.14.5.1.1.3(RAW WATER RESERVOIR) | 206818694
RCC | CIV | 2023-12-07 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.14.5.1.1.3(RAW WATER RESERVOIR) | 206818695
Backfilling | CIV | 2024-03-06 08:00 | 2024-03-20 17:00 |  |  |  |  | 1.14.5.1.1.3(RAW WATER RESERVOIR) | 206818696
Finishing works | CIV | 2024-03-21 08:00 | 2024-04-09 17:00 |  |  |  |  | 1.14.5.1.1.3(RAW WATER RESERVOIR) | 206818697
RAW WATER CONTROL ROOM | CIV | 2023-07-14 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.5.1.1(Civil) | 206818698
EXCAVATION | CIV | 2023-07-14 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.5.1.1.4(RAW WATER CONTROL ROOM) | 206818699
PCC | CIV | 2023-08-08 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.5.1.1.4(RAW WATER CONTROL ROOM) | 206818700
RCC | CIV | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.5.1.1.4(RAW WATER CONTROL ROOM) | 206818701
Backfilling | CIV | 2023-11-21 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.5.1.1.4(RAW WATER CONTROL ROOM) | 206818702
Finishing works | CIV | 2023-12-06 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.5.1.1.4(RAW WATER CONTROL ROOM) | 206818703
Raw Water Pump House | CIV | 2024-01-26 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.5.1.1(Civil) | 206818704
Raw Water Pump House: EXCAVATION | CIV | 2024-01-26 08:00 | 2024-02-19 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818705
Raw Water Pump House: RCC in substructure including PCC | CIV | 2024-02-20 08:00 | 2024-05-19 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818706
Raw Water Pump House: RCC in superstructure including equipment foundation | CIV | 2024-05-20 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818707
Raw Water Pump House: Brick Work & Plastering | CIV | 2024-09-17 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818708
Raw Water Pump House: Flooring | CIV | 2024-12-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818709
Raw Water Pump House: Backfilling | CIV | 2025-01-15 08:00 | 2025-02-13 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818710
Raw Water Pump House: Finishing works | CIV | 2025-02-14 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.5.1.1.5(Raw Water Pump House) | 206818711
Erection | ERC | 2023-11-01 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.14.5.1(Raw Water Storage Reservoir & Pump house) | 206818712
Raw water Piping and associated work | CIV | 2023-11-01 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.14.5.1.2(Erection) | 206818713
Readiness of Control room | CIV | 2023-12-06 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.14.5.1.2(Erection) | 206818714
Pre-treatment Plant | CIV | 2023-06-04 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.5(Water Treatment system ) | 206818715
PT Plant Execution Agency | PRC | 2023-06-04 08:00 | 2024-06-15 17:00 |  |  |  |  | 1.14.5.2(Pre-treatment Plant) | 206818716
Enquiry | ENQ | 2023-06-04 08:00 | 2023-06-04 17:00 |  |  |  |  | 1.14.5.2.1( PT Plant Execution Agency) | 206818717
PO Placement | ORD | 2023-11-17 08:00 | 2023-11-17 17:00 |  |  |  |  | 1.14.5.2.1( PT Plant Execution Agency) | 206818718
Rel of Drawing for Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume | PE - RFC | 2024-05-16 08:00 | 2024-05-16 17:00 |  |  |  |  | 1.14.5.2.1( PT Plant Execution Agency) | 206818719
Rel of Drg for CLARI FOCULATOR | PE - RFC | 2024-06-15 08:00 | 2024-06-15 17:00 |  |  |  |  | 1.14.5.2.1( PT Plant Execution Agency) | 206818720
Rel of Drg for Chemical House | PE - RFC | 2024-06-15 08:00 | 2024-06-15 17:00 |  |  |  | PCE-06100 | 1.14.5.2.1( PT Plant Execution Agency) | 206818721
Rel of Drg for Pump House | PE - RFC | 2024-06-15 08:00 | 2024-06-15 17:00 |  |  |  | PCE-06200 | 1.14.5.2.1( PT Plant Execution Agency) | 206818722
Civil Work | CIV | 2024-06-16 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.14.5.2(Pre-treatment Plant) | 206818723
Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume | CIV | 2024-06-16 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.14.5.2.2(Civil Work) | 206818724
EXCAVATION | CIV | 2024-06-16 08:00 | 2024-07-10 17:00 |  |  |  |  | 1.14.5.2.2.1( Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume) | 206818725
RCC in substructure including PCC | CIV | 2024-07-11 08:00 | 2024-08-14 17:00 |  |  |  |  | 1.14.5.2.2.1( Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume) | 206818726
RCC in superstructure | CIV | 2024-08-15 08:00 | 2024-10-13 17:00 |  |  |  |  | 1.14.5.2.2.1( Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume) | 206818727
Backfilling | CIV | 2024-10-14 08:00 | 2024-10-28 17:00 |  |  |  |  | 1.14.5.2.2.1( Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume) | 206818728
Finishing works | CIV | 2024-10-29 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.14.5.2.2.1( Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume) | 206818729
CLARI FOCULATOR | CIV | 2024-06-26 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.14.5.2.2(Civil Work) | 206818730
EXCAVATION | CIV | 2024-06-26 08:00 | 2024-07-20 17:00 |  |  |  |  | 1.14.5.2.2.2( CLARI FOCULATOR) | 206818731
RCC in substructure including PCC | CIV | 2024-07-21 08:00 | 2024-09-13 17:00 |  |  |  |  | 1.14.5.2.2.2( CLARI FOCULATOR) | 206818732
RCC in superstructure | CIV | 2024-09-14 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.14.5.2.2.2( CLARI FOCULATOR) | 206818733
Backfilling | CIV | 2024-12-08 08:00 | 2024-12-22 17:00 |  |  |  |  | 1.14.5.2.2.2( CLARI FOCULATOR) | 206818734
Finishing works | CIV | 2025-02-11 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.14.5.2.2.2( CLARI FOCULATOR) | 206818735
Chemical House | CIV | 2024-06-26 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.14.5.2.2(Civil Work) | 206818736
EXCAVATION | CIV | 2024-06-26 08:00 | 2024-07-10 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818737
RCC in substructure including PCC | CIV | 2024-07-11 08:00 | 2024-08-14 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818738
RCC in superstructure including equipment foundation | CIV | 2024-08-15 08:00 | 2024-11-12 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818739
Brick Work & Plastering | CIV | 2024-12-13 08:00 | 2025-03-12 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818740
Flooring | CIV | 2025-03-13 08:00 | 2025-04-01 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818741
Backfilling | CIV | 2025-04-02 08:00 | 2025-04-21 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818742
Finishing works | CIV | 2025-04-22 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.14.5.2.2.3( Chemical House) | 206818743
Pump House | CIV | 2024-06-26 08:00 | 2025-06-15 17:00 |  |  |  |  | 1.14.5.2.2(Civil Work) | 206818744
EXCAVATION | CIV | 2024-06-26 08:00 | 2024-07-15 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818745
RCC in substructure including PCC | CIV | 2024-07-16 08:00 | 2024-08-19 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818746
RCC in superstructure including equipment foundation | CIV | 2024-08-20 08:00 | 2024-11-17 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818747
Brick Work & Plastering | CIV | 2024-12-08 08:00 | 2025-02-05 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818748
Flooring | CIV | 2025-02-06 08:00 | 2025-02-25 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818749
Backfilling | CIV | 2025-02-26 08:00 | 2025-03-17 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818750
Finishing works | CIV | 2025-03-18 08:00 | 2025-06-15 17:00 |  |  |  |  | 1.14.5.2.2.4( Pump House) | 206818751
Supply | SUP | 2024-07-15 08:00 | 2024-12-08 17:00 |  |  |  |  | 1.14.5.2(Pre-treatment Plant) | 206818752
Dispatch of Rake mechanism with drive & motor | DIS | 2024-08-04 08:00 | 2024-11-02 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818753
Dispatch of Transfer Pumps | DIS | 2024-07-15 08:00 | 2024-10-07 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818754
Dispatch of Injection Pumps | DIS | 2024-08-14 08:00 | 2024-10-24 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818755
Dispatch of Dosing Pumps | DIS | 2024-08-14 08:00 | 2024-10-24 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818756
Dispatch of Agitator with motor | DIS | 2024-08-04 08:00 | 2024-10-03 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818757
Dispatch of Piping, Fittings and valves | DIS | 2024-08-14 08:00 | 2024-11-13 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818758
Dispatch of Electrical & C&I items (Transmitters, local instruments, cable, junction box, PLC etc.) | DIS | 2024-08-14 08:00 | 2024-12-08 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818759
Dispatch of Misc. Items & Potable pump | DIS | 2024-08-14 08:00 | 2024-12-08 17:00 |  |  |  |  | 1.14.5.2.3(Supply) | 206818760
Erection | ERC | 2024-11-18 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.5.2(Pre-treatment Plant) | 206818761
Erection of Mixer cum solid recirculation device with drive and motor | ERC | 2024-12-23 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818762
Erection of Rake mechanism with drive & motor | ERC | 2024-12-23 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818763
Erection of Transfer Pumps (Sludge, Lime Slake etc) | ERC | 2024-11-23 08:00 | 2024-12-12 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818764
Erection of Injection Pumps (Alum etc) | ERC | 2024-11-18 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818765
Erection of Dosing Pumps (Poly electrolyte, lime solution etc) | ERC | 2024-11-18 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818766
Erection of Agitator and motor for Alum/Lime Slaking/Lime Solution | ERC | 2024-11-18 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818767
Erection of Piping, Fittings and valves | ERC | 2024-12-13 08:00 | 2025-02-10 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818768
Erection of Electrical, C&I & Misc. items | ERC | 2025-02-11 08:00 | 2025-04-16 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818769
Commissioning of clarifier along with Chlorination and Filter water system to feed the DM Plant | COM | 2025-02-11 08:00 | 2025-02-15 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818770
Commissioning of 1st CW Clarifier, clarified water pumps and associated System to feed clarified water to CW system | COM | 2025-04-17 08:00 | 2025-07-26 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818771
Commissioning of 2nd Clarifier for CW System | COM | 2025-07-27 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818772
Commissioning of Potable Water System | COM | 2025-03-13 08:00 | 2025-05-26 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818773
Commissioning of Service water system | COM | 2025-03-13 08:00 | 2025-07-26 17:00 |  |  |  |  | 1.14.5.2.4(Erection) | 206818774
DM Plant | OTH | 2023-06-23 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.14.5(Water Treatment system ) | 206818775
Rel of Dwg for DM Plant Building | PE - RFC | 2024-02-09 08:00 | 2024-02-09 17:00 |  |  |  | PCE-06300 | 1.14.5.3(DM Plant) | 206818776
Rel of Dwg for DM Plant equipment foundation | PE - RFC | 2025-02-07 08:00 | 2025-02-07 17:00 |  |  |  | PCE-06400 | 1.14.5.3(DM Plant) | 206818777
Rel of Dwg for DM Plant Neutralization Pit | PE - RFC | 2024-09-09 08:00 | 2024-09-09 17:00 |  |  |  | PCE-06500 | 1.14.5.3(DM Plant) | 206818778
DM Plant Execution Agency | PRC | 2023-06-23 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.5.3(DM Plant) | 206818779
Enquiry | ENQ | 2023-06-23 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.5.3.4( DM Plant Execution Agency) | 206818780
PO Placement | ORD | 2023-06-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.5.3.4( DM Plant Execution Agency) | 206818781
Submission of Basic Engineering Design/Drgs | ENG | 2023-11-21 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.5.3.4( DM Plant Execution Agency) | 206818782
Civil Works | CIV | 2024-02-10 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.14.5.3(DM Plant) | 206818783
Acid alkali Unloading & storage area | CIV | 2024-02-10 08:00 | 2024-12-25 17:00 |  |  |  |  | 1.14.5.3.5( Civil Works) | 206818784
EXCAVATION | CIV | 2024-02-10 08:00 | 2024-02-29 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818785
RCC in substructure including PCC | CIV | 2024-03-01 08:00 | 2024-04-04 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818786
RCC in superstructure including equipment foundation | CIV | 2024-04-05 08:00 | 2024-05-19 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818787
Brick Work & Plastering | CIV | 2024-11-16 08:00 | 2024-11-25 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818788
Flooring | CIV | 2024-11-26 08:00 | 2024-12-05 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818789
Backfilling | CIV | 2024-12-06 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818790
Finishing works | CIV | 2024-12-16 08:00 | 2024-12-25 17:00 |  |  |  |  | 1.14.5.3.5.1( Acid alkali Unloading & storage area) | 206818791
DM Plant Building including Vessel Foundation | CIV | 2024-02-10 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.14.5.3.5( Civil Works) | 206818792
EXCAVATION | CIV | 2024-02-10 08:00 | 2024-03-10 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818793
RCC in substructure including PCC | CIV | 2024-03-11 08:00 | 2024-04-29 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818794
RCC in superstructure including equipment foundation | CIV | 2024-04-30 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818795
Backfilling | CIV | 2024-07-29 08:00 | 2024-08-17 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818796
Brick Work & Plastering | CIV | 2024-12-01 08:00 | 2025-01-29 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818797
Flooring | CIV | 2025-01-30 08:00 | 2025-02-18 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818798
Finishing works | CIV | 2025-02-19 08:00 | 2025-05-19 17:00 |  |  |  |  | 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | 206818799
Neutralization Pit | CIV | 2024-09-10 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.14.5.3.5( Civil Works) | 206818800
EXCAVATION | CIV | 2024-09-10 08:00 | 2024-10-14 17:00 |  |  |  |  | 1.14.5.3.5.3( Neutralization Pit) | 206818801
RCC in substructure including PCC | CIV | 2024-10-15 08:00 | 2024-11-23 17:00 |  |  |  |  | 1.14.5.3.5.3( Neutralization Pit) | 206818802
RCC in superstructure | CIV | 2024-11-24 08:00 | 2024-12-23 17:00 |  |  |  |  | 1.14.5.3.5.3( Neutralization Pit) | 206818803
Backfilling | CIV | 2024-12-24 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.14.5.3.5.3( Neutralization Pit) | 206818804
Acid Proof lining | CIV | 2025-01-08 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.14.5.3.5.3( Neutralization Pit) | 206818805
Supply for DM Plant | SUP | 2024-04-04 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.5.3(DM Plant) | 206818806
Dispatch of Activated carbon filter | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818807
Dispatch of Cation Exchange Unit | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818808
Dispatch of Anion Exchange Unit | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818809
Dispatch of Mix Bed Exchanger Unit | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818810
Dispatch of Agitators | DIS | 2024-05-19 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818811
Dispatch of Air Blowers | DIS | 2024-05-19 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818812
Dispatch of Supply & Transfer Pumps | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818813
Dispatch of Unloading Pumps | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818814
Dispatch of Storage/Measuring Tanks | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818815
Dispatch of Pipe, Fittings & Valves | DIS | 2024-04-04 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818816
Dispatch of Electrical & C&I Items (Motors, Measuring instruments, Cable tray, JBs, Control panel etc.) | DIS | 2024-06-18 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818817
Dispatch of Balance Items | DIS | 2024-06-18 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.5.3.6(Supply for DM Plant) | 206818818
Erection | ERC | 2024-07-19 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.14.5.3(DM Plant) | 206818819
Erection of Activated carbon filter | ERC | 2024-07-29 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818820
Erection of Cation Exchange Unit | ERC | 2024-07-29 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818821
Erection of Anion Exchange Unit | ERC | 2024-07-29 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818822
Erection of Mix Bed Exchanger | ERC | 2024-07-29 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818823
Agitators | ERC | 2024-10-27 08:00 | 2024-11-10 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818824
Erection of Air Blowers | ERC | 2024-11-11 08:00 | 2024-11-30 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818825
Erection of Supply & Transfer Pumps | ERC | 2024-08-18 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818826
Erection of Unloading Pumps | ERC | 2024-08-08 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818827
Erection of Storage/Measuring Tanks | ERC | 2024-07-29 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818828
Erection of Pipe, Fittings & Valves | ERC | 2024-07-19 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818829
Electrical , C&I and Misc. Items (DTT, Motors, Measuring instruments, Cable tray, JBs, Control panel etc.) | ERC | 2024-09-22 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818830
Readiness for HT(Completion of DM Plant: 1st Stream along with associated systems and Charging of DM Fill System) | ERC | 2025-02-16 08:00 | 2025-02-20 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818831
Completion of DM Plant (Balance streams) | ERC | 2025-02-21 08:00 | 2025-07-20 17:00 |  |  |  |  | 1.14.5.3.7(Erection) | 206818832
Effluent Treatment Plant with ZLD | OTH | 2023-12-01 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14.5(Water Treatment system ) | 206818833
ETP Execution Agency | PRC | 2023-12-01 08:00 | 2024-08-27 17:00 |  |  |  |  | 1.14.5.4(Effluent Treatment Plant with ZLD) | 206818834
Enquiry | ENQ | 2023-12-01 08:00 | 2023-12-01 17:00 |  |  |  |  | 1.14.5.4.1(ETP Execution Agency) | 206818835
PO Placement | ORD | 2023-12-02 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.14.5.4.1(ETP Execution Agency) | 206818836
Engineering Design/Drgs | ENG | 2024-06-29 08:00 | 2024-08-27 17:00 |  |  |  |  | 1.14.5.4.1(ETP Execution Agency) | 206818837
Civil | CIV | 2024-09-13 08:00 | 2025-07-14 17:00 |  |  |  |  | 1.14.5.4(Effluent Treatment Plant with ZLD) | 206818838
EXCAVATION | CIV | 2024-09-13 08:00 | 2024-10-27 17:00 |  |  |  |  | 1.14.5.4.2(Civil) | 206818839
RCC in substructure including PCC | CIV | 2024-10-28 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.5.4.2(Civil) | 206818840
RCC in superstructure including equipment foundation | CIV | 2025-01-16 08:00 | 2025-05-15 17:00 |  |  |  |  | 1.14.5.4.2(Civil) | 206818841
Backfilling | CIV | 2025-05-16 08:00 | 2025-06-14 17:00 |  |  |  |  | 1.14.5.4.2(Civil) | 206818842
Finishing works | CIV | 2025-06-15 08:00 | 2025-07-14 17:00 |  |  |  |  | 1.14.5.4.2(Civil) | 206818843
Supply | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4(Effluent Treatment Plant with ZLD) | 206818844
ATMOSPHERIC TANKS (Flash Mixer, Floculator, Alkali Dosing and Alum Dosing Tank) | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818845
AGITATORS, STRAINERS | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818846
TUBES/MEDIA FOR INCLINED SURFACE SETTLER AND OIL WATER SEPERATOR | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818847
PUMPS & BLOWERS | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818848
PIPING AND FITTINGS | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818849
VALVES | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818850
ELECTRICAL ITEMS | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818851
INSTRUMENTS AND CONTROL SYSTEM | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818852
MISC ITEMS | SUP | 2025-03-16 08:00 | 2025-05-14 17:00 |  |  |  |  | 1.14.5.4.3(Supply) | 206818853
Erection | ERC | 2025-07-15 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14.5.4(Effluent Treatment Plant with ZLD) | 206818854
ATMOSPHERIC TANKS (Flash Mixer, Floculator, Alkali Dosing and Alum Dosing Tank) | ERC | 2025-07-15 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818855
TUBES/MEDIA FOR INCLINED SURFACE SETTLER AND OIL WATER SEPERATOR | ERC | 2025-08-04 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818856
AGITATORS, STRAINERS | ERC | 2025-09-18 08:00 | 2025-10-07 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818857
PUMPS & BLOWERS | ERC | 2025-07-15 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818858
PIPING AND FITTINGS ALOGWITH VALVES | ERC | 2025-08-04 08:00 | 2025-10-02 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818859
ELECTRICAL ITEMS | ERC | 2025-09-03 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818860
INSTRUMENTS AND CONTROL SYSTEM | ERC | 2025-09-03 08:00 | 2025-11-11 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818861
MISC ITEMS | ERC | 2025-10-28 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818862
COMMISSIONING | COM | 2025-11-27 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14.5.4.4(Erection) | 206818863
Fuel Oil Handling system | OTH | 2023-08-23 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818864
Rel of DWG for LDO | PE - RFC | 2024-06-14 08:00 | 2024-06-14 17:00 |  |  |  |  | 1.14.6(Fuel Oil Handling system) | 206818865
Rel of DWG for FO TR Pump House | PE - RFC | 2024-06-28 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.14.6(Fuel Oil Handling system) | 206818866
Rel of DWG for FO Pressurizing Pump House | PE - RFC | 2024-06-14 08:00 | 2024-06-14 17:00 |  |  |  | PCE-06800 | 1.14.6(Fuel Oil Handling system) | 206818867
FO system Execution Agency | PRC | 2023-08-23 08:00 | 2024-03-20 17:00 |  |  |  |  | 1.14.6(Fuel Oil Handling system) | 206818868
Enquiry | ENQ | 2023-08-23 08:00 | 2023-08-23 17:00 |  |  |  |  | 1.14.6.4( FO system Execution Agency) | 206818869
PO Placement | ORD | 2023-08-24 08:00 | 2024-03-20 17:00 |  |  |  |  | 1.14.6.4( FO system Execution Agency) | 206818870
Civil | CIV | 2024-06-24 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.14.6(Fuel Oil Handling system) | 206818871
LDO Day Tank Foundation | CIV | 2024-06-24 08:00 | 2024-10-27 17:00 |  |  |  |  | 1.14.6.5( Civil) | 206818872
LDO Day Tank Foundation: EXCAVATION | CIV | 2024-06-24 08:00 | 2024-07-13 17:00 |  |  |  |  | 1.14.6.5.1(LDO Day Tank Foundation) | 206818873
LDO Day Tank Foundation: RCC in substructure including PCC | CIV | 2024-07-14 08:00 | 2024-08-17 17:00 |  |  |  |  | 1.14.6.5.1(LDO Day Tank Foundation) | 206818874
LDO Day Tank Foundation: RCC in superstructure | CIV | 2024-08-18 08:00 | 2024-10-01 17:00 |  |  |  |  | 1.14.6.5.1(LDO Day Tank Foundation) | 206818875
LDO Day Tank Foundation: Backfilling | CIV | 2024-10-02 08:00 | 2024-10-11 17:00 |  |  |  |  | 1.14.6.5.1(LDO Day Tank Foundation) | 206818876
LDO Day Tank Foundation: Finishing works | CIV | 2024-10-12 08:00 | 2024-10-27 17:00 |  |  |  |  | 1.14.6.5.1(LDO Day Tank Foundation) | 206818877
FO Pressurizing pump house & Unloading pump house | CIV | 2024-06-25 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.14.6.5( Civil) | 206818878
FO Pressurizing pump house: Foundation | CIV | 2024-06-25 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818879
FO Pressurizing pump house: Mixer, Floculator, Alkali | CIV | 2024-12-22 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818880
FO Pressurizing pump house: Grade Slab | CIV | 2025-04-21 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818881
FO Pressurizing pump house: Cladding & Sheeting | CIV | 2025-04-21 08:00 | 2025-05-20 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818882
FO Pressurizing pump house: Mixer, Floculator, Alkali | CIV | 2025-05-21 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818883
FO Pressurizing pump house: Brick Work & Plastering | CIV | 2025-05-21 08:00 | 2025-08-18 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818884
FO Pressurizing pump house: Flooring | CIV | 2025-05-21 08:00 | 2025-06-14 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818885
FO Pressurizing pump house: Finishing works | CIV | 2025-08-19 08:00 | 2025-09-17 17:00 |  |  |  |  | 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | 206818886
Supply | SUP | 2024-07-19 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.6(Fuel Oil Handling system) | 206818887
FOPH Dispatch- Steel for Day Tanks | SUP | 2024-07-19 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.14.6.6(Supply) | 206818888
FOPH Dispatch-Transfer Pumps | SUP | 2024-10-17 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.14.6.6(Supply) | 206818889
FOPH Dispatch- Pipes & Fittings | SUP | 2024-11-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.6.6(Supply) | 206818890
FOPH Dispatch- Valves | SUP | 2024-11-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.6.6(Supply) | 206818891
FOPH Dispatch- Electrical and C&l items(Instruments, Cable & Cable Trays etc.) | SUP | 2024-11-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.6.6(Supply) | 206818892
FOPH Dispatch- Misc. items | SUP | 2024-11-16 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.6.6(Supply) | 206818893
Erection | ERC | 2024-11-07 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.6(Fuel Oil Handling system) | 206818894
E&C FO System: Fabrication of LDO Day Tank | ERC | 2024-11-07 08:00 | 2025-03-21 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818895
E&C FO System: Water fill Test of LDO Tank | ERC | 2025-03-22 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818896
E&C FO System: Erection of transfer Pumps | ERC | 2025-04-01 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818897
E&C FO Misc. of LDO Pump | ERC | 2025-05-21 08:00 | 2025-07-19 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818898
E&C FO Misc. of Piping from PUMP House to Boiler | ERC | 2025-07-20 08:00 | 2025-11-07 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818899
E&C FO Misc. of piping and valves | ERC | 2025-04-21 08:00 | 2025-05-30 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818900
E&C FO System: Electrical and C&I /misc. items | ERC | 2025-05-31 08:00 | 2025-06-19 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818901
E&C FO System: Painting of Tanks | ERC | 2025-06-20 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818902
E&C FO System: Testing & Commissioning | COM | 2025-11-08 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.6.7(Erection) | 206818903
Site fabricated tank | OTH | 2023-05-05 08:00 | 2025-12-24 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818904
Rel of dwg for Condensate storage tank | PE - RFC | 2024-03-10 08:00 | 2024-03-10 17:00 |  |  |  | PCE-06900 | 1.14.7(Site fabricated tank) | 206818905
Condensate Storage Tank | OTH | 2023-05-05 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.14.7(Site fabricated tank) | 206818906
Site fabricated tank execution agency | OTH | 2023-05-05 08:00 | 2024-04-02 17:00 |  |  |  |  | 1.14.7.2(Condensate Storage Tank) | 206818907
Enquiry | ENQ | 2023-05-05 08:00 | 2023-05-05 17:00 |  |  |  |  | 1.14.7.2.1(Site fabricated tank execution agency) | 206818908
PO placement | ORD | 2023-05-06 08:00 | 2023-10-02 17:00 |  |  |  |  | 1.14.7.2.1(Site fabricated tank execution agency) | 206818909
Supply | SUP | 2024-02-03 08:00 | 2024-04-02 17:00 |  |  |  |  | 1.14.7.2.1(Site fabricated tank execution agency) | 206818910
Civil Work | CIV | 2024-03-11 08:00 | 2024-07-23 17:00 |  |  |  |  | 1.14.7.2(Condensate Storage Tank) | 206818911
Condensate Storage Tank Foundation | CIV | 2024-03-11 08:00 | 2024-07-23 17:00 |  |  |  |  | 1.14.7.2.2(Civil Work) | 206818912
Condensate Storage Tank Foundation - EXCAVATION | CIV | 2024-03-11 08:00 | 2024-03-30 17:00 |  |  |  |  | 1.14.7.2.2.1(Condensate Storage Tank Foundation) | 206818913
Condensate Storage Tank Foundation- PCC including RCC substructure | CIV | 2024-03-31 08:00 | 2024-05-14 17:00 |  |  |  |  | 1.14.7.2.2.1(Condensate Storage Tank Foundation) | 206818914
Condensate Storage Tank Foundation - RCC in super structure | CIV | 2024-05-15 08:00 | 2024-06-28 17:00 |  |  |  |  | 1.14.7.2.2.1(Condensate Storage Tank Foundation) | 206818915
Condensate Storage Tank Foundation - Backfilling | CIV | 2024-06-29 08:00 | 2024-07-13 17:00 |  |  |  |  | 1.14.7.2.2.1(Condensate Storage Tank Foundation) | 206818916
Condensate Storage Tank Foundation - Finishing | CIV | 2024-07-14 08:00 | 2024-07-23 17:00 |  |  |  |  | 1.14.7.2.2.1(Condensate Storage Tank Foundation) | 206818917
Erection | ERC | 2024-07-24 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.14.7.2(Condensate Storage Tank) | 206818918
E&C of CST - Fabrication &Erection of Bottom Plate | ERC | 2024-07-24 08:00 | 2024-08-07 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818919
E&C of CST -Marking of edge preparation & Rolling of shell plates | ERC | 2024-08-03 08:00 | 2024-08-27 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818920
E&C of CST -Shifting, Erection & Alignment of Shell Plates | ERC | 2024-08-28 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818921
E&C of CST -Erection of Curb Angle | ERC | 2024-10-27 08:00 | 2024-11-07 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818922
E&C of CST -NDT of Tee & Horizontal Joint | ERC | 2024-11-10 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818923
E&C of CST -Erection of Roof Structure | ERC | 2024-11-17 08:00 | 2024-11-23 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818924
E&C of CST -Erection of Roof Plate | ERC | 2024-11-24 08:00 | 2024-11-30 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818925
E&C of CST -Erection of Nozzles | ERC | 2024-12-03 08:00 | 2024-12-05 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818926
E&C of CST -Vacuum Test of Bottom Plate | ERC | 2024-12-06 08:00 | 2024-12-07 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818927
E&C of CST -Vacuum Test of Roof Plate | ERC | 2024-12-08 08:00 | 2024-12-09 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818928
E&C of CST -Erection of Staircase & Railing | ERC | 2024-12-10 08:00 | 2024-12-21 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818929
E&C of CST -Water Filled Test | ERC | 2024-12-24 08:00 | 2024-12-28 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818930
E&C of CST -Cleaning , Sand Blasting & Painting of Tank (Internal) | ERC | 2024-12-31 08:00 | 2025-01-08 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818931
E&C of CST -Cleaning & Painting of Tank (External) | ERC | 2025-01-09 08:00 | 2025-01-17 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818932
E&C of CST -Erection of NaOH Breather & Seal Pot | ERC | 2025-01-28 08:00 | 2025-02-05 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818933
E&C of CST - Readiness of CST | ERC | 2025-02-06 08:00 | 2025-02-07 17:00 |  |  |  |  | 1.14.7.2.3(Erection) | 206818934
Readiness of other site fabricated tank | ERC | 2025-02-08 08:00 | 2025-12-24 17:00 |  |  |  |  | 1.14.7(Site fabricated tank) | 206818935
CW & ACW System | ERC | 2022-09-27 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14(BOP Systems) | 206818936
Civil Work | CIV | 2024-01-10 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.8(CW & ACW System) | 206818937
Rel of Drawing for CW Sump | PE - RFC | 2024-01-10 08:00 | 2024-01-10 17:00 |  |  |  | PCE-07000 | 1.14.8.1(Civil Work) | 206818938
Rel of Drawing for CW Pump House | PE - RFC | 2024-07-08 08:00 | 2024-07-08 17:00 |  |  |  | PCE-07100 | 1.14.8.1(Civil Work) | 206818939
Rel of Drawing for CW Channel | PE - RFC | 2024-12-05 08:00 | 2024-12-05 17:00 |  |  |  |  | 1.14.8.1(Civil Work) | 206818940
CW Pump House & ACW pump house | OTH | 2024-01-11 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.8.1(Civil Work) | 206818941
CW & ACW Sump & Forebay | CIV | 2024-01-11 08:00 | 2024-08-22 17:00 |  |  |  |  | 1.14.8.1.4( CW Pump House & ACW pump house) | 206818942
CW & ACW Sump & Forebay: Excavation & PCC | CIV | 2024-01-11 08:00 | 2024-02-09 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818943
CW & ACW Sump & Forebay: Sump Raft Casting | CIV | 2024-02-10 08:00 | 2024-03-25 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818944
CW & ACW Sump & Forebay: Fore Bay Raft Casting | CIV | 2024-03-26 08:00 | 2024-05-09 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818945
CW & ACW Sump & Forebay: Fore Bay Retaining walls Casting | CIV | 2024-05-10 08:00 | 2024-08-07 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818946
CW & ACW Sump & Forebay: Backfilling | CIV | 2024-08-08 08:00 | 2024-08-22 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818947
CW & ACW Sump & Forebay: Sump wall 1st Lift | CIV | 2024-03-26 08:00 | 2024-04-14 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818948
CW & ACW Sump & Forebay: Sump wall 2nd Lift | CIV | 2024-04-15 08:00 | 2024-05-04 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818949
CW & ACW Sump & Forebay: Sump wall final Lift | CIV | 2024-05-05 08:00 | 2024-05-24 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818950
CW & ACW Sump & Forebay: Pump slab casting | CIV | 2024-05-25 08:00 | 2024-06-23 17:00 |  |  |  |  | 1.14.8.1.4.1( CW & ACW Sump & Forebay) | 206818951
Concrete Volute Pump | CIV | 2024-05-05 08:00 | 2024-10-11 17:00 |  |  |  |  | 1.14.8.1.4( CW Pump House & ACW pump house) | 206818952
Concrete Volute Pump: First Stage Casting | CIV | 2024-05-05 08:00 | 2024-06-18 17:00 |  |  |  |  | 1.14.8.1.4.2( Concrete Volute Pump) | 206818953
Concrete Volute Pump: Second Stage casting | CIV | 2024-06-24 08:00 | 2024-08-07 17:00 |  |  |  |  | 1.14.8.1.4.2( Concrete Volute Pump) | 206818954
Concrete Volute Pump: Third Stage Casting | CIV | 2024-08-13 08:00 | 2024-09-11 17:00 |  |  |  |  | 1.14.8.1.4.2( Concrete Volute Pump) | 206818955
Concrete Volute Pump: Final Stage Casting & HT | CIV | 2024-09-17 08:00 | 2024-10-11 17:00 |  |  |  |  | 1.14.8.1.4.2( Concrete Volute Pump) | 206818956
CW Pump House Building | CIV | 2024-07-09 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.8.1.4( CW Pump House & ACW pump house) | 206818957
CW Pump House Building: Foundation | CIV | 2024-07-09 08:00 | 2025-01-04 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818958
CW Pump House Building: Forebay: Fore | CIV | 2025-01-05 08:00 | 2025-05-04 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818959
CW Pump House Building: Grade Slab | CIV | 2025-05-05 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818960
CW Pump House Building: Cladding & Sheeting | CIV | 2025-05-05 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818961
CW Pump House Building: EOT Erection | ERC | 2025-06-04 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818962
CW Pump House Building:: Brick Work & Plastering | CIV | 2025-07-04 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818963
CW Pump House Building: Flooring | CIV | 2025-10-02 08:00 | 2025-10-26 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818964
CW Pump House Building: Finishing works | CIV | 2025-10-27 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.8.1.4.3( CW Pump House Building) | 206818965
CW Channel | CIV | 2024-07-19 08:00 | 2025-08-02 17:00 |  |  |  |  | 1.14.8.1(Civil Work) | 206818966
Excavation | CIV | 2025-02-04 08:00 | 2025-08-02 17:00 |  |  |  |  | 1.14.8.1.5(CW Channel) | 206818967
PCC | CIV | 2024-11-06 08:00 | 2025-05-04 17:00 |  |  |  |  | 1.14.8.1.5(CW Channel) | 206818968
RCC | CIV | 2024-07-19 08:00 | 2025-02-03 17:00 |  |  |  |  | 1.14.8.1.5(CW Channel) | 206818969
Mechanical Erection (Valves/Gates etc) | ERC | 2025-02-04 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.14.8.1.5(CW Channel) | 206818970
Supply | SUP | 2022-09-27 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.14.8(CW & ACW System) | 206818971
BOI- PEM - MISC.PUMPS (VERTICAL) | SUP | 2023-07-14 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.8.2(Supply) | 206818972
Ordering | ORD | 2023-07-14 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.8.2.1(BOI- PEM - MISC.PUMPS (VERTICAL) ) | 206818973
Detailed Engineering | ENG | 2023-10-12 08:00 | 2024-03-09 17:00 |  |  |  |  | 1.14.8.2.1(BOI- PEM - MISC.PUMPS (VERTICAL) ) | 206818974
Manufacturing | MFG | 2024-03-10 08:00 | 2024-08-06 17:00 |  |  |  |  | 1.14.8.2.1(BOI- PEM - MISC.PUMPS (VERTICAL) ) | 206818975
Dispatch | DIS | 2024-08-07 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.8.2.1(BOI- PEM - MISC.PUMPS (VERTICAL) ) | 206818976
BOI-PEM - M.E. BELLOWS | SUP | 2023-08-23 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.8.2(Supply) | 206818977
Ordering | ORD | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.8.2.2(BOI-PEM - M.E. BELLOWS ) | 206818978
Detailed Engineering | ENG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.8.2.2(BOI-PEM - M.E. BELLOWS ) | 206818979
Manufacturing | MFG | 2024-04-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.8.2.2(BOI-PEM - M.E. BELLOWS ) | 206818980
Dispatch | DIS | 2024-09-16 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.8.2.2(BOI-PEM - M.E. BELLOWS ) | 206818981
BOI-PEM - SELF CLEANING STRAINERS | SUP | 2023-09-12 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.14.8.2(Supply) | 206818982
Ordering | ORD | 2023-09-12 08:00 | 2023-12-10 17:00 |  |  |  |  | 1.14.8.2.3(BOI-PEM - SELF CLEANING STRAINERS ) | 206818983
Detailed Engineering | ENG | 2023-12-11 08:00 | 2024-05-08 17:00 |  |  |  |  | 1.14.8.2.3(BOI-PEM - SELF CLEANING STRAINERS ) | 206818984
Manufacturing | MFG | 2024-05-09 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.14.8.2.3(BOI-PEM - SELF CLEANING STRAINERS ) | 206818985
Dispatch | DIS | 2024-10-06 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.14.8.2.3(BOI-PEM - SELF CLEANING STRAINERS ) | 206818986
BPL - CW Pump Motor | SUP | 2023-07-27 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.14.8.2(Supply) | 206818987
Engineering, INDENTING AND PROCUREMENT | ENG | 2023-07-27 08:00 | 2024-05-24 17:00 |  |  |  |  | 1.14.8.2.4(BPL - CW Pump Motor) | 206818988
Manufacturing & TESTING | MFG | 2024-05-25 08:00 | 2025-02-21 17:00 |  |  |  |  | 1.14.8.2.4(BPL - CW Pump Motor) | 206818989
Dispatch | DIS | 2025-02-22 08:00 | 2025-03-23 17:00 |  |  |  |  | 1.14.8.2.4(BPL - CW Pump Motor) | 206818990
RECEIPT AT SITE | REC | 2025-03-24 08:00 | 2025-04-22 17:00 |  |  |  |  | 1.14.8.2.4(BPL - CW Pump Motor) | 206818991
COOLING WATER PUMP (CV TYPE) -2 Nos (1 No Common for Both Units) | OTH | 2022-09-27 08:00 | 2025-01-17 17:00 |  |  |  |  | 1.14.8.2(Supply) | 206818992
ENGINEERING & PROCUREMENT | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.8.2.5(COOLING WATER PUMP (CV TYPE) -2 Nos (1 No Common for Both Units)) | 206818993
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.14.8.2.5(COOLING WATER PUMP (CV TYPE) -2 Nos (1 No Common for Both Units)) | 206818994
ASSEMBLY& TESTING | MFG | 2024-09-01 08:00 | 2024-12-18 17:00 |  |  |  |  | 1.14.8.2.5(COOLING WATER PUMP (CV TYPE) -2 Nos (1 No Common for Both Units)) | 206818995
Dispatch OF COOLING WATER PUMP AND ALL ASSOCIATED ITEMS | DIS | 2024-12-19 08:00 | 2025-01-17 17:00 |  |  |  |  | 1.14.8.2.5(COOLING WATER PUMP (CV TYPE) -2 Nos (1 No Common for Both Units)) | 206818996
Erection | ERC | 2024-11-06 08:00 | 2025-10-09 17:00 |  |  |  |  | 1.14.8(CW & ACW System) | 206818997
Placement and alignment of CW Pump | ERC | 2025-06-04 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206818998
Placement and alignment of CW Pump Motor | ERC | 2025-06-04 08:00 | 2025-06-18 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206818999
Placement and alignment of ACW Pump | ERC | 2025-06-04 08:00 | 2025-06-28 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819000
Erection of SCS | ERC | 2025-06-29 08:00 | 2025-07-13 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819001
Pipe, fittings & Valves for ACW system | ERC | 2025-07-14 08:00 | 2025-10-09 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819002
Erection of DISCHARGE PIPING FROM CWP TO CONDENSOR | ERC | 2024-11-06 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819003
Erection of CW PIPING-CW INLET HEADER OF CONDENSER | ERC | 2025-05-05 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819004
Erection of CW PIPING- CW OUTLET HEADER OF CONDENSER | ERC | 2025-05-05 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819005
Erection of CW PIPING-HOT WATER PIPING FROM CONDENSER TO CT | ERC | 2024-11-06 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819006
CW pump Electrical and C&I intersection | ERC | 2025-02-04 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819007
CW pump trial | COM | 2025-07-04 08:00 | 2025-07-13 17:00 |  |  |  |  | 1.14.8.3(Erection) | 206819008
EOT Cranes For PH | OTH | 2023-01-18 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819009
Supply | SUP | 2023-01-18 08:00 | 2024-03-12 17:00 |  |  |  |  | 1.14.9(EOT Cranes For PH) | 206819010
BOI-PEM - D/G EOT CRANE | SUP | 2023-01-18 08:00 | 2024-03-12 17:00 |  |  |  |  | 1.14.9.1(Supply) | 206819011
Ordering | ORD | 2023-01-18 08:00 | 2023-04-17 17:00 |  |  |  |  | 1.14.9.1.1(BOI-PEM - D/G EOT CRANE) | 206819012
Detailed Engineering | ENG | 2023-04-18 08:00 | 2023-09-14 17:00 |  |  |  |  | 1.14.9.1.1(BOI-PEM - D/G EOT CRANE) | 206819013
Manufacturing | MFG | 2023-09-15 08:00 | 2024-02-11 17:00 |  |  |  |  | 1.14.9.1.1(BOI-PEM - D/G EOT CRANE) | 206819014
Dispatch | DIS | 2024-02-12 08:00 | 2024-03-12 17:00 |  |  |  |  | 1.14.9.1.1(BOI-PEM - D/G EOT CRANE) | 206819015
Erection | ERC | 2024-03-28 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.14.9(EOT Cranes For PH) | 206819016
Inspection of power house AB Bay | ERC | 2024-03-28 08:00 | 2024-04-01 17:00 |  |  |  |  | 1.14.9.2(Erection) | 206819017
Erection of Crane girder in AB Bay | ERC | 2024-04-02 08:00 | 2024-04-29 17:00 |  |  |  |  | 1.14.9.2(Erection) | 206819018
Erection of Rails in AB Bay | ERC | 2024-04-30 08:00 | 2024-06-10 17:00 |  |  |  |  | 1.14.9.2(Erection) | 206819019
Assembly of Crane on girder in AB Bay | ERC | 2024-06-11 08:00 | 2024-07-08 17:00 |  |  |  |  | 1.14.9.2(Erection) | 206819020
Load testing of EOT crane in AB Bay | COM | 2024-07-09 08:00 | 2024-07-18 17:00 |  |  |  |  | 1.14.9.2(Erection) | 206819021
Commissioning of EOT crane in AB Bay | COM | 2024-07-19 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.14.9.2(Erection) | 206819022
Ventilation System | OTH | 2023-08-23 08:00 | 2026-03-26 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819023
RFC Air Washer Building drawings | PE - RFC | 2024-05-29 08:00 | 2024-05-29 17:00 |  |  |  | PCE-07500 | 1.14.10(Ventilation System) | 206819024
Ventilation system Execution Agency | PRC | 2023-08-23 08:00 | 2024-01-20 17:00 |  |  |  |  | 1.14.10(Ventilation System) | 206819025
Enquiry | ENQ | 2023-08-23 08:00 | 2023-08-23 17:00 |  |  |  |  | 1.14.10.2( Ventilation system Execution Agency) | 206819026
PO Placement | ORD | 2023-08-24 08:00 | 2024-01-20 17:00 |  |  |  |  | 1.14.10.2( Ventilation system Execution Agency) | 206819027
Ventilation System | PRC | 2024-05-30 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.14.10(Ventilation System) | 206819028
Air Washer Building: EXCAVATION | CIV | 2024-05-30 08:00 | 2024-06-18 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819029
Air Washer Building: RCC in substructure including PCC | CIV | 2024-06-19 08:00 | 2024-07-28 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819030
Air Washer Building: RCC in superstructure along with equipment foundation | CIV | 2024-07-29 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819031
Air Washer Building: Brick Work & Plastering | CIV | 2024-10-27 08:00 | 2025-01-24 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819032
Air Washer Building: Flooring | CIV | 2025-01-25 08:00 | 2025-02-18 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819033
Air Washer Building: Backfilling | CIV | 2025-02-19 08:00 | 2025-03-05 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819034
Air Washer Building: Finishing works | CIV | 2025-03-06 08:00 | 2025-06-03 17:00 |  |  |  |  | 1.14.10.3( Ventilation System) | 206819035
Supply | SUP | 2024-09-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.10(Ventilation System) | 206819036
Ventilation System | SUP | 2024-09-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.10.4(Supply) | 206819037
VENTILATION SYSTEM Dispatch-Centrifugal Fans | DIS | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.10.4.1(Ventilation System) | 206819038
VENTILATION SYSTEM Dispatch-Air washer units | DIS | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.10.4.1(Ventilation System) | 206819039
VENTILATION SYSTEM Dispatch-Air Filtration system | DIS | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.10.4.1(Ventilation System) | 206819040
VENTILATION SYSTEM Dispatch-Roof Exhausters | DIS | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.10.4.1(Ventilation System) | 206819041
VENTILATION SYSTEM Dispatch-Ducting / Dampers / Hangers / Supports / Fire dampers etc | DIS | 2024-09-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.10.4.1(Ventilation System) | 206819042
VENTILATION SYSTEM Dispatch-Misc. Items | DIS | 2024-10-17 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.10.4.1(Ventilation System) | 206819043
E&C for VENTILATION SYSTEM | ERC | 2024-11-16 08:00 | 2026-03-26 17:00 |  |  |  |  | 1.14.10(Ventilation System) | 206819044
E&C for VENTILATION Misc. of Centrifugal Fans complete | ERC | 2024-11-16 08:00 | 2025-01-04 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819045
E&C for VENTILATION Misc. of Air washer units complete | ERC | 2025-01-05 08:00 | 2025-03-05 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819046
E&C for VENTILATION Misc. of Air Filtration system complete | ERC | 2025-03-06 08:00 | 2025-04-20 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819047
E&C for VENTILATION Misc. of Roof Exhausters complete | ERC | 2025-04-21 08:00 | 2025-05-30 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819048
E&C for VENTILATION Misc. of Ducting / Dampers / Hangers / Supports / Fire dampers complete | ERC | 2025-05-31 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819049
E&C for VENTILATION SYSTEM: Electrical & C&I/Misc. items | ERC | 2025-05-31 08:00 | 2025-11-26 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819050
E&C for VENTILATION SYSTEM:VENTILATION SYSTEM COMPLETE | ERC | 2025-11-27 08:00 | 2026-03-26 17:00 |  |  |  |  | 1.14.10.5(E&C for VENTILATION SYSTEM) | 206819051
Condensate Polishing Unit | OTH | 2023-07-24 08:00 | 2026-02-24 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819052
Rel of Dwg for CPU foundation | PE - RFC | 2024-03-21 08:00 | 2024-03-21 17:00 |  |  |  | PCE-07600 | 1.14.11(Condensate Polishing Unit ) | 206819053
Condensate Polishing Unit | OTH | 2023-07-24 08:00 | 2023-12-21 17:00 |  |  |  |  | 1.14.11(Condensate Polishing Unit ) | 206819054
Enquiry | ENQ | 2023-07-24 08:00 | 2023-07-24 17:00 |  |  |  |  | 1.14.11.2(Condensate Polishing Unit) | 206819055
PO Placement | ORD | 2023-07-25 08:00 | 2023-12-21 17:00 |  |  |  |  | 1.14.11.2(Condensate Polishing Unit) | 206819056
Civil | CIV | 2024-04-21 08:00 | 2025-03-16 17:00 |  |  |  |  | 1.14.11(Condensate Polishing Unit ) | 206819057
Condensate Polishing Unit Regeneration Building: EXCAVATION | CIV | 2024-04-21 08:00 | 2024-05-20 17:00 |  |  |  |  | 1.14.11.3(Civil) | 206819058
Condensate Polishing Unit Regeneration Building: RCC in substructure including PCC | CIV | 2024-05-21 08:00 | 2024-08-08 17:00 |  |  |  |  | 1.14.11.3(Civil) | 206819059
Condensate Polishing Unit Regeneration Building: RCC in superstructure | CIV | 2024-08-09 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.11.3(Civil) | 206819060
Condensate Polishing Unit Regeneration Building: Backfilling | CIV | 2025-01-16 08:00 | 2025-02-14 17:00 |  |  |  |  | 1.14.11.3(Civil) | 206819061
Condensate Polishing Unit Regeneration Building: Finishing works | CIV | 2025-02-15 08:00 | 2025-03-16 17:00 |  |  |  |  | 1.14.11.3(Civil) | 206819062
Supply for Condensate POLISHING SYSTEM | SUP | 2024-08-08 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.14.11(Condensate Polishing Unit ) | 206819063
CONDENSATE POLISHING SYSTEM: Dispatch of CPU-Condensate Polisher Mixed Beds | DIS | 2024-08-08 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.14.11.4(Supply for Condensate POLISHING SYSTEM) | 206819064
CONDENSATE POLISHING SYSTEM: Dispatch of CPU-Interconnecting Pipe, Valves & Fittings | DIS | 2024-08-18 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.14.11.4(Supply for Condensate POLISHING SYSTEM) | 206819065
CONDENSATE POLISHING SYSTEM: Dispatch of CPU External Regeneration System | DIS | 2024-08-18 08:00 | 2024-11-15 17:00 |  |  |  |  | 1.14.11.4(Supply for Condensate POLISHING SYSTEM) | 206819066
CONDENSATE POLISHING SYSTEM: Dispatch of Misc. Items | DIS | 2024-08-18 08:00 | 2024-12-15 17:00 |  |  |  |  | 1.14.11.4(Supply for Condensate POLISHING SYSTEM) | 206819067
E&C for Condensate POLISHING SYSTEM | DIS | 2025-03-17 08:00 | 2026-02-24 17:00 |  |  |  |  | 1.14.11(Condensate Polishing Unit ) | 206819068
CONDENSATE POLISHING SYSTEM: Dispatch of CPU-Erection of Condensate Polisher Mixed Beds complete | ERC | 2025-03-17 08:00 | 2025-07-04 17:00 |  |  |  |  | 1.14.11.5(E&C for Condensate POLISHING SYSTEM) | 206819069
CONDENSATE POLISHING SYSTEM: Dispatch of CPU-Erection of Interconnecting Piping Valves, Fittings complete | ERC | 2025-07-05 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.11.5(E&C for Condensate POLISHING SYSTEM) | 206819070
CONDENSATE POLISHING SYSTEM: Dispatch of CPU-Erection of External Regeneration System complete | ERC | 2025-11-02 08:00 | 2026-01-15 17:00 |  |  |  |  | 1.14.11.5(E&C for Condensate POLISHING SYSTEM) | 206819071
CONDENSATE POLISHING SYSTEM: Dispatch of CPU ready for testing and commissioning | COM | 2026-01-16 08:00 | 2026-02-24 17:00 |  |  |  |  | 1.14.11.5(E&C for Condensate POLISHING SYSTEM) | 206819072
CW Treatment System | OTH | 2023-08-24 08:00 | 2025-12-15 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819073
Rel of Dwg for CW treatment building | PE - RFC | 2024-09-16 08:00 | 2024-09-16 17:00 |  |  |  |  | 1.14.12(CW Treatment System) | 206819074
Supply | SUP | 2023-08-24 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.12(CW Treatment System) | 206819075
Enquiry | ENQ | 2023-08-24 08:00 | 2023-08-24 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819076
PO placement | ORD | 2023-08-25 08:00 | 2024-01-21 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819077
Tanks - (Sulphuric acid storage tanks, Sulphuric acid day tanks, Corrosion inhibitor tank, Scale inhibitor /corrosion inhibitor tank, Biocide tank etc) | SUP | 2024-08-09 08:00 | 2024-11-06 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819078
Pumps - (Transfer & Dosing etc.) | SUP | 2024-08-29 08:00 | 2024-11-26 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819079
Skid/Ladder/Platform for Tanks | SUP | 2024-09-18 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819080
Strainer | SUP | 2024-09-18 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819081
Valves | SUP | 2024-09-18 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819082
C&I ITEMS | SUP | 2024-10-18 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819083
ELECTRICAL ITEMS | SUP | 2024-10-18 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819084
INTERCONNECTING PIPING & FITTINGS | SUP | 2024-10-18 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819085
MISCELLANEOUS ITEMS | SUP | 2024-10-18 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.12.2(Supply) | 206819086
Civil | CIV | 2024-10-07 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.12(CW Treatment System) | 206819087
CW treatment Building including Equipment Foundation | CIV | 2024-10-07 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.12.3(Civil) | 206819088
EXCAVATION | CIV | 2024-10-07 08:00 | 2024-11-05 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819089
RCC in substructure including PCC | CIV | 2024-11-06 08:00 | 2024-12-25 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819090
RCC in superstructure including equipment foundation | CIV | 2024-12-26 08:00 | 2025-03-25 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819091
Backfilling | CIV | 2025-03-26 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819092
Brick Work & Plastering | CIV | 2025-04-15 08:00 | 2025-06-13 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819093
Flooring | CIV | 2025-06-14 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819094
Finishing works | CIV | 2025-07-04 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.12.3.1(CW treatment Building including Equipment Foundation) | 206819095
Erection | ERC | 2025-04-15 08:00 | 2025-12-15 17:00 |  |  |  |  | 1.14.12(CW Treatment System) | 206819096
Tanks - (Sulphuric acid storage tanks, Sulphuric acid day tanks, Corrosion inhibitor tank, Scale inhibitor /corrosion inhibitor tank, Biocide tank etc) | ERC | 2025-04-15 08:00 | 2025-06-13 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819097
Pumps - (Transfer & Dosing etc.) | ERC | 2025-04-30 08:00 | 2025-06-28 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819098
Skid/Ladder/Platform for Tanks | ERC | 2025-06-29 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819099
Strainer | ERC | 2025-06-29 08:00 | 2025-10-26 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819100
Valves | ERC | 2025-06-29 08:00 | 2025-10-26 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819101
C&I ITEMS | ERC | 2025-07-29 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819102
ELECTRICAL ITEMS | ERC | 2025-07-29 08:00 | 2025-11-25 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819103
INTERCONNECTING PIPING & FITTINGS | ERC | 2025-06-29 08:00 | 2025-10-26 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819104
MISCELLANEOUS ITEMS | ERC | 2025-09-12 08:00 | 2025-12-05 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819105
Commissioning | COM | 2025-12-06 08:00 | 2025-12-15 17:00 |  |  |  |  | 1.14.12.4(Erection) | 206819106
Fire Detection & Protection Sys | OTH | 2023-02-24 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819107
Supply (BHEL- PESD) | SUP | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13(Fire Detection & Protection Sys) | 206819108
Hydrant Valve | SUP | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819109
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.1(Hydrant Valve) | 206819110
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.1(Hydrant Valve) | 206819111
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.1(Hydrant Valve) | 206819112
Water Monitor & Water cum Foam monitor | SUP | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819113
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.2(Water Monitor & Water cum Foam monitor) | 206819114
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.2(Water Monitor & Water cum Foam monitor) | 206819115
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.2(Water Monitor & Water cum Foam monitor) | 206819116
Deluge Valve | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819117
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.3(Deluge Valve) | 206819118
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.3(Deluge Valve) | 206819119
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.3(Deluge Valve) | 206819120
Spray Nozzles | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819121
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.4(Spray Nozzles) | 206819122
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.4(Spray Nozzles) | 206819123
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.4(Spray Nozzles) | 206819124
QBD | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819125
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.5(QBD) | 206819126
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.5(QBD) | 206819127
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.5(QBD) | 206819128
Hose Box | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819129
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.6(Hose Box) | 206819130
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.6(Hose Box) | 206819131
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.6(Hose Box) | 206819132
Foam Branch Pipe | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819133
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.7(Foam Branch Pipe) | 206819134
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.7(Foam Branch Pipe) | 206819135
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.7(Foam Branch Pipe) | 206819136
Inline Balance Proportioner | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819137
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.8(Inline Balance Proportioner) | 206819138
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.8(Inline Balance Proportioner) | 206819139
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.8(Inline Balance Proportioner) | 206819140
Foam Chamber with Deflector | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819141
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.9(Foam Chamber with Deflector) | 206819142
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.9(Foam Chamber with Deflector) | 206819143
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.9(Foam Chamber with Deflector) | 206819144
Fire Hose with Coupling | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819145
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.10(Fire Hose with Coupling) | 206819146
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.10(Fire Hose with Coupling) | 206819147
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.10(Fire Hose with Coupling) | 206819148
Hose Reel | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819149
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.11(Hose Reel) | 206819150
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.11(Hose Reel) | 206819151
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.11(Hose Reel) | 206819152
Branch Pipe with Nozzle | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819153
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.12(Branch Pipe with Nozzle) | 206819154
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.12(Branch Pipe with Nozzle) | 206819155
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.12(Branch Pipe with Nozzle) | 206819156
Foam Concentrated Control Valve | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819157
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.13(Foam Concentrated Control Valve) | 206819158
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.13(Foam Concentrated Control Valve) | 206819159
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.13(Foam Concentrated Control Valve) | 206819160
Solenoid Valve | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819161
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.14(Solenoid Valve) | 206819162
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.14(Solenoid Valve) | 206819163
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.14(Solenoid Valve) | 206819164
Foam Concentrate | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819165
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.15(Foam Concentrate) | 206819166
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.15(Foam Concentrate) | 206819167
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.15(Foam Concentrate) | 206819168
Gun Metal Valve for ARV | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819169
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.16(Gun Metal Valve for ARV) | 206819170
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.16(Gun Metal Valve for ARV) | 206819171
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.16(Gun Metal Valve for ARV) | 206819172
Air Release Valve | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819173
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.17(Air Release Valve) | 206819174
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.17(Air Release Valve) | 206819175
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.17(Air Release Valve) | 206819176
DV LCP | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819177
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.18(DV LCP) | 206819178
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.18(DV LCP) | 206819179
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.18(DV LCP) | 206819180
Sprinkler system | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819181
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.19(Sprinkler system) | 206819182
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.19(Sprinkler system) | 206819183
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.19(Sprinkler system) | 206819184
Pressure Regulating Valve (Foam System) | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819185
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.20(Pressure Regulating Valve (Foam System)) | 206819186
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.20(Pressure Regulating Valve (Foam System)) | 206819187
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.20(Pressure Regulating Valve (Foam System)) | 206819188
Pressure Relief Valve | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819189
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.21(Pressure Relief Valve) | 206819190
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.21(Pressure Relief Valve) | 206819191
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.21(Pressure Relief Valve) | 206819192
Foam Tank | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819193
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.22(Foam Tank) | 206819194
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.22(Foam Tank) | 206819195
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.22(Foam Tank) | 206819196
Air Compressor | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819197
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.23(Air Compressor) | 206819198
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.23(Air Compressor) | 206819199
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.23(Air Compressor) | 206819200
Hydro Pneumatic Tank | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819201
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.24(Hydro Pneumatic Tank) | 206819202
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.24(Hydro Pneumatic Tank) | 206819203
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.24(Hydro Pneumatic Tank) | 206819204
Foam Pump | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819205
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.25(Foam Pump) | 206819206
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.25(Foam Pump) | 206819207
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.25(Foam Pump) | 206819208
Pressure Transmitters | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819209
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.26(Pressure Transmitters) | 206819210
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.26(Pressure Transmitters) | 206819211
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.26(Pressure Transmitters) | 206819212
Pressure Switches | OTH | 2023-04-15 08:00 | 2024-04-19 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819213
Engineering | ENG | 2023-04-15 08:00 | 2023-12-13 17:00 |  |  |  |  | 1.14.13.1.27(Pressure Switches) | 206819214
Ordering & Manufacturing | ORD | 2023-12-14 08:00 | 2024-03-20 17:00 |  |  |  |  | 1.14.13.1.27(Pressure Switches) | 206819215
Dispatch | DIS | 2024-03-21 08:00 | 2024-04-19 17:00 |  |  |  |  | 1.14.13.1.27(Pressure Switches) | 206819216
Level Switches | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819217
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.28(Level Switches) | 206819218
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.28(Level Switches) | 206819219
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.28(Level Switches) | 206819220
Flow Switches | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819221
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.29(Flow Switches) | 206819222
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.29(Flow Switches) | 206819223
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.29(Flow Switches) | 206819224
Pressure Gauges | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819225
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.30(Pressure Gauges) | 206819226
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.30(Pressure Gauges) | 206819227
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.30(Pressure Gauges) | 206819228
Differential pressure Gauges | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819229
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.31(Differential pressure Gauges) | 206819230
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.31(Differential pressure Gauges) | 206819231
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.31(Differential pressure Gauges) | 206819232
Radar Level Transmitters | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819233
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.32(Radar Level Transmitters) | 206819234
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.32(Radar Level Transmitters) | 206819235
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.32(Radar Level Transmitters) | 206819236
IGES Package | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819237
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.33(IGES Package) | 206819238
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.33(IGES Package) | 206819239
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.33(IGES Package) | 206819240
Portable Fire Extinguishers | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819241
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.34(Portable Fire Extinguishers) | 206819242
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.34(Portable Fire Extinguishers) | 206819243
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.34(Portable Fire Extinguishers) | 206819244
Fire Water Pipes | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819245
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.35(Fire Water Pipes) | 206819246
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.35(Fire Water Pipes) | 206819247
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.35(Fire Water Pipes) | 206819248
Fire Fighting System Conventional Valves | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819249
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.36(Fire Fighting System Conventional Valves) | 206819250
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.36(Fire Fighting System Conventional Valves) | 206819251
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.36(Fire Fighting System Conventional Valves) | 206819252
Fire Water Flanges | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819253
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.37(Fire Water Flanges) | 206819254
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.37(Fire Water Flanges) | 206819255
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.37(Fire Water Flanges) | 206819256
Fire Water Butt welded Fittings | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819257
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.38(Fire Water Butt welded Fittings) | 206819258
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.38(Fire Water Butt welded Fittings) | 206819259
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.38(Fire Water Butt welded Fittings) | 206819260
Fire Water Flanged Fittings | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819261
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.39(Fire Water Flanged Fittings) | 206819262
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.39(Fire Water Flanged Fittings) | 206819263
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.39(Fire Water Flanged Fittings) | 206819264
Gaskets | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819265
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.40(Gaskets) | 206819266
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.40(Gaskets) | 206819267
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.40(Gaskets) | 206819268
Bolts, U Bolts, Nuts & Clamps | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819269
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.41(Bolts, U Bolts, Nuts & Clamps) | 206819270
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.41(Bolts, U Bolts, Nuts & Clamps) | 206819271
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.41(Bolts, U Bolts, Nuts & Clamps) | 206819272
Structural Material | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819273
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.42(Structural Material) | 206819274
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.42(Structural Material) | 206819275
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.42(Structural Material) | 206819276
Fire Detection & Alarm System | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819277
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.43(Fire Detection & Alarm System) | 206819278
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.43(Fire Detection & Alarm System) | 206819279
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.43(Fire Detection & Alarm System) | 206819280
Fire Alarm Cables | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819281
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.44(Fire Alarm Cables) | 206819282
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.44(Fire Alarm Cables) | 206819283
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.44(Fire Alarm Cables) | 206819284
Fire Protection System PLC | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819285
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.45(Fire Protection System PLC) | 206819286
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.45(Fire Protection System PLC) | 206819287
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.45(Fire Protection System PLC) | 206819288
E&C for PLC system | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819289
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.46(E&C for PLC system) | 206819290
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.46(E&C for PLC system) | 206819291
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.46(E&C for PLC system) | 206819292
Spares for PLC system | OTH | 2023-04-15 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819293
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.47(Spares for PLC system) | 206819294
Ordering & Manufacturing | ORD | 2023-11-15 08:00 | 2024-04-15 17:00 |  |  |  |  | 1.14.13.1.47(Spares for PLC system) | 206819295
Dispatch | DIS | 2024-04-16 08:00 | 2024-08-13 17:00 |  |  |  |  | 1.14.13.1.47(Spares for PLC system) | 206819296
Cable Trays & Accessories | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819297
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.48(Cable Trays & Accessories) | 206819298
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.48(Cable Trays & Accessories) | 206819299
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.48(Cable Trays & Accessories) | 206819300
Fire Water Pumps & Auxiliaries | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819301
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.49(Fire Water Pumps & Auxiliaries) | 206819302
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.49(Fire Water Pumps & Auxiliaries) | 206819303
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.49(Fire Water Pumps & Auxiliaries) | 206819304
Fire Water Storage Tank | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819305
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.50(Fire Water Storage Tank) | 206819306
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.50(Fire Water Storage Tank) | 206819307
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.50(Fire Water Storage Tank) | 206819308
Paint & Primer | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819309
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.51(Paint & Primer) | 206819310
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.51(Paint & Primer) | 206819311
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.51(Paint & Primer) | 206819312
Wrapping & Coating for Underground Piping | OTH | 2023-04-15 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1(Supply (BHEL- PESD)) | 206819313
Engineering | ENG | 2023-04-15 08:00 | 2024-01-13 17:00 |  |  |  |  | 1.14.13.1.52(Wrapping & Coating for Underground Piping) | 206819314
Ordering & Manufacturing | ORD | 2024-01-14 08:00 | 2024-12-13 17:00 |  |  |  |  | 1.14.13.1.52(Wrapping & Coating for Underground Piping) | 206819315
Dispatch | DIS | 2024-12-14 08:00 | 2025-04-15 17:00 |  |  |  |  | 1.14.13.1.52(Wrapping & Coating for Underground Piping) | 206819316
Civil | CIV | 2023-02-24 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.13(Fire Detection & Protection Sys) | 206819317
Civil Readiness of Fire water pump house including pipe pedestal & tank foundation and Booster pump house | CIV | 2023-02-24 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.13.2(Civil ) | 206819318
Erection | ERC | 2025-03-31 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13(Fire Detection & Protection Sys) | 206819319
Erection: PUMPs with motor | ERC | 2025-04-16 08:00 | 2025-07-24 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819320
Erection: TANK | ERC | 2025-04-26 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819321
Erection: AIR COMPRESSOR | ERC | 2025-06-05 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819322
Erection: Pipe, Fittings & Valves | ERC | 2025-07-25 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819323
Erection: Electrical & C&I work | ERC | 2025-08-19 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819324
Erection: Commissioning of pump | COM | 2025-11-02 08:00 | 2025-11-06 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819325
Erection: Commissioning of FPS for BLU including foam system | COM | 2025-11-07 08:00 | 2026-01-05 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819326
Erection: Commissioning of Balance FPS | COM | 2026-01-06 08:00 | 2026-04-15 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819327
HYDRANT SYSTEM | ERC | 2025-07-25 08:00 | 2026-05-20 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819328
HYDRANT SYSTEM: PIPING | ERC | 2025-07-25 08:00 | 2026-03-21 17:00 |  |  |  |  | 1.14.13.3.9(HYDRANT SYSTEM) | 206819329
HYDRANT SYSTEM: VALVE | ERC | 2026-01-21 08:00 | 2026-04-20 17:00 |  |  |  |  | 1.14.13.3.9(HYDRANT SYSTEM) | 206819330
HYDRANT SYSTEM: FIRE HOSE | ERC | 2026-02-20 08:00 | 2026-05-20 17:00 |  |  |  |  | 1.14.13.3.9(HYDRANT SYSTEM) | 206819331
SPRAY SYSTEM | ERC | 2025-08-24 08:00 | 2026-06-29 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819332
SPRAY SYSTEM: PIPING | ERC | 2025-08-24 08:00 | 2026-06-19 17:00 |  |  |  |  | 1.14.13.3.10(SPRAY SYSTEM) | 206819333
SPRAY SYSTEM: VALVE | ERC | 2026-02-20 08:00 | 2026-06-09 17:00 |  |  |  |  | 1.14.13.3.10(SPRAY SYSTEM) | 206819334
SPRAY SYSTEM: FITTINGS | ERC | 2026-03-12 08:00 | 2026-06-29 17:00 |  |  |  |  | 1.14.13.3.10(SPRAY SYSTEM) | 206819335
HVWS SYSTEM FOR TRANSFORMERS | ERC | 2025-09-03 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819336
HVWS SYSTEM FOR TRANSFORMERS: DELUGE VALVES | ERC | 2025-09-03 08:00 | 2026-05-10 17:00 |  |  |  |  | 1.14.13.3.11(HVWS SYSTEM FOR TRANSFORMERS) | 206819337
HVWS SYSTEM FOR TRANSFORMERS: Pipe, valves and fittings | ERC | 2025-10-23 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3.11(HVWS SYSTEM FOR TRANSFORMERS) | 206819338
N2 injection system for GT & ST (if applicable) | ERC | 2026-03-09 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819339
HVWS SYSTEM FOR OIL EQUIPMENTS | ERC | 2025-04-30 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819340
HVWS SYSTEM FOR OIL EQUIPMENTS: DELUGE VALVES | ERC | 2025-04-30 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.14.13.3.13(HVWS SYSTEM FOR OIL EQUIPMENTS) | 206819341
HVWS SYSTEM FOR OIL EQUIPMENTS: Pipe, valves and fittings | ERC | 2025-04-30 08:00 | 2025-09-16 17:00 |  |  |  |  | 1.14.13.3.13(HVWS SYSTEM FOR OIL EQUIPMENTS) | 206819342
HVWS SYSTEM FOR OIL EQUIPMENTS: INSTRUMENT & GAUGES | ERC | 2025-09-17 08:00 | 2025-10-01 17:00 |  |  |  |  | 1.14.13.3.13(HVWS SYSTEM FOR OIL EQUIPMENTS) | 206819343
HVWS SYSTEM FOR BOILER BURNER FRONT | ERC | 2025-11-07 08:00 | 2026-01-17 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819344
HVWS SYSTEM FOR BOILER BURNER FRONT: DELUGE VALVES | ERC | 2025-11-07 08:00 | 2026-01-17 17:00 |  |  |  |  | 1.14.13.3.14(HVWS SYSTEM FOR BOILER BURNER FRONT) | 206819345
HVWS SYSTEM FOR BOILER BURNER FRONT: Pipe, valves and fittings | ERC | 2025-11-07 08:00 | 2026-01-17 17:00 |  |  |  |  | 1.14.13.3.14(HVWS SYSTEM FOR BOILER BURNER FRONT) | 206819346
HVWS SYSTEM FOR BOILER BURNER FRONT: INSTRUMENT & GAUGES | ERC | 2025-11-07 08:00 | 2026-01-17 17:00 |  |  |  |  | 1.14.13.3.14(HVWS SYSTEM FOR BOILER BURNER FRONT) | 206819347
MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION | ERC | 2025-07-06 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819348
MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION: DELUGE VALVES | ERC | 2025-07-06 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.14.13.3.15(MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION) | 206819349
MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION: Pipe, valves and fittings | ERC | 2025-07-06 08:00 | 2025-11-02 17:00 |  |  |  |  | 1.14.13.3.15(MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION) | 206819350
MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION: INSTRUMENT & GAUGES | ERC | 2025-11-03 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.13.3.15(MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION) | 206819351
MVWS SYSTEM - TG BUILDING CABLE GALLERIES | ERC | 2025-09-02 08:00 | 2026-02-18 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819352
MVWS SYSTEM - TG BUILDING CABLE GALLERIES: DELUGE VALVES | ERC | 2025-09-02 08:00 | 2025-12-30 17:00 |  |  |  |  | 1.14.13.3.16(MVWS SYSTEM - TG BUILDING CABLE GALLERIES) | 206819353
MVWS SYSTEM - TG BUILDING CABLE GALLERIES: Pipe, valves and fittings | ERC | 2025-09-02 08:00 | 2026-01-29 17:00 |  |  |  |  | 1.14.13.3.16(MVWS SYSTEM - TG BUILDING CABLE GALLERIES) | 206819354
MVWS SYSTEM - TG BUILDING CABLE GALLERIES: INSTRUMENT & GAUGES | ERC | 2026-01-30 08:00 | 2026-02-18 17:00 |  |  |  |  | 1.14.13.3.16(MVWS SYSTEM - TG BUILDING CABLE GALLERIES) | 206819355
MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE | ERC | 2025-05-23 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819356
MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE: DELUGE VALVES | ERC | 2025-06-07 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.14.13.3.17(MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE) | 206819357
MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE: Pipe, valves and fittings | ERC | 2025-05-23 08:00 | 2025-07-21 17:00 |  |  |  |  | 1.14.13.3.17(MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE) | 206819358
MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE: INSTRUMENT & GAUGES | ERC | 2025-07-22 08:00 | 2025-08-05 17:00 |  |  |  |  | 1.14.13.3.17(MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE) | 206819359
FIRE DETECTION SYSTEM | ERC | 2026-01-06 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819360
FIRE DETECTION SYSTEM: FIRE ALARM PANELS | ERC | 2026-01-06 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3.18(FIRE DETECTION SYSTEM) | 206819361
FIRE DETECTION SYSTEM: DETECTORS | ERC | 2026-01-06 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3.18(FIRE DETECTION SYSTEM) | 206819362
FIRE DETECTION SYSTEM: CABLES | ERC | 2026-01-06 08:00 | 2026-08-05 17:00 |  |  |  |  | 1.14.13.3.18(FIRE DETECTION SYSTEM) | 206819363
Inert Gas System | ERC | 2025-03-31 08:00 | 2025-11-15 17:00 |  |  |  |  | 1.14.13.3(Erection) | 206819364
Coal Handling Plant | OTH | 2022-09-27 08:00 | 2026-01-26 17:00 | 2022-09-27 |  |  |  | 1.14(BOP Systems) | 206819365
Civil Works | CIV | 2022-09-27 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.14.14(Coal Handling Plant) | 206819366
Rel of Dwg for Track Hopper | PE - RFC | 2023-10-01 17:00 | 2023-10-01 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819367
Rel of Dwg for MCCs | PE - RFC | 2023-07-23 17:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819368
Rel of Dwg for penthouse | PE - RFC | 2023-08-12 17:00 | 2023-08-12 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819369
Rel of Dwg for Stacker Reclaimer | PE - RFC | 2023-09-26 17:00 | 2023-09-26 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819370
Rel of Dwg for Stock yard | PE - RFC | 2023-07-23 17:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819371
Rel of Dwg for Coal Shed | PE - RFC | 2022-09-27 08:00 | 2022-09-27 08:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819372
Rel of Dwg for Crusher House | PE - RFC | 2023-11-20 17:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819373
Rel of Dwg for Conveyor Gallery & Trestles | PE - RFC | 2023-07-23 17:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819374
Rel of Dwg for TPs | PE - RFC | 2023-10-01 17:00 | 2023-10-01 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819375
Track Hopper | OTH | 2023-10-02 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819376
Track Hopper: EXCAVATION | CIV | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.14.14.1.10( Track Hopper) | 206819377
Track Hopper: RCC in substructure including PCC | CIV | 2023-11-01 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.14.1.10( Track Hopper) | 206819378
Track Hopper: Grade Slab | CIV | 2024-03-30 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.14.1.10( Track Hopper) | 206819379
Track Hopper: RCC in superstructure | CIV | 2024-04-14 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.14.14.1.10( Track Hopper) | 206819380
Track Hopper: Backfilling | CIV | 2024-05-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.14.1.10( Track Hopper) | 206819381
Track Hopper: Finishing works | CIV | 2024-06-13 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.14.1.10( Track Hopper) | 206819382
CHP Main Control cum MCC Room | CIV | 2023-07-24 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819383
Main Control Room: EXCAVATION | CIV | 2023-07-24 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819384
Main Control Room: RCC in substructure including PCC | CIV | 2023-08-23 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819385
Main Control Room: RCC/Structure work in superstructure | CIV | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819386
Main Control Room: backfilling | CIV | 2024-08-02 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819387
Main Control Room: Brick Work & Plastering | CIV | 2024-08-17 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819388
Main Control Room: Flooring | CIV | 2024-10-16 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819389
Main Control Room: Finishing work | CIV | 2024-12-15 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.14.14.1.11( CHP Main Control cum MCC Room) | 206819390
CHP MCC Room | CIV | 2023-07-24 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819391
MCC Room: EXCAVATION | CIV | 2023-07-24 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819392
MCC Room: RCC in substructure including PCC | CIV | 2023-08-08 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819393
MCC Room: RCC/Structure work in superstructure | CIV | 2023-09-07 08:00 | 2024-03-07 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819394
MCC Room: Brick Work & Plastering | CIV | 2024-03-08 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819395
MCC Room: Flooring | CIV | 2024-05-07 08:00 | 2024-05-21 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819396
MCC Room: Backfilling | CIV | 2024-05-22 08:00 | 2024-06-05 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819397
MCC Room: Finishing works | CIV | 2024-06-06 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1.12( CHP MCC Room) | 206819398
Common CHP, LHP & GHP Pump House | COM | 2023-07-24 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819399
Pump House: EXCAVATION | CIV | 2023-07-24 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819400
Pump House: RCC in substructure including PCC | CIV | 2023-08-08 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819401
Pump House: RCC/Structure work in superstructure | CIV | 2023-09-07 08:00 | 2024-03-07 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819402
Pump House: Brick Work & Plastering | CIV | 2024-03-08 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819403
Pump House: Flooring | CIV | 2024-05-07 08:00 | 2024-05-21 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819404
Pump House: Backfilling | CIV | 2024-05-22 08:00 | 2024-06-05 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819405
Pump House: Finishing works | CIV | 2024-06-06 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | 206819406
CHP Workshop cum office Building | CIV | 2023-07-24 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819407
CHP Workshop: EXCAVATION | CIV | 2023-07-24 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819408
CHP Workshop: RCC in substructure including PCC | CIV | 2023-08-08 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819409
CHP Workshop: RCC/Structure work in superstructure | CIV | 2023-09-07 08:00 | 2024-03-07 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819410
CHP Workshop: Brick Work & Plastering | CIV | 2024-03-08 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819411
CHP Workshop: Flooring | CIV | 2024-05-07 08:00 | 2024-05-21 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819412
CHP Workshop: Backfilling | CIV | 2024-05-22 08:00 | 2024-06-05 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819413
CHP Workshop: Finishing works | CIV | 2024-06-06 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1.14(CHP Workshop cum office Building ) | 206819414
CHP Dozer Shed | CIV | 2023-07-24 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819415
Dozer Shed: EXCAVATION | CIV | 2023-07-24 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819416
Dozer Shed: RCC in substructure including PCC | CIV | 2023-08-08 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819417
Dozer Shed: RCC/Structure work in superstructure | CIV | 2023-09-07 08:00 | 2024-03-07 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819418
Dozer Shed: Brick Work & Plastering | CIV | 2024-03-08 08:00 | 2024-05-06 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819419
Dozer Shed: Flooring | CIV | 2024-05-07 08:00 | 2024-05-21 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819420
Dozer Shed: Backfilling | CIV | 2024-05-22 08:00 | 2024-06-05 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819421
Dozer Shed: Finishing works | CIV | 2024-06-06 08:00 | 2024-08-04 17:00 |  |  |  |  | 1.14.14.1.15(CHP Dozer Shed) | 206819422
CHP Coal Settling Pond ( CSSP) | CIV | 2023-10-02 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819423
CSSP: EXCAVATION | CIV | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | 206819424
CSSP: RCC in substructure including PCC | CIV | 2023-11-01 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | 206819425
CSSP: Grade Slab | CIV | 2024-03-30 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | 206819426
CSSP: RCC in superstructure | CIV | 2024-04-14 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | 206819427
CSSP: Backfilling | CIV | 2024-05-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | 206819428
CSSP: Finishing works | CIV | 2024-06-13 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | 206819429
Stacker Reclaimer | CIV | 2023-09-27 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819430
Stacker Reclaimer: EXCAVATION | CIV | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.14.1.17( Stacker Reclaimer ) | 206819431
Stacker Reclaimer: RCC in substructure including PCC | CIV | 2023-11-26 08:00 | 2024-03-24 17:00 |  |  |  |  | 1.14.14.1.17( Stacker Reclaimer ) | 206819432
Stacker Reclaimer: RCC in superstructure (Drive house) | CIV | 2024-03-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.14.1.17( Stacker Reclaimer ) | 206819433
Stacker Reclaimer: Backfilling | CIV | 2024-04-24 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.14.1.17( Stacker Reclaimer ) | 206819434
Stacker Reclaimer: Finishing works | CIV | 2024-05-24 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.14.1.17( Stacker Reclaimer ) | 206819435
Stock Yard | CIV | 2023-07-24 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819436
Stock Yard: EXCAVATION | CIV | 2023-07-24 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.14.1.18( Stock Yard) | 206819437
Stock Yard: RCC with PCC | CIV | 2023-09-07 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.14.1.18( Stock Yard) | 206819438
Crusher House | CIV | 2023-11-01 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.14.14.1( Civil Works) | 206819439
Crusher House: EXCAVATION | CIV | 2023-11-21 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819440
Crusher House: RCC in substructure including PCC | CIV | 2023-12-06 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819441
Crusher House: RCC/Steel Structure in superstructure | CIV | 2024-01-20 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819442
Crusher House: Backfilling | CIV | 2025-01-04 08:00 | 2025-01-18 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819443
Crusher House: Finishing works | CIV | 2025-01-19 08:00 | 2025-02-02 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819444
Transfer Points | CIV | 2023-11-21 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819445
CHP Transfer Point-1 | CIV | 2023-11-21 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6( Transfer Points) | 206819446
Transfer Point-2: EXCAVATION | CIV | 2023-11-21 08:00 | 2023-11-27 17:00 |  |  |  |  | 1.14.14.1.19.6.1(CHP Transfer Point-1) | 206819447
Transfer Point-2: RCC in substructure including PCC | CIV | 2023-11-28 08:00 | 2024-01-11 17:00 |  |  |  |  | 1.14.14.1.19.6.1(CHP Transfer Point-1) | 206819448
Transfer Point-2: RCC in superstructure | CIV | 2024-01-12 08:00 | 2024-01-31 17:00 |  |  |  |  | 1.14.14.1.19.6.1(CHP Transfer Point-1) | 206819449
Transfer Point-2: Backfilling | CIV | 2024-02-01 08:00 | 2024-02-15 17:00 |  |  |  |  | 1.14.14.1.19.6.1(CHP Transfer Point-1) | 206819450
Transfer Point-2: Finishing works | CIV | 2024-02-16 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.6.1(CHP Transfer Point-1) | 206819451
Transfer Point-2: Structural works | CIV | 2024-03-02 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6.1(CHP Transfer Point-1) | 206819452
CHP Transfer Point-2 | CIV | 2023-11-21 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6( Transfer Points) | 206819453
Transfer Point-2: EXCAVATION | CIV | 2023-11-21 08:00 | 2023-11-27 17:00 |  |  |  |  | 1.14.14.1.19.6.2(CHP Transfer Point-2) | 206819454
Transfer Point-2: RCC in substructure including PCC | CIV | 2023-11-28 08:00 | 2024-01-11 17:00 |  |  |  |  | 1.14.14.1.19.6.2(CHP Transfer Point-2) | 206819455
Transfer Point-2: RCC in superstructure | CIV | 2024-01-12 08:00 | 2024-01-31 17:00 |  |  |  |  | 1.14.14.1.19.6.2(CHP Transfer Point-2) | 206819456
Transfer Point-2: Backfilling | CIV | 2024-02-01 08:00 | 2024-02-15 17:00 |  |  |  |  | 1.14.14.1.19.6.2(CHP Transfer Point-2) | 206819457
Transfer Point-2: Finishing works | CIV | 2024-02-16 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.6.2(CHP Transfer Point-2) | 206819458
Transfer Point-2: Structural works | CIV | 2024-03-02 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6.2(CHP Transfer Point-2) | 206819459
CHP Transfer Point-3 & any additional TPs | CIV | 2023-11-21 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6( Transfer Points) | 206819460
Transfer Point-3: EXCAVATION | CIV | 2023-11-21 08:00 | 2023-11-27 17:00 |  |  |  |  | 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | 206819461
Transfer Point-3: RCC in substructure including PCC | CIV | 2023-11-28 08:00 | 2024-01-11 17:00 |  |  |  |  | 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | 206819462
Transfer Point-3: RCC in superstructure | CIV | 2024-01-12 08:00 | 2024-01-31 17:00 |  |  |  |  | 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | 206819463
Transfer Point-3: Backfilling | CIV | 2024-02-01 08:00 | 2024-02-15 17:00 |  |  |  |  | 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | 206819464
Transfer Point-3: Finishing works | CIV | 2024-02-16 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | 206819465
Transfer Point-3: Structural works | CIV | 2024-03-02 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | 206819466
Drive House | CIV | 2023-11-21 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6( Transfer Points) | 206819467
Drive House: EXCAVATION | CIV | 2023-11-21 08:00 | 2023-11-27 17:00 |  |  |  |  | 1.14.14.1.19.6.4(Drive House) | 206819468
Drive House: RCC in substructure including PCC | CIV | 2023-11-28 08:00 | 2024-01-11 17:00 |  |  |  |  | 1.14.14.1.19.6.4(Drive House) | 206819469
Drive House: RCC in superstructure | CIV | 2024-01-12 08:00 | 2024-01-31 17:00 |  |  |  |  | 1.14.14.1.19.6.4(Drive House) | 206819470
Drive House: Backfilling | CIV | 2024-02-01 08:00 | 2024-02-15 17:00 |  |  |  |  | 1.14.14.1.19.6.4(Drive House) | 206819471
Drive House: Finishing works | CIV | 2024-02-16 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.6.4(Drive House) | 206819472
Drive House: Structural works | CIV | 2024-03-02 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.6.4(Drive House) | 206819473
Conveyor Tunnel | CIV | 2023-11-01 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819474
Conv. 1A & 1B TUNNEL: Excavation | CIV | 2023-11-21 08:00 | 2023-11-27 17:00 |  |  |  |  | 1.14.14.1.19.7( Conveyor Tunnel) | 206819475
Conv. 1A & 1B TUNNEL: RCC in substructure including PCC | CIV | 2023-11-01 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.14.1.19.7( Conveyor Tunnel) | 206819476
Conv. 1A & 1B TUNNEL: Grade Slab | CIV | 2024-03-30 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.14.1.19.7( Conveyor Tunnel) | 206819477
Conv. 1A & 1B TUNNEL: RCC in superstructure | CIV | 2024-04-14 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.14.14.1.19.7( Conveyor Tunnel) | 206819478
Conv. 1A & 1B TUNNEL: Backfilling | CIV | 2024-05-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.14.1.19.7( Conveyor Tunnel) | 206819479
Conv. 1A & 1B TUNNEL: Finishing works | CIV | 2024-06-13 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.14.1.19.7( Conveyor Tunnel) | 206819480
Conveyor Galleries with Trestles | CIV | 2023-11-21 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19( Crusher House) | 206819481
Conveyor Gallery -1A & 1B | CIV | 2024-02-01 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8( Conveyor Galleries with Trestles) | 206819482
Conveyor Gallery -1A & 1B: EXCAVATION | CIV | 2024-02-01 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | 206819483
Conveyor Gallery -1A & 1B: RCC in substructure including PCC | CIV | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | 206819484
Conveyor Gallery -1A & 1B: RCC/Structure in superstructure | CIV | 2024-05-01 08:00 | 2024-05-30 17:00 |  |  |  |  | 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | 206819485
Conveyor Gallery -1A & 1B: Backfilling | CIV | 2024-05-31 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | 206819486
Conveyor Gallery -1A & 1B: Finishing works | CIV | 2024-06-30 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | 206819487
Conveyor Gallery -1A & 1B: Structural work | ERC | 2024-05-31 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | 206819488
Conveyor Gallery -2A & 2B | CIV | 2024-02-01 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8( Conveyor Galleries with Trestles) | 206819489
Conveyor Gallery -2A & 2B: EXCAVATION | CIV | 2024-02-01 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | 206819490
Conveyor Gallery -2A & 2B: RCC in substructure including PCC | CIV | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | 206819491
Conveyor Gallery -2A & 2B: RCC/Structure in superstructure | CIV | 2024-05-01 08:00 | 2024-05-30 17:00 |  |  |  |  | 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | 206819492
Conveyor Gallery -2A & 2B: Backfilling | CIV | 2024-05-31 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | 206819493
Conveyor Gallery -2A & 2B: Finishing works | CIV | 2024-06-30 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | 206819494
Conveyor Gallery -2A & 2B: Structural work | ERC | 2024-05-31 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | 206819495
Conveyor Gallery -3A & 3B | CIV | 2024-02-01 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8( Conveyor Galleries with Trestles) | 206819496
Conveyor Gallery -3A & 3B: EXCAVATION | CIV | 2024-02-01 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | 206819497
Conveyor Gallery -3A & 3B: RCC in substructure including PCC | CIV | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | 206819498
Conveyor Gallery -3A & 3B: RCC/Structure in superstructure | CIV | 2024-05-01 08:00 | 2024-05-30 17:00 |  |  |  |  | 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | 206819499
Conveyor Gallery -3A & 3B: Backfilling | CIV | 2024-05-31 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | 206819500
Conveyor Gallery -3A & 3B: Finishing works | CIV | 2024-06-30 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | 206819501
Conveyor Gallery -3A & 3B: Structural work | ERC | 2024-05-31 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | 206819502
Conveyor Gallery -4A & 4B | CIV | 2024-02-01 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8( Conveyor Galleries with Trestles) | 206819503
Conveyor Gallery -4A & 4B: EXCAVATION | CIV | 2024-02-01 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | 206819504
Conveyor Gallery -4A & 4B: RCC in substructure including PCC | CIV | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | 206819505
Conveyor Gallery -4A & 4B: RCC/Structure in superstructure | CIV | 2024-05-01 08:00 | 2024-05-30 17:00 |  |  |  |  | 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | 206819506
Conveyor Gallery -4A & 4B: Backfilling | CIV | 2024-05-31 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | 206819507
Conveyor Gallery -4A & 4B: Finishing works | CIV | 2024-06-30 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | 206819508
Conveyor Gallery -4A & 4B: Structural work | ERC | 2024-05-31 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | 206819509
Conveyor Gallery -5A & 5B | CIV | 2024-02-01 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8( Conveyor Galleries with Trestles) | 206819510
Conveyor Gallery -5A & 5B: EXCAVATION | CIV | 2024-02-01 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | 206819511
Conveyor Gallery -5A & 5B: RCC in substructure including PCC | CIV | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | 206819512
Conveyor Gallery -5A & 5B: RCC/Structure in superstructure | CIV | 2024-05-01 08:00 | 2024-05-30 17:00 |  |  |  |  | 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | 206819513
Conveyor Gallery -5A & 5B: Backfilling | CIV | 2024-05-31 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | 206819514
Conveyor Gallery -5A & 5B: Finishing works | CIV | 2024-06-30 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | 206819515
Conveyor Gallery -5A & 5B: Structural work | ERC | 2024-05-31 08:00 | 2024-09-27 17:00 |  |  |  |  | 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | 206819516
Reversible Yard Conveyor Gallery -6 | CIV | 2023-11-21 08:00 | 2024-08-28 17:00 |  |  |  |  | 1.14.14.1.19.8( Conveyor Galleries with Trestles) | 206819517
Conveyor Gallery -6: EXCAVATION | CIV | 2024-02-01 08:00 | 2024-03-01 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819518
Conveyor Gallery -6: RCC in substructure including PCC | CIV | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819519
Conveyor Gallery -6: RCC/Structure in superstructure | CIV | 2024-05-01 08:00 | 2024-05-30 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819520
Conveyor Gallery -6: Backfilling | CIV | 2024-05-31 08:00 | 2024-06-29 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819521
Conveyor Gallery -6: Finishing works | CIV | 2024-06-30 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819522
Conveyor Gallery -6: Structural work | ERC | 2024-05-31 08:00 | 2024-08-28 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819523
Cable Trestle/Cable Gallery | CIV | 2023-11-21 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | 206819524
Cable Gallery: EXCAVATION | CIV | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | 206819525
Cable Gallery: RCC in substructure including PCC | CIV | 2023-12-21 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | 206819526
Cable Gallery: RCC/Structure in superstructure | CIV | 2024-02-19 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | 206819527
Cable Gallery: Backfilling | CIV | 2024-03-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | 206819528
Cable Gallery: Finishing works | CIV | 2024-04-19 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | 206819529
Cable Gallery: Structural work | ERC | 2024-03-20 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | 206819530
Engineering, Supply &Erection | CIV | 2022-09-27 08:00 | 2026-01-26 17:00 | 2022-09-27 |  |  |  | 1.14.14(Coal Handling Plant) | 206819531
Finalisation of CHP layout | ENG | 2022-09-27 08:00 | 2022-10-06 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819532
Basic Engineering for CHP ( Flow Diagram, Profiles ) | ENG | 2022-10-07 08:00 | 2022-10-21 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819533
Track Hopper (Paddle Feeder) | PRC | 2022-11-20 17:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819534
NIT | ENQ | 2022-11-20 17:00 | 2022-11-20 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819535
Order Placement | ORD | 2022-11-21 08:00 | 2023-03-20 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819536
Detailed Engineering& Approval of Dwgs datasheet and QAP | ENG | 2023-03-21 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819537
Manufacturing | MFG | 2023-11-16 08:00 | 2024-09-10 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819538
Dispatch | DIS | 2024-02-14 08:00 | 2024-12-09 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819539
Erection of mechanical equipments | ERC | 2024-05-24 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819540
Erection of Electrical & C&I Items including cabling etc | ERC | 2025-04-09 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819541
Commissioning | COM | 2025-07-08 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819542
Trial Run with load | COM | 2025-12-28 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2.3( Track Hopper (Paddle Feeder)) | 206819543
Stacker Reclaimer (Reversible) | PRC | 2022-11-20 17:00 | 2026-01-26 17:00 | 2022-09-27 |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819544
NIT | ENQ | 2022-11-20 17:00 | 2022-11-20 17:00 | 2022-09-27 |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819545
Order Placement | ORD | 2022-11-21 08:00 | 2023-02-18 17:00 | 2022-12-02 |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819546
Detailed Engineering& Approval of Dwgs datasheet and QAP | ENG | 2023-02-19 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819547
Manufacturing | MFG | 2023-07-19 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819548
dispatch | OTH | 2023-10-17 08:00 | 2024-08-11 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819549
Erection of mechanical equipments | ERC | 2024-05-14 08:00 | 2025-03-09 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819550
Erection of Electrical & C&I Items including cabling etc | ERC | 2025-02-08 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819551
Commissioning | COM | 2025-05-09 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819552
Trial Run with load | COM | 2025-12-28 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2.4( Stacker Reclaimer (Reversible)) | 206819553
Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper) | PRC | 2022-12-20 17:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819554
NIT | ENQ | 2022-12-20 17:00 | 2022-12-20 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819555
Order Placement | ORD | 2022-12-21 08:00 | 2023-04-19 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819556
Detailed Engineering& Approval of Dwgs datasheet and QAP | ENG | 2023-04-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819557
Manufacturing | MFG | 2024-01-20 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819558
Inspection, Dispatch and RECEIPT at site | DIS | 2024-04-19 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819559
Erection of technological structure | ERC | 2024-10-26 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819560
Erection of mechanical equipments including tripper | ERC | 2025-01-24 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819561
DE Erection | ERC | 2025-01-14 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819562
Erection of Belt | ERC | 2025-05-24 08:00 | 2025-07-22 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819563
Erection of Electrical & C&I Items including cabling etc | ERC | 2025-01-24 08:00 | 2025-06-22 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819564
Commissioning | COM | 2025-06-23 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819565
Trial Run with load | COM | 2025-12-28 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | 206819566
Crusher House (Part of Conv. System) | ERC | 2023-04-20 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819567
Detailed Engineering& Approval of Dwgs datasheet and QAP | ENG | 2023-04-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819568
Manufacturing | MFG | 2024-01-20 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819569
Inspection, Dispatch and RECEIPT at site | DIS | 2024-04-19 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819570
Erection of mechanical equipments | ERC | 2024-10-26 08:00 | 2025-06-22 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819571
and RECEIPT | REC | 2025-03-25 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819572
Erection of Electrical & C&I Items including cabling etc | ERC | 2025-05-09 08:00 | 2025-09-05 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819573
Commissioning | COM | 2025-07-08 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819574
Trial Run with load | COM | 2025-12-28 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.14.2.6( Crusher House (Part of Conv. System)) | 206819575
DS & Water System + BOBR | PRC | 2023-02-18 17:00 | 2025-06-04 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819576
NIT | ENQ | 2023-02-18 17:00 | 2023-02-18 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819577
Order Placement | ORD | 2023-02-19 08:00 | 2023-06-18 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819578
Detailed Engineering& Approval of Dwgs datasheet and QAP | ENG | 2023-06-19 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819579
Manufacturing | MFG | 2024-01-15 08:00 | 2024-11-09 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819580
Inspection, Dispatch and RECEIPT at site | DIS | 2024-04-14 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819581
Erection of mechanical equipments | ERC | 2024-06-13 08:00 | 2025-03-06 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819582
Erection of Electrical & C&I Items including cabling etc | ERC | 2025-03-07 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.14.14.2.7( DS & Water System + BOBR) | 206819583
JHS - 16MVA, 11/3.45 KV CHP AUX Transformer | ERC | 2023-04-05 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819584
Engineering | ENG | 2023-04-05 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.14.14.2.8(JHS - 16MVA, 11/3.45 KV CHP AUX Transformer ) | 206819585
Manufacturing & testing | MFG | 2023-08-03 08:00 | 2024-11-16 17:00 |  |  |  |  | 1.14.14.2.8(JHS - 16MVA, 11/3.45 KV CHP AUX Transformer ) | 206819586
Packing, Dispatch | DIS | 2024-07-20 08:00 | 2024-12-16 17:00 |  |  |  |  | 1.14.14.2.8(JHS - 16MVA, 11/3.45 KV CHP AUX Transformer ) | 206819587
Erection of Aux Transformer | ERC | 2025-01-16 08:00 | 2025-06-04 17:00 |  |  |  |  | 1.14.14.2.8(JHS - 16MVA, 11/3.45 KV CHP AUX Transformer ) | 206819588
Commissioning of Stacker Reclaimer & Crusher House for coal feeding | COM | 2025-06-23 08:00 | 2025-11-27 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819589
Commissioning of Coal Handling system including Coal Transportation system for achieving Coal Firing of Unit # 1 | COM | 2025-11-05 08:00 | 2026-01-25 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819590
Trial Run with load | COM | 2025-11-28 08:00 | 2025-12-27 17:00 |  |  |  |  | 1.14.14.2(Engineering, Supply &Erection) | 206819591
Ash Handling Plant | OTH | 2022-12-25 17:00 | 2026-04-26 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819592
Civil Works | CIV | 2023-04-10 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15(Ash Handling Plant) | 206819593
Rel of Dwg for ASH WATER, ASH SLURRY PUMP HOUSE | PE - RFC | 2024-02-18 17:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819594
Rel of dwg for Compressor House | PE - RFC | 2023-09-26 17:00 | 2023-09-26 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819595
Rel of dwg for Silos | PE - RFC | 2023-11-25 17:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819596
Rel of dwg for Pipe Rack | PE - RFC | 2023-11-25 17:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819597
Rel of dwg for Pipe pedestal | PE - RFC | 2023-10-26 17:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819598
Rel of dwg for MCCs | PE - RFC | 2023-09-26 17:00 | 2023-09-26 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819599
Bottom Ash Hopper | CIV | 2023-04-10 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819600
Bottom Ash Hopper: EXCAVATION | OTH | 2023-04-10 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.14.15.1.7( Bottom Ash Hopper) | 206819601
Bottom Ash Hopper: RCC in substructure including PCC | CIV | 2023-04-25 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.14.15.1.7( Bottom Ash Hopper) | 206819602
Bottom Ash Hopper: RCC in superstructure | CIV | 2023-05-25 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.15.1.7( Bottom Ash Hopper) | 206819603
Bottom Ash Hopper: Backfilling | CIV | 2023-07-24 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.15.1.7( Bottom Ash Hopper) | 206819604
Bottom Ash Hopper: Finishing works | CIV | 2023-08-08 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.15.1.7( Bottom Ash Hopper) | 206819605
ASH SLURRY PUMP HOUSE | CIV | 2024-03-20 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819606
ASH SLURRY PUMP HOUSE: EXCAVATION | CIV | 2024-03-20 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819607
ASH SLURRY PUMP HOUSE: RCC in substructure including PCC | CIV | 2024-05-04 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819608
ASH SLURRY PUMP HOUSE: RCC in superstructure | CIV | 2024-07-28 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819609
ASH SLURRY PUMP HOUSE: Brick Work & Plastering | CIV | 2024-11-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819610
ASH SLURRY PUMP HOUSE: Flooring | CIV | 2025-01-24 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819611
ASH SLURRY PUMP HOUSE: Backfilling | CIV | 2025-02-23 08:00 | 2025-03-09 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819612
ASH SLURRY PUMP HOUSE: Finishing works | CIV | 2025-03-10 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | 206819613
ASH WATER PUMP HOUSE | CIV | 2024-03-20 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819614
ASH WATER PUMP HOUSE: EXCAVATION | CIV | 2024-03-20 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819615
ASH WATER PUMP HOUSE: RCC in substructure including PCC | CIV | 2024-05-04 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819616
ASH WATER PUMP HOUSE: RCC in superstructure | CIV | 2024-07-28 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819617
ASH WATER PUMP HOUSE: Brick Work & Plastering | CIV | 2024-11-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819618
ASH WATER PUMP HOUSE: Flooring | CIV | 2025-01-24 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819619
ASH WATER PUMP HOUSE: Backfilling | CIV | 2025-02-23 08:00 | 2025-03-09 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819620
ASH WATER PUMP HOUSE: Finishing works | CIV | 2025-03-10 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15.1.9(ASH WATER PUMP HOUSE) | 206819621
Compressor House | CIV | 2023-10-27 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819622
Compressor House: EXCAVATION | CIV | 2023-10-27 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.15.1.10(Compressor House) | 206819623
Compressor House: RCC in substructure including PCC | CIV | 2023-11-06 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.15.1.10(Compressor House) | 206819624
Compressor House: RCC in superstructure | CIV | 2024-01-20 08:00 | 2024-05-08 17:00 |  |  |  |  | 1.14.15.1.10(Compressor House) | 206819625
Compressor House: Backfilling | CIV | 2024-05-09 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.15.1.10(Compressor House) | 206819626
Compressor House: Finishing works | CIV | 2024-05-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.15.1.10(Compressor House) | 206819627
Fly Ash Silo | CIV | 2023-12-26 08:00 | 2024-10-31 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819628
Fly Ash Silo: EXCAVATION | CIV | 2023-12-26 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.14.15.1.11(Fly Ash Silo) | 206819629
Fly Ash Silo: RCC in substructure including PCC | CIV | 2024-01-05 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.14.15.1.11(Fly Ash Silo) | 206819630
Fly Ash Silo: RCC shell, column, tie beam and staircase | CIV | 2024-03-06 08:00 | 2024-09-11 17:00 |  |  |  |  | 1.14.15.1.11(Fly Ash Silo) | 206819631
Fly Ash Silo: RCC slab | CIV | 2024-09-12 08:00 | 2024-10-11 17:00 |  |  |  |  | 1.14.15.1.11(Fly Ash Silo) | 206819632
Fly Ash Silo: Backfilling | CIV | 2024-10-12 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.15.1.11(Fly Ash Silo) | 206819633
Fly Ash Silo: Finishing works | CIV | 2024-10-22 08:00 | 2024-10-31 17:00 |  |  |  |  | 1.14.15.1.11(Fly Ash Silo) | 206819634
Intermediate Silo | CIV | 2023-12-26 08:00 | 2024-10-31 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819635
Intermediate Silo: EXCAVATION | CIV | 2023-12-26 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.14.15.1.12(Intermediate Silo) | 206819636
Intermediate Silo: RCC in substructure including PCC | CIV | 2024-01-05 08:00 | 2024-03-05 17:00 |  |  |  |  | 1.14.15.1.12(Intermediate Silo) | 206819637
Intermediate Silo: RCC shell, column, tie beam and staircase | CIV | 2024-03-06 08:00 | 2024-09-11 17:00 |  |  |  |  | 1.14.15.1.12(Intermediate Silo) | 206819638
Intermediate Silo: RCC slab | CIV | 2024-09-12 08:00 | 2024-10-11 17:00 |  |  |  |  | 1.14.15.1.12(Intermediate Silo) | 206819639
Intermediate Silo: Backfilling | CIV | 2024-10-12 08:00 | 2024-10-21 17:00 |  |  |  |  | 1.14.15.1.12(Intermediate Silo) | 206819640
Intermediate Silo: Finishing works | CIV | 2024-10-22 08:00 | 2024-10-31 17:00 |  |  |  |  | 1.14.15.1.12(Intermediate Silo) | 206819641
Silo Utility Building | CIV | 2023-10-27 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819642
Silo Utility Building: EXCAVATION | CIV | 2023-10-27 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819643
Silo Utility Building: RCC in substructure including PCC | CIV | 2023-11-06 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819644
Silo Utility Building: RCC in superstructure | CIV | 2024-02-04 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819645
Silo Utility Building: Brick work & plastering | CIV | 2024-05-24 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819646
Silo Utility Building: Flooring | CIV | 2024-08-22 08:00 | 2024-09-20 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819647
Silo Utility Building: Backfilling | CIV | 2024-09-21 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819648
Silo Utility Building: Finishing works | CIV | 2024-10-01 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.14.15.1.13(Silo Utility Building) | 206819649
Classifier Silo | CIV | 2023-10-27 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819650
Classifier Silo: EXCAVATION | CIV | 2023-10-27 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819651
Classifier Silo: RCC in substructure including PCC | CIV | 2023-11-06 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819652
Classifier Silo: RCC in superstructure | CIV | 2024-02-04 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819653
Classifier Silo: Brick work & plastering | CIV | 2024-05-24 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819654
Classifier Silo: Flooring | CIV | 2024-08-22 08:00 | 2024-09-20 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819655
Classifier Silo: Backfilling | CIV | 2024-09-21 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819656
Classifier Silo: Finishing works | CIV | 2024-10-01 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.14.15.1.14(Classifier Silo) | 206819657
Pipe Rack (Inside Plant) | CIV | 2023-11-26 08:00 | 2024-05-20 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819658
Pipe Rack (Inside Plant): EXCAVATION | CIV | 2023-11-26 08:00 | 2023-12-02 17:00 |  |  |  |  | 1.14.15.1.15( Pipe Rack (Inside Plant)) | 206819659
Pipe Rack (Inside Plant): RCC & Steel Structure in substructure including PCC | CIV | 2023-12-03 08:00 | 2024-01-01 17:00 |  |  |  |  | 1.14.15.1.15( Pipe Rack (Inside Plant)) | 206819660
Pipe Rack (Inside Plant): RCC in superstructure | CIV | 2024-01-02 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.15.1.15( Pipe Rack (Inside Plant)) | 206819661
Pipe Rack (Inside Plant): Backfilling | CIV | 2024-05-01 08:00 | 2024-05-10 17:00 |  |  |  |  | 1.14.15.1.15( Pipe Rack (Inside Plant)) | 206819662
Pipe Rack (Inside Plant): Finishing works | CIV | 2024-05-11 08:00 | 2024-05-20 17:00 |  |  |  |  | 1.14.15.1.15( Pipe Rack (Inside Plant)) | 206819663
Pipe pedestal | CIV | 2023-09-27 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.14.15.1( Civil Works) | 206819664
Pipe pedestal: EXCAVATION | CIV | 2023-10-27 08:00 | 2023-11-02 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819665
Pipe pedestal : RCC in substructure including PCC | CIV | 2023-11-03 08:00 | 2023-12-02 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819666
Pipe pedestal: RCC in superstructure | CIV | 2023-12-03 08:00 | 2024-01-06 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819667
Pipe pedestal : Backfilling | CIV | 2024-01-07 08:00 | 2024-01-16 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819668
Pipe pedestal (Outside Plant): Finishing works | CIV | 2024-01-17 08:00 | 2024-01-26 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819669
AHP Main Control cum MCC Room & LHS MCC Room | CIV | 2023-09-27 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819670
Main Control Room: EXCAVATION | CIV | 2023-09-27 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819671
Main Control Room: RCC in substructure including PCC | CIV | 2023-10-12 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819672
Main Control Room: RCC/Structure work in superstructure | CIV | 2023-11-11 08:00 | 2024-05-11 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819673
Main Control Room: Brick Work & Plastering | CIV | 2024-05-12 08:00 | 2024-07-10 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819674
Main Control Room: Flooring | CIV | 2024-07-11 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819675
Main Control Room: Backfilling | CIV | 2024-07-26 08:00 | 2024-08-09 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819676
Main Control Room: Finishing works | CIV | 2024-08-10 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | 206819677
AHP MCC Room | CIV | 2023-09-27 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.14.15.1.16( Pipe pedestal) | 206819678
MCC Room: EXCAVATION | CIV | 2023-09-27 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819679
MCC Room: RCC in substructure including PCC | CIV | 2023-10-12 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819680
MCC Room: RCC/Structure work in superstructure | CIV | 2023-11-11 08:00 | 2024-05-11 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819681
MCC Room: Brick Work & Plastering | CIV | 2024-05-12 08:00 | 2024-07-10 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819682
MCC Room: Flooring | CIV | 2024-07-11 08:00 | 2024-07-25 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819683
MCC Room: Backfilling | CIV | 2024-07-26 08:00 | 2024-08-09 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819684
MCC Room: Finishing works | CIV | 2024-08-10 08:00 | 2024-10-08 17:00 |  |  |  |  | 1.14.15.1.16.7( AHP MCC Room) | 206819685
Engineering, Supply &Erection | ENG | 2022-12-25 17:00 | 2026-04-26 17:00 |  |  |  |  | 1.14.15(Ash Handling Plant) | 206819686
Bottom Ash Handling & Coarse Ash Handling System | PRC | 2022-12-25 17:00 | 2026-01-13 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819687
NIT | ENQ | 2022-12-25 17:00 | 2022-12-25 17:00 |  |  |  |  | 1.14.15.2.1(Bottom Ash Handling & Coarse Ash Handling System) | 206819688
Order placement | ORD | 2022-12-26 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.14.15.2.1(Bottom Ash Handling & Coarse Ash Handling System) | 206819689
Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH | OTH | 2023-04-25 08:00 | 2026-01-13 17:00 |  |  |  |  | 1.14.15.2.1(Bottom Ash Handling & Coarse Ash Handling System) | 206819690
Detailed Engineering | ENG | 2023-04-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | 206819691
Manufacturing | MFG | 2024-01-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | 206819692
Inspection, Dispatch and RECEIPT at site | DIS | 2024-07-23 08:00 | 2025-05-18 17:00 |  |  |  |  | 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | 206819693
Equipment Erection | ERC | 2024-09-21 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | 206819694
BAH: Structure Fabrication | ERC | 2024-09-21 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819695
BAH: and RECEIPT | ERC | 2024-12-05 08:00 | 2025-02-17 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819696
Application of Refractory | ERC | 2025-02-18 08:00 | 2025-04-18 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819697
Erection of BAH area Equipment(Clinker grinder, jet pump etc) | ERC | 2025-04-19 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819698
Erection in Eco, APH and Duct area | ERC | 2024-09-21 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819699
BAH: Erection of BAH Slurry Piping & APH/Duct slurry piping | ERC | 2025-05-19 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819700
Botheration of Electrical & C&I Items including cabling etc | ERC | 2025-06-18 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.14.15.2.1.3.4( Equipment Erection) | 206819701
Bottom ash: Commissioning | COM | 2025-09-16 08:00 | 2025-12-14 17:00 |  |  |  |  | 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | 206819702
Readiness of Bottom Ash Handling system including Ash transportation system up to slurry pump house for BLU of U#1 | ERC | 2025-12-15 08:00 | 2026-01-13 17:00 |  |  |  |  | 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | 206819703
Ash water PH, Ash Slurry PH & piping upto plant Boundary | OTH | 2023-04-25 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.15.2.1(Bottom Ash Handling & Coarse Ash Handling System) | 206819704
Detailed Engineering | ENG | 2023-04-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | 206819705
Manufacturing | MFG | 2024-01-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | 206819706
Inspection, Dispatch and RECEIPT at site | DIS | 2024-07-23 08:00 | 2025-05-18 17:00 |  |  |  |  | 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | 206819707
and RECEIPT | ERC | 2024-09-21 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | 206819708
Erection of mechanical Equipment in Slurry PH & Ash Water PH | ERC | 2024-09-21 08:00 | 2025-02-27 17:00 |  |  |  |  | 1.14.15.2.1.4.4( and RECEIPT) | 206819709
Ash Slurry Pump House and Ash Water Pump House - Piping | ERC | 2025-02-28 08:00 | 2025-06-27 17:00 |  |  |  |  | 1.14.15.2.1.4.4( and RECEIPT) | 206819710
Piping upto Plant Boundary | ERC | 2025-03-30 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.15.2.1.4.4( and RECEIPT) | 206819711
Erection of Electrical & C&I Items including cabling etc. | ERC | 2025-06-28 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.15.2.1.4.4( and RECEIPT) | 206819712
Commissioning | COM | 2024-09-22 08:00 | 2024-12-20 17:00 |  |  |  |  | 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | 206819713
Trial Run with load | COM | 2024-12-21 08:00 | 2025-01-19 17:00 |  |  |  |  | 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | 206819714
Fly Ash Conveying System | PRC | 2022-12-25 17:00 | 2026-01-18 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819715
NIT | ENQ | 2022-12-25 17:00 | 2022-12-25 17:00 |  |  |  |  | 1.14.15.2.2( Fly Ash Conveying System) | 206819716
Order Placement | ORD | 2022-12-26 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.14.15.2.2( Fly Ash Conveying System) | 206819717
Compressor house | OTH | 2023-04-25 08:00 | 2026-01-18 17:00 |  |  |  |  | 1.14.15.2.2( Fly Ash Conveying System) | 206819718
Detailed Engineering | ENG | 2023-04-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.15.2.2.3(Compressor house) | 206819719
Manufacturing | MFG | 2024-01-25 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.14.15.2.2.3(Compressor house) | 206819720
Inspection, Dispatch and RECEIPT at site | DIS | 2024-05-19 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.14.15.2.2.3(Compressor house) | 206819721
and RECEIPT | REC | 2025-01-04 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.15.2.2.3(Compressor house) | 206819722
Compressor house -Erection of mechanical equipments | ERC | 2025-01-04 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.14.15.2.2.3.4( and RECEIPT) | 206819723
Compressor house - Piping | ERC | 2025-05-04 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.15.2.2.3.4( and RECEIPT) | 206819724
Compressor house -Erection of Electrical & C&I items including cabling | ERC | 2025-05-04 08:00 | 2025-08-31 17:00 |  |  |  |  | 1.14.15.2.2.3.4( and RECEIPT) | 206819725
Commissioning | COM | 2025-09-01 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.14.15.2.2.3(Compressor house) | 206819726
Trial Run with load | COM | 2025-12-20 08:00 | 2026-01-18 17:00 |  |  |  |  | 1.14.15.2.2.3(Compressor house) | 206819727
ESP area | ERC | 2023-04-25 08:00 | 2025-12-14 17:00 |  |  |  |  | 1.14.15.2.2( Fly Ash Conveying System) | 206819728
Detailed Engineering | ENG | 2023-04-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.15.2.2.4(ESP area) | 206819729
Manufacturing | MFG | 2024-01-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.2.2.4(ESP area) | 206819730
Inspection, Dispatch and RECEIPT at site | DIS | 2024-07-23 08:00 | 2025-05-18 17:00 |  |  |  |  | 1.14.15.2.2.4(ESP area) | 206819731
and RECEIPT | REC | 2024-10-31 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.14.15.2.2.4(ESP area) | 206819732
Erection of mechanical equipments | ERC | 2024-11-20 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.14.15.2.2.4.4( and RECEIPT) | 206819733
Erection of Structure & Pipe Trestle from ESP to FA Silo | ERC | 2024-10-31 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.15.2.2.4.4( and RECEIPT) | 206819734
Piping from ESP to Intermediate Silo/Classifier Silo/Fly Ash Silo | ERC | 2024-11-20 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.14.15.2.2.4.4( and RECEIPT) | 206819735
Erection of Electrical & C&I Items including cabling etc. | ERC | 2025-06-18 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.14.15.2.2.4.4( and RECEIPT) | 206819736
Commissioning | COM | 2025-08-17 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14.15.2.2.4(ESP area) | 206819737
Trial Run with load | COM | 2025-11-15 08:00 | 2025-12-14 17:00 |  |  |  |  | 1.14.15.2.2.4(ESP area) | 206819738
Intermediate Silo & Fly Ash Silo Equipment | ERC | 2023-04-25 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14.15.2.2( Fly Ash Conveying System) | 206819739
Detailed Engineering | ERC | 2023-04-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | 206819740
Manufacturing | MFG | 2024-01-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | 206819741
Inspection, Dispatch and RECEIPT at site | DIS | 2024-07-23 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | 206819742
and RECEIPT | REC | 2024-11-20 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | 206819743
and RECEIPT in Intermediate silo | REC | 2024-11-20 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.14.15.2.2.5.4( and RECEIPT) | 206819744
and RECEIPT in FA silo | REC | 2024-11-20 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.14.15.2.2.5.4( and RECEIPT) | 206819745
Erection of Electrical & C&I Items including cabling etc. | ERC | 2025-07-18 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14.15.2.2.5.4( and RECEIPT) | 206819746
Commissioning | COM | 2025-07-18 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | 206819747
Trial Run with load | COM | 2025-10-16 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | 206819748
Fly ash Classifier | ERC | 2023-04-25 08:00 | 2026-01-13 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819749
Detailed Engineering | ENG | 2023-04-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.15.2.3(Fly ash Classifier) | 206819750
Manufacturing | MFG | 2024-01-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.15.2.3(Fly ash Classifier) | 206819751
Inspection, Dispatch and RECEIPT at site | DIS | 2024-07-23 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.15.2.3(Fly ash Classifier) | 206819752
and RECEIPT | REC | 2024-11-20 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.15.2.3(Fly ash Classifier) | 206819753
Erection of mechanical Equipment | ERC | 2024-11-20 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.14.15.2.3.4( and RECEIPT) | 206819754
Piping from clarifier to FA silo | ERC | 2024-11-20 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.14.15.2.3.4( and RECEIPT) | 206819755
Erection of Electrical & C&I Items including cabling etc. | ERC | 2025-07-18 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.15.2.3.4( and RECEIPT) | 206819756
Commissioning | COM | 2025-08-17 08:00 | 2025-12-14 17:00 |  |  |  |  | 1.14.15.2.3(Fly ash Classifier) | 206819757
Trial Run with load | ERC | 2025-12-15 08:00 | 2026-01-13 17:00 |  |  |  |  | 1.14.15.2.3(Fly ash Classifier) | 206819758
Fly ash Bagging System | ERC | 2023-04-25 08:00 | 2026-01-08 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819759
Detailed Engineering | ENG | 2023-04-25 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819760
Manufacturing | MFG | 2023-12-21 08:00 | 2024-12-19 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819761
Inspection, Dispatch and RECEIPT at site | DIS | 2024-06-18 08:00 | 2025-04-03 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819762
Erection of mechanical Equipment | ERC | 2024-10-16 08:00 | 2025-08-11 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819763
Erection of Electrical & C&I Items including cabling etc. | ERC | 2025-08-12 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819764
Commissioning | COM | 2025-08-12 08:00 | 2025-12-09 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819765
Trial Run with load | ERC | 2025-12-10 08:00 | 2026-01-08 17:00 |  |  |  |  | 1.14.15.2.4(Fly ash Bagging System) | 206819766
JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer | ERC | 2023-06-04 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819767
Engineering | ENG | 2023-06-04 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.15.2.5(JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer) | 206819768
Manufacturing & testing | MFG | 2023-10-02 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.15.2.5(JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer) | 206819769
Packing, Dispatch | DIS | 2024-09-18 08:00 | 2025-02-14 17:00 |  |  |  |  | 1.14.15.2.5(JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer) | 206819770
Erection of Aux Transformer | ERC | 2025-03-17 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.14.15.2.5(JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer) | 206819771
Commissioning of Aux Transformer | COM | 2025-08-04 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.15.2.5(JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer) | 206819772
Readiness of Ash Handling system for Steam Blowing | ERC | 2026-01-14 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819773
Readiness of Fly Ash system Handling system | ERC | 2026-01-19 08:00 | 2026-04-26 17:00 |  |  |  |  | 1.14.15.2(Engineering, Supply &Erection) | 206819774
Illumination Package for CHP, AHP, LHP & GHP | PRC | 2023-02-18 17:00 | 2025-05-08 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819775
NIT | ENQ | 2023-02-18 17:00 | 2023-02-18 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819776
Order Placement | ORD | 2023-02-19 08:00 | 2023-06-18 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819777
Detailed Engineering& Approval of Dwgs datasheet and QAP | ENG | 2023-06-19 08:00 | 2024-03-14 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819778
Manufacturing | MFG | 2023-09-17 08:00 | 2024-08-06 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819779
Inspection, Dispatch and RECEIPT at site | DIS | 2024-02-09 08:00 | 2024-11-04 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819780
Erection of Illumination package | ERC | 2024-04-09 08:00 | 2025-04-08 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819781
Commissioning | COM | 2025-01-09 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | 206819782
Electrical: E&C for CHP, AHP, LHP & GHP | PRC | 2023-09-21 17:00 | 2025-12-19 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819783
NIT | ENQ | 2023-09-21 17:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819784
Order placement | ORD | 2023-09-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819785
Detailed Engineering | ENG | 2024-01-20 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819786
Manufacturing | MFG | 2024-03-30 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819787
Dispatch | DIS | 2024-09-26 08:00 | 2025-06-12 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819788
EARTHING | ERC | 2024-11-25 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819789
CABLE TRAY & SUPPORTS AND CABLE LAYING | ERC | 2025-01-24 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819790
OIL TYPE TRANSFORMER | OTH | 2025-03-25 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819791
BUSDUCT | OTH | 2025-05-24 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819792
MCC | OTH | 2025-05-24 08:00 | 2025-08-21 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819793
DCS INCLUDING BATTERY, CHARGER, UPS | OTH | 2025-07-23 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819794
220V DC BATTERY & CHARGER | OTH | 2025-07-23 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819795
COMMISSIONING OF TRANSFORMER, BUSDUCT, MCC, DCS, BATTERY & CHARGER | COM | 2025-04-24 08:00 | 2025-12-19 17:00 |  |  |  |  | 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | 206819796
DG | OTH | 2023-06-15 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819797
Rel of Dwg for DG | PE - RFC | 2024-05-29 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.14.18(DG) | 206819798
Supply | SUP | 2023-06-15 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.14.18(DG) | 206819799
DG Set | SUP | 2023-06-15 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.14.18.2(Supply) | 206819800
PO Placement | ORD | 2023-06-15 08:00 | 2023-10-15 17:00 |  |  |  |  | 1.14.18.2.1(DG Set) | 206819801
Engineering | ENG | 2023-10-16 08:00 | 2024-02-12 17:00 |  |  |  |  | 1.14.18.2.1(DG Set) | 206819802
Dispatch of DG Set with Associated items | DIS | 2024-10-10 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.14.18.2.1(DG Set) | 206819803
E&C DG SET | OTH | 2025-04-08 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.14.18(DG) | 206819804
E&C DG SET: Erection of Diesel Generator set | ERC | 2025-04-08 08:00 | 2025-05-07 17:00 |  |  |  |  | 1.14.18.3(E&C DG SET) | 206819805
E&C DG Redefection of Fuel Oil System (DG SET) | ERC | 2025-05-08 08:00 | 2025-06-06 17:00 |  |  |  |  | 1.14.18.3(E&C DG SET) | 206819806
E&C DG Redefection of Cooling water system consisting of Pumps / Heaters / expansion tanks/ radiators etc | ERC | 2025-06-07 08:00 | 2025-07-01 17:00 |  |  |  |  | 1.14.18.3(E&C DG SET) | 206819807
E&C DG Redefection of DG Battery Bank along with DG Battery Charger | ERC | 2025-07-02 08:00 | 2025-07-26 17:00 |  |  |  |  | 1.14.18.3(E&C DG SET) | 206819808
E&C DG Redefection of DG Switchgear | ERC | 2025-07-27 08:00 | 2025-08-20 17:00 |  |  |  |  | 1.14.18.3(E&C DG SET) | 206819809
E&C DG SET: Commissioning of DG Set | COM | 2025-08-21 08:00 | 2025-08-27 17:00 |  |  |  |  | 1.14.18.3(E&C DG SET) | 206819810
MILL REJECT SYSTEM | SUP | 2023-05-15 08:00 | 2026-06-20 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819811
Supply | SUP | 2023-05-15 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.14.19(MILL REJECT SYSTEM) | 206819812
MILL REJECT SYSTEM | OTH | 2023-05-15 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.14.19.1(Supply) | 206819813
Ordering | ORD | 2023-05-15 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.19.1.1(MILL REJECT SYSTEM ) | 206819814
Engineering | ENG | 2023-10-12 08:00 | 2024-07-07 17:00 |  |  |  |  | 1.14.19.1.1(MILL REJECT SYSTEM ) | 206819815
Manufacturing | MFG | 2024-07-08 08:00 | 2025-08-14 17:00 |  |  |  |  | 1.14.19.1.1(MILL REJECT SYSTEM ) | 206819816
Dispatch of Conveying Air compressors | DIS | 2025-08-15 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.14.19.1.1(MILL REJECT SYSTEM ) | 206819817
Dispatch of Pyrite hoppers | DIS | 2025-08-15 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.14.19.1.1(MILL REJECT SYSTEM ) | 206819818
Dispatch of pipings and other balance items | DIS | 2025-08-15 08:00 | 2026-01-11 17:00 |  |  |  |  | 1.14.19.1.1(MILL REJECT SYSTEM ) | 206819819
Civil | CIV | 2024-09-16 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.19(MILL REJECT SYSTEM) | 206819820
Conveying Air Compressor Foundation | CIV | 2024-09-16 08:00 | 2025-04-28 17:00 |  |  |  |  | 1.14.19.2(Civil) | 206819821
EXCAVATION | CIV | 2024-09-16 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.14.19.2.1(Conveying Air Compressor Foundation) | 206819822
RCC in substructure including PCC | CIV | 2024-10-31 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.14.19.2.1(Conveying Air Compressor Foundation) | 206819823
RCC in superstructure | CIV | 2025-01-04 08:00 | 2025-04-03 17:00 |  |  |  |  | 1.14.19.2.1(Conveying Air Compressor Foundation) | 206819824
Backfilling | CIV | 2025-04-04 08:00 | 2025-04-18 17:00 |  |  |  |  | 1.14.19.2.1(Conveying Air Compressor Foundation) | 206819825
Finishing works | CIV | 2025-04-19 08:00 | 2025-04-28 17:00 |  |  |  |  | 1.14.19.2.1(Conveying Air Compressor Foundation) | 206819826
Silo Structure Foundation | CIV | 2025-04-29 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.19.2(Civil) | 206819827
EXCAVATION | CIV | 2025-04-29 08:00 | 2025-05-08 17:00 |  |  |  |  | 1.14.19.2.2(Silo Structure Foundation) | 206819828
RCC in substructure including PCC | CIV | 2025-05-09 08:00 | 2025-06-02 17:00 |  |  |  |  | 1.14.19.2.2(Silo Structure Foundation) | 206819829
RCC in superstructure | CIV | 2025-06-03 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.19.2.2(Silo Structure Foundation) | 206819830
Backfilling | CIV | 2025-07-13 08:00 | 2025-07-22 17:00 |  |  |  |  | 1.14.19.2.2(Silo Structure Foundation) | 206819831
Finishing works | CIV | 2025-07-23 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.19.2.2(Silo Structure Foundation) | 206819832
Erection | ERC | 2025-04-29 08:00 | 2026-06-20 17:00 |  |  |  |  | 1.14.19(MILL REJECT SYSTEM) | 206819833
MILL REJECT SYSTEM: Conveying Air compressors: inspection of foundations | ERC | 2025-04-29 08:00 | 2025-05-18 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819834
MILL REJECT SYSTEM: Conveying Air compressors: placement of Conveying Air compressors on foundation | ERC | 2025-05-19 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819835
MILL REJECT SYSTEM: Conveying Air compressors: Erection of Valves | ERC | 2025-06-08 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819836
MILL REJECT SYSTEM:PYRITE HOPPERS: Placement of pyrite hoppers | ERC | 2025-07-28 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819837
MILL REJECT SYSTEM:PYRITE Hoppers: Erection of Deluge Valves | ERC | 2025-09-26 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819838
MILL REJECT SYSTEM: Conveying piping: Erection of Conveying Air piping for compressor | ERC | 2025-11-10 08:00 | 2025-12-13 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819839
MILL REJECT SYSTEM: Conveying SYSTEM: Conveying of associated fittings | ERC | 2025-12-14 08:00 | 2026-01-16 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819840
MILL REJECT SYSTEM:MILL REJECT SILO: Fabrication of Structure | ERC | 2026-01-17 08:00 | 2026-02-10 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819841
MILL REJECT SYSTEM:MILL REJECT SILO: Fabrication of Silo | ERC | 2026-02-11 08:00 | 2026-03-27 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819842
MILL REJECT SYSTEM:MILL REJECT SILO: Erection of support structure for Silo | ERC | 2026-03-28 08:00 | 2026-04-16 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819843
MILL REJECT SYSTEM:MILL REJECT SILO: Lifting of Silo cone | ERC | 2026-04-17 08:00 | 2026-04-21 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819844
MILL REJECT SYSTEM:MILL REJECT SILO: Welding of Silo Cone with structure | ERC | 2026-04-22 08:00 | 2026-05-01 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819845
MILL REJECT SYSTEM:MILL REJECT SILO: lifting of Silo Shell | ERC | 2026-05-02 08:00 | 2026-05-06 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819846
MILL REJECT SYSTEM:MILL REJECT SILO:WELDING OF SILO SHELL | ERC | 2026-05-07 08:00 | 2026-05-16 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819847
MILL REJECT SYSTEM:MILL REJECT SILO:LINING INSIDE MILL REJECT SILO | ERC | 2026-05-17 08:00 | 2026-05-23 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819848
MILL REJECT SYSTEM:ERECTION OF Electrical, C&I and PLC SYSTEM | ERC | 2026-05-24 08:00 | 2026-06-12 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819849
MILL REJECT SYSTEM:COMMISSIONING of MRS | COM | 2026-06-13 08:00 | 2026-06-20 17:00 |  |  |  |  | 1.14.19.3(Erection) | 206819850
400kV Switchyard | OTH | 2023-04-25 08:00 | 2026-03-27 17:00 |  |  |  |  | 1.14(BOP Systems) | 206819851
Engineering Activities | ENG | 2023-04-25 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206819852
400 kV Single Line Diagram | ENG | 2023-04-25 08:00 | 2023-05-09 17:00 |  |  |  |  | 1.14.20.1(Engineering Activities) | 206819853
Layout Plan & Section - 400 kV | ENG | 2023-05-10 08:00 | 2023-05-29 17:00 |  |  |  |  | 1.14.20.1(Engineering Activities) | 206819854
Civil Design Basis | ENG | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.1(Engineering Activities) | 206819855
Ordering of BOIs - 400 kV Switchyard | ORD | 2023-05-30 08:00 | 2023-09-11 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206819856
400 kV Gas Insulated Switchgear | ORD | 2023-05-30 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819857
400 kV BPI | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819858
336 kV LA | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819859
400 kV WT | ORD | 2023-06-04 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819860
FOTE | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819861
Control & Power Cable | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819862
Marshalling Kiosk & JBs | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819863
Earthing Material | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819864
Shield Wire | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819865
ACSR Conductor | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819866
Al tube | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819867
Cable Trench Material | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819868
Structures & Hardwares | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819869
Battery & Battery Chargers | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819870
Auxiliary Transformer | ORD | 2023-07-24 08:00 | 2023-09-11 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819871
Illumination System | ORD | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819872
Fire Protection System | OTH | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819873
Air Conditioning and Ventilation System | OTH | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819874
EOT Crane | OTH | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819875
Self Power Hydraulic Aerial Working Platform | OTH | 2023-05-30 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | 206819876
Detailed Engineering for 400 kV Switchyard | ENG | 2023-04-25 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206819877
400 kV Structure Layout and Section | OTH | 2023-06-09 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819878
400 kV EKD - Plan, Section and BOM | OTH | 2023-06-29 08:00 | 2023-07-28 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819879
400 kV Clearance Check Diagram | OTH | 2023-06-19 08:00 | 2023-07-18 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819880
400 kV DSLP Calculation and Layout - Overall | OTH | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819881
400 kV Earthing Layout - Overall | OTH | 2023-06-14 08:00 | 2023-07-13 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819882
400 kV CVT - Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819883
400 kV CVT - Structural Design, Drawing | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819884
400 kV CVT - Proto Corrected Structural Drawing | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819885
400 kV CVT - Foundation Design, Drawing | CIV | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819886
336 kV LA - Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819887
336 kV LA - Structural Design, Drawing | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819888
336 kV LA - Proto Corrected Structural Drawing | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819889
336 kV LA - Foundation Design, Drawing | CIV | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819890
400 kV BPI - Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819891
400 kV BPI - Structural Design, Drawing | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819892
400 kV BPI - Proto Corrected Structural Drawing | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819893
400 kV BPI - Foundation Design, Drawing | CIV | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819894
400 kV Wave Trap - Drawing, Data Sheet, TTR, MQP | ENG | 2023-08-03 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819895
400 kV Wave Trap - Structural Design, Drawing | ENG | 2023-08-03 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819896
400 kV Wave Trap - Proto Corrected Structural Drawing | ENG | 2023-08-03 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819897
400 kV Wave Trap- Foundation Design, Drawing | CIV | 2023-08-03 08:00 | 2023-09-01 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819898
FOTE - Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819899
125 MVAr Reactor | OTH | 2023-04-25 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819900
Composite Long Rod Insulator | OTH | 2023-04-25 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819901
LT Switchgear | OTH | 2023-04-25 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819902
Control & Power Cable- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819903
Marshalling Kiosk & JBs- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819904
Shield Wire - Drawing and Data sheet | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819905
ACSR Conductor- Drawing and Data sheet | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819906
Al tube- Drawing and Data sheet | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819907
Cable Trench Material- Drawing and Data sheet | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819908
Battery & Battery Chargers- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819909
Auxiliary Transformer- Drawing, Data Sheet, TTR, MQP | ENG | 2023-09-22 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819910
Illumination System- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819911
Fire Protection System- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819912
Air Conditioning and Ventilation System- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819913
EOT Crane- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819914
Self Power Hydraulic Aerial Working Platform- Drawing, Data Sheet, TTR, MQP | ENG | 2023-07-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819915
Control & Relay Panel & SAS for 400 kV Switchyard | OTH | 2023-04-25 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819916
400 kV Protection SLD | OTH | 2023-05-30 08:00 | 2023-06-28 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819917
Control & Power Cable Schedule | ENG | 2023-07-24 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819918
GA & Architectural Plan, Elevation and Sections for 400 kV GIS Building | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819919
GA and Data Sheet of Circuit Breaker (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819920
GA and Data Sheet of Disconnecting Switch (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819921
GA and Data Sheet of Earthing Switch (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819922
GA and Data Sheet of Operating Mechanism for DS & ES (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819923
GA and Data Sheet of Current Transformer (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819924
GA and Data Sheet of Bus Voltage Transformer (For reference) (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819925
GA and Data Sheet of Circuit Breaker (GIS) | ENG | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819926
400 kV GIS Building - Load Calculation, Analysis & Design | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819927
400 kV GIS Building - Design of Crane Runway girder | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819928
400 kV GIS Building - Design of Roof Purlins | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819929
400 kV GIS Building - Design of Indoor Cable Trench | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819930
400 kV GIS Building - Layout and details of foundations and column pedestals | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819931
400 kV GIS Building - GA and Details of structural steel columns including tie beams and bracings | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819932
400 kV GIS Building - GA and RC details of plinth beam | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819933
400 kV GIS Building - GA and details of Roof Truss including roof bracings | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819934
400 kV GIS Building - Layout & details of Roof and wall | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819935
400 kV GIS Building - Details of EOT crane girder | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819936
400 kV GIS Building - Layout and RCC details of Indoor cable trenches | CIV | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819937
400 kV GIS Building - GA and RC details of GIS equipments | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819938
400 kV GIS Building - Details of Door & Windows | ENG | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | 206819939
Manufacturing, Testing and Dispatch | MFG | 2023-05-25 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206819940
400 kV Gas Insulated Switchgear | OTH | 2023-11-26 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819941
Manufacturing | MFG | 2023-11-26 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.20.4.1(400 kV Gas Insulated Switchgear) | 206819942
Testing, Inspection &Dispatch | DIS | 2024-05-24 08:00 | 2024-07-22 17:00 |  |  |  |  | 1.14.20.4.1(400 kV Gas Insulated Switchgear) | 206819943
Receipt at Site | OTH | 2024-07-23 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.20.4.1(400 kV Gas Insulated Switchgear) | 206819944
400 kV CVT | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819945
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.2(400 kV CVT) | 206819946
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.2(400 kV CVT) | 206819947
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.2(400 kV CVT) | 206819948
400 kV BPI | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819949
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.3(400 kV BPI) | 206819950
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.3(400 kV BPI) | 206819951
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.3(400 kV BPI) | 206819952
336 kV LA | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819953
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.4(336 kV LA) | 206819954
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.4(336 kV LA) | 206819955
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.4(336 kV LA) | 206819956
400 kV WT | OTH | 2023-09-02 08:00 | 2023-12-10 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819957
Manufacturing | MFG | 2023-09-02 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.20.4.5(400 kV WT) | 206819958
Testing, Inspection &Dispatch | DIS | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.20.4.5(400 kV WT) | 206819959
Receipt at Site | OTH | 2023-11-21 08:00 | 2023-12-10 17:00 |  |  |  |  | 1.14.20.4.5(400 kV WT) | 206819960
400 kV Control & Relay Panels and SAS |  | 2023-06-24 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819961
Manufacturing | MFG | 2023-06-24 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.20.4.6(400 kV Control & Relay Panels and SAS) | 206819962
Testing, Inspection &Dispatch | DIS | 2023-09-22 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.20.4.6(400 kV Control & Relay Panels and SAS) | 206819963
Receipt at Site | OTH | 2023-10-22 08:00 | 2023-11-10 17:00 |  |  |  |  | 1.14.20.4.6(400 kV Control & Relay Panels and SAS) | 206819964
FOTE | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819965
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.7(FOTE) | 206819966
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.7(FOTE) | 206819967
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.7(FOTE) | 206819968
Control & Power Cable | OTH | 2023-08-28 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819969
Manufacturing | MFG | 2023-08-28 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.8(Control & Power Cable) | 206819970
Testing, Inspection &Dispatch | DIS | 2023-11-26 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.20.4.8(Control & Power Cable) | 206819971
Receipt at Site | OTH | 2023-12-26 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4.8(Control & Power Cable) | 206819972
125 MVAr Reactor | OTH | 2023-05-25 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819973
Manufacturing | MFG | 2023-05-25 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.20.4.9(125 MVAr Reactor) | 206819974
Testing, Inspection &Dispatch | DIS | 2023-08-23 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.20.4.9(125 MVAr Reactor) | 206819975
Receipt at Site | OTH | 2023-09-22 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.20.4.9(125 MVAr Reactor) | 206819976
Composite Long Rod Insulator | OTH | 2023-05-25 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819977
Manufacturing | MFG | 2023-05-25 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.20.4.10(Composite Long Rod Insulator) | 206819978
Testing, Inspection &Dispatch | DIS | 2023-08-23 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.20.4.10(Composite Long Rod Insulator) | 206819979
Receipt at Site | OTH | 2023-09-22 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.20.4.10(Composite Long Rod Insulator) | 206819980
LT Switchgear | OTH | 2023-05-25 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819981
Manufacturing | MFG | 2023-05-25 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.20.4.11(LT Switchgear) | 206819982
Testing, Inspection &Dispatch | DIS | 2023-08-23 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.20.4.11(LT Switchgear) | 206819983
Receipt at Site | OTH | 2023-09-22 08:00 | 2023-10-11 17:00 |  |  |  |  | 1.14.20.4.11(LT Switchgear) | 206819984
Marshalling Kiosk & JBs | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819985
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.12(Marshalling Kiosk & JBs) | 206819986
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.12(Marshalling Kiosk & JBs) | 206819987
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.12(Marshalling Kiosk & JBs) | 206819988
Earthing Material | OTH | 2023-07-19 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819989
Manufacturing | MFG | 2023-07-19 08:00 | 2023-08-17 17:00 |  |  |  |  | 1.14.20.4.13(Earthing Material) | 206819990
Testing, Inspection &Dispatch | DIS | 2023-08-18 08:00 | 2023-09-16 17:00 |  |  |  |  | 1.14.20.4.13(Earthing Material) | 206819991
Receipt at Site | OTH | 2023-09-17 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.20.4.13(Earthing Material) | 206819992
Shield Wire | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819993
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.14(Shield Wire) | 206819994
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.14(Shield Wire) | 206819995
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.14(Shield Wire) | 206819996
ACSR Conductor | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206819997
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.15(ACSR Conductor) | 206819998
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.15(ACSR Conductor) | 206819999
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.15(ACSR Conductor) | 206820000
Al tube | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820001
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.16(Al tube) | 206820002
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.16(Al tube) | 206820003
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.16(Al tube) | 206820004
Cable Trench Material | OTH | 2023-08-28 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820005
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.20.4.17(Cable Trench Material) | 206820006
Testing, Inspection &Dispatch | DIS | 2023-10-17 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.20.4.17(Cable Trench Material) | 206820007
Receipt at Site | OTH | 2023-11-16 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.20.4.17(Cable Trench Material) | 206820008
Structures & Hardwares | OTH | 2023-08-18 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820009
Manufacturing | MFG | 2023-08-18 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.20.4.18(Structures & Hardwares) | 206820010
Testing, Inspection &Dispatch | DIS | 2023-10-07 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.20.4.18(Structures & Hardwares) | 206820011
Receipt at Site | OTH | 2023-11-06 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.18(Structures & Hardwares) | 206820012
Battery & Battery Chargers | OTH | 2023-08-28 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820013
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.4.19(Battery & Battery Chargers) | 206820014
Testing, Inspection &Dispatch | DIS | 2023-10-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.19(Battery & Battery Chargers) | 206820015
Receipt at Site | OTH | 2023-11-26 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.20.4.19(Battery & Battery Chargers) | 206820016
Auxiliary Transformer | OTH | 2023-10-22 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820017
Manufacturing | MFG | 2023-10-22 08:00 | 2023-12-10 17:00 |  |  |  |  | 1.14.20.4.20(Auxiliary Transformer) | 206820018
Testing, Inspection &Dispatch | DIS | 2023-12-11 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.14.20.4.20(Auxiliary Transformer) | 206820019
Receipt at Site | OTH | 2024-01-10 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.20.4.20(Auxiliary Transformer) | 206820020
Illumination System | OTH | 2023-08-28 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820021
Manufacturing | MFG | 2023-08-28 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.20.4.21(Illumination System) | 206820022
Testing, Inspection &Dispatch | DIS | 2023-10-27 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.21(Illumination System) | 206820023
Receipt at Site | OTH | 2023-11-26 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.20.4.21(Illumination System) | 206820024
Fire Protection System | OTH | 2023-08-28 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820025
Manufacturing | MFG | 2023-08-28 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.22(Fire Protection System) | 206820026
Testing, Inspection &Dispatch | DIS | 2023-11-26 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.20.4.22(Fire Protection System) | 206820027
Receipt at Site | OTH | 2023-12-26 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4.22(Fire Protection System) | 206820028
Air Conditioning and Ventilation System | OTH | 2023-08-28 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820029
Manufacturing | MFG | 2023-08-28 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.23(Air Conditioning and Ventilation System) | 206820030
Testing, Inspection &Dispatch | DIS | 2023-11-26 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.20.4.23(Air Conditioning and Ventilation System) | 206820031
Receipt at Site | OTH | 2023-12-26 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4.23(Air Conditioning and Ventilation System) | 206820032
EOT Crane | OTH | 2023-08-28 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820033
Manufacturing | MFG | 2023-08-28 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.24(EOT Crane) | 206820034
Testing, Inspection &Dispatch | DIS | 2023-11-26 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.20.4.24(EOT Crane) | 206820035
Receipt at Site | OTH | 2023-12-26 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4.24(EOT Crane) | 206820036
Self Power Hydraulic Aerial Working Platform | OTH | 2023-08-28 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4(Manufacturing, Testing and Dispatch) | 206820037
Manufacturing | MFG | 2023-08-28 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.4.25(Self Power Hydraulic Aerial Working Platform) | 206820038
Testing, Inspection &Dispatch | DIS | 2023-11-26 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.20.4.25(Self Power Hydraulic Aerial Working Platform) | 206820039
Receipt at Site | OTH | 2023-12-26 08:00 | 2024-01-14 17:00 |  |  |  |  | 1.14.20.4.25(Self Power Hydraulic Aerial Working Platform) | 206820040
Civil | CIV | 2023-05-30 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206820041
Switchyard Equipment foundation | CIV | 2023-05-30 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.20.5(Civil) | 206820042
GIS Building | CIV | 2023-05-30 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.20.5(Civil) | 206820043
Foundation | CIV | 2023-05-30 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.20.5.2(GIS Building) | 206820044
Columns & Superstructure | CIV | 2023-08-28 08:00 | 2023-11-25 17:00 |  |  |  |  | 1.14.20.5.2(GIS Building) | 206820045
Roof sheeting | CIV | 2023-11-26 08:00 | 2024-02-23 17:00 |  |  |  |  | 1.14.20.5.2(GIS Building) | 206820046
Brick work and finishing work | CIV | 2023-12-16 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.20.5.2(GIS Building) | 206820047
Control Room | CIV | 2023-09-07 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.20.5(Civil) | 206820048
EXCAVATION | CIV | 2023-09-07 08:00 | 2023-10-01 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820049
RCC in substructure including PCC | CIV | 2023-10-02 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820050
RCC/Structure work in superstructure | CIV | 2023-12-31 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820051
Brick Work & Plastering | CIV | 2024-05-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820052
Flooring | CIV | 2024-07-28 08:00 | 2024-09-10 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820053
Backfilling | CIV | 2024-09-11 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820054
Finishing works | CIV | 2024-09-26 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.20.5.3(Control Room) | 206820055
AHU Building | CIV | 2023-09-07 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.20.5(Civil) | 206820056
EXCAVATION | CIV | 2023-09-07 08:00 | 2023-10-01 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820057
RCC in substructure including PCC | CIV | 2023-10-02 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820058
RCC/Structure work in superstructure | CIV | 2023-12-31 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820059
Brick Work & Plastering | CIV | 2024-07-28 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820060
Flooring | CIV | 2024-09-26 08:00 | 2024-11-09 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820061
Backfilling | CIV | 2024-11-10 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820062
Finishing works | CIV | 2024-11-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.20.5.4(AHU Building) | 206820063
and Dispatch | OTH | 2023-09-18 08:00 | 2025-08-04 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206820064
Towers and Gantry | ERC | 2023-09-18 08:00 | 2024-01-15 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820065
400 kV Reactor | ERC | 2024-05-01 08:00 | 2024-08-08 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820066
EOT Crane | ERC | 2024-02-24 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820067
Air Conditioning and Ventilation System | ERC | 2025-01-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820068
Fire Protection System | ERC | 2024-04-04 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820069
Illumination System | ERC | 2023-12-26 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820070
LT System (Including Battery and Battery Chargers) (Control room Building) | ERC | 2024-11-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820071
Outdoor Equipments (LA, BPI, CVT, WT) (Outdoor) | ERC | 2023-12-26 08:00 | 2024-03-14 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820072
400 kV Control & Relay Panel & SAS (Control room Building) | ERC | 2024-11-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820073
FOTE (Control room Building) | ERC | 2024-11-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820074
Auxiliary Transformer (Outdoor) | ERC | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820075
Readiness of Priority bays for charging for Start-up Power(400 kV Priority area for start up power including priority bays with bus bar covering GIS & AIS system) | ERC | 2024-08-22 08:00 | 2025-04-26 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820076
400 kV Balance Area | ERC | 2025-04-27 08:00 | 2025-08-04 17:00 |  |  |  |  | 1.14.20.6(and Dispatch) | 206820077
Readiness of line bays, Generator Transformer Bay for Unit # 1, Coupler Bays, Transfer Bays etc. with Common | COM | 2025-08-05 08:00 | 2026-01-26 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206820078
Balance COF U#1 | ERC | 2026-01-27 08:00 | 2026-03-27 17:00 |  |  |  |  | 1.14.20(400kV Switchyard) | 206820079
Station C&I | ERC | 2025-02-03 08:00 | 2026-06-17 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820080
Readiness of DDCMIS for Water System & Make-Up Water System | ERC | 2025-02-03 08:00 | 2025-03-26 17:00 |  |  |  |  | 1.14.21(Station C&I) | 206820081
Readiness of DDCMIS Systems required for Boiler Light Up | ERC | 2025-02-03 08:00 | 2025-11-09 17:00 |  |  |  |  | 1.14.21(Station C&I) | 206820082
Readiness of DDCMIS For Main Plant & Standalone Common System | COM | 2025-02-03 08:00 | 2026-01-08 17:00 |  |  |  |  | 1.14.21(Station C&I) | 206820083
Readiness of DDCMIS for AHP & CHP and other balance works | ERC | 2025-02-03 08:00 | 2026-02-17 17:00 |  |  |  |  | 1.14.21(Station C&I) | 206820084
Completion of facilities for C&I system | ERC | 2026-02-18 08:00 | 2026-06-17 17:00 |  |  |  |  | 1.14.21(Station C&I) | 206820085
Chlorine Dioxide dosing system | OTH | 2022-12-26 08:00 | 2025-08-13 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820086
Rel of Dwg for CW Chlorination system | PE - RFC | 2024-06-04 08:00 | 2024-06-04 17:00 |  |  |  |  | 1.14.22(Chlorine Dioxide dosing system) | 206820087
Award of Execution Agency | PRC | 2022-12-26 08:00 | 2023-05-25 17:00 |  |  |  |  | 1.14.22(Chlorine Dioxide dosing system) | 206820088
Enquiry | ENQ | 2022-12-26 08:00 | 2022-12-26 17:00 |  |  |  |  | 1.14.22.2(Award of Execution Agency) | 206820089
PO Placement | ORD | 2022-12-27 08:00 | 2023-05-25 17:00 |  |  |  |  | 1.14.22.2(Award of Execution Agency) | 206820090
Civil | OTH | 2024-06-05 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.14.22(Chlorine Dioxide dosing system) | 206820091
Excavation | CIV | 2024-06-05 08:00 | 2024-07-04 17:00 |  |  |  |  | 1.14.22.3( Civil) | 206820092
RCC Sub-structure | CIV | 2024-07-05 08:00 | 2024-12-01 17:00 |  |  |  |  | 1.14.22.3( Civil) | 206820093
RCC Super-Structure | CIV | 2024-12-02 08:00 | 2025-03-31 17:00 |  |  |  |  | 1.14.22.3( Civil) | 206820094
Supply | OTH | 2023-11-22 08:00 | 2024-05-19 17:00 |  |  |  |  | 1.14.22(Chlorine Dioxide dosing system) | 206820095
Tanks | OTH | 2023-11-22 08:00 | 2024-03-20 17:00 |  |  |  |  | 1.14.22.4(Supply) | 206820096
Pumps | OTH | 2023-11-22 08:00 | 2024-05-19 17:00 |  |  |  |  | 1.14.22.4(Supply) | 206820097
Pipes, fittings & Valves | OTH | 2023-11-22 08:00 | 2024-05-19 17:00 |  |  |  |  | 1.14.22.4(Supply) | 206820098
Erection | ERC | 2025-04-01 08:00 | 2025-08-13 17:00 |  |  |  |  | 1.14.22(Chlorine Dioxide dosing system) | 206820099
Tanks | ERC | 2025-04-01 08:00 | 2025-05-15 17:00 |  |  |  |  | 1.14.22.5(Erection) | 206820100
Pumps | ERC | 2025-05-16 08:00 | 2025-06-14 17:00 |  |  |  |  | 1.14.22.5(Erection) | 206820101
INTERCONNECTING PIPING & FITTINGS | ERC | 2025-06-15 08:00 | 2025-07-14 17:00 |  |  |  |  | 1.14.22.5(Erection) | 206820102
Commissioning | COM | 2025-07-15 08:00 | 2025-08-13 17:00 |  |  |  |  | 1.14.22.5(Erection) | 206820103
Pipe Rack and Cable Trestle, Station Piping | OTH | 2023-08-23 08:00 | 2026-01-29 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820104
Release of Drawings | PE - RFC | 2023-08-23 08:00 | 2023-08-23 17:00 |  |  |  |  | 1.14.23(Pipe Rack and Cable Trestle, Station Piping) | 206820105
Award of Execution Agency | PRC | 2023-08-23 08:00 | 2024-01-20 17:00 |  |  |  |  | 1.14.23(Pipe Rack and Cable Trestle, Station Piping) | 206820106
NIT | ENQ | 2023-08-23 08:00 | 2023-08-23 17:00 |  |  |  |  | 1.14.23.2(Award of Execution Agency) | 206820107
PO Placement | ORD | 2023-08-24 08:00 | 2024-01-20 17:00 |  |  |  |  | 1.14.23.2(Award of Execution Agency) | 206820108
Civil | CIV | 2024-02-20 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.23(Pipe Rack and Cable Trestle, Station Piping) | 206820109
Excavation | CIV | 2024-02-20 08:00 | 2024-03-20 17:00 |  |  |  |  | 1.14.23.3( Civil) | 206820110
Pedestal footing- Priority path | OTH | 2024-03-21 08:00 | 2024-06-18 17:00 |  |  |  |  | 1.14.23.3( Civil) | 206820111
Pedestal footing- Balance | OTH | 2024-06-19 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.23.3( Civil) | 206820112
Supply | OTH | 2024-09-07 08:00 | 2025-03-05 17:00 |  |  |  |  | 1.14.23(Pipe Rack and Cable Trestle, Station Piping) | 206820113
Cable trestle | OTH | 2024-09-07 08:00 | 2025-01-04 17:00 |  |  |  |  | 1.14.23.4(Supply) | 206820114
Pipe rack | OTH | 2024-09-07 08:00 | 2025-03-05 17:00 |  |  |  |  | 1.14.23.4(Supply) | 206820115
Erection | ERC | 2025-04-05 08:00 | 2026-01-29 17:00 |  |  |  |  | 1.14.23(Pipe Rack and Cable Trestle, Station Piping) | 206820116
Pipe rack, Cable trestle, Piping & Cable laying | ERC | 2025-04-05 08:00 | 2026-01-29 17:00 |  |  |  |  | 1.14.23.5(Erection) | 206820117
Readiness for HT | ERC | 2025-05-05 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.23.5(Erection) | 206820118
Readiness for BLU | ERC | 2025-07-04 08:00 | 2025-09-01 17:00 |  |  |  |  | 1.14.23.5(Erection) | 206820119
Readiness for Full loading | ERC | 2025-09-02 08:00 | 2026-01-29 17:00 |  |  |  |  | 1.14.23.5(Erection) | 206820120
Misc. Elevators | OTH | 2023-09-03 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820121
Supply | OTH | 2023-09-03 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.24(Misc. Elevators) | 206820122
Elevator | OTH | 2023-09-03 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.24.1(Supply) | 206820123
Ordering | OTH | 2023-09-03 08:00 | 2023-12-01 17:00 |  |  |  |  | 1.14.24.1.1(Elevator) | 206820124
Detailed Engineering | ENG | 2023-12-02 08:00 | 2024-04-29 17:00 |  |  |  |  | 1.14.24.1.1(Elevator) | 206820125
Manufacturing | MFG | 2024-04-30 08:00 | 2024-09-26 17:00 |  |  |  |  | 1.14.24.1.1(Elevator) | 206820126
Dispatch | DIS | 2024-09-27 08:00 | 2024-10-26 17:00 |  |  |  |  | 1.14.24.1.1(Elevator) | 206820127
Civil | OTH | 2024-09-24 08:00 | 2025-05-21 17:00 |  |  |  |  | 1.14.24.1(Supply) | 206820128
Readiness of Elevator Pit & Shaft | OTH | 2024-09-24 08:00 | 2025-05-21 17:00 |  |  |  |  | 1.14.24.1.2(Civil) | 206820129
Erection | ERC | 2025-05-22 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.24.1(Supply) | 206820130
Erection and commissioning of Elevator | COM | 2025-05-22 08:00 | 2025-11-17 17:00 |  |  |  |  | 1.14.24.1.3(Erection) | 206820131
Lifting Equipments | OTH | 2023-05-15 08:00 | 2026-06-03 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820132
Supply | SUP | 2023-05-15 08:00 | 2026-06-03 17:00 |  |  |  |  | 1.14.25(Lifting Equipments) | 206820133
Lifting Tackles (PG-99) | SUP | 2023-05-15 08:00 | 2025-07-28 17:00 |  |  |  | PG99 | 1.14.25.1(Supply) | 206820134
MISC CHAIN PULLEY BLOCKS (PGMA-99099) | SUP | 2023-10-21 08:00 | 2025-07-28 17:00 |  |  |  | 99099 | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820135
Ordering & Engineering | ENG | 2023-10-21 08:00 | 2024-10-15 17:00 |  |  |  | 99099 | 1.14.25.1.1.1(MISC CHAIN PULLEY BLOCKS (PGMA-99099)) | 206820136
Manufacturing | MFG | 2024-10-16 08:00 | 2025-07-28 17:00 |  |  |  | 99099 | 1.14.25.1.1.1(MISC CHAIN PULLEY BLOCKS (PGMA-99099)) | 206820137
Dispatch | DIS | 2025-04-30 08:00 | 2025-05-29 17:00 |  |  |  | 99099 | 1.14.25.1.1.1(MISC CHAIN PULLEY BLOCKS (PGMA-99099)) | 206820138
FAN HANDLING EQUIPMENT (PGMA-99100) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 99100 | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820139
Ordering & Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 99100 | 1.14.25.1.1.2(FAN HANDLING EQUIPMENT (PGMA-99100)) | 206820140
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 99100 | 1.14.25.1.1.2(FAN HANDLING EQUIPMENT (PGMA-99100)) | 206820141
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 99100 | 1.14.25.1.1.2(FAN HANDLING EQUIPMENT (PGMA-99100)) | 206820142
CIR PUMP / FEED PUMP HANDLING EQUIPMENT (PGMA-99300) | SUP | 2023-05-24 08:00 | 2024-12-26 17:00 |  |  |  | 99300 | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820143
Ordering & Engineering | ENG | 2023-05-24 08:00 | 2024-02-17 17:00 |  |  |  | 99300 | 1.14.25.1.1.3(CIR PUMP / FEED PUMP HANDLING EQUIPMENT (PGMA-99300)) | 206820144
Manufacturing | MFG | 2024-02-18 08:00 | 2024-11-26 17:00 |  |  |  | 99300 | 1.14.25.1.1.3(CIR PUMP / FEED PUMP HANDLING EQUIPMENT (PGMA-99300)) | 206820145
Dispatch | DIS | 2024-11-27 08:00 | 2024-12-26 17:00 |  |  |  | 99300 | 1.14.25.1.1.3(CIR PUMP / FEED PUMP HANDLING EQUIPMENT (PGMA-99300)) | 206820146
AIRHEATER,STEAMCOIL AIRHEATER HANDLG E (PGMA-99400) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 99400 | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820147
Ordering & Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 99400 | 1.14.25.1.1.4(AIRHEATER,STEAMCOIL AIRHEATER HANDLG E (PGMA-99400)) | 206820148
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 99400 | 1.14.25.1.1.4(AIRHEATER,STEAMCOIL AIRHEATER HANDLG E (PGMA-99400)) | 206820149
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 99400 | 1.14.25.1.1.4(AIRHEATER,STEAMCOIL AIRHEATER HANDLG E (PGMA-99400)) | 206820150
FURNACE CRADLE -WALL COVERAGE ELECTR (PGMA-99512) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 99512 | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820151
Ordering & Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 99512 | 1.14.25.1.1.5(FURNACE CRADLE -WALL COVERAGE ELECTR (PGMA-99512)) | 206820152
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 99512 | 1.14.25.1.1.5(FURNACE CRADLE -WALL COVERAGE ELECTR (PGMA-99512)) | 206820153
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 99512 | 1.14.25.1.1.5(FURNACE CRADLE -WALL COVERAGE ELECTR (PGMA-99512)) | 206820154
FO SYSTEM HANDLING EQUIPMENT (PGMA-99600) | SUP | 2023-07-23 08:00 | 2025-02-27 17:00 |  |  |  | 99600 | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820155
Ordering & Engineering | ENG | 2023-07-23 08:00 | 2024-04-17 17:00 |  |  |  | 99600 | 1.14.25.1.1.6(FO SYSTEM HANDLING EQUIPMENT (PGMA-99600)) | 206820156
Manufacturing | MFG | 2024-04-18 08:00 | 2025-01-28 17:00 |  |  |  | 99600 | 1.14.25.1.1.6(FO SYSTEM HANDLING EQUIPMENT (PGMA-99600)) | 206820157
Dispatch | DIS | 2025-01-29 08:00 | 2025-02-27 17:00 |  |  |  | 99600 | 1.14.25.1.1.6(FO SYSTEM HANDLING EQUIPMENT (PGMA-99600)) | 206820158
BOI-PEM - CHAIN PULLEY BLOCK | SUP | 2023-12-05 08:00 | 2025-01-27 17:00 |  |  |  |  | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820159
Ordering | ORD | 2023-12-05 08:00 | 2024-03-03 17:00 |  |  |  |  | 1.14.25.1.1.7(BOI-PEM - CHAIN PULLEY BLOCK ) | 206820160
Detailed Engineering | ENG | 2024-03-04 08:00 | 2024-07-31 17:00 |  |  |  |  | 1.14.25.1.1.7(BOI-PEM - CHAIN PULLEY BLOCK ) | 206820161
Manufacturing | MFG | 2024-08-01 08:00 | 2024-12-28 17:00 |  |  |  |  | 1.14.25.1.1.7(BOI-PEM - CHAIN PULLEY BLOCK ) | 206820162
Dispatch | DIS | 2024-12-29 08:00 | 2025-01-27 17:00 |  |  |  |  | 1.14.25.1.1.7(BOI-PEM - CHAIN PULLEY BLOCK ) | 206820163
BOI-PEM - ELECTRIC HOIST | SUP | 2023-12-01 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820164
Ordering | ORD | 2023-12-01 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.14.25.1.1.8(BOI-PEM - ELECTRIC HOIST ) | 206820165
Detailed Engineering | ENG | 2024-02-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.25.1.1.8(BOI-PEM - ELECTRIC HOIST ) | 206820166
Manufacturing | MFG | 2024-07-28 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.25.1.1.8(BOI-PEM - ELECTRIC HOIST ) | 206820167
Dispatch | DIS | 2024-12-25 08:00 | 2025-01-23 17:00 |  |  |  |  | 1.14.25.1.1.8(BOI-PEM - ELECTRIC HOIST ) | 206820168
BOI-PEM - D/G EOT CRANE (UPTO 100 T) | SUP | 2023-05-15 08:00 | 2024-07-07 17:00 |  |  |  |  | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820169
Ordering | ORD | 2023-05-15 08:00 | 2023-08-12 17:00 |  |  |  |  | 1.14.25.1.1.9(BOI-PEM - D/G EOT CRANE (UPTO 100 T) ) | 206820170
Detailed Engineering | ENG | 2023-08-13 08:00 | 2024-01-09 17:00 |  |  |  |  | 1.14.25.1.1.9(BOI-PEM - D/G EOT CRANE (UPTO 100 T) ) | 206820171
Manufacturing | MFG | 2024-01-10 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.14.25.1.1.9(BOI-PEM - D/G EOT CRANE (UPTO 100 T) ) | 206820172
Dispatch | DIS | 2024-06-08 08:00 | 2024-07-07 17:00 |  |  |  |  | 1.14.25.1.1.9(BOI-PEM - D/G EOT CRANE (UPTO 100 T) ) | 206820173
BOI-PEM - Single Girder EOT / HOT Misc. Cranes | SUP | 2023-11-11 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.14.25.1.1(Lifting Tackles (PG-99)) | 206820174
Ordering | ORD | 2023-11-11 08:00 | 2024-02-08 17:00 |  |  |  |  | 1.14.25.1.1.10(BOI-PEM - Single Girder EOT / HOT Misc. Cranes ) | 206820175
Detailed Engineering | ENG | 2024-02-09 08:00 | 2024-07-07 17:00 |  |  |  |  | 1.14.25.1.1.10(BOI-PEM - Single Girder EOT / HOT Misc. Cranes ) | 206820176
Manufacturing | MFG | 2024-07-08 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.14.25.1.1.10(BOI-PEM - Single Girder EOT / HOT Misc. Cranes ) | 206820177
Dispatch | DIS | 2024-12-05 08:00 | 2025-01-03 17:00 |  |  |  |  | 1.14.25.1.1.10(BOI-PEM - Single Girder EOT / HOT Misc. Cranes ) | 206820178
Erection | ERC | 2025-05-30 08:00 | 2026-06-03 17:00 |  |  |  |  | 1.14.25.1(Supply) | 206820179
E&C of Lifting equipments | ERC | 2025-05-30 08:00 | 2026-06-03 17:00 |  |  |  |  | 1.14.25.1.2(Erection) | 206820180
Misc. Building | OTH | 2023-01-05 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820181
NON PLANT Building | OTH | 2023-01-05 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26(Misc. Building) | 206820182
Rel of Dwg for Administration Building | PE - RFC | 2024-01-10 08:00 | 2024-01-10 17:00 |  |  |  | PCE-09700 | 1.14.26.1(NON PLANT Building) | 206820183
Rel of Dwg for Construction office | PE - RFC | 2023-01-05 08:00 | 2023-01-05 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820184
Rel of Dwg for Canteen Building | PE - RFC | 2024-08-27 08:00 | 2024-08-27 17:00 |  |  |  | PCE-04300 | 1.14.26.1(NON PLANT Building) | 206820185
Rel of Dwg for O&M Workshop Building | PE - RFC | 2024-07-08 08:00 | 2024-07-08 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820186
Rel of Dwg for Gate Complex along with CISF Building | PE - RFC | 2023-06-04 08:00 | 2023-06-04 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820187
Rel of Dwg for Fire station building with Drill Tower | PE - RFC | 2023-11-11 08:00 | 2023-11-11 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820188
Rel of Dwg for CHP office cum Workshop Building | PE - RFC | 2023-07-24 08:00 | 2023-07-24 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820189
Rel of Dwg for Dozer Shed | PE - RFC | 2025-03-15 08:00 | 2025-03-15 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820190
Gate Complex along with CISF Building | CIV | 2024-01-16 08:00 | 2024-09-20 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820191
TIME OFFICE & SECURITY OFFICE: EXCAVATION | CIV | 2024-01-16 08:00 | 2024-01-30 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820192
TIME OFFICE & SECURITY OFFICE:RCC in substructure including PCC | CIV | 2024-01-31 08:00 | 2024-02-19 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820193
TIME OFFICE & SECURITY OFFICE: RCC in superstructure | CIV | 2024-02-20 08:00 | 2024-04-19 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820194
TIME OFFICE & SECURITY OFFICE: Brick Work & Plastering | CIV | 2024-05-04 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820195
TIME OFFICE & SECURITY OFFICE: Flooring | CIV | 2024-06-18 08:00 | 2024-07-07 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820196
TIME OFFICE & SECURITY OFFICE: Backfilling | CIV | 2024-07-08 08:00 | 2024-07-22 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820197
TIME OFFICE & SECURITY OFFICE: Finishing works | CIV | 2024-07-23 08:00 | 2024-09-20 17:00 |  |  |  |  | 1.14.26.1.9(Gate Complex along with CISF Building) | 206820198
Construction office | CIV | 2023-01-06 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820199
EXCAVATION | CIV | 2023-01-06 08:00 | 2023-01-20 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820200
RCC in substructure including PCC | CIV | 2023-01-21 08:00 | 2023-02-04 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820201
RCC in superstructure | CIV | 2023-02-05 08:00 | 2023-03-06 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820202
Brick Work & Plastering | CIV | 2023-03-21 08:00 | 2023-04-19 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820203
Flooring | CIV | 2023-04-20 08:00 | 2023-05-04 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820204
Backfilling | CIV | 2023-05-05 08:00 | 2023-05-14 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820205
Finishing works | CIV | 2023-05-15 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.26.1.10(Construction office) | 206820206
CANTEEN BUILDING | CIV | 2024-09-02 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820207
EXCAVATION | CIV | 2024-09-02 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820208
RCC in substructure including PCC | CIV | 2024-09-22 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820209
RCC in superstructure | CIV | 2024-10-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820210
Brick Work & Plastering | CIV | 2025-01-15 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820211
Flooring | CIV | 2025-03-11 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820212
Backfilling | CIV | 2025-04-05 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820213
Finishing works | CIV | 2025-04-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1.11( CANTEEN BUILDING) | 206820214
Fire Station building and Drill Tower | CIV | 2024-09-02 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820215
EXCAVATION | CIV | 2024-09-02 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820216
RCC in substructure including PCC | CIV | 2024-09-22 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820217
RCC in superstructure | CIV | 2024-10-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820218
Brick Work & Plastering | CIV | 2025-01-15 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820219
Flooring | CIV | 2025-03-11 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820220
Backfilling | CIV | 2025-04-05 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820221
Finishing works | CIV | 2025-04-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1.12(Fire Station building and Drill Tower) | 206820222
FQA Lab building | CIV | 2024-09-02 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820223
EXCAVATION | CIV | 2024-09-02 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820224
RCC in substructure including PCC | CIV | 2024-09-22 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820225
RCC in superstructure | CIV | 2024-10-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820226
Brick Work & Plastering | CIV | 2025-01-15 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820227
Flooring | CIV | 2025-03-11 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820228
Backfilling | CIV | 2025-04-05 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820229
Finishing works | CIV | 2025-04-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1.13(FQA Lab building) | 206820230
CHP office cum Workshop Building | CIV | 2024-09-02 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820231
EXCAVATION | CIV | 2024-09-02 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820232
RCC in substructure including PCC | CIV | 2024-09-22 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820233
RCC in superstructure | CIV | 2024-10-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820234
Brick Work & Plastering | CIV | 2025-01-15 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820235
Flooring | CIV | 2025-03-11 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820236
Backfilling | CIV | 2025-04-05 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820237
Finishing works | CIV | 2025-04-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1.14(CHP office cum Workshop Building) | 206820238
Administration Building | CIV | 2024-09-02 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820239
EXCAVATION | CIV | 2024-09-02 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820240
RCC in substructure including PCC | CIV | 2024-09-22 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820241
RCC in superstructure | CIV | 2024-10-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820242
Brick Work & Plastering | CIV | 2025-01-15 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820243
Flooring | CIV | 2025-03-11 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820244
Backfilling | CIV | 2025-04-05 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820245
Finishing works | CIV | 2025-04-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1.15(Administration Building) | 206820246
O&M Workshop Building | CIV | 2024-09-02 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1(NON PLANT Building) | 206820247
EXCAVATION | CIV | 2024-09-02 08:00 | 2024-09-21 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820248
RCC in substructure including PCC | CIV | 2024-09-22 08:00 | 2024-10-16 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820249
RCC in superstructure | CIV | 2024-10-17 08:00 | 2025-01-14 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820250
Brick Work & Plastering | CIV | 2025-01-15 08:00 | 2025-03-10 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820251
Flooring | CIV | 2025-03-11 08:00 | 2025-04-04 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820252
Backfilling | CIV | 2025-04-05 08:00 | 2025-04-19 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820253
Finishing works | CIV | 2025-04-20 08:00 | 2025-07-03 17:00 |  |  |  |  | 1.14.26.1.16(O&M Workshop Building) | 206820254
1.4 MWp Solar Rooftop Pkg | OTH | 2024-02-19 08:00 | 2026-06-21 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820255
Engineering | ENG | 2024-02-19 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.27(1.4 MWp Solar Rooftop Pkg) | 206820256
Submission of quality plan | ENG | 2024-02-19 08:00 | 2024-03-09 17:00 |  |  |  |  | 1.14.27.1(Engineering) | 206820257
Submission of field quality plan | ENG | 2024-03-10 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.27.1(Engineering) | 206820258
Subcontracting & Vendor List Approval | ENG | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.27.1(Engineering) | 206820259
Drawing Submission from BHEL | ENG | 2024-04-29 08:00 | 2024-05-13 17:00 |  |  |  |  | 1.14.27.1(Engineering) | 206820260
Drawing Approval from customer | ENG | 2024-05-14 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.27.1(Engineering) | 206820261
Procurement, Manufacturing & Dispatch | MFG | 2024-06-28 08:00 | 2026-02-09 17:00 |  |  |  |  | 1.14.27(1.4 MWp Solar Rooftop Pkg) | 206820262
Sub-tendering for SPV Modules | OTH | 2024-06-28 08:00 | 2024-08-11 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820263
Placement of Order on SPV modules OEM | OTH | 2024-08-12 08:00 | 2024-08-18 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820264
Manufacturing of SPV Modules | MFG | 2024-08-19 08:00 | 2024-10-17 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820265
Inspection of SPV Modules | MFG | 2024-10-18 08:00 | 2024-11-01 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820266
Dispatch of SPV modules | DIS | 2024-11-02 08:00 | 2024-12-01 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820267
Procurement of Inverters | PRC | 2024-12-02 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820268
Dispatch of Inverters | DIS | 2025-01-16 08:00 | 2025-03-16 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820269
Procurement of MMS | PRC | 2025-03-17 08:00 | 2025-05-15 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820270
Inspection &Dispatch | DIS | 2025-05-16 08:00 | 2025-07-14 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820271
Procurement of Transformers | PRC | 2025-07-15 08:00 | 2025-09-12 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820272
Inspection &Dispatch | DIS | 2025-09-13 08:00 | 2025-10-27 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820273
Procurement of BOS | PRC | 2025-10-28 08:00 | 2025-12-26 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820274
Dispatch of BOS | DIS | 2025-12-27 08:00 | 2026-02-09 17:00 |  |  |  |  | 1.14.27.2(Procurement, Manufacturing & Dispatch) | 206820275
Site Mobilisation | OTH | 2024-04-06 08:00 | 2024-04-20 17:00 |  |  |  |  | 1.14.27(1.4 MWp Solar Rooftop Pkg) | 206820276
Erection & Commissioning | OTH | 2025-01-15 08:00 | 2026-06-21 17:00 |  |  |  |  | 1.14.27(1.4 MWp Solar Rooftop Pkg) | 206820277
Civil Work - Structures & buildings | CIV | 2025-01-15 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820278
Civil Work -Others | CIV | 2025-01-15 08:00 | 2025-04-14 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820279
415V/11 kV Substation Erection | ERC | 2025-11-02 08:00 | 2025-12-31 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820280
Steel Structures Erection | ERC | 2025-11-02 08:00 | 2026-03-01 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820281
Modules Laying | ERC | 2026-01-16 08:00 | 2026-05-05 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820282
Cable Laying | ERC | 2026-01-16 08:00 | 2026-05-05 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820283
Inverters Erection | ERC | 2026-01-16 08:00 | 2026-02-14 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820284
BOS Erection | ERC | 2026-01-16 08:00 | 2026-05-15 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820285
Commissioning | COM | 2026-05-16 08:00 | 2026-06-14 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820286
Synchronisation | ERC | 2026-06-15 08:00 | 2026-06-21 17:00 |  |  |  |  | 1.14.27.4(Erection & Commissioning) | 206820287
Aux Boiler | OTH | 2023-04-29 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820288
Engineering (LO, GA and P&ID) | ENG | 2023-04-29 08:00 | 2023-10-25 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820289
Foundation Materials and Structure | CIV | 2023-10-26 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820290
Release of MIs | ENG | 2023-10-26 08:00 | 2023-12-24 17:00 |  |  |  |  | 1.14.28.2(Foundation Materials and Structure) | 206820291
Engineering Documents | ENG | 2023-10-26 08:00 | 2024-01-03 17:00 |  |  |  |  | 1.14.28.2(Foundation Materials and Structure) | 206820292
Release of Purchase Orders | PRC | 2023-12-25 08:00 | 2024-02-22 17:00 |  |  |  |  | 1.14.28.2(Foundation Materials and Structure) | 206820293
Receipt of material at HPVP | OTH | 2024-02-23 08:00 | 2024-06-01 17:00 |  |  |  |  | 1.14.28.2(Foundation Materials and Structure) | 206820294
Fabrication | OTH | 2024-06-02 08:00 | 2024-09-29 17:00 |  |  |  |  | 1.14.28.2(Foundation Materials and Structure) | 206820295
Dispatches | DIS | 2024-08-21 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.28.2(Foundation Materials and Structure) | 206820296
Boiler Drums, PG 04 | OTH | 2024-01-04 08:00 | 2025-07-31 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820297
Release of MIs | ENG | 2024-01-04 08:00 | 2024-03-18 17:00 |  |  |  |  | 1.14.28.3(Boiler Drums, PG 04) | 206820298
Engineering Documents | ENG | 2024-03-19 08:00 | 2024-04-17 17:00 |  |  |  |  | 1.14.28.3(Boiler Drums, PG 04) | 206820299
Release of Purchase Orders | PRC | 2024-03-19 08:00 | 2024-05-17 17:00 |  |  |  |  | 1.14.28.3(Boiler Drums, PG 04) | 206820300
Receipt of material at HPVP | OTH | 2024-05-18 08:00 | 2024-09-14 17:00 |  |  |  |  | 1.14.28.3(Boiler Drums, PG 04) | 206820301
Shop Fabrication | OTH | 2024-09-15 08:00 | 2025-05-22 17:00 |  |  |  |  | 1.14.28.3(Boiler Drums, PG 04) | 206820302
Dispatches | DIS | 2025-05-23 08:00 | 2025-07-31 17:00 |  |  |  |  | 1.14.28.3(Boiler Drums, PG 04) | 206820303
Pressure Parts, PG 06,07,08,09,10,11,12,19 | OTH | 2024-02-03 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820304
Release of MIs | ENG | 2024-02-03 08:00 | 2024-04-17 17:00 |  |  |  |  | 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | 206820305
Engineering Documents | ENG | 2024-04-18 08:00 | 2024-05-17 17:00 |  |  |  |  | 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | 206820306
Release of Purchase Orders | PRC | 2024-04-18 08:00 | 2024-06-16 17:00 |  |  |  |  | 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | 206820307
Receipt of material at HPVP | OTH | 2024-06-17 08:00 | 2024-10-14 17:00 |  |  |  |  | 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | 206820308
Shop Fabrication | OTH | 2024-10-15 08:00 | 2025-06-27 17:00 |  |  |  |  | 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | 206820309
Dispatches | DIS | 2025-06-28 08:00 | 2025-09-25 17:00 |  |  |  |  | 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | 206820310
Soot Blowers Valves & Fittings, PG 20,21 | OTH | 2024-04-18 08:00 | 2025-02-16 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820311
Release of MIs | ENG | 2024-04-18 08:00 | 2024-07-11 17:00 |  |  |  |  | 1.14.28.5(Soot Blowers Valves & Fittings, PG 20,21) | 206820312
Engineering Documents | ENG | 2024-07-12 08:00 | 2024-08-10 17:00 |  |  |  |  | 1.14.28.5(Soot Blowers Valves & Fittings, PG 20,21) | 206820313
Release of Purchase Orders | PRC | 2024-07-12 08:00 | 2024-08-20 17:00 |  |  |  |  | 1.14.28.5(Soot Blowers Valves & Fittings, PG 20,21) | 206820314
Receipt | OTH | 2024-08-21 08:00 | 2025-02-16 17:00 |  |  |  |  | 1.14.28.5(Soot Blowers Valves & Fittings, PG 20,21) | 206820315
Fuel Firing System, PG 41, 42 | OTH | 2024-04-18 08:00 | 2025-07-05 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820316
Release of MIs | ENG | 2024-04-18 08:00 | 2024-06-16 17:00 |  |  |  |  | 1.14.28.6(Fuel Firing System, PG 41, 42) | 206820317
Engineering Documents | ENG | 2024-06-17 08:00 | 2024-07-26 17:00 |  |  |  |  | 1.14.28.6(Fuel Firing System, PG 41, 42) | 206820318
Release of Purchase Orders | ENG | 2024-06-17 08:00 | 2024-08-15 17:00 |  |  |  |  | 1.14.28.6(Fuel Firing System, PG 41, 42) | 206820319
Receipt of material at HPVP | OTH | 2024-08-16 08:00 | 2024-11-13 17:00 |  |  |  |  | 1.14.28.6(Fuel Firing System, PG 41, 42) | 206820320
Fabrication | OTH | 2024-11-14 08:00 | 2025-06-21 17:00 |  |  |  |  | 1.14.28.6(Fuel Firing System, PG 41, 42) | 206820321
Dispatches | DIS | 2025-06-22 08:00 | 2025-07-05 17:00 |  |  |  |  | 1.14.28.6(Fuel Firing System, PG 41, 42) | 206820322
Ducts, PG 48 | OTH | 2024-06-17 08:00 | 2025-03-17 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820323
Release of MIs | ENG | 2024-06-17 08:00 | 2024-07-16 17:00 |  |  |  |  | 1.14.28.7(Ducts, PG 48) | 206820324
Engineering Documents | ENG | 2024-07-17 08:00 | 2024-08-15 17:00 |  |  |  |  | 1.14.28.7(Ducts, PG 48) | 206820325
Release of Purchase Orders | PRC | 2024-07-17 08:00 | 2024-09-14 17:00 |  |  |  |  | 1.14.28.7(Ducts, PG 48) | 206820326
Receipt of material at HPVP | OTH | 2024-09-15 08:00 | 2024-11-03 17:00 |  |  |  |  | 1.14.28.7(Ducts, PG 48) | 206820327
Fabrication | OTH | 2024-11-04 08:00 | 2025-03-03 17:00 |  |  |  |  | 1.14.28.7(Ducts, PG 48) | 206820328
Dispatches | DIS | 2025-03-04 08:00 | 2025-03-17 17:00 |  |  |  |  | 1.14.28.7(Ducts, PG 48) | 206820329
BAP - Damper FD fan outlet (PGMA 57013) | SUP | 2024-05-19 08:00 | 2025-06-22 17:00 |  |  |  | 57013 | 1.14.28(Aux Boiler) | 206820330
Engineering | ENG | 2024-05-19 08:00 | 2024-06-17 17:00 |  |  |  | 57013 | 1.14.28.8(BAP - Damper FD fan outlet (PGMA 57013)) | 206820331
Manufacturing | MFG | 2024-06-18 08:00 | 2025-02-22 17:00 |  |  |  | 57013 | 1.14.28.8(BAP - Damper FD fan outlet (PGMA 57013)) | 206820332
Dispatch | DIS | 2025-02-23 08:00 | 2025-06-22 17:00 |  |  |  | 57013 | 1.14.28.8(BAP - Damper FD fan outlet (PGMA 57013)) | 206820333
BAP - Aux fan (PG 56) | SUP | 2024-05-19 08:00 | 2025-06-22 17:00 |  |  |  | PG 56 | 1.14.28(Aux Boiler) | 206820334
Engineering | ENG | 2024-05-19 08:00 | 2024-06-17 17:00 |  |  |  | 56 | 1.14.28.9(BAP - Aux fan (PG 56)) | 206820335
Manufacturing | MFG | 2024-06-18 08:00 | 2025-02-22 17:00 |  |  |  | 56 | 1.14.28.9(BAP - Aux fan (PG 56)) | 206820336
Dispatch | DIS | 2025-02-23 08:00 | 2025-06-22 17:00 |  |  |  | 56 | 1.14.28.9(BAP - Aux fan (PG 56)) | 206820337
BAP - CYLINDRICAL Chimney (SELF SUPPORTED)- H-35 M (PG- 87) | SUP | 2024-05-19 08:00 | 2025-06-22 17:00 |  |  |  | 87 | 1.14.28(Aux Boiler) | 206820338
Engineering | ENG | 2024-05-19 08:00 | 2024-06-17 17:00 |  |  |  | 87 | 1.14.28.10(BAP - CYLINDRICAL Chimney (SELF SUPPORTED)- H-35 M (PG- 87)) | 206820339
Manufacturing | MFG | 2024-06-18 08:00 | 2025-02-22 17:00 |  |  |  | 87 | 1.14.28.10(BAP - CYLINDRICAL Chimney (SELF SUPPORTED)- H-35 M (PG- 87)) | 206820340
Dispatch | DIS | 2025-02-23 08:00 | 2025-06-22 17:00 |  |  |  | 87 | 1.14.28.10(BAP - CYLINDRICAL Chimney (SELF SUPPORTED)- H-35 M (PG- 87)) | 206820341
Lining & Insulation, PG 33 | SUP | 2024-07-17 08:00 | 2025-10-19 17:00 |  |  |  | 33 | 1.14.28(Aux Boiler) | 206820342
Release of MIs | ENG | 2024-07-17 08:00 | 2024-08-25 17:00 |  |  |  |  | 1.14.28.11(Lining & Insulation, PG 33) | 206820343
Engineering Documents | ENG | 2024-07-17 08:00 | 2024-11-13 17:00 |  |  |  |  | 1.14.28.11(Lining & Insulation, PG 33) | 206820344
Release of Purchase Orders | PRC | 2024-11-14 08:00 | 2025-01-22 17:00 |  |  |  |  | 1.14.28.11(Lining & Insulation, PG 33) | 206820345
Manufacturing & Dispatch | MFG | 2025-04-23 08:00 | 2025-10-19 17:00 |  |  |  |  | 1.14.28.11(Lining & Insulation, PG 33) | 206820346
Electrical and C&I, PG 95, 97 | OTH | 2024-07-17 08:00 | 2025-03-27 17:00 |  |  |  | 95/97 | 1.14.28(Aux Boiler) | 206820347
Release of MIs | ENG | 2024-07-17 08:00 | 2024-08-14 17:00 |  |  |  |  | 1.14.28.12(Electrical and C&I, PG 95, 97) | 206820348
Engineering Documents | ENG | 2024-08-15 08:00 | 2024-09-13 17:00 |  |  |  |  | 1.14.28.12(Electrical and C&I, PG 95, 97) | 206820349
Release of Purchase Orders | PRC | 2024-08-15 08:00 | 2024-11-12 17:00 |  |  |  |  | 1.14.28.12(Electrical and C&I, PG 95, 97) | 206820350
Manufacturing & Dispatch | MFG | 2024-11-13 08:00 | 2025-03-27 17:00 |  |  |  |  | 1.14.28.12(Electrical and C&I, PG 95, 97) | 206820351
Dispatch of piping & valves | DIS | 2024-11-29 08:00 | 2025-05-31 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820352
Foundation work | CIV | 2024-10-10 08:00 | 2025-04-27 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820353
Erection of pressure parts, drum, ducting | ERC | 2025-04-28 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820354
Erection of Chimney | ERC | 2025-04-28 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820355
Erection of fan, Gate and dampers | ERC | 2025-04-28 08:00 | 2025-11-13 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820356
Erection of piping valve | ERC | 2025-06-07 08:00 | 2025-09-24 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820357
Hydro test | ERC | 2025-09-25 08:00 | 2025-09-27 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820358
Insulation and refractory work | ERC | 2025-09-28 08:00 | 2025-10-27 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820359
Aux Boiler light up | COM | 2025-10-27 17:00 | 2025-10-27 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820360
Chemical cleaning | ERC | 2025-10-28 08:00 | 2025-10-30 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820361
Steam blowing of piping up to Aux PRDS | ERC | 2025-10-31 08:00 | 2025-11-14 17:00 |  |  |  |  | 1.14.28(Aux Boiler) | 206820362
FGD | OTH | 2022-09-27 08:00 | 2026-05-18 17:00 |  |  |  |  | 1.14(BOP Systems) | 206820363
Engineering | ENG | 2022-10-27 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820364
Basic Engineering | ENG | 2022-10-27 08:00 | 2023-02-23 17:00 |  |  |  |  | 1.14.29.1(Engineering) | 206820365
Detailed Engineering | ENG | 2023-02-24 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.29.1(Engineering) | 206820366
Gypsum Dewatering building | OTH | 2023-11-12 08:00 | 2026-01-20 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820367
Engineering &Supply | ENG | 2023-11-12 08:00 | 2025-05-29 17:00 |  |  |  |  | 1.14.29.2(Gypsum Dewatering building) | 206820368
FOUNDATION MATERIALS | SUP | 2024-02-14 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820369
Engineering | ENG | 2024-02-14 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.14.29.2.1.1(FOUNDATION MATERIALS) | 206820370
Manufacturing | MFG | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.2.1.1(FOUNDATION MATERIALS) | 206820371
Dispatch | DIS | 2024-04-29 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.2.1.1(FOUNDATION MATERIALS) | 206820372
COLUMNS | SUP | 2024-07-03 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820373
Engineering | ENG | 2024-07-03 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.2.1.2(COLUMNS) | 206820374
Manufacturing | MFG | 2024-08-17 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.29.2.1.2(COLUMNS) | 206820375
Dispatch | DIS | 2024-10-16 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.2.1.2(COLUMNS) | 206820376
BEAMS & BRACING | SUP | 2024-08-17 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820377
Engineering | ENG | 2024-08-17 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.29.2.1.3(BEAMS & BRACING) | 206820378
Manufacturing | MFG | 2024-10-01 08:00 | 2024-11-29 17:00 |  |  |  |  | 1.14.29.2.1.3(BEAMS & BRACING) | 206820379
Dispatch | DIS | 2024-11-30 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.2.1.3(BEAMS & BRACING) | 206820380
FLOOR & PLATFORMS | SUP | 2024-08-17 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820381
Engineering | ENG | 2024-08-17 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.29.2.1.4(FLOOR & PLATFORMS) | 206820382
Manufacturing | MFG | 2024-10-01 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.14.29.2.1.4(FLOOR & PLATFORMS) | 206820383
Dispatch | DIS | 2024-12-15 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.14.29.2.1.4(FLOOR & PLATFORMS) | 206820384
WALL BEAMS | SUP | 2024-08-17 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820385
Engineering | ENG | 2024-08-17 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.29.2.1.5(WALL BEAMS) | 206820386
Manufacturing | MFG | 2024-10-01 08:00 | 2024-11-29 17:00 |  |  |  |  | 1.14.29.2.1.5(WALL BEAMS) | 206820387
Dispatch | DIS | 2024-11-30 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.2.1.5(WALL BEAMS) | 206820388
STAIRS | SUP | 2024-10-01 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820389
Engineering | ENG | 2024-10-01 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.2.1.6(STAIRS) | 206820390
Manufacturing | MFG | 2024-11-15 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.14.29.2.1.6(STAIRS) | 206820391
Dispatch | DIS | 2025-01-14 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.14.29.2.1.6(STAIRS) | 206820392
MISC STRUCTURES | SUP | 2024-10-01 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820393
Engineering | ENG | 2024-10-01 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.2.1.7(MISC STRUCTURES) | 206820394
Manufacturing | MFG | 2024-11-15 08:00 | 2025-01-13 17:00 |  |  |  |  | 1.14.29.2.1.7(MISC STRUCTURES) | 206820395
Dispatch | DIS | 2025-01-14 08:00 | 2025-02-12 17:00 |  |  |  |  | 1.14.29.2.1.7(MISC STRUCTURES) | 206820396
Equipments (Sub-Assembly) | SUP | 2024-04-14 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820397
Enquiry & NIT | ENQ | 2024-04-14 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.2.1.8(Equipments (Sub-Assembly)) | 206820398
Ordering | ORD | 2024-04-29 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.2.1.8(Equipments (Sub-Assembly)) | 206820399
Detailed Engineering | ENG | 2024-05-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.2.1.8(Equipments (Sub-Assembly)) | 206820400
Dispatch | DIS | 2025-01-24 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.29.2.1.8(Equipments (Sub-Assembly)) | 206820401
LIME FEEDING/DOSING SYSTEM | SUP | 2023-11-12 08:00 | 2025-05-29 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820402
Enquiry & NIT | ENQ | 2023-11-12 08:00 | 2023-11-26 17:00 |  |  |  |  | 1.14.29.2.1.9(LIME FEEDING/DOSING SYSTEM) | 206820403
Ordering & Engineering | ORD | 2023-11-27 08:00 | 2024-06-13 17:00 |  |  |  |  | 1.14.29.2.1.9(LIME FEEDING/DOSING SYSTEM) | 206820404
Manufacturing | MFG | 2024-06-14 08:00 | 2024-12-10 17:00 |  |  |  |  | 1.14.29.2.1.9(LIME FEEDING/DOSING SYSTEM) | 206820405
Dispatch | DIS | 2024-12-11 08:00 | 2025-05-29 17:00 |  |  |  |  | 1.14.29.2.1.9(LIME FEEDING/DOSING SYSTEM) | 206820406
BOI-PEM- ELEVATORS | SUP | 2024-06-03 08:00 | 2025-05-17 17:00 |  |  |  |  | 1.14.29.2.1(Engineering &Supply) | 206820407
Enquiry & NIT | ENQ | 2024-06-03 08:00 | 2024-07-12 17:00 |  |  |  |  | 1.14.29.2.1.10(BOI-PEM- ELEVATORS) | 206820408
Ordering & Engineering | ORD | 2024-07-13 08:00 | 2024-09-09 17:00 |  |  |  |  | 1.14.29.2.1.10(BOI-PEM- ELEVATORS) | 206820409
Manufacturing | MFG | 2024-09-10 08:00 | 2025-01-07 17:00 |  |  |  |  | 1.14.29.2.1.10(BOI-PEM- ELEVATORS) | 206820410
Dispatch | DIS | 2025-04-18 08:00 | 2025-05-17 17:00 |  |  |  |  | 1.14.29.2.1.10(BOI-PEM- ELEVATORS) | 206820411
Civil Works | OTH | 2024-04-14 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.2(Gypsum Dewatering building) | 206820412
RFC Superstructure drawing | PE - RFC | 2024-06-03 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.14.29.2.2(Civil Works) | 206820413
RFC Civil Building foundation | PE - RFC | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.2.2(Civil Works) | 206820414
RFC Civil Equipment foundation | PE - RFC | 2024-06-03 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.14.29.2.2(Civil Works) | 206820415
Excavation | CIV | 2024-06-13 08:00 | 2024-07-12 17:00 |  |  |  |  | 1.14.29.2.2(Civil Works) | 206820416
RCC | CIV | 2024-07-13 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.2.2(Civil Works) | 206820417
Erection of Structure | ERC | 2025-06-08 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.2(Gypsum Dewatering building) | 206820418
FOUNDATION MATERIALSGYPSUM DEWAT | ERC | 2025-06-08 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820419
GYPSUM DEWAT COLUMNS | ERC | 2025-07-08 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820420
GYPSUM DEWAT BEAMS & BRACING | ERC | 2025-07-23 08:00 | 2025-10-20 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820421
GYPSUM DEWAT FLOOR & PLATFORMS | ERC | 2025-08-07 08:00 | 2025-10-20 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820422
GYPSUM DEWAT WALL BEAMS | ERC | 2025-07-23 08:00 | 2025-10-05 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820423
GYPSUM DEWAT STAIRS | ERC | 2025-08-22 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820424
GYPSUM DEWAT MISC STRUCTURES | ERC | 2025-08-22 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.2.3(Erection of Structure) | 206820425
Erection of Equipment | ERC | 2025-05-18 08:00 | 2025-11-21 17:00 |  |  |  |  | 1.14.29.2(Gypsum Dewatering building) | 206820426
Gypsum Dewatering Eqpt(Sub-Assembly of FGD) | ERC | 2025-08-07 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.2.4(Erection of Equipment) | 206820427
LIME FEEDING/DOSING SYSTEM | ERC | 2025-09-21 08:00 | 2025-11-19 17:00 |  |  |  |  | 1.14.29.2.4(Erection of Equipment) | 206820428
ELEVATORS | ERC | 2025-05-18 08:00 | 2025-11-21 17:00 |  |  |  |  | 1.14.29.2.4(Erection of Equipment) | 206820429
Commissioning of Equipments | COM | 2025-09-06 08:00 | 2026-01-20 17:00 |  |  |  |  | 1.14.29.2(Gypsum Dewatering building) | 206820430
Gypsum Dewatering Eqpt/(Sub-Assembly of FGD) | OTH | 2025-09-06 08:00 | 2026-01-03 17:00 |  |  |  |  | 1.14.29.2.5(Commissioning of Equipments) | 206820431
LIME FEEDING/DOSING SYSTEM | OTH | 2025-09-21 08:00 | 2026-01-18 17:00 |  |  |  |  | 1.14.29.2.5(Commissioning of Equipments) | 206820432
ELEVATORS | OTH | 2025-11-22 08:00 | 2026-01-20 17:00 |  |  |  |  | 1.14.29.2.5(Commissioning of Equipments) | 206820433
Ball Mill Building and Ball Mills | OTH | 2022-09-27 08:00 | 2025-05-07 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820434
Engineering &Supply | ENG | 2022-09-27 08:00 | 2024-10-29 17:00 |  |  |  |  | 1.14.29.3(Ball Mill Building and Ball Mills) | 206820435
HYD - Wet Ball Mill | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820436
PROCUREMENT | ORD | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.29.3.1.1(HYD - Wet Ball Mill) | 206820437
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.14.29.3.1.1(HYD - Wet Ball Mill) | 206820438
ASSEMBLY & TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.14.29.3.1.1(HYD - Wet Ball Mill) | 206820439
Dispatch OF WET BALL MILLING SYSTEM AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.29.3.1.1(HYD - Wet Ball Mill) | 206820440
BPL - Ball Mill Motor | SUP | 2022-09-27 08:00 | 2024-10-29 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820441
Engineering | ENG | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.29.3.1.2(BPL - Ball Mill Motor) | 206820442
Manufacturing | MFG | 2023-12-26 08:00 | 2024-07-12 17:00 |  |  |  |  | 1.14.29.3.1.2(BPL - Ball Mill Motor) | 206820443
Dispatch | DIS | 2024-07-13 08:00 | 2024-10-29 17:00 |  |  |  |  | 1.14.29.3.1.2(BPL - Ball Mill Motor) | 206820444
FOUNDATION MATERIALS FOR BALL MILL BLDG | SUP | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820445
Engineering | ENG | 2023-12-21 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.14.29.3.1.3(FOUNDATION MATERIALS FOR BALL MILL BLDG) | 206820446
Manufacturing | MFG | 2024-01-05 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.14.29.3.1.3(FOUNDATION MATERIALS FOR BALL MILL BLDG) | 206820447
Dispatch | DIS | 2024-03-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.3.1.3(FOUNDATION MATERIALS FOR BALL MILL BLDG) | 206820448
BALL MILL BLDG COLUMNS | SUP | 2023-12-21 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820449
Engineering | ENG | 2023-12-21 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.14.29.3.1.4( BALL MILL BLDG COLUMNS) | 206820450
Manufacturing | MFG | 2024-02-04 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.3.1.4( BALL MILL BLDG COLUMNS) | 206820451
Dispatch | DIS | 2024-04-04 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.3.1.4( BALL MILL BLDG COLUMNS) | 206820452
BALL MILL BUILDING BEAMS & BRACING | SUP | 2024-01-05 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820453
Engineering | ENG | 2024-01-05 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.29.3.1.5(BALL MILL BUILDING BEAMS & BRACING) | 206820454
Manufacturing | MFG | 2024-02-19 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.3.1.5(BALL MILL BUILDING BEAMS & BRACING) | 206820455
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.3.1.5(BALL MILL BUILDING BEAMS & BRACING) | 206820456
BALL MILL BUILDING FLOOR & PLATFORMS | SUP | 2024-01-05 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820457
Engineering | ENG | 2024-01-05 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.3.1.6(BALL MILL BUILDING FLOOR & PLATFORMS) | 206820458
Manufacturing | MFG | 2024-03-05 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.3.1.6(BALL MILL BUILDING FLOOR & PLATFORMS) | 206820459
Dispatch | DIS | 2024-05-04 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.14.29.3.1.6(BALL MILL BUILDING FLOOR & PLATFORMS) | 206820460
BALL MILL BUILDING WALL BEAMS | SUP | 2024-01-05 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.3.1(Engineering &Supply) | 206820461
Engineering | ENG | 2024-01-05 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.29.3.1.7(BALL MILL BUILDING WALL BEAMS) | 206820462
Manufacturing | MFG | 2024-02-19 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.3.1.7(BALL MILL BUILDING WALL BEAMS) | 206820463
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.3.1.7(BALL MILL BUILDING WALL BEAMS) | 206820464
Civil Works | OTH | 2023-09-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.3(Ball Mill Building and Ball Mills) | 206820465
RFC Civil Mill Foundation drawing | PE - RFC | 2023-09-22 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.3.2(Civil Works) | 206820466
RFC Civil Building foundation drawing | PE - RFC | 2023-10-22 08:00 | 2023-11-30 17:00 |  |  |  |  | 1.14.29.3.2(Civil Works) | 206820467
RFC Superstructure drawing | PE - RFC | 2023-11-11 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.3.2(Civil Works) | 206820468
Excavation | CIV | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.3.2(Civil Works) | 206820469
RCC | CIV | 2023-11-21 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.3.2(Civil Works) | 206820470
Erection | ERC | 2024-05-19 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.14.29.3(Ball Mill Building and Ball Mills) | 206820471
Erection of Structure | ERC | 2024-05-19 08:00 | 2024-12-14 17:00 |  |  |  |  | 1.14.29.3.3(Erection) | 206820472
Erection of Wet Ball Mill | ERC | 2024-10-20 08:00 | 2025-03-18 17:00 |  |  |  |  | 1.14.29.3.3(Erection) | 206820473
Erection of Ball Mill Motor | ERC | 2025-03-09 08:00 | 2025-04-07 17:00 |  |  |  |  | 1.14.29.3.3(Erection) | 206820474
Commissioning | COM | 2025-03-09 08:00 | 2025-05-07 17:00 |  |  |  |  | 1.14.29.3(Ball Mill Building and Ball Mills) | 206820475
Day Silo | OTH | 2022-09-27 08:00 | 2025-05-02 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820476
Engineering &Supply | ENG | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.29.4(Day Silo) | 206820477
FOUNDATION MATERIALS | SUP | 2023-10-02 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820478
Engineering | ENG | 2023-10-02 08:00 | 2023-10-16 17:00 |  |  |  |  | 1.14.29.4.1.1( FOUNDATION MATERIALS) | 206820479
Manufacturing | MFG | 2023-10-17 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.29.4.1.1( FOUNDATION MATERIALS) | 206820480
Dispatch | DIS | 2023-12-31 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.29.4.1.1( FOUNDATION MATERIALS) | 206820481
COLUMNS | SUP | 2023-10-02 08:00 | 2024-03-14 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820482
Engineering | ENG | 2023-10-02 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.29.4.1.2(COLUMNS) | 206820483
Manufacturing | MFG | 2023-11-16 08:00 | 2024-02-13 17:00 |  |  |  |  | 1.14.29.4.1.2(COLUMNS) | 206820484
Dispatch | DIS | 2024-02-14 08:00 | 2024-03-14 17:00 |  |  |  |  | 1.14.29.4.1.2(COLUMNS) | 206820485
BEAMS & BRACING | SUP | 2023-11-16 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820486
Engineering | ENG | 2023-11-16 08:00 | 2023-12-15 17:00 |  |  |  |  | 1.14.29.4.1.3(BEAMS & BRACING) | 206820487
Manufacturing | MFG | 2023-12-16 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.14.29.4.1.3(BEAMS & BRACING) | 206820488
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4.1.3(BEAMS & BRACING) | 206820489
FLOOR & PLATFORMS | SUP | 2023-11-16 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820490
Engineering | ENG | 2023-11-16 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.29.4.1.4(FLOOR & PLATFORMS) | 206820491
Manufacturing | MFG | 2023-12-31 08:00 | 2024-03-14 17:00 |  |  |  |  | 1.14.29.4.1.4(FLOOR & PLATFORMS) | 206820492
Dispatch | DIS | 2024-03-15 08:00 | 2024-04-13 17:00 |  |  |  |  | 1.14.29.4.1.4(FLOOR & PLATFORMS) | 206820493
WALL BEAMS | SUP | 2023-11-16 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820494
Engineering | ENG | 2023-11-16 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.29.4.1.5(WALL BEAMS) | 206820495
Manufacturing | MFG | 2023-12-31 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.14.29.4.1.5(WALL BEAMS) | 206820496
Dispatch | DIS | 2024-02-29 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4.1.5(WALL BEAMS) | 206820497
STAIRS | SUP | 2023-11-16 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820498
Engineering | ENG | 2023-11-16 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.29.4.1.6(STAIRS) | 206820499
Manufacturing | MFG | 2023-12-31 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4.1.6(STAIRS) | 206820500
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.4.1.6(STAIRS) | 206820501
MISC STRUCTURES | SUP | 2023-12-16 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820502
Engineering | ENG | 2023-12-16 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.29.4.1.7(MISC STRUCTURES) | 206820503
Manufacturing | MFG | 2024-01-30 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.4.1.7(MISC STRUCTURES) | 206820504
Dispatch | DIS | 2024-04-29 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.4.1.7(MISC STRUCTURES) | 206820505
HYD- LIMESTONE DAY SILO AND ACCESSORIES | SUP | 2022-09-27 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.29.4.1(Engineering &Supply) | 206820506
PROCUREMENT | ORD | 2022-09-27 08:00 | 2023-12-25 17:00 |  |  |  |  | 1.14.29.4.1.8( HYD- LIMESTONE DAY SILO AND ACCESSORIES) | 206820507
MANUFACTURING | MFG | 2023-12-26 08:00 | 2024-06-02 17:00 |  |  |  |  | 1.14.29.4.1.8( HYD- LIMESTONE DAY SILO AND ACCESSORIES) | 206820508
ASSEMBLY& TESTING | MFG | 2024-06-03 08:00 | 2024-09-19 17:00 |  |  |  |  | 1.14.29.4.1.8( HYD- LIMESTONE DAY SILO AND ACCESSORIES) | 206820509
Dispatch OF LIME STONE DAY SILO AND ACCESSORIES AND ALL ASSOCIATED ITEMS | DIS | 2024-09-20 08:00 | 2024-10-19 17:00 |  |  |  |  | 1.14.29.4.1.8( HYD- LIMESTONE DAY SILO AND ACCESSORIES) | 206820510
Civil Works | OTH | 2023-09-02 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4(Day Silo) | 206820511
RFC Civil foundation | PE - RFC | 2023-09-02 08:00 | 2023-10-01 17:00 |  |  |  |  | 1.14.29.4.2( Civil Works) | 206820512
RFC Superstructure drawing | PE - RFC | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.14.29.4.2( Civil Works) | 206820513
Excavation | CIV | 2023-10-02 08:00 | 2023-11-30 17:00 |  |  |  |  | 1.14.29.4.2( Civil Works) | 206820514
RCC | CIV | 2023-12-01 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.4.2( Civil Works) | 206820515
Erection | ERC | 2024-03-30 08:00 | 2025-05-02 17:00 |  |  |  |  | 1.14.29.4(Day Silo) | 206820516
Erection of Structure | ERC | 2024-03-30 08:00 | 2024-08-26 17:00 |  |  |  |  | 1.14.29.4.3(Erection) | 206820517
Erection of Silos | ERC | 2024-10-20 08:00 | 2025-03-18 17:00 |  |  |  |  | 1.14.29.4.3(Erection) | 206820518
Erection of Bag Filter | ERC | 2025-03-19 08:00 | 2025-05-02 17:00 |  |  |  |  | 1.14.29.4.3(Erection) | 206820519
Erection of Air Cannon | ERC | 2025-03-19 08:00 | 2025-05-02 17:00 |  |  |  |  | 1.14.29.4.3(Erection) | 206820520
Erection of Bucket Elevator | ERC | 2024-08-27 08:00 | 2025-03-14 17:00 |  |  |  |  | 1.14.29.4.3(Erection) | 206820521
LHS & GHS System | OTH | 2022-11-26 08:00 | 2026-05-18 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820522
Ordering & Engineering of LHS & GHS | ENG | 2022-11-26 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820523
Enquiry | ENQ | 2022-11-26 08:00 | 2022-12-25 17:00 |  |  |  |  | 1.14.29.5.1(Ordering & Engineering of LHS & GHS) | 206820524
Ordering | ORD | 2022-12-26 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.14.29.5.1(Ordering & Engineering of LHS & GHS) | 206820525
Detailed Engineering | ENG | 2023-04-25 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.1(Ordering & Engineering of LHS & GHS) | 206820526
Limestone Transfer Point-1 | OTH | 2023-02-24 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820527
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2(Limestone Transfer Point-1) | 206820528
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.1(Equipment Dispatch) | 206820529
Engineering &Supply of Structure | ENG | 2023-02-24 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2(Limestone Transfer Point-1) | 206820530
FOUNDATION MATERIALS LTP1 | SUP | 2023-10-22 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820531
Engineering | ENG | 2023-10-22 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.29.5.2.2.1( FOUNDATION MATERIALS LTP1) | 206820532
Manufacturing | MFG | 2023-11-06 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.14.29.5.2.2.1( FOUNDATION MATERIALS LTP1) | 206820533
Dispatch | DIS | 2024-02-04 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.5.2.2.1( FOUNDATION MATERIALS LTP1) | 206820534
LTP1 COLUMNS | SUP | 2023-10-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820535
Engineering | ENG | 2023-10-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.2.2.2(LTP1 COLUMNS) | 206820536
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.2.2.2(LTP1 COLUMNS) | 206820537
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2.2(LTP1 COLUMNS) | 206820538
LTP1 BEAMS & BRACING | SUP | 2023-10-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820539
Engineering | ENG | 2023-10-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.2.2.3(LTP1 BEAMS & BRACING) | 206820540
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.2.2.3(LTP1 BEAMS & BRACING) | 206820541
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2.3(LTP1 BEAMS & BRACING) | 206820542
LTP1 FLOOR & PLATFORMS | SUP | 2023-10-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820543
Engineering | ENG | 2023-10-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.2.2.4(LTP1 FLOOR & PLATFORMS) | 206820544
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.2.2.4(LTP1 FLOOR & PLATFORMS) | 206820545
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2.4(LTP1 FLOOR & PLATFORMS) | 206820546
LTP1 WALL BEAMS | SUP | 2023-10-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820547
Engineering | ENG | 2023-10-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.2.2.5( LTP1 WALL BEAMS) | 206820548
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.2.2.5( LTP1 WALL BEAMS) | 206820549
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2.5( LTP1 WALL BEAMS) | 206820550
LTP1 FASTENERS | SUP | 2023-02-24 08:00 | 2023-12-12 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820551
Enquiry | ENQ | 2023-02-24 08:00 | 2023-03-02 17:00 |  |  |  |  | 1.14.29.5.2.2.6( LTP1 FASTENERS) | 206820552
Ordering | ORD | 2023-03-03 08:00 | 2023-06-30 17:00 |  |  |  |  | 1.14.29.5.2.2.6( LTP1 FASTENERS) | 206820553
Engineering | ENG | 2023-07-01 08:00 | 2023-09-28 17:00 |  |  |  |  | 1.14.29.5.2.2.6( LTP1 FASTENERS) | 206820554
Dispatch | DIS | 2023-11-13 08:00 | 2023-12-12 17:00 |  |  |  |  | 1.14.29.5.2.2.6( LTP1 FASTENERS) | 206820555
LTP1 STAIRS & LADDERS | SUP | 2023-10-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820556
Engineering | ENG | 2023-10-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.2.2.7( LTP1 STAIRS & LADDERS) | 206820557
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.2.2.7( LTP1 STAIRS & LADDERS) | 206820558
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2.7( LTP1 STAIRS & LADDERS) | 206820559
LTP1 MISC STRUCTURES | SUP | 2023-10-22 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2(Engineering &Supply of Structure) | 206820560
Engineering | ENG | 2023-10-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.2.2.8(LTP1 MISC STRUCTURES) | 206820561
Manufacturing | MFG | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.2.2.8(LTP1 MISC STRUCTURES) | 206820562
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.2.2.8(LTP1 MISC STRUCTURES) | 206820563
Civil Works | CIV | 2023-02-24 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.2(Limestone Transfer Point-1) | 206820564
Engineering: Superstructure & Foundation | CIV | 2023-02-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.2.3(Civil Works) | 206820565
Excavation | CIV | 2023-07-24 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.29.5.2.3(Civil Works) | 206820566
RCC | CIV | 2023-11-06 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.2.3(Civil Works) | 206820567
Erection | ERC | 2024-05-19 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.29.5.2(Limestone Transfer Point-1) | 206820568
Erection of Structure | ERC | 2024-05-19 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.14.29.5.2.4(Erection) | 206820569
Erection of Equipment | ERC | 2024-10-16 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.29.5.2.4(Erection) | 206820570
ISG- Limestone Truck Tippler | OTH | 2023-02-24 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820571
Equipment Dispatch | DIS | 2024-07-18 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.3(ISG- Limestone Truck Tippler ) | 206820572
Dispatch | DIS | 2024-07-18 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.3.1(Equipment Dispatch) | 206820573
Civil Works | OTH | 2023-02-24 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.3(ISG- Limestone Truck Tippler ) | 206820574
Engineering: Foundation | CIV | 2023-02-24 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.14.29.5.3.2(Civil Works) | 206820575
Excavation | CIV | 2023-04-25 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.29.5.3.2(Civil Works) | 206820576
RCC | CIV | 2023-06-24 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.3.2(Civil Works) | 206820577
Erection of Equipment | ERC | 2024-08-17 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.5.3(ISG- Limestone Truck Tippler ) | 206820578
ISG- Surface Feeder | OTH | 2023-02-24 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820579
Equipment Dispatch | DIS | 2024-06-28 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.5.4(ISG- Surface Feeder) | 206820580
Dispatch | DIS | 2024-06-28 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.5.4.1(Equipment Dispatch) | 206820581
Civil Works | OTH | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.4(ISG- Surface Feeder) | 206820582
Engineering: Foundation | CIV | 2023-02-24 08:00 | 2023-04-24 17:00 |  |  |  |  | 1.14.29.5.4.2(Civil Works) | 206820583
Excavation | CIV | 2023-04-25 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.29.5.4.2(Civil Works) | 206820584
RCC | CIV | 2023-06-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.4.2(Civil Works) | 206820585
Erection of Equipment | ERC | 2024-07-28 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.14.29.5.4(ISG- Surface Feeder) | 206820586
Belt Conveyor-1A/B | OTH | 2023-06-24 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820587
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.5( Belt Conveyor-1A/B) | 206820588
LSBC1-Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.5.1(Equipment Dispatch) | 206820589
Engineering &Supply of Structure | ENG | 2023-11-21 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.29.5.5( Belt Conveyor-1A/B) | 206820590
FOUNDATION MATERIALS CONVEYOR-LC-1A/B | SUP | 2023-11-21 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.5.2(Engineering &Supply of Structure) | 206820591
Engineering | ENG | 2023-11-21 08:00 | 2023-12-05 17:00 |  |  |  |  | 1.14.29.5.5.2.1(FOUNDATION MATERIALS CONVEYOR-LC-1A/B) | 206820592
Manufacturing | MFG | 2023-12-06 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.5.5.2.1(FOUNDATION MATERIALS CONVEYOR-LC-1A/B) | 206820593
Dispatch | DIS | 2024-03-05 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.5.2.1(FOUNDATION MATERIALS CONVEYOR-LC-1A/B) | 206820594
CONVEYOR-LC-1A/B COLUMNS - TRESTLES | SUP | 2023-12-06 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.29.5.5.2(Engineering &Supply of Structure) | 206820595
Engineering | ENG | 2023-12-06 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.5.5.2.2(CONVEYOR-LC-1A/B COLUMNS - TRESTLES) | 206820596
Manufacturing | MFG | 2024-03-05 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.14.29.5.5.2.2(CONVEYOR-LC-1A/B COLUMNS - TRESTLES) | 206820597
Dispatch | DIS | 2024-07-03 08:00 | 2024-08-01 17:00 |  |  |  |  | 1.14.29.5.5.2.2(CONVEYOR-LC-1A/B COLUMNS - TRESTLES) | 206820598
CONVEYOR-LC-1A/B BEAMS & BRACING | SUP | 2023-12-11 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.29.5.5.2(Engineering &Supply of Structure) | 206820599
Engineering | ENG | 2023-12-11 08:00 | 2024-01-24 17:00 |  |  |  |  | 1.14.29.5.5.2.3( CONVEYOR-LC-1A/B BEAMS & BRACING) | 206820600
Manufacturing | MFG | 2024-01-25 08:00 | 2024-04-23 17:00 |  |  |  |  | 1.14.29.5.5.2.3( CONVEYOR-LC-1A/B BEAMS & BRACING) | 206820601
Dispatch | DIS | 2024-04-24 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.29.5.5.2.3( CONVEYOR-LC-1A/B BEAMS & BRACING) | 206820602
CONVEYOR-LC-1A/B FLOOR & PLATFORMS | SUP | 2023-12-16 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.29.5.5.2(Engineering &Supply of Structure) | 206820603
Engineering | ENG | 2023-12-16 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.29.5.5.2.4(CONVEYOR-LC-1A/B FLOOR & PLATFORMS) | 206820604
Manufacturing | MFG | 2024-01-30 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.5.5.2.4(CONVEYOR-LC-1A/B FLOOR & PLATFORMS) | 206820605
Dispatch | DIS | 2024-05-29 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.29.5.5.2.4(CONVEYOR-LC-1A/B FLOOR & PLATFORMS) | 206820606
CONVEYOR-LC-1A/B STAIRS & LADDERS | SUP | 2023-12-16 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.5.5.2(Engineering &Supply of Structure) | 206820607
Engineering | ENG | 2023-12-16 08:00 | 2024-01-29 17:00 |  |  |  |  | 1.14.29.5.5.2.5(CONVEYOR-LC-1A/B STAIRS & LADDERS) | 206820608
Manufacturing | MFG | 2024-01-30 08:00 | 2024-03-29 17:00 |  |  |  |  | 1.14.29.5.5.2.5(CONVEYOR-LC-1A/B STAIRS & LADDERS) | 206820609
Dispatch | DIS | 2024-03-30 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.5.5.2.5(CONVEYOR-LC-1A/B STAIRS & LADDERS) | 206820610
CONVEYOR-LC-1A/B MISC STRUCTURES | SUP | 2023-12-21 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.5.2(Engineering &Supply of Structure) | 206820611
Engineering | ENG | 2023-12-21 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.5.2.6(CONVEYOR-LC-1A/B MISC STRUCTURES) | 206820612
Manufacturing | MFG | 2024-01-20 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.5.5.2.6(CONVEYOR-LC-1A/B MISC STRUCTURES) | 206820613
Dispatch | DIS | 2024-03-05 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.5.2.6(CONVEYOR-LC-1A/B MISC STRUCTURES) | 206820614
Civil Works | CIV | 2023-06-24 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.5.5( Belt Conveyor-1A/B) | 206820615
Engineering: Foundation | PE - RFC | 2023-06-24 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.29.5.5.3(Civil Works) | 206820616
Engineering: Superstructure | ENG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.5.3(Civil Works) | 206820617
Excavation | CIV | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.5.3(Civil Works) | 206820618
RCC | CIV | 2024-02-04 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.5.5.3(Civil Works) | 206820619
Erection | ERC | 2024-05-04 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.14.29.5.5( Belt Conveyor-1A/B) | 206820620
Erection of Structure | ERC | 2024-05-04 08:00 | 2024-11-19 17:00 |  |  |  |  | 1.14.29.5.5.4(Erection) | 206820621
Erection of Equipment | ERC | 2024-11-20 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.14.29.5.5.4(Erection) | 206820622
Limestone Crusher House | OTH | 2023-06-24 08:00 | 2025-09-10 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820623
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.6(Limestone Crusher House) | 206820624
Dispatch | DIS | 2024-04-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.6.1(Equipment Dispatch) | 206820625
Engineering &Supply of Structure | ENG | 2023-06-24 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.5.6(Limestone Crusher House) | 206820626
FOUNDATION MATERIALS | SUP | 2023-06-24 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820627
Engineering | ENG | 2023-06-24 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.14.29.5.6.2.1( FOUNDATION MATERIALS) | 206820628
Manufacturing | MFG | 2023-07-09 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.6.2.1( FOUNDATION MATERIALS) | 206820629
Dispatch | DIS | 2023-10-07 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.29.5.6.2.1( FOUNDATION MATERIALS) | 206820630
COLUMNS | SUP | 2023-06-24 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820631
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.6.2.2(COLUMNS) | 206820632
Manufacturing | MFG | 2023-07-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2.2(COLUMNS) | 206820633
Dispatch | DIS | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.5.6.2.2(COLUMNS) | 206820634
BEAMS & BRACING | SUP | 2023-06-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820635
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.6.2.3(BEAMS & BRACING) | 206820636
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.6.2.3(BEAMS & BRACING) | 206820637
Dispatch | DIS | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2.3(BEAMS & BRACING) | 206820638
FLOOR & PLATFORMS | SUP | 2023-06-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820639
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.6.2.4(FLOOR & PLATFORMS) | 206820640
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.6.2.4(FLOOR & PLATFORMS) | 206820641
Dispatch | DIS | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2.4(FLOOR & PLATFORMS) | 206820642
WALL BEAMS | SUP | 2023-06-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820643
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.6.2.5(WALL BEAMS) | 206820644
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.6.2.5(WALL BEAMS) | 206820645
Dispatch | DIS | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.2.5(WALL BEAMS) | 206820646
STAIRS & LADDERS | SUP | 2023-06-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820647
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.6.2.6(STAIRS & LADDERS) | 206820648
Manufacturing | MFG | 2023-07-24 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.5.6.2.6(STAIRS & LADDERS) | 206820649
Dispatch | DIS | 2023-09-22 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.6.2.6(STAIRS & LADDERS) | 206820650
MISC STRUCTURES | SUP | 2023-06-24 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.6.2(Engineering &Supply of Structure) | 206820651
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.6.2.7(MISC STRUCTURES) | 206820652
Manufacturing | MFG | 2023-07-24 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.29.5.6.2.7(MISC STRUCTURES) | 206820653
Dispatch | DIS | 2023-09-07 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.6.2.7(MISC STRUCTURES) | 206820654
Civil Works | CIV | 2023-06-24 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.6(Limestone Crusher House) | 206820655
Engineering: Foundation | CIV | 2023-06-24 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.29.5.6.3(Civil Works) | 206820656
Engineering: Superstructure | ENG | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.3(Civil Works) | 206820657
Excavation | CIV | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.6.3(Civil Works) | 206820658
RCC | CIV | 2023-09-22 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.6.3(Civil Works) | 206820659
Erection of Structure | ERC | 2024-04-19 08:00 | 2025-04-13 17:00 |  |  |  |  | 1.14.29.5.6(Limestone Crusher House) | 206820660
Erection of Equipment | ERC | 2025-04-14 08:00 | 2025-09-10 17:00 |  |  |  |  | 1.14.29.5.6(Limestone Crusher House) | 206820661
Limestone Belt Feeder | OTH | 2023-02-24 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820662
Equipment Dispatch | DIS | 2023-02-24 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.14.29.5.7(Limestone Belt Feeder) | 206820663
Ordering & Engineering | ENG | 2024-05-09 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.29.5.7.1(Equipment Dispatch) | 206820664
Manufacturing | MFG | 2023-02-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.7.1(Equipment Dispatch) | 206820665
Dispatch | DIS | 2024-09-06 08:00 | 2024-12-04 17:00 |  |  |  |  | 1.14.29.5.7.1(Equipment Dispatch) | 206820666
Equipment Dispatch | DIS | 2024-12-05 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.5.7(Limestone Belt Feeder) | 206820667
Limestone Bulk Storage Silo and Bucket Elevator | OTH | 2023-05-25 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820668
Engineering &Supply | ENG | 2023-07-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8(Limestone Bulk Storage Silo and Bucket Elevator) | 206820669
FOUNDATION MATERIALS SILO STR | SUP | 2023-07-24 08:00 | 2024-07-22 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820670
Engineering | ENG | 2023-07-24 08:00 | 2023-11-15 17:00 |  |  |  |  | 1.14.29.5.8.1.1(FOUNDATION MATERIALS SILO STR) | 206820671
Manufacturing | MFG | 2023-11-16 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.29.5.8.1.1(FOUNDATION MATERIALS SILO STR) | 206820672
Dispatch | DIS | 2024-06-23 08:00 | 2024-07-22 17:00 |  |  |  |  | 1.14.29.5.8.1.1(FOUNDATION MATERIALS SILO STR) | 206820673
SILO STR COLUMNS | SUP | 2023-07-24 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820674
Engineering | ENG | 2023-07-24 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.29.5.8.1.2(SILO STR COLUMNS) | 206820675
Manufacturing | MFG | 2024-02-19 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.14.29.5.8.1.2(SILO STR COLUMNS) | 206820676
Dispatch | DIS | 2024-09-26 08:00 | 2024-10-25 17:00 |  |  |  |  | 1.14.29.5.8.1.2(SILO STR COLUMNS) | 206820677
SILO STR BEAMS & BRACING | SUP | 2024-02-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820678
Engineering | ENG | 2024-02-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.29.5.8.1.3(SILO STR BEAMS & BRACING) | 206820679
Manufacturing | MFG | 2024-09-16 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.29.5.8.1.3(SILO STR BEAMS & BRACING) | 206820680
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1.3(SILO STR BEAMS & BRACING) | 206820681
SILO STR FLOOR & PLATFORMS | SUP | 2024-02-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820682
Engineering | ENG | 2024-02-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.29.5.8.1.4(SILO STR FLOOR & PLATFORMS) | 206820683
Manufacturing | MFG | 2024-09-16 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.29.5.8.1.4(SILO STR FLOOR & PLATFORMS) | 206820684
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1.4(SILO STR FLOOR & PLATFORMS) | 206820685
SILO STR WALL BEAMS | SUP | 2024-02-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820686
Engineering | ENG | 2024-02-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.29.5.8.1.5(SILO STR WALL BEAMS) | 206820687
Manufacturing | MFG | 2024-09-16 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.29.5.8.1.5(SILO STR WALL BEAMS) | 206820688
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1.5(SILO STR WALL BEAMS) | 206820689
SILO STR STAIRS & LADDERS | SUP | 2024-02-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820690
Engineering | ENG | 2024-02-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.29.5.8.1.6(SILO STR STAIRS & LADDERS) | 206820691
Manufacturing | MFG | 2024-09-16 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.29.5.8.1.6(SILO STR STAIRS & LADDERS) | 206820692
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1.6(SILO STR STAIRS & LADDERS) | 206820693
SILO STR MISC STRUCTURES | SUP | 2024-02-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820694
Engineering | ENG | 2024-02-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.29.5.8.1.7(SILO STR MISC STRUCTURES) | 206820695
Manufacturing | MFG | 2024-09-16 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.29.5.8.1.7(SILO STR MISC STRUCTURES) | 206820696
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1.7(SILO STR MISC STRUCTURES) | 206820697
SILO SHELL | SUP | 2024-02-19 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820698
Engineering | ENG | 2024-02-19 08:00 | 2024-09-15 17:00 |  |  |  |  | 1.14.29.5.8.1.8(SILO SHELL) | 206820699
Manufacturing | MFG | 2024-09-16 08:00 | 2025-04-23 17:00 |  |  |  |  | 1.14.29.5.8.1.8(SILO SHELL) | 206820700
Dispatch | DIS | 2025-04-24 08:00 | 2025-05-23 17:00 |  |  |  |  | 1.14.29.5.8.1.8(SILO SHELL) | 206820701
Equipments | SUP | 2023-07-24 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.29.5.8.1(Engineering &Supply) | 206820702
Engineering | ENG | 2023-07-24 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.5.8.1.9(Equipments) | 206820703
Ordering | OTH | 2023-09-22 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.8.1.9(Equipments) | 206820704
Manufacturing | MFG | 2024-01-20 08:00 | 2024-08-06 17:00 |  |  |  |  | 1.14.29.5.8.1.9(Equipments) | 206820705
Dispatch | DIS | 2024-08-07 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.29.5.8.1.9(Equipments) | 206820706
Civil Works | CIV | 2023-05-25 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.29.5.8(Limestone Bulk Storage Silo and Bucket Elevator) | 206820707
Engineering: Foundation | ENG | 2023-05-25 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.8.2(Civil Works) | 206820708
Engineering: Superstructure | ENG | 2023-06-09 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.8.2(Civil Works) | 206820709
Excavation | CIV | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.8.2(Civil Works) | 206820710
RCC | CIV | 2024-01-25 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.29.5.8.2(Civil Works) | 206820711
Erection | ERC | 2024-11-10 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.5.8(Limestone Bulk Storage Silo and Bucket Elevator) | 206820712
Erection of Structure | ERC | 2024-11-10 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.5.8.3(Erection) | 206820713
Erection of Equipment | ERC | 2025-07-08 08:00 | 2025-11-04 17:00 |  |  |  |  | 1.14.29.5.8.3(Erection) | 206820714
Limestone Bucket Elevator and Reversible Belt Feeder | OTH | 2024-05-25 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820715
Equipment Dispatch | DIS | 2024-05-25 08:00 | 2024-09-01 17:00 |  |  |  |  | 1.14.29.5.9(Limestone Bucket Elevator and Reversible Belt Feeder) | 206820716
Dispatch | DIS | 2024-05-25 08:00 | 2024-09-01 17:00 |  |  |  |  | 1.14.29.5.9.1(Equipment Dispatch) | 206820717
Erection of Equipment | ERC | 2024-09-02 08:00 | 2024-12-30 17:00 |  |  |  |  | 1.14.29.5.9(Limestone Bucket Elevator and Reversible Belt Feeder) | 206820718
Gypsum Conveyor-1A/B | OTH | 2023-06-24 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820719
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.10(Gypsum Conveyor-1A/B) | 206820720
Dispatch | DIS | 2024-04-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.10.1(Equipment Dispatch) | 206820721
Engineering &Supply of Structure | ENG | 2023-06-24 08:00 | 2023-12-14 17:00 |  |  |  |  | 1.14.29.5.10(Gypsum Conveyor-1A/B) | 206820722
FOUNDATION MATERIALSCONVEYOR-GC-1A/B | SUP | 2023-06-24 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820723
Engineering | ENG | 2023-06-24 08:00 | 2023-07-08 17:00 |  |  |  |  | 1.14.29.5.10.2.1(FOUNDATION MATERIALSCONVEYOR-GC-1A/B) | 206820724
Manufacturing | MFG | 2023-07-09 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.29.5.10.2.1(FOUNDATION MATERIALSCONVEYOR-GC-1A/B) | 206820725
Dispatch | DIS | 2023-09-07 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.10.2.1(FOUNDATION MATERIALSCONVEYOR-GC-1A/B) | 206820726
FX110 - CONVEYOR-GC-1A/B COLUMNS - TRESTLES | SUP | 2023-06-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820727
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.10.2.2(FX110 - CONVEYOR-GC-1A/B COLUMNS - TRESTLES) | 206820728
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.10.2.2(FX110 - CONVEYOR-GC-1A/B COLUMNS - TRESTLES) | 206820729
Dispatch | DIS | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.10.2.2(FX110 - CONVEYOR-GC-1A/B COLUMNS - TRESTLES) | 206820730
FX210 - CONVEYOR-GC-1A/B BEAMS & BRACING | SUP | 2023-06-24 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820731
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.10.2.3(FX210 - CONVEYOR-GC-1A/B BEAMS & BRACING) | 206820732
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.10.2.3(FX210 - CONVEYOR-GC-1A/B BEAMS & BRACING) | 206820733
Dispatch | DIS | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.10.2.3(FX210 - CONVEYOR-GC-1A/B BEAMS & BRACING) | 206820734
FX310 - CONVEYOR-GC-1A/B FLOOR & PLATFORMS | SUP | 2023-06-24 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820735
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.10.2.4(FX310 - CONVEYOR-GC-1A/B FLOOR & PLATFORMS) | 206820736
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.10.2.4(FX310 - CONVEYOR-GC-1A/B FLOOR & PLATFORMS) | 206820737
Dispatch | DIS | 2023-10-07 08:00 | 2023-11-05 17:00 |  |  |  |  | 1.14.29.5.10.2.4(FX310 - CONVEYOR-GC-1A/B FLOOR & PLATFORMS) | 206820738
FX710 - CONVEYOR-GC-1A/B FASTENERS | SUP | 2023-07-04 08:00 | 2023-12-14 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820739
Enquiry | OTH | 2023-07-04 08:00 | 2023-07-10 17:00 |  |  |  |  | 1.14.29.5.10.2.5(FX710 - CONVEYOR-GC-1A/B FASTENERS) | 206820740
Ordering | OTH | 2023-07-11 08:00 | 2023-09-08 17:00 |  |  |  |  | 1.14.29.5.10.2.5(FX710 - CONVEYOR-GC-1A/B FASTENERS) | 206820741
Engineering | ENG | 2023-09-09 08:00 | 2023-09-15 17:00 |  |  |  |  | 1.14.29.5.10.2.5(FX710 - CONVEYOR-GC-1A/B FASTENERS) | 206820742
Dispatch | DIS | 2023-11-15 08:00 | 2023-12-14 17:00 |  |  |  |  | 1.14.29.5.10.2.5(FX710 - CONVEYOR-GC-1A/B FASTENERS) | 206820743
FX810 - CONVEYOR-GC-1A/B STAIRS & LADDERS | SUP | 2023-07-14 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820744
Engineering | ENG | 2023-07-14 08:00 | 2023-08-12 17:00 |  |  |  |  | 1.14.29.5.10.2.6(FX810 - CONVEYOR-GC-1A/B STAIRS & LADDERS) | 206820745
Manufacturing | MFG | 2023-08-13 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.14.29.5.10.2.6(FX810 - CONVEYOR-GC-1A/B STAIRS & LADDERS) | 206820746
Dispatch | DIS | 2023-09-27 08:00 | 2023-10-26 17:00 |  |  |  |  | 1.14.29.5.10.2.6(FX810 - CONVEYOR-GC-1A/B STAIRS & LADDERS) | 206820747
FX910 - CONVEYOR-GC-1A/B MISC STRUCTURES | SUP | 2023-07-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.10.2(Engineering &Supply of Structure) | 206820748
Engineering | ENG | 2023-07-24 08:00 | 2023-08-07 17:00 |  |  |  |  | 1.14.29.5.10.2.7(FX910 - CONVEYOR-GC-1A/B MISC STRUCTURES) | 206820749
Manufacturing | MFG | 2023-08-08 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.5.10.2.7(FX910 - CONVEYOR-GC-1A/B MISC STRUCTURES) | 206820750
Dispatch | DIS | 2023-09-22 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.10.2.7(FX910 - CONVEYOR-GC-1A/B MISC STRUCTURES) | 206820751
Civil Works | CIV | 2023-11-21 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.29.5.10(Gypsum Conveyor-1A/B) | 206820752
Engineering: Foundation | PE - RFC | 2023-11-21 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.10.3(Civil Works) | 206820753
Engineering: Superstructure | PE - RFC | 2024-01-20 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.10.3(Civil Works) | 206820754
Excavation | CIV | 2024-01-20 08:00 | 2024-03-19 17:00 |  |  |  |  | 1.14.29.5.10.3(Civil Works) | 206820755
RCC | CIV | 2024-11-15 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.29.5.10.3(Civil Works) | 206820756
Erection of Structure | ERC | 2025-02-23 08:00 | 2025-06-22 17:00 |  |  |  |  | 1.14.29.5.10(Gypsum Conveyor-1A/B) | 206820757
Erection of Equipment | ERC | 2025-06-23 08:00 | 2025-09-30 17:00 |  |  |  |  | 1.14.29.5.10(Gypsum Conveyor-1A/B) | 206820758
Gypsum Travelling Tripper/Gypsum Storage Shed | OTH | 2023-05-25 08:00 | 2026-02-17 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820759
Equipment Dispatch | DIS | 2024-07-14 08:00 | 2024-09-11 17:00 |  |  |  |  | 1.14.29.5.11(Gypsum Travelling Tripper/Gypsum Storage Shed) | 206820760
Dispatch | DIS | 2024-07-14 08:00 | 2024-09-11 17:00 |  |  |  |  | 1.14.29.5.11.1(Equipment Dispatch) | 206820761
Engineering &Supply of Structure | ENG | 2023-07-24 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.5.11(Gypsum Travelling Tripper/Gypsum Storage Shed) | 206820762
FX014 - FOUNDATION MATERIALSGYPSUM SHED | SUP | 2023-07-24 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820763
Engineering | ENG | 2023-07-24 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.29.5.11.2.1(FX014 - FOUNDATION MATERIALSGYPSUM SHED) | 206820764
Manufacturing | MFG | 2023-08-23 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.11.2.1(FX014 - FOUNDATION MATERIALSGYPSUM SHED) | 206820765
Dispatch | DIS | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.5.11.2.1(FX014 - FOUNDATION MATERIALSGYPSUM SHED) | 206820766
FX140 - GYPSUM SHED COLUMNS | SUP | 2023-07-24 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820767
Engineering | ENG | 2023-07-24 08:00 | 2023-09-06 17:00 |  |  |  |  | 1.14.29.5.11.2.2(FX140 - GYPSUM SHED COLUMNS) | 206820768
Manufacturing | MFG | 2023-09-07 08:00 | 2024-01-04 17:00 |  |  |  |  | 1.14.29.5.11.2.2(FX140 - GYPSUM SHED COLUMNS) | 206820769
Dispatch | DIS | 2024-01-05 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.5.11.2.2(FX140 - GYPSUM SHED COLUMNS) | 206820770
FX240 - GYPSUM SHED BEAMS & BRACING | SUP | 2023-08-23 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820771
Engineering | ENG | 2023-08-23 08:00 | 2023-10-06 17:00 |  |  |  |  | 1.14.29.5.11.2.3(FX240 - GYPSUM SHED BEAMS & BRACING) | 206820772
Manufacturing | MFG | 2023-10-07 08:00 | 2024-02-03 17:00 |  |  |  |  | 1.14.29.5.11.2.3(FX240 - GYPSUM SHED BEAMS & BRACING) | 206820773
Dispatch | DIS | 2024-02-04 08:00 | 2024-05-03 17:00 |  |  |  |  | 1.14.29.5.11.2.3(FX240 - GYPSUM SHED BEAMS & BRACING) | 206820774
FX340 - GYPSUM SHED FLOOR & PLATFORMS | SUP | 2024-02-09 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820775
Engineering | ENG | 2024-02-09 08:00 | 2024-03-24 17:00 |  |  |  |  | 1.14.29.5.11.2.4(FX340 - GYPSUM SHED FLOOR & PLATFORMS) | 206820776
Manufacturing | MFG | 2024-03-25 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.29.5.11.2.4(FX340 - GYPSUM SHED FLOOR & PLATFORMS) | 206820777
Dispatch | DIS | 2024-05-24 08:00 | 2024-08-21 17:00 |  |  |  |  | 1.14.29.5.11.2.4(FX340 - GYPSUM SHED FLOOR & PLATFORMS) | 206820778
FX640 - GYPSUM SHED WALL BEAMS | SUP | 2023-09-02 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820779
Engineering | ENG | 2023-09-02 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.14.29.5.11.2.5(FX640 - GYPSUM SHED WALL BEAMS) | 206820780
Manufacturing | MFG | 2023-11-01 08:00 | 2024-02-28 17:00 |  |  |  |  | 1.14.29.5.11.2.5(FX640 - GYPSUM SHED WALL BEAMS) | 206820781
Dispatch | DIS | 2024-02-29 08:00 | 2024-05-28 17:00 |  |  |  |  | 1.14.29.5.11.2.5(FX640 - GYPSUM SHED WALL BEAMS) | 206820782
FX740 - GYPSUM SHED FASTENERS | SUP | 2023-09-07 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820783
Enquiry | ENQ | 2023-09-07 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.5.11.2.6(FX740 - GYPSUM SHED FASTENERS) | 206820784
Ordering | ORD | 2023-10-22 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.29.5.11.2.6(FX740 - GYPSUM SHED FASTENERS) | 206820785
Engineering | ENG | 2024-02-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.11.2.6(FX740 - GYPSUM SHED FASTENERS) | 206820786
Dispatch | DIS | 2024-07-18 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.11.2.6(FX740 - GYPSUM SHED FASTENERS) | 206820787
FX840 - GYPSUM SHED STAIRS & LADDERS | SUP | 2023-11-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820788
Engineering | ENG | 2023-11-21 08:00 | 2024-01-19 17:00 |  |  |  |  | 1.14.29.5.11.2.7(FX840 - GYPSUM SHED STAIRS & LADDERS) | 206820789
Manufacturing | MFG | 2024-01-20 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.11.2.7(FX840 - GYPSUM SHED STAIRS & LADDERS) | 206820790
Dispatch | DIS | 2024-05-19 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.11.2.7(FX840 - GYPSUM SHED STAIRS & LADDERS) | 206820791
FX940 - GYPSUM SHED MISC STRUCTURES | SUP | 2024-01-20 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.5.11.2(Engineering &Supply of Structure) | 206820792
Engineering | ENG | 2024-01-20 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.5.11.2.8(FX940 - GYPSUM SHED MISC STRUCTURES) | 206820793
Manufacturing | MFG | 2024-03-05 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.14.29.5.11.2.8(FX940 - GYPSUM SHED MISC STRUCTURES) | 206820794
Dispatch | DIS | 2024-09-01 08:00 | 2024-12-29 17:00 |  |  |  |  | 1.14.29.5.11.2.8(FX940 - GYPSUM SHED MISC STRUCTURES) | 206820795
Civil Works | CIV | 2023-05-25 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.29.5.11(Gypsum Travelling Tripper/Gypsum Storage Shed) | 206820796
RFC Civil - Foundation | PE - RFC | 2023-05-25 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.11.3(Civil Works) | 206820797
RFC Civil - Superstructure | PE - RFC | 2023-05-25 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.5.11.3(Civil Works) | 206820798
Excavation | CIV | 2023-12-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.5.11.3(Civil Works) | 206820799
GYPSUM SHED: RCC | CIV | 2024-05-19 08:00 | 2025-02-22 17:00 |  |  |  |  | 1.14.29.5.11.3(Civil Works) | 206820800
Erection of Structure | ERC | 2025-02-23 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.29.5.11(Gypsum Travelling Tripper/Gypsum Storage Shed) | 206820801
Erection & Commissioning of Equipments | COM | 2025-09-21 08:00 | 2026-02-17 17:00 |  |  |  |  | 1.14.29.5.11(Gypsum Travelling Tripper/Gypsum Storage Shed) | 206820802
Pump House for LHP/ GHP | OTH | 2024-02-19 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820803
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.12(Pump House for LHP/ GHP) | 206820804
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.12.1(Equipment Dispatch) | 206820805
Civil Works | CIV | 2024-02-19 08:00 | 2025-01-28 17:00 |  |  |  |  | 1.14.29.5.12(Pump House for LHP/ GHP) | 206820806
RFC Civil - Superstructure | PE - RFC | 2024-02-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.12.2(Civil Works ) | 206820807
RFC Civil - Foundation | PE - RFC | 2024-05-19 08:00 | 2024-07-17 17:00 |  |  |  |  | 1.14.29.5.12.2(Civil Works ) | 206820808
Excavation | CIV | 2024-07-18 08:00 | 2024-08-31 17:00 |  |  |  |  | 1.14.29.5.12.2(Civil Works ) | 206820809
RCC | CIV | 2024-09-01 08:00 | 2025-01-28 17:00 |  |  |  |  | 1.14.29.5.12.2(Civil Works ) | 206820810
Erection of Equipment | ERC | 2025-01-29 08:00 | 2025-07-27 17:00 |  |  |  |  | 1.14.29.5.12(Pump House for LHP/ GHP) | 206820811
Weigh Bridge | OTH | 2024-02-19 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820812
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.13(Weigh Bridge) | 206820813
Dispatch | DIS | 2024-04-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.13.1(Equipment Dispatch) | 206820814
Civil Works of Weigh Bridge GHP | OTH | 2024-02-19 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.29.5.13(Weigh Bridge) | 206820815
Weigh Bridge-GHP Foundation | CIV | 2024-02-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.13.2(Civil Works of Weigh Bridge GHP) | 206820816
Excavation | CIV | 2024-05-19 08:00 | 2024-07-17 17:00 |  |  |  |  | 1.14.29.5.13.2(Civil Works of Weigh Bridge GHP) | 206820817
RCC | CIV | 2024-07-18 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.29.5.13.2(Civil Works of Weigh Bridge GHP) | 206820818
Civil Works of Weigh Bridge LHP | OTH | 2024-02-19 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.29.5.13(Weigh Bridge) | 206820819
Weigh Bridge-GHP Foundation | CIV | 2024-02-19 08:00 | 2024-05-18 17:00 |  |  |  |  | 1.14.29.5.13.3(Civil Works of Weigh Bridge LHP) | 206820820
Excavation | CIV | 2024-05-19 08:00 | 2024-07-02 17:00 |  |  |  |  | 1.14.29.5.13.3(Civil Works of Weigh Bridge LHP) | 206820821
RCC | CIV | 2024-07-03 08:00 | 2024-09-30 17:00 |  |  |  |  | 1.14.29.5.13.3(Civil Works of Weigh Bridge LHP) | 206820822
Erection of Equipment | ERC | 2024-07-18 08:00 | 2024-10-15 17:00 |  |  |  |  | 1.14.29.5.13(Weigh Bridge) | 206820823
Electrical and C&I Items | OTH | 2024-04-19 08:00 | 2026-02-02 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820824
Equipment Dispatch | DIS | 2024-04-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.14(Electrical and C&I Items) | 206820825
Dispatch | DIS | 2024-04-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.14.1(Equipment Dispatch) | 206820826
Erection of Equipment | ERC | 2025-10-06 08:00 | 2026-02-02 17:00 |  |  |  |  | 1.14.29.5.14(Electrical and C&I Items) | 206820827
Misc./Auxiliary Systems | OTH | 2024-02-19 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820828
Equipment Dispatch | DIS | 2024-02-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.15(Misc./Auxiliary Systems) | 206820829
Dispatch | DIS | 2024-02-19 08:00 | 2024-06-17 17:00 |  |  |  |  | 1.14.29.5.15.1(Equipment Dispatch) | 206820830
Erection of Equipment | ERC | 2024-08-17 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.29.5.15(Misc./Auxiliary Systems) | 206820831
MCC building | OTH | 2023-07-24 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820832
Civil Works | OTH | 2023-07-24 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.16(MCC building) | 206820833
Engineering: Foundation | CIV | 2023-07-24 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.5.16.1(Civil Works) | 206820834
Engineering: Superstructure | ENG | 2023-09-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.5.16.1(Civil Works) | 206820835
Excavation | CIV | 2023-11-21 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.5.16.1(Civil Works) | 206820836
RCC | CIV | 2023-12-21 08:00 | 2024-08-16 17:00 |  |  |  |  | 1.14.29.5.16.1(Civil Works) | 206820837
Erection of Panels | ERC | 2024-10-16 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.5.16(MCC building) | 206820838
Erection of panels | ERC | 2024-10-16 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.5.16.2(Erection of Panels) | 206820839
Commissioning of Limestone handling & Crushing System | COM | 2025-11-05 08:00 | 2026-02-02 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820840
Commissioning of Gypsum Handling System | COM | 2026-02-18 08:00 | 2026-05-18 17:00 |  |  |  |  | 1.14.29.5(LHS & GHS System) | 206820841
Pumps | OTH | 2023-04-05 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820842
Engineering &Supply | ENG | 2023-04-05 08:00 | 2023-11-18 17:00 |  |  |  |  | 1.14.29.6(Pumps) | 206820843
BOI-FW701 SLURRY PUMPS & ACCESSORIES(A,B,C&D) | SUP | 2023-04-05 08:00 | 2023-11-18 17:00 |  |  |  | FW701 | 1.14.29.6.1(Engineering &Supply) | 206820844
Ordering | ORD | 2023-04-05 08:00 | 2023-06-23 17:00 |  |  |  | FW701 | 1.14.29.6.1.1(BOI-FW701 SLURRY PUMPS & ACCESSORIES(A,B,C&D)) | 206820845
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  | FW701 | 1.14.29.6.1.1(BOI-FW701 SLURRY PUMPS & ACCESSORIES(A,B,C&D)) | 206820846
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-19 17:00 |  |  |  | FW701 | 1.14.29.6.1.1(BOI-FW701 SLURRY PUMPS & ACCESSORIES(A,B,C&D)) | 206820847
Dispatch | DIS | 2023-10-20 08:00 | 2023-11-18 17:00 |  |  |  | FW701 | 1.14.29.6.1.1(BOI-FW701 SLURRY PUMPS & ACCESSORIES(A,B,C&D)) | 206820848
BOI- FW702 -WATER PUMPS & ACCESSORIES | SUP | 2023-04-15 08:00 | 2023-11-18 17:00 |  |  |  | FW702 | 1.14.29.6.1(Engineering &Supply) | 206820849
Ordering | ORD | 2023-04-15 08:00 | 2023-06-23 17:00 |  |  |  | FW702 | 1.14.29.6.1.2(BOI- FW702 -WATER PUMPS & ACCESSORIES) | 206820850
Engineering | ENG | 2023-06-24 08:00 | 2023-07-23 17:00 |  |  |  | FW702 | 1.14.29.6.1.2(BOI- FW702 -WATER PUMPS & ACCESSORIES) | 206820851
Manufacturing | MFG | 2023-07-24 08:00 | 2023-10-19 17:00 |  |  |  | FW702 | 1.14.29.6.1.2(BOI- FW702 -WATER PUMPS & ACCESSORIES) | 206820852
Dispatch | DIS | 2023-10-20 08:00 | 2023-11-18 17:00 |  |  |  | FW702 | 1.14.29.6.1.2(BOI- FW702 -WATER PUMPS & ACCESSORIES) | 206820853
Civil Works | OTH | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.6(Pumps) | 206820854
RFC MISC PUMPS-GA & RC DETAILS OF FOUNDATION | PE - RFC | 2023-08-23 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.6.2(Civil Works) | 206820855
Excavation | CIV | 2023-10-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.6.2(Civil Works) | 206820856
RCC | CIV | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  |  | 1.14.29.6.2(Civil Works) | 206820857
Erection of Equipment | ERC | 2023-12-19 08:00 | 2024-01-17 17:00 |  |  |  |  | 1.14.29.6(Pumps) | 206820858
FW701 - SLURRY PUMPS & ACCESSORIES | ERC | 2023-12-19 08:00 | 2024-01-17 17:00 |  |  |  | FW701 | 1.14.29.6.3(Erection of Equipment) | 206820859
FW702 - WATER PUMPS & ACCESSORIES | ERC | 2023-12-19 08:00 | 2024-01-17 17:00 |  |  |  | FW702 | 1.14.29.6.3(Erection of Equipment) | 206820860
BOI-Tanks-PEM | OTH | 2023-02-24 08:00 | 2025-08-11 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820861
Engineering &Supply | ENG | 2023-02-24 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7(BOI-Tanks-PEM) | 206820862
Ordering | ORD | 2023-02-24 08:00 | 2023-10-31 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820863
Detailed Engineering | ENG | 2023-11-01 08:00 | 2024-04-28 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820864
Fabrication /Manufacturing | MFG | 2024-04-29 08:00 | 2024-11-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820865
Dispatch of Primary Hydro Cyclone Feed Tank | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820866
Dispatch of Secondary Hydro Cyclone Feed Tank | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820867
Dispatch of AUXILIARY ABSORBENT TANK | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820868
Dispatch of Limestone Slurry storage Tank | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820869
Dispatch of FILTRATE WATER TANK | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820870
Dispatch of PROCES WATER TANK | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820871
Dispatch of WASTE WATER TANK | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820872
Dispatch of BELT WASH TANK | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820873
Dispatch of CAKE WASH TANK | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  |  | 1.14.29.7.1(Engineering &Supply) | 206820874
Civil | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7(BOI-Tanks-PEM) | 206820875
PCE-51400 RFC PRIMARY Hydro CYCLONE FEED TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820876
PCE-51400 RFC SECONDARY Hydro CYCLONE TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820877
PCE-51400 RFC LIMESTONE SLURRY TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820878
PCE-51400 RFC AUXILIARY ABSORBENT TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820879
PCE-51400 RFC FILTRATE WATER TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820880
PCE-51400 RFC WASTE WATER TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820881
PCE-51400 RFC PROCESS WATER TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820882
PCE-51400 RFC BELT FILTER WASHING TANKS: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820883
PCE-51400 RFC CLARIFIED WATER TANK: GA & RCC DETAILS OF FOUNDATION | CIV | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820884
PCE-51400 RFC CAKE WASH TANK: GA & RC DETAIL OF FOUNDATION | PE - RFC | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820885
PCE-51400 RFC NEUTRALIZATION TANK: GA & RC DETAIL OF FOUNDATION | PE - RFC | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820886
PWI-13640 Data sheet & General Arrangement of Agitators | OTH | 2024-04-14 08:00 | 2024-06-12 17:00 |  |  |  |  | 1.14.29.7.2(Civil) | 206820887
Erection / Assembly | ERC | 2024-12-25 08:00 | 2025-08-11 17:00 |  |  |  |  | 1.14.29.7(BOI-Tanks-PEM) | 206820888
Primary Hydro cyclone feed tank | ERC | 2025-01-24 08:00 | 2025-08-11 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820889
Secondary Hydro cyclone feed tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820890
Limestone Slurry Storage tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820891
Auxiliary Absorbent Tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820892
Filtrate Water Tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820893
Waste Water Tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820894
Process Water Tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820895
Belt Filter Wash Tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820896
Cake Wash tank | ERC | 2024-12-25 08:00 | 2025-07-12 17:00 |  |  |  |  | 1.14.29.7.3(Erection / Assembly) | 206820897
Electrical Items | OTH | 2023-08-23 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820898
Engineering &Supply | ENG | 2023-08-23 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.8(Electrical Items) | 206820899
FW806 - CONTROL JUNCTION BOX | SUP | 2023-09-12 08:00 | 2024-08-13 17:00 |  |  |  | 806 | 1.14.29.8.1(Engineering &Supply) | 206820900
Enquiry | ENQ | 2023-09-12 08:00 | 2023-10-11 17:00 |  |  |  | FW806 | 1.14.29.8.1.1(FW806 - CONTROL JUNCTION BOX) | 206820901
Ordering | ORD | 2023-10-12 08:00 | 2023-11-10 17:00 |  |  |  | FW806 | 1.14.29.8.1.1(FW806 - CONTROL JUNCTION BOX) | 206820902
Engineering | ENG | 2023-11-11 08:00 | 2024-02-06 17:00 |  |  |  | FW806 | 1.14.29.8.1.1(FW806 - CONTROL JUNCTION BOX) | 206820903
Dispatch | DIS | 2024-07-15 08:00 | 2024-08-13 17:00 |  |  |  | FW806 | 1.14.29.8.1.1(FW806 - CONTROL JUNCTION BOX) | 206820904
FW807 - POWER JUNCTION BOX | SUP | 2023-09-12 08:00 | 2024-07-14 17:00 |  |  |  | 807 | 1.14.29.8.1(Engineering &Supply) | 206820905
Enquiry | ENQ | 2023-09-12 08:00 | 2023-10-11 17:00 |  |  |  | FW807 | 1.14.29.8.1.2(FW807 - POWER JUNCTION BOX) | 206820906
Ordering | ORD | 2023-10-12 08:00 | 2023-11-10 17:00 |  |  |  | FW807 | 1.14.29.8.1.2(FW807 - POWER JUNCTION BOX) | 206820907
Engineering | ENG | 2023-11-11 08:00 | 2024-02-06 17:00 |  |  |  | FW807 | 1.14.29.8.1.2(FW807 - POWER JUNCTION BOX) | 206820908
Dispatch | DIS | 2024-06-15 08:00 | 2024-07-14 17:00 |  |  |  | FW807 | 1.14.29.8.1.2(FW807 - POWER JUNCTION BOX) | 206820909
FW779 - SUPPORTS FOR CABLE TRAYS/CONTR | SUP | 2023-09-12 08:00 | 2024-11-04 17:00 |  |  |  | 779 | 1.14.29.8.1(Engineering &Supply) | 206820910
Enquiry | ENQ | 2023-09-12 08:00 | 2023-09-26 17:00 |  |  |  | FW779 | 1.14.29.8.1.3(FW779 - SUPPORTS FOR CABLE TRAYS/CONTR) | 206820911
Ordering | ORD | 2023-09-27 08:00 | 2023-11-25 17:00 |  |  |  | FW779 | 1.14.29.8.1.3(FW779 - SUPPORTS FOR CABLE TRAYS/CONTR) | 206820912
Engineering | ENG | 2023-11-26 08:00 | 2024-02-08 17:00 |  |  |  | FW779 | 1.14.29.8.1.3(FW779 - SUPPORTS FOR CABLE TRAYS/CONTR) | 206820913
Dispatch | DIS | 2024-10-06 08:00 | 2024-11-04 17:00 |  |  |  | FW779 | 1.14.29.8.1.3(FW779 - SUPPORTS FOR CABLE TRAYS/CONTR) | 206820914
FW841 - CONTROL VALVES | SUP | 2023-10-02 08:00 | 2024-12-24 17:00 |  |  |  | 841 | 1.14.29.8.1(Engineering &Supply) | 206820915
Enquiry | ENQ | 2023-10-02 08:00 | 2023-10-31 17:00 |  |  |  | FW841 | 1.14.29.8.1.4(FW841 - CONTROL VALVES) | 206820916
Ordering | ORD | 2023-11-01 08:00 | 2023-12-30 17:00 |  |  |  | FW841 | 1.14.29.8.1.4(FW841 - CONTROL VALVES) | 206820917
Engineering | ENG | 2023-12-31 08:00 | 2024-03-29 17:00 |  |  |  | FW841 | 1.14.29.8.1.4(FW841 - CONTROL VALVES) | 206820918
Dispatch | DIS | 2024-11-25 08:00 | 2024-12-24 17:00 |  |  |  | FW841 | 1.14.29.8.1.4(FW841 - CONTROL VALVES) | 206820919
Electrical - Balance BOIs | SUP | 2023-08-23 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.8.1(Engineering &Supply) | 206820920
Enquiry | ENQ | 2023-08-23 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.8.1.5(Electrical - Balance BOIs) | 206820921
Ordering | ORD | 2023-09-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.8.1.5(Electrical - Balance BOIs) | 206820922
Engineering | ENG | 2023-11-21 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.29.8.1.5(Electrical - Balance BOIs) | 206820923
Dispatch | DIS | 2024-12-05 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.8.1.5(Electrical - Balance BOIs) | 206820924
Balance BOIs- HOIST, VALVES, CHAIN PULLEY, COMMISSIONING SPARES etc. | SUP | 2023-08-23 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.8(Electrical Items) | 206820925
Enquiry | ENQ | 2023-08-23 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.8.2( Balance BOIs- HOIST, VALVES, CHAIN PULLEY, COMMISSIONING SPARES etc.) | 206820926
Ordering | ORD | 2023-09-22 08:00 | 2023-11-20 17:00 |  |  |  |  | 1.14.29.8.2( Balance BOIs- HOIST, VALVES, CHAIN PULLEY, COMMISSIONING SPARES etc.) | 206820927
Engineering | ENG | 2023-11-21 08:00 | 2024-02-18 17:00 |  |  |  |  | 1.14.29.8.2( Balance BOIs- HOIST, VALVES, CHAIN PULLEY, COMMISSIONING SPARES etc.) | 206820928
Dispatch | DIS | 2024-12-05 08:00 | 2025-03-04 17:00 |  |  |  |  | 1.14.29.8.2( Balance BOIs- HOIST, VALVES, CHAIN PULLEY, COMMISSIONING SPARES etc.) | 206820929
Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning | COM | 2025-04-19 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.14.29.8(Electrical Items) | 206820930
Absorber | ERC | 2025-09-19 08:00 | 2025-12-27 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820931
Duct & Structure | ERC | 2025-08-02 08:00 | 2025-12-29 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820932
Gates & Dampers | ERC | 2025-10-31 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820933
RC Pumps | ERC | 2025-07-23 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820934
Oxidation Blower | ERC | 2025-05-18 08:00 | 2025-07-16 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820935
FGD Control Room | ERC | 2025-05-24 08:00 | 2025-09-20 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820936
Gypsum Dewatering System | ERC | 2025-04-19 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820937
Agitators | ERC | 2025-04-19 08:00 | 2025-06-17 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820938
ACW System | ERC | 2025-10-24 08:00 | 2026-01-21 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820939
Compressor House | ERC | 2025-04-19 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820940
Pumps | ERC | 2025-04-19 08:00 | 2025-07-02 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820941
Valves | ERC | 2025-04-19 08:00 | 2025-07-02 17:00 |  |  |  |  | 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | 206820942
HT Motors | OTH | 2023-06-24 08:00 | 2025-05-17 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820943
Engineering and Supply | ENG | 2023-06-24 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.14.29.9( HT Motors) | 206820944
RC PUMP MOTOR | OTH | 2023-06-24 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.29.9.1(Engineering and Supply) | 206820945
Engineering | ENG | 2023-06-24 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.29.9.1.1(RC PUMP MOTOR) | 206820946
Manufacturing | MFG | 2023-08-23 08:00 | 2024-08-06 17:00 |  |  |  |  | 1.14.29.9.1.1(RC PUMP MOTOR) | 206820947
Dispatch | DIS | 2024-08-07 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.29.9.1.1(RC PUMP MOTOR) | 206820948
OXIDATION BLOWER MOTOR | SUP | 2023-06-24 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.14.29.9.1(Engineering and Supply) | 206820949
Engineering | ENG | 2023-06-24 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.9.1.2(OXIDATION BLOWER MOTOR) | 206820950
Manufacturing | MFG | 2023-09-22 08:00 | 2024-09-05 17:00 |  |  |  |  | 1.14.29.9.1.2(OXIDATION BLOWER MOTOR) | 206820951
Dispatch | DIS | 2024-09-06 08:00 | 2024-10-05 17:00 |  |  |  |  | 1.14.29.9.1.2(OXIDATION BLOWER MOTOR) | 206820952
Erection | ERC | 2025-04-03 08:00 | 2025-05-17 17:00 |  |  |  |  | 1.14.29.9( HT Motors) | 206820953
RC PUMP MOTOR | ERC | 2025-04-03 08:00 | 2025-05-02 17:00 |  |  |  |  | 1.14.29.9.2(Erection) | 206820954
OXIDATION BLOWER MOTOR | ERC | 2025-04-18 08:00 | 2025-05-17 17:00 |  |  |  |  | 1.14.29.9.2(Erection) | 206820955
Earthing | OTH | 2023-03-26 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820956
Ordering | OTH | 2023-03-26 08:00 | 2023-05-24 17:00 |  |  |  |  | 1.14.29.10(Earthing) | 206820957
Engineering | ENG | 2023-05-25 08:00 | 2023-07-23 17:00 |  |  |  |  | 1.14.29.10(Earthing) | 206820958
Manufacturing | MFG | 2023-06-29 08:00 | 2023-08-27 17:00 |  |  |  |  | 1.14.29.10(Earthing) | 206820959
Dispatch | DIS | 2023-08-28 08:00 | 2023-09-26 17:00 |  |  |  |  | 1.14.29.10(Earthing) | 206820960
Sub Systems | OTH | 2023-02-24 08:00 | 2025-12-28 17:00 |  |  |  |  | 1.14.29(FGD ) | 206820961
Absorber | OTH | 2023-02-24 08:00 | 2025-12-28 17:00 |  |  |  |  | 1.14.29.11(Sub Systems) | 206820962
Engineering and Supplies | ENG | 2023-02-24 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.29.11.1(Absorber) | 206820963
Absorber-Structure | OTH | 2023-02-24 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206820964
FW226 - EQWT | SUP | 2023-02-24 08:00 | 2024-01-31 17:00 |  |  |  | FW226 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820965
Engineering | ENG | 2023-02-24 08:00 | 2023-07-15 17:00 |  |  |  | FW226 | 1.14.29.11.1.1.1.1(FW226 - EQWT) | 206820966
Manufacturing | MFG | 2023-07-16 08:00 | 2024-01-01 17:00 |  |  |  | FW226 | 1.14.29.11.1.1.1.1(FW226 - EQWT) | 206820967
Dispatch | DIS | 2023-12-03 08:00 | 2024-01-31 17:00 |  |  |  | FW226 | 1.14.29.11.1.1.1.1(FW226 - EQWT) | 206820968
FW281 - FOUNDATION MATL FOR ABSORBER | SUP | 2023-02-24 08:00 | 2024-01-01 17:00 |  |  |  | FW281 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820969
Engineering | ENG | 2023-02-24 08:00 | 2023-07-15 17:00 |  |  |  | FW281 | 1.14.29.11.1.1.1.2(FW281 - FOUNDATION MATL FOR ABSORBER) | 206820970
Manufacturing | MFG | 2023-07-16 08:00 | 2023-12-02 17:00 |  |  |  | FW281 | 1.14.29.11.1.1.1.2(FW281 - FOUNDATION MATL FOR ABSORBER) | 206820971
Dispatch | DIS | 2023-11-03 08:00 | 2024-01-01 17:00 |  |  |  | FW281 | 1.14.29.11.1.1.1.2(FW281 - FOUNDATION MATL FOR ABSORBER) | 206820972
FW285 - SUPRTING STR FOR EMERGENCY QWT | SUP | 2023-02-24 08:00 | 2024-02-28 17:00 |  |  |  | 285 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820973
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW285 | 1.14.29.11.1.1.1.3(FW285 - SUPRTING STR FOR EMERGENCY QWT) | 206820974
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW285 | 1.14.29.11.1.1.1.3(FW285 - SUPRTING STR FOR EMERGENCY QWT) | 206820975
Manufacturing | MFG | 2023-08-23 08:00 | 2024-01-29 17:00 |  |  |  | FW285 | 1.14.29.11.1.1.1.3(FW285 - SUPRTING STR FOR EMERGENCY QWT) | 206820976
Dispatch | DIS | 2023-12-31 08:00 | 2024-02-28 17:00 |  |  |  | FW285 | 1.14.29.11.1.1.1.3(FW285 - SUPRTING STR FOR EMERGENCY QWT) | 206820977
FW300 - ABSORBER COLUMN | SUP | 2023-02-24 08:00 | 2024-03-29 17:00 |  |  |  | 300 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820978
Engineering | ENG | 2023-02-24 08:00 | 2023-10-12 17:00 |  |  |  | FW300 | 1.14.29.11.1.1.1.4(FW300 - ABSORBER COLUMN) | 206820979
Manufacturing | MFG | 2023-10-13 08:00 | 2024-02-28 17:00 |  |  |  | FW300 | 1.14.29.11.1.1.1.4(FW300 - ABSORBER COLUMN) | 206820980
Dispatch | DIS | 2024-01-30 08:00 | 2024-03-29 17:00 |  |  |  | FW300 | 1.14.29.11.1.1.1.4(FW300 - ABSORBER COLUMN) | 206820981
FW301 - ABSORBER BEAM AND BRACINGS | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 301 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820982
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW301 | 1.14.29.11.1.1.1.5(FW301 - ABSORBER BEAM AND BRACINGS) | 206820983
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW301 | 1.14.29.11.1.1.1.5(FW301 - ABSORBER BEAM AND BRACINGS) | 206820984
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW301 | 1.14.29.11.1.1.1.5(FW301 - ABSORBER BEAM AND BRACINGS) | 206820985
FW302 - ABSORBER LOWER FLOORS | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 302 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820986
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW302 | 1.14.29.11.1.1.1.6(FW302 - ABSORBER LOWER FLOORS) | 206820987
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW302 | 1.14.29.11.1.1.1.6(FW302 - ABSORBER LOWER FLOORS) | 206820988
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW302 | 1.14.29.11.1.1.1.6(FW302 - ABSORBER LOWER FLOORS) | 206820989
FW303 - ABSORBER UPPER FLOORS | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 303 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820990
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW303 | 1.14.29.11.1.1.1.7(FW303 - ABSORBER UPPER FLOORS) | 206820991
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW303 | 1.14.29.11.1.1.1.7(FW303 - ABSORBER UPPER FLOORS) | 206820992
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW303 | 1.14.29.11.1.1.1.7(FW303 - ABSORBER UPPER FLOORS) | 206820993
FW304 - ABSORBER FLOOR GRILLS | SUP | 2023-02-24 08:00 | 2024-06-18 17:00 |  |  |  | 304 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820994
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW304 | 1.14.29.11.1.1.1.8(FW304 - ABSORBER FLOOR GRILLS) | 206820995
Manufacturing | MFG | 2023-09-13 08:00 | 2024-05-19 17:00 |  |  |  | FW304 | 1.14.29.11.1.1.1.8(FW304 - ABSORBER FLOOR GRILLS) | 206820996
Dispatch | DIS | 2024-04-20 08:00 | 2024-06-18 17:00 |  |  |  | FW304 | 1.14.29.11.1.1.1.8(FW304 - ABSORBER FLOOR GRILLS) | 206820997
FW305 - ABSORBER STAIR & HANDRAILS | SUP | 2023-02-24 08:00 | 2024-07-27 17:00 |  |  |  | 305 | 1.14.29.11.1.1.1(Absorber-Structure) | 206820998
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW305 | 1.14.29.11.1.1.1.9(FW305 - ABSORBER STAIR & HANDRAILS) | 206820999
Engineering | ENG | 2023-04-25 08:00 | 2023-10-21 17:00 |  |  |  | FW305 | 1.14.29.11.1.1.1.9(FW305 - ABSORBER STAIR & HANDRAILS) | 206821000
Manufacturing | MFG | 2023-10-22 08:00 | 2024-06-27 17:00 |  |  |  | FW305 | 1.14.29.11.1.1.1.9(FW305 - ABSORBER STAIR & HANDRAILS) | 206821001
Dispatch | DIS | 2024-05-29 08:00 | 2024-07-27 17:00 |  |  |  | FW305 | 1.14.29.11.1.1.1.9(FW305 - ABSORBER STAIR & HANDRAILS) | 206821002
FW306 - ABSORBER HSFG FASTNERS | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 306 | 1.14.29.11.1.1.1(Absorber-Structure) | 206821003
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW306 | 1.14.29.11.1.1.1.10(FW306 - ABSORBER HSFG FASTNERS) | 206821004
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW306 | 1.14.29.11.1.1.1.10(FW306 - ABSORBER HSFG FASTNERS) | 206821005
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW306 | 1.14.29.11.1.1.1.10(FW306 - ABSORBER HSFG FASTNERS) | 206821006
FW307 - ABSORBER MISCELLANEOUS | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 307 | 1.14.29.11.1.1.1(Absorber-Structure) | 206821007
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW307 | 1.14.29.11.1.1.1.11(FW307 - ABSORBER MISCELLANEOUS) | 206821008
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW307 | 1.14.29.11.1.1.1.11(FW307 - ABSORBER MISCELLANEOUS) | 206821009
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW307 | 1.14.29.11.1.1.1.11(FW307 - ABSORBER MISCELLANEOUS) | 206821010
Absorber Casing | OTH | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206821011
FW201-ABSORBER RC PUMP NOZZLE | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 201 | 1.14.29.11.1.1.2( Absorber Casing) | 206821012
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW201 | 1.14.29.11.1.1.2.1(FW201-ABSORBER RC PUMP NOZZLE) | 206821013
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW201 | 1.14.29.11.1.1.2.1(FW201-ABSORBER RC PUMP NOZZLE) | 206821014
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW201 | 1.14.29.11.1.1.2.1(FW201-ABSORBER RC PUMP NOZZLE) | 206821015
FW202-ABS NOZZLE NB300 & ABOVE | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 202 | 1.14.29.11.1.1.2( Absorber Casing) | 206821016
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW202 | 1.14.29.11.1.1.2.2(FW202-ABS NOZZLE NB300 & ABOVE) | 206821017
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW202 | 1.14.29.11.1.1.2.2(FW202-ABS NOZZLE NB300 & ABOVE) | 206821018
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW202 | 1.14.29.11.1.1.2.2(FW202-ABS NOZZLE NB300 & ABOVE) | 206821019
FW203-ABS NOZZLE NB 25 TO NB250 | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 203 | 1.14.29.11.1.1.2( Absorber Casing) | 206821020
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW203 | 1.14.29.11.1.1.2.3(FW203-ABS NOZZLE NB 25 TO NB250) | 206821021
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW203 | 1.14.29.11.1.1.2.3(FW203-ABS NOZZLE NB 25 TO NB250) | 206821022
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW203 | 1.14.29.11.1.1.2.3(FW203-ABS NOZZLE NB 25 TO NB250) | 206821023
FW209-MANHOLE DOOR FOR ABSORBER | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 209 | 1.14.29.11.1.1.2( Absorber Casing) | 206821024
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW209 | 1.14.29.11.1.1.2.4(FW209-MANHOLE DOOR FOR ABSORBER) | 206821025
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW209 | 1.14.29.11.1.1.2.4(FW209-MANHOLE DOOR FOR ABSORBER) | 206821026
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW209 | 1.14.29.11.1.1.2.4(FW209-MANHOLE DOOR FOR ABSORBER) | 206821027
FW216-ABSORBER BAFFLE GRATING SUPPORT | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 216 | 1.14.29.11.1.1.2( Absorber Casing) | 206821028
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW216 | 1.14.29.11.1.1.2.5(FW216-ABSORBER BAFFLE GRATING SUPPORT) | 206821029
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW216 | 1.14.29.11.1.1.2.5(FW216-ABSORBER BAFFLE GRATING SUPPORT) | 206821030
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW216 | 1.14.29.11.1.1.2.5(FW216-ABSORBER BAFFLE GRATING SUPPORT) | 206821031
FW217-ABSORBER ME SUPPORT | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 217 | 1.14.29.11.1.1.2( Absorber Casing) | 206821032
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW217 | 1.14.29.11.1.1.2.6(FW217-ABSORBER ME SUPPORT) | 206821033
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW217 | 1.14.29.11.1.1.2.6(FW217-ABSORBER ME SUPPORT) | 206821034
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW217 | 1.14.29.11.1.1.2.6(FW217-ABSORBER ME SUPPORT) | 206821035
FW218-ABSORBER SPRAY PIPE SUPPORT | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 218 | 1.14.29.11.1.1.2( Absorber Casing) | 206821036
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW218 | 1.14.29.11.1.1.2.7(FW218-ABSORBER SPRAY PIPE SUPPORT) | 206821037
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW218 | 1.14.29.11.1.1.2.7(FW218-ABSORBER SPRAY PIPE SUPPORT) | 206821038
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW218 | 1.14.29.11.1.1.2.7(FW218-ABSORBER SPRAY PIPE SUPPORT) | 206821039
FW219-ABSORBER SYSTEM-BASE | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | FW219 | 1.14.29.11.1.1.2( Absorber Casing) | 206821040
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW219 | 1.14.29.11.1.1.2.8(FW219-ABSORBER SYSTEM-BASE) | 206821041
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW219 | 1.14.29.11.1.1.2.8(FW219-ABSORBER SYSTEM-BASE) | 206821042
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW219 | 1.14.29.11.1.1.2.8(FW219-ABSORBER SYSTEM-BASE) | 206821043
FW221-ABSORBER SYSTEM-CASING BOTTOM | SUP | 2023-02-24 08:00 | 2024-04-28 17:00 |  |  |  | FW221 | 1.14.29.11.1.1.2( Absorber Casing) | 206821044
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW221 | 1.14.29.11.1.1.2.9(FW221-ABSORBER SYSTEM-CASING BOTTOM) | 206821045
Manufacturing | MFG | 2023-10-22 08:00 | 2024-03-29 17:00 |  |  |  | FW221 | 1.14.29.11.1.1.2.9(FW221-ABSORBER SYSTEM-CASING BOTTOM) | 206821046
Dispatch | DIS | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  | FW221 | 1.14.29.11.1.1.2.9(FW221-ABSORBER SYSTEM-CASING BOTTOM) | 206821047
FW222-ABSORBER SYSTEM-CASING TOP | SUP | 2023-02-24 08:00 | 2024-04-28 17:00 |  |  |  | FW222 | 1.14.29.11.1.1.2( Absorber Casing) | 206821048
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW222 | 1.14.29.11.1.1.2.10(FW222-ABSORBER SYSTEM-CASING TOP) | 206821049
Manufacturing | MFG | 2023-10-22 08:00 | 2024-03-29 17:00 |  |  |  | FW222 | 1.14.29.11.1.1.2.10(FW222-ABSORBER SYSTEM-CASING TOP) | 206821050
Dispatch | DIS | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  | FW222 | 1.14.29.11.1.1.2.10(FW222-ABSORBER SYSTEM-CASING TOP) | 206821051
FW224-ABSORBER LINING - C276 | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 224 | 1.14.29.11.1.1.2( Absorber Casing) | 206821052
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW224 | 1.14.29.11.1.1.2.11(FW224-ABSORBER LINING - C276) | 206821053
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW224 | 1.14.29.11.1.1.2.11(FW224-ABSORBER LINING - C276) | 206821054
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW224 | 1.14.29.11.1.1.2.11(FW224-ABSORBER LINING - C276) | 206821055
FW228-ABSORBER-W/D INTERFACE- C276 zone | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | FW228 | 1.14.29.11.1.1.2( Absorber Casing) | 206821056
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW228 | 1.14.29.11.1.1.2.12(FW228-ABSORBER-W/D INTERFACE- C276 zone) | 206821057
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW228 | 1.14.29.11.1.1.2.12(FW228-ABSORBER-W/D INTERFACE- C276 zone) | 206821058
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW228 | 1.14.29.11.1.1.2.12(FW228-ABSORBER-W/D INTERFACE- C276 zone) | 206821059
FW328-ABSORBER-W/D INTERFACE- CS zone | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 328 | 1.14.29.11.1.1.2( Absorber Casing) | 206821060
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW328 | 1.14.29.11.1.1.2.13(FW328-ABSORBER-W/D INTERFACE- CS zone) | 206821061
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW328 | 1.14.29.11.1.1.2.13(FW328-ABSORBER-W/D INTERFACE- CS zone) | 206821062
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW328 | 1.14.29.11.1.1.2.13(FW328-ABSORBER-W/D INTERFACE- CS zone) | 206821063
FW231-ABSORBER SHEAR PLATE | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | 231 | 1.14.29.11.1.1.2( Absorber Casing) | 206821064
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW231 | 1.14.29.11.1.1.2.14(FW231-ABSORBER SHEAR PLATE) | 206821065
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW231 | 1.14.29.11.1.1.2.14(FW231-ABSORBER SHEAR PLATE) | 206821066
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW231 | 1.14.29.11.1.1.2.14(FW231-ABSORBER SHEAR PLATE) | 206821067
FW322-ABSORBER SYSTEM-CASING INTERMEDIATE | SUP | 2023-02-24 08:00 | 2024-04-28 17:00 |  |  |  | 322 | 1.14.29.11.1.1.2( Absorber Casing) | 206821068
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW322 | 1.14.29.11.1.1.2.15(FW322-ABSORBER SYSTEM-CASING INTERMEDIATE) | 206821069
Manufacturing | MFG | 2023-10-22 08:00 | 2024-03-29 17:00 |  |  |  | FW322 | 1.14.29.11.1.1.2.15(FW322-ABSORBER SYSTEM-CASING INTERMEDIATE) | 206821070
Dispatch | DIS | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  | FW322 | 1.14.29.11.1.1.2.15(FW322-ABSORBER SYSTEM-CASING INTERMEDIATE) | 206821071
FW324-HOOD OVER ABSORBER | SUP | 2023-02-24 08:00 | 2024-04-28 17:00 |  |  |  | 324 | 1.14.29.11.1.1.2( Absorber Casing) | 206821072
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW324 | 1.14.29.11.1.1.2.16(FW324-HOOD OVER ABSORBER) | 206821073
Manufacturing | MFG | 2023-10-22 08:00 | 2024-03-29 17:00 |  |  |  | FW324 | 1.14.29.11.1.1.2.16(FW324-HOOD OVER ABSORBER) | 206821074
Dispatch | DIS | 2024-02-29 08:00 | 2024-04-28 17:00 |  |  |  | FW324 | 1.14.29.11.1.1.2.16(FW324-HOOD OVER ABSORBER) | 206821075
FW227-EMERGENCY QUENCHING SYSTEM | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | FW227 | 1.14.29.11.1.1.2( Absorber Casing) | 206821076
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW227 | 1.14.29.11.1.1.2.17(FW227-EMERGENCY QUENCHING SYSTEM) | 206821077
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW227 | 1.14.29.11.1.1.2.17(FW227-EMERGENCY QUENCHING SYSTEM) | 206821078
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW227 | 1.14.29.11.1.1.2.17(FW227-EMERGENCY QUENCHING SYSTEM) | 206821079
FW229-W/D WASH SYSTEM | SUP | 2023-02-24 08:00 | 2024-06-27 17:00 |  |  |  | FW229 | 1.14.29.11.1.1.2( Absorber Casing) | 206821080
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW229 | 1.14.29.11.1.1.2.18(FW229-W/D WASH SYSTEM) | 206821081
Manufacturing | MFG | 2023-10-22 08:00 | 2024-05-28 17:00 |  |  |  | FW229 | 1.14.29.11.1.1.2.18(FW229-W/D WASH SYSTEM) | 206821082
Dispatch | DIS | 2024-04-29 08:00 | 2024-06-27 17:00 |  |  |  | FW229 | 1.14.29.11.1.1.2.18(FW229-W/D WASH SYSTEM) | 206821083
Absorber Internals | SUP | 2023-02-24 08:00 | 2024-08-11 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206821084
FW 215-SUBDELIVERY - MIST ELIMINATOR | SUP | 2023-02-24 08:00 | 2024-06-07 17:00 |  |  |  | 215 | 1.14.29.11.1.1.3(Absorber Internals) | 206821085
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW215 | 1.14.29.11.1.1.3.1(FW 215-SUBDELIVERY - MIST ELIMINATOR) | 206821086
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW215 | 1.14.29.11.1.1.3.1(FW 215-SUBDELIVERY - MIST ELIMINATOR) | 206821087
Manufacturing | MFG | 2023-08-23 08:00 | 2024-05-08 17:00 |  |  |  | FW215 | 1.14.29.11.1.1.3.1(FW 215-SUBDELIVERY - MIST ELIMINATOR) | 206821088
Dispatch | DIS | 2024-04-09 08:00 | 2024-06-07 17:00 |  |  |  | FW215 | 1.14.29.11.1.1.3.1(FW 215-SUBDELIVERY - MIST ELIMINATOR) | 206821089
FW213- Absorber system | SUP | 2023-02-24 08:00 | 2024-08-11 17:00 |  |  |  | FW213 | 1.14.29.11.1.1.3(Absorber Internals) | 206821090
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW213 | 1.14.29.11.1.1.3.2( FW213- Absorber system ) | 206821091
Engineering | ENG | 2023-06-24 08:00 | 2023-10-21 17:00 |  |  |  | FW213 | 1.14.29.11.1.1.3.2( FW213- Absorber system ) | 206821092
Manufacturing | MFG | 2023-10-22 08:00 | 2024-07-07 17:00 |  |  |  | FW213 | 1.14.29.11.1.1.3.2( FW213- Absorber system ) | 206821093
Dispatch | DIS | 2024-06-13 08:00 | 2024-08-11 17:00 |  |  |  | FW213 | 1.14.29.11.1.1.3.2( FW213- Absorber system ) | 206821094
FW720-ABSORBER AGITATOR- BOI | SUP | 2023-02-24 08:00 | 2024-05-28 17:00 |  |  |  | FW720 | 1.14.29.11.1.1.3(Absorber Internals) | 206821095
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW720 | 1.14.29.11.1.1.3.3(FW720-ABSORBER AGITATOR- BOI) | 206821096
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW720 | 1.14.29.11.1.1.3.3(FW720-ABSORBER AGITATOR- BOI) | 206821097
Manufacturing | MFG | 2023-08-23 08:00 | 2024-05-13 17:00 |  |  |  | FW720 | 1.14.29.11.1.1.3.3(FW720-ABSORBER AGITATOR- BOI) | 206821098
Dispatch | DIS | 2024-03-30 08:00 | 2024-05-28 17:00 |  |  |  | FW720 | 1.14.29.11.1.1.3.3(FW720-ABSORBER AGITATOR- BOI) | 206821099
Absorber-Supporting systems | SUP | 2023-02-24 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206821100
RC Pump Shed | OTH | 2023-04-10 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.29.11.1.1.4(Absorber-Supporting systems) | 206821101
Engineering &Supply | SUP | 2023-04-10 08:00 | 2024-06-22 17:00 |  |  |  |  | 1.14.29.11.1.1.4.1(RC Pump Shed) | 206821102
FW371 - HSFG BOLT-RC SHED-BOI | SUP | 2023-09-12 08:00 | 2024-06-22 17:00 |  |  |  | 371 | 1.14.29.11.1.1.4.1.1(Engineering &Supply) | 206821103
Ordering | ORD | 2023-09-12 08:00 | 2024-01-09 17:00 |  |  |  | FW371 | 1.14.29.11.1.1.4.1.1.1(FW371 - HSFG BOLT-RC SHED-BOI) | 206821104
Engineering | ENG | 2023-11-11 08:00 | 2024-01-24 17:00 |  |  |  | FW371 | 1.14.29.11.1.1.4.1.1.1(FW371 - HSFG BOLT-RC SHED-BOI) | 206821105
Manufacturing | MFG | 2024-01-25 08:00 | 2024-04-23 17:00 |  |  |  | FW371 | 1.14.29.11.1.1.4.1.1.1(FW371 - HSFG BOLT-RC SHED-BOI) | 206821106
Dispatch | DIS | 2024-04-24 08:00 | 2024-06-22 17:00 |  |  |  | FW371 | 1.14.29.11.1.1.4.1.1.1(FW371 - HSFG BOLT-RC SHED-BOI) | 206821107
FW283 FOUNDATION MATERIAL & FW236 -STRUCTURES | SUP | 2023-07-24 08:00 | 2024-05-18 17:00 |  |  |  | 283 FOUNDATION MATERIAL & FW236 | 1.14.29.11.1.1.4.1.1(Engineering &Supply) | 206821108
Engineering | ENG | 2023-07-24 08:00 | 2023-11-20 17:00 |  |  |  | FW283 | 1.14.29.11.1.1.4.1.1.2(FW283 FOUNDATION MATERIAL & FW236 -STRUCTURES ) | 206821109
Manufacturing | MFG | 2023-11-21 08:00 | 2024-04-18 17:00 |  |  |  | FW283 | 1.14.29.11.1.1.4.1.1.2(FW283 FOUNDATION MATERIAL & FW236 -STRUCTURES ) | 206821110
Dispatch | DIS | 2024-03-20 08:00 | 2024-05-18 17:00 |  |  |  | FW283 | 1.14.29.11.1.1.4.1.1.2(FW283 FOUNDATION MATERIAL & FW236 -STRUCTURES ) | 206821111
FW208- RC PUMP OXIDATION BLOWER SUPPORT | SUP | 2023-05-25 08:00 | 2024-05-08 17:00 |  |  |  | 208 | 1.14.29.11.1.1.4.1.1(Engineering &Supply) | 206821112
Ordering | ORD | 2023-05-25 08:00 | 2023-09-21 17:00 |  |  |  | FW208 | 1.14.29.11.1.1.4.1.1.3(FW208- RC PUMP OXIDATION BLOWER SUPPORT) | 206821113
Engineering | ENG | 2023-07-24 08:00 | 2023-11-10 17:00 |  |  |  | FW208 | 1.14.29.11.1.1.4.1.1.3(FW208- RC PUMP OXIDATION BLOWER SUPPORT) | 206821114
Manufacturing | MFG | 2023-11-11 08:00 | 2024-04-08 17:00 |  |  |  | FW208 | 1.14.29.11.1.1.4.1.1.3(FW208- RC PUMP OXIDATION BLOWER SUPPORT) | 206821115
Dispatch | DIS | 2024-03-10 08:00 | 2024-05-08 17:00 |  |  |  | FW208 | 1.14.29.11.1.1.4.1.1.3(FW208- RC PUMP OXIDATION BLOWER SUPPORT) | 206821116
FW236- STRUCTURE FOR RC PUMP HOUSE | SUP | 2023-04-10 08:00 | 2024-03-24 17:00 |  |  |  | 236 | 1.14.29.11.1.1.4.1.1(Engineering &Supply) | 206821117
Ordering | ORD | 2023-04-10 08:00 | 2023-08-07 17:00 |  |  |  | FW236 | 1.14.29.11.1.1.4.1.1.4(FW236- STRUCTURE FOR RC PUMP HOUSE) | 206821118
Engineering | ENG | 2023-06-09 08:00 | 2023-09-26 17:00 |  |  |  | FW236 | 1.14.29.11.1.1.4.1.1.4(FW236- STRUCTURE FOR RC PUMP HOUSE) | 206821119
Manufacturing | MFG | 2023-09-27 08:00 | 2024-02-23 17:00 |  |  |  | FW236 | 1.14.29.11.1.1.4.1.1.4(FW236- STRUCTURE FOR RC PUMP HOUSE) | 206821120
Dispatch | DIS | 2024-01-25 08:00 | 2024-03-24 17:00 |  |  |  | FW236 | 1.14.29.11.1.1.4.1.1.4(FW236- STRUCTURE FOR RC PUMP HOUSE) | 206821121
Absorbers Duct, Duct Structure & Duct support | SUP | 2023-02-24 08:00 | 2024-04-30 17:00 |  |  |  |  | 1.14.29.11.1.1.4(Absorber-Supporting systems) | 206821122
FW207-OUTLET GUIDE VANE | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 207 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821123
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW207 | 1.14.29.11.1.1.4.2.1(FW207-OUTLET GUIDE VANE) | 206821124
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW207 | 1.14.29.11.1.1.4.2.1(FW207-OUTLET GUIDE VANE) | 206821125
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW207 | 1.14.29.11.1.1.4.2.1(FW207-OUTLET GUIDE VANE) | 206821126
FW232-DUCT SUPPORT BTW BYPASS DUCT & BUF/GGH | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 232 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821127
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW232 | 1.14.29.11.1.1.4.2.2(FW232-DUCT SUPPORT BTW BYPASS DUCT & BUF/GGH) | 206821128
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW232 | 1.14.29.11.1.1.4.2.2(FW232-DUCT SUPPORT BTW BYPASS DUCT & BUF/GGH) | 206821129
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW232 | 1.14.29.11.1.1.4.2.2(FW232-DUCT SUPPORT BTW BYPASS DUCT & BUF/GGH) | 206821130
FW234-DUCT SUPPORT B/T ABSORBER & STACK/BYPASS | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 234 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821131
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW234 | 1.14.29.11.1.1.4.2.3(FW234-DUCT SUPPORT B/T ABSORBER & STACK/BYPASS) | 206821132
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW234 | 1.14.29.11.1.1.4.2.3(FW234-DUCT SUPPORT B/T ABSORBER & STACK/BYPASS) | 206821133
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW234 | 1.14.29.11.1.1.4.2.3(FW234-DUCT SUPPORT B/T ABSORBER & STACK/BYPASS) | 206821134
FW251-EXPANSION JOINT - METALLIC | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | FW251 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821135
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW251 | 1.14.29.11.1.1.4.2.4(FW251-EXPANSION JOINT - METALLIC) | 206821136
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW251 | 1.14.29.11.1.1.4.2.4(FW251-EXPANSION JOINT - METALLIC) | 206821137
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW251 | 1.14.29.11.1.1.4.2.4(FW251-EXPANSION JOINT - METALLIC) | 206821138
FW252-EXPANSION JOINT - NON-METALLIC | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 252 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821139
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW252 | 1.14.29.11.1.1.4.2.5(FW252-EXPANSION JOINT - NON-METALLIC) | 206821140
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW252 | 1.14.29.11.1.1.4.2.5(FW252-EXPANSION JOINT - NON-METALLIC) | 206821141
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW252 | 1.14.29.11.1.1.4.2.5(FW252-EXPANSION JOINT - NON-METALLIC) | 206821142
FW255-DUCT BETWEEN BYPASS AND BUF | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 255 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821143
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW255 | 1.14.29.11.1.1.4.2.6(FW255-DUCT BETWEEN BYPASS AND BUF) | 206821144
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW255 | 1.14.29.11.1.1.4.2.6(FW255-DUCT BETWEEN BYPASS AND BUF) | 206821145
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW255 | 1.14.29.11.1.1.4.2.6(FW255-DUCT BETWEEN BYPASS AND BUF) | 206821146
FW257-DUCT BETWEEN ABSORBER AND BYPASS/STACK | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 257 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821147
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW257 | 1.14.29.11.1.1.4.2.7(FW257-DUCT BETWEEN ABSORBER AND BYPASS/STACK) | 206821148
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW257 | 1.14.29.11.1.1.4.2.7(FW257-DUCT BETWEEN ABSORBER AND BYPASS/STACK) | 206821149
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW257 | 1.14.29.11.1.1.4.2.7(FW257-DUCT BETWEEN ABSORBER AND BYPASS/STACK) | 206821150
FW267-INSULATION MATERIALS FOR DUCT | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | FW267 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821151
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW267 | 1.14.29.11.1.1.4.2.8(FW267-INSULATION MATERIALS FOR DUCT) | 206821152
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW267 | 1.14.29.11.1.1.4.2.8(FW267-INSULATION MATERIALS FOR DUCT) | 206821153
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW267 | 1.14.29.11.1.1.4.2.8(FW267-INSULATION MATERIALS FOR DUCT) | 206821154
FW268-FIXING COMPONENTS FOR DUCT | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | FW268 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821155
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW268 | 1.14.29.11.1.1.4.2.9(FW268-FIXING COMPONENTS FOR DUCT) | 206821156
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW268 | 1.14.29.11.1.1.4.2.9(FW268-FIXING COMPONENTS FOR DUCT) | 206821157
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW268 | 1.14.29.11.1.1.4.2.9(FW268-FIXING COMPONENTS FOR DUCT) | 206821158
FW269-CLADDING SHEET FOR DUCT | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 269 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821159
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW269 | 1.14.29.11.1.1.4.2.10(FW269-CLADDING SHEET FOR DUCT) | 206821160
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW269 | 1.14.29.11.1.1.4.2.10(FW269-CLADDING SHEET FOR DUCT) | 206821161
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW269 | 1.14.29.11.1.1.4.2.10(FW269-CLADDING SHEET FOR DUCT) | 206821162
FW260-DUCT STRUCTURE BETWEEN BYPASS AND BUF | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 260 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821163
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW260 | 1.14.29.11.1.1.4.2.11(FW260-DUCT STRUCTURE BETWEEN BYPASS AND BUF) | 206821164
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW260 | 1.14.29.11.1.1.4.2.11(FW260-DUCT STRUCTURE BETWEEN BYPASS AND BUF) | 206821165
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW260 | 1.14.29.11.1.1.4.2.11(FW260-DUCT STRUCTURE BETWEEN BYPASS AND BUF) | 206821166
FW262-DUCT STRUCTURE B/T ABSORBER&STACK | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 262 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821167
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW262 | 1.14.29.11.1.1.4.2.12(FW262-DUCT STRUCTURE B/T ABSORBER&STACK) | 206821168
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW262 | 1.14.29.11.1.1.4.2.12(FW262-DUCT STRUCTURE B/T ABSORBER&STACK) | 206821169
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW262 | 1.14.29.11.1.1.4.2.12(FW262-DUCT STRUCTURE B/T ABSORBER&STACK) | 206821170
FW280-FOUNDATION MATL FOR DUCT STRUCTURE | SUP | 2023-02-24 08:00 | 2024-02-29 17:00 |  |  |  | 280 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821171
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW280 | 1.14.29.11.1.1.4.2.13(FW280-FOUNDATION MATL FOR DUCT STRUCTURE) | 206821172
Manufacturing | MFG | 2023-09-13 08:00 | 2024-01-30 17:00 |  |  |  | FW280 | 1.14.29.11.1.1.4.2.13(FW280-FOUNDATION MATL FOR DUCT STRUCTURE) | 206821173
Dispatch | DIS | 2024-01-01 08:00 | 2024-02-29 17:00 |  |  |  | FW280 | 1.14.29.11.1.1.4.2.13(FW280-FOUNDATION MATL FOR DUCT STRUCTURE) | 206821174
FW297-PLATFORM FOR DUCT | SUP | 2023-02-24 08:00 | 2024-04-30 17:00 |  |  |  | 297 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821175
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW297 | 1.14.29.11.1.1.4.2.14(FW297-PLATFORM FOR DUCT) | 206821176
Manufacturing | MFG | 2023-09-13 08:00 | 2024-03-31 17:00 |  |  |  | FW297 | 1.14.29.11.1.1.4.2.14(FW297-PLATFORM FOR DUCT) | 206821177
Dispatch | DIS | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  | FW297 | 1.14.29.11.1.1.4.2.14(FW297-PLATFORM FOR DUCT) | 206821178
FW298-PLATFORM FOR G&D | SUP | 2023-02-24 08:00 | 2024-04-30 17:00 |  |  |  | 298 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821179
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW298 | 1.14.29.11.1.1.4.2.15(FW298-PLATFORM FOR G&D) | 206821180
Manufacturing | MFG | 2023-09-13 08:00 | 2024-03-31 17:00 |  |  |  | FW298 | 1.14.29.11.1.1.4.2.15(FW298-PLATFORM FOR G&D) | 206821181
Dispatch | DIS | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  | FW298 | 1.14.29.11.1.1.4.2.15(FW298-PLATFORM FOR G&D) | 206821182
FW612-GALLERIES AND RAILINGS FOR DAMPERS | SUP | 2023-02-24 08:00 | 2024-04-30 17:00 |  |  |  | 612 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821183
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW612 | 1.14.29.11.1.1.4.2.16(FW612-GALLERIES AND RAILINGS FOR DAMPERS) | 206821184
Manufacturing | MFG | 2023-09-13 08:00 | 2024-03-31 17:00 |  |  |  | FW612 | 1.14.29.11.1.1.4.2.16(FW612-GALLERIES AND RAILINGS FOR DAMPERS) | 206821185
Dispatch | DIS | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  | FW612 | 1.14.29.11.1.1.4.2.16(FW612-GALLERIES AND RAILINGS FOR DAMPERS) | 206821186
FW 613-GALLERIES AND RAILINGS FOR DUCTS | SUP | 2023-02-24 08:00 | 2024-04-30 17:00 |  |  |  | 613 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821187
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW613 | 1.14.29.11.1.1.4.2.17(FW 613-GALLERIES AND RAILINGS FOR DUCTS) | 206821188
Manufacturing | MFG | 2023-09-13 08:00 | 2024-03-31 17:00 |  |  |  | FW613 | 1.14.29.11.1.1.4.2.17(FW 613-GALLERIES AND RAILINGS FOR DUCTS) | 206821189
Dispatch | DIS | 2024-03-02 08:00 | 2024-04-30 17:00 |  |  |  | FW613 | 1.14.29.11.1.1.4.2.17(FW 613-GALLERIES AND RAILINGS FOR DUCTS) | 206821190
FW373-HSFG Bolt–Duct Struct | SUP | 2023-02-24 08:00 | 2024-03-30 17:00 |  |  |  | 373 | 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | 206821191
Engineering | ENG | 2023-02-24 08:00 | 2023-09-12 17:00 |  |  |  | FW373 | 1.14.29.11.1.1.4.2.18(FW373-HSFG Bolt–Duct Struct) | 206821192
Manufacturing | MFG | 2023-09-13 08:00 | 2024-02-29 17:00 |  |  |  | FW373 | 1.14.29.11.1.1.4.2.18(FW373-HSFG Bolt–Duct Struct) | 206821193
Dispatch | DIS | 2024-01-31 08:00 | 2024-03-30 17:00 |  |  |  | FW373 | 1.14.29.11.1.1.4.2.18(FW373-HSFG Bolt–Duct Struct) | 206821194
HYD- ABSORBER SLURRY RECIRCULATION PUMP | SUP | 2023-05-10 08:00 | 2025-03-18 17:00 |  |  |  |  | 1.14.29.11.1.1.4(Absorber-Supporting systems) | 206821195
RC Pump-4 NOS | OTH | 2023-05-10 08:00 | 2025-03-18 17:00 |  |  |  |  | 1.14.29.11.1.1.4.3(HYD- ABSORBER SLURRY RECIRCULATION PUMP) | 206821196
ENGINEERING & PROCUREMENT | ORD | 2023-05-10 08:00 | 2024-05-23 17:00 |  |  |  |  | 1.14.29.11.1.1.4.3.1(RC Pump-4 NOS) | 206821197
MANUFACTURING | MFG | 2024-05-24 08:00 | 2024-10-30 17:00 |  |  |  |  | 1.14.29.11.1.1.4.3.1(RC Pump-4 NOS) | 206821198
ASSEMBLY& TESTING | MFG | 2024-10-31 08:00 | 2025-02-16 17:00 |  |  |  |  | 1.14.29.11.1.1.4.3.1(RC Pump-4 NOS) | 206821199
Dispatch OF ABSORBER SLURRY RECIRCULATION PUMP AND ALL ASSOCIATED ITEMS | DIS | 2025-02-17 08:00 | 2025-03-18 17:00 |  |  |  |  | 1.14.29.11.1.1.4.3.1(RC Pump-4 NOS) | 206821200
HYD-Oxidation blower | OTH | 2023-05-25 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.14.29.11.1.1.4(Absorber-Supporting systems) | 206821201
Oxidation Blower-A(100% Capacity, 1 Standby) | OTH | 2023-05-25 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.14.29.11.1.1.4.4(HYD-Oxidation blower) | 206821202
ENGINEERING & PROCUREMENT | ORD | 2023-05-25 08:00 | 2024-06-07 17:00 |  |  |  |  | 1.14.29.11.1.1.4.4.1(Oxidation Blower-A(100% Capacity, 1 Standby)) | 206821203
MANUFACTURING | MFG | 2024-06-08 08:00 | 2024-11-14 17:00 |  |  |  |  | 1.14.29.11.1.1.4.4.1(Oxidation Blower-A(100% Capacity, 1 Standby)) | 206821204
ASSEMBLY& TESTING | MFG | 2024-11-15 08:00 | 2025-03-03 17:00 |  |  |  |  | 1.14.29.11.1.1.4.4.1(Oxidation Blower-A(100% Capacity, 1 Standby)) | 206821205
Dispatch OF OXIDATION AIR BLOWER AND ALL ASSOCIATED ITEMS | DIS | 2025-03-04 08:00 | 2025-04-02 17:00 |  |  |  |  | 1.14.29.11.1.1.4.4.1(Oxidation Blower-A(100% Capacity, 1 Standby)) | 206821206
Absorber Handling System | OTH | 2023-02-24 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.11.1.1.4(Absorber-Supporting systems) | 206821207
FH990-ABSORBER ISLAND-HANDLING SYSTEM-BOI | SUP | 2023-02-24 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.11.1.1.4.5(Absorber Handling System) | 206821208
Ordering | ORD | 2023-02-24 08:00 | 2023-04-14 17:00 |  |  |  |  | 1.14.29.11.1.1.4.5.1(FH990-ABSORBER ISLAND-HANDLING SYSTEM-BOI) | 206821209
Engineering | ENG | 2023-04-15 08:00 | 2023-09-21 17:00 |  |  |  |  | 1.14.29.11.1.1.4.5.1(FH990-ABSORBER ISLAND-HANDLING SYSTEM-BOI) | 206821210
Manufacturing | MFG | 2023-09-22 08:00 | 2024-07-12 17:00 |  |  |  |  | 1.14.29.11.1.1.4.5.1(FH990-ABSORBER ISLAND-HANDLING SYSTEM-BOI) | 206821211
Dispatch | DIS | 2024-05-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.11.1.1.4.5.1(FH990-ABSORBER ISLAND-HANDLING SYSTEM-BOI) | 206821212
Absorber Piping &Valves | OTH | 2023-02-24 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206821213
FW860-FRP PIPING (LS,GS) | SUP | 2023-02-24 08:00 | 2024-03-29 17:00 |  |  |  | 860 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821214
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW860 | 1.14.29.11.1.1.5.1(FW860-FRP PIPING (LS,GS)) | 206821215
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW860 | 1.14.29.11.1.1.5.1(FW860-FRP PIPING (LS,GS)) | 206821216
Manufacturing | MFG | 2023-08-23 08:00 | 2024-02-28 17:00 |  |  |  | FW860 | 1.14.29.11.1.1.5.1(FW860-FRP PIPING (LS,GS)) | 206821217
Dispatch | DIS | 2024-01-30 08:00 | 2024-03-29 17:00 |  |  |  | FW860 | 1.14.29.11.1.1.5.1(FW860-FRP PIPING (LS,GS)) | 206821218
FW861-CSRL PIPE-1 (GS,LS) | SUP | 2023-02-24 08:00 | 2024-03-29 17:00 |  |  |  | 861 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821219
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW861 | 1.14.29.11.1.1.5.2(FW861-CSRL PIPE-1 (GS,LS)) | 206821220
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW861 | 1.14.29.11.1.1.5.2(FW861-CSRL PIPE-1 (GS,LS)) | 206821221
Manufacturing | MFG | 2023-08-23 08:00 | 2024-02-28 17:00 |  |  |  | FW861 | 1.14.29.11.1.1.5.2(FW861-CSRL PIPE-1 (GS,LS)) | 206821222
Dispatch | DIS | 2024-01-30 08:00 | 2024-03-29 17:00 |  |  |  | FW861 | 1.14.29.11.1.1.5.2(FW861-CSRL PIPE-1 (GS,LS)) | 206821223
FW862-CSRL PIPE-2 (GS,LS) | SUP | 2023-02-24 08:00 | 2024-06-07 17:00 |  |  |  | 862 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821224
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW862 | 1.14.29.11.1.1.5.3(FW862-CSRL PIPE-2 (GS,LS)) | 206821225
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW862 | 1.14.29.11.1.1.5.3(FW862-CSRL PIPE-2 (GS,LS)) | 206821226
Manufacturing | MFG | 2023-08-23 08:00 | 2024-05-08 17:00 |  |  |  | FW862 | 1.14.29.11.1.1.5.3(FW862-CSRL PIPE-2 (GS,LS)) | 206821227
Dispatch | DIS | 2024-04-09 08:00 | 2024-06-07 17:00 |  |  |  | FW862 | 1.14.29.11.1.1.5.3(FW862-CSRL PIPE-2 (GS,LS)) | 206821228
FW863-CS PIPING (PW,CW,SW) | SUP | 2023-02-24 08:00 | 2024-06-07 17:00 |  |  |  | 863 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821229
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  | FW863 | 1.14.29.11.1.1.5.4(FW863-CS PIPING (PW,CW,SW)) | 206821230
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  | FW863 | 1.14.29.11.1.1.5.4(FW863-CS PIPING (PW,CW,SW)) | 206821231
Manufacturing | MFG | 2023-08-23 08:00 | 2024-05-08 17:00 |  |  |  | FW863 | 1.14.29.11.1.1.5.4(FW863-CS PIPING (PW,CW,SW)) | 206821232
Dispatch | DIS | 2024-04-09 08:00 | 2024-06-07 17:00 |  |  |  | FW863 | 1.14.29.11.1.1.5.4(FW863-CS PIPING (PW,CW,SW)) | 206821233
FW864-SS PIPING (W/D) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 864 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821234
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW864 | 1.14.29.11.1.1.5.5(FW864-SS PIPING (W/D)) | 206821235
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW864 | 1.14.29.11.1.1.5.5(FW864-SS PIPING (W/D)) | 206821236
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW864 | 1.14.29.11.1.1.5.5(FW864-SS PIPING (W/D)) | 206821237
FW865-GI PIPING (IA, DW) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 865 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821238
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW865 | 1.14.29.11.1.1.5.6(FW865-GI PIPING (IA, DW)) | 206821239
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW865 | 1.14.29.11.1.1.5.6(FW865-GI PIPING (IA, DW)) | 206821240
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW865 | 1.14.29.11.1.1.5.6(FW865-GI PIPING (IA, DW)) | 206821241
FW866-FASTENERS CS & SS | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 866 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821242
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW866 | 1.14.29.11.1.1.5.7(FW866-FASTENERS CS & SS) | 206821243
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW866 | 1.14.29.11.1.1.5.7(FW866-FASTENERS CS & SS) | 206821244
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW866 | 1.14.29.11.1.1.5.7(FW866-FASTENERS CS & SS) | 206821245
FW867-RUBBER GASKET, SHEET | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 867 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821246
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW867 | 1.14.29.11.1.1.5.8(FW867-RUBBER GASKET, SHEET) | 206821247
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW867 | 1.14.29.11.1.1.5.8(FW867-RUBBER GASKET, SHEET) | 206821248
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW867 | 1.14.29.11.1.1.5.8(FW867-RUBBER GASKET, SHEET) | 206821249
FW868-U-BOLTS | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 868 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821250
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW868 | 1.14.29.11.1.1.5.9(FW868-U-BOLTS) | 206821251
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW868 | 1.14.29.11.1.1.5.9(FW868-U-BOLTS) | 206821252
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW868 | 1.14.29.11.1.1.5.9(FW868-U-BOLTS) | 206821253
FW869-RUBBER EXP. BELLOWS | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 869 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821254
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW869 | 1.14.29.11.1.1.5.10(FW869-RUBBER EXP. BELLOWS) | 206821255
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW869 | 1.14.29.11.1.1.5.10(FW869-RUBBER EXP. BELLOWS) | 206821256
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW869 | 1.14.29.11.1.1.5.10(FW869-RUBBER EXP. BELLOWS) | 206821257
FW870-PIPING ACC. | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 870 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821258
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW870 | 1.14.29.11.1.1.5.11(FW870-PIPING ACC.) | 206821259
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW870 | 1.14.29.11.1.1.5.11(FW870-PIPING ACC.) | 206821260
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW870 | 1.14.29.11.1.1.5.11(FW870-PIPING ACC.) | 206821261
FW871-PIPING SUPPORT STRUCTURES | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 871 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821262
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW871 | 1.14.29.11.1.1.5.12(FW871-PIPING SUPPORT STRUCTURES) | 206821263
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW871 | 1.14.29.11.1.1.5.12(FW871-PIPING SUPPORT STRUCTURES) | 206821264
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW871 | 1.14.29.11.1.1.5.12(FW871-PIPING SUPPORT STRUCTURES) | 206821265
FW875-FRP PIPING (LOT-2) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 875 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821266
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW875 | 1.14.29.11.1.1.5.13(FW875-FRP PIPING (LOT-2)) | 206821267
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW875 | 1.14.29.11.1.1.5.13(FW875-FRP PIPING (LOT-2)) | 206821268
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW875 | 1.14.29.11.1.1.5.13(FW875-FRP PIPING (LOT-2)) | 206821269
FW876-CSRL PIPIE-1 (LOT-2) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 876 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821270
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW876 | 1.14.29.11.1.1.5.14(FW876-CSRL PIPIE-1 (LOT-2)) | 206821271
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW876 | 1.14.29.11.1.1.5.14(FW876-CSRL PIPIE-1 (LOT-2)) | 206821272
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW876 | 1.14.29.11.1.1.5.14(FW876-CSRL PIPIE-1 (LOT-2)) | 206821273
FW877-CS PIPING (LOT-2) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 877 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821274
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW877 | 1.14.29.11.1.1.5.15(FW877-CS PIPING (LOT-2)) | 206821275
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW877 | 1.14.29.11.1.1.5.15(FW877-CS PIPING (LOT-2)) | 206821276
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW877 | 1.14.29.11.1.1.5.15(FW877-CS PIPING (LOT-2)) | 206821277
FW878-SS PIPING (LOT-2) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 878 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821278
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW878 | 1.14.29.11.1.1.5.16(FW878-SS PIPING (LOT-2)) | 206821279
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW878 | 1.14.29.11.1.1.5.16(FW878-SS PIPING (LOT-2)) | 206821280
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW878 | 1.14.29.11.1.1.5.16(FW878-SS PIPING (LOT-2)) | 206821281
FW- Balance Valves & Commissioning spares | SUP | 2023-11-01 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821282
Engineering | ENG | 2023-11-01 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.29.11.1.1.5.17(FW- Balance Valves & Commissioning spares) | 206821283
Manufacturing | MFG | 2024-06-28 08:00 | 2025-06-07 17:00 |  |  |  |  | 1.14.29.11.1.1.5.17(FW- Balance Valves & Commissioning spares) | 206821284
Dispatch | DIS | 2025-05-09 08:00 | 2025-07-07 17:00 |  |  |  |  | 1.14.29.11.1.1.5.17(FW- Balance Valves & Commissioning spares) | 206821285
FW879-GI PIPING (LOT-2) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 879 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821286
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW879 | 1.14.29.11.1.1.5.18(FW879-GI PIPING (LOT-2)) | 206821287
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW879 | 1.14.29.11.1.1.5.18(FW879-GI PIPING (LOT-2)) | 206821288
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW879 | 1.14.29.11.1.1.5.18(FW879-GI PIPING (LOT-2)) | 206821289
FW880-PIPING ACC (LOT-2) | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 880 | 1.14.29.11.1.1.5(Absorber Piping &Valves) | 206821290
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW880 | 1.14.29.11.1.1.5.19(FW880-PIPING ACC (LOT-2)) | 206821291
Manufacturing | MFG | 2023-10-22 08:00 | 2024-09-30 17:00 |  |  |  | FW880 | 1.14.29.11.1.1.5.19(FW880-PIPING ACC (LOT-2)) | 206821292
Dispatch | DIS | 2024-09-01 08:00 | 2024-10-30 17:00 |  |  |  | FW880 | 1.14.29.11.1.1.5.19(FW880-PIPING ACC (LOT-2)) | 206821293
Absorber Elevator | SUP | 2023-02-24 08:00 | 2025-09-16 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206821294
Ordering | ORD | 2023-02-24 08:00 | 2023-04-15 17:00 |  |  |  |  | 1.14.29.11.1.1.6(Absorber Elevator) | 206821295
Engineering | ENG | 2023-04-16 08:00 | 2023-08-13 17:00 |  |  |  |  | 1.14.29.11.1.1.6(Absorber Elevator) | 206821296
Manufacturing | MFG | 2023-08-14 08:00 | 2024-05-19 17:00 |  |  |  |  | 1.14.29.11.1.1.6(Absorber Elevator) | 206821297
Dispatch | DIS | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  |  | 1.14.29.11.1.1.6(Absorber Elevator) | 206821298
FW282-FOUNDATION MATL FOR ELEVATOR | SUP | 2024-05-05 08:00 | 2024-08-12 17:00 |  |  |  | FW282 | 1.14.29.11.1.1.6.4(Dispatch) | 206821299
FW372-HSFG Bolt–Elevator Struct | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 372 | 1.14.29.11.1.1.6.4(Dispatch) | 206821300
FW380-Elevator Column | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 380 | 1.14.29.11.1.1.6.4(Dispatch) | 206821301
FW381-Elevator Beam and Bracing | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 381 | 1.14.29.11.1.1.6.4(Dispatch) | 206821302
FW382-Elevator Floors | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 382 | 1.14.29.11.1.1.6.4(Dispatch) | 206821303
FW383-Elevator Stair and Hand rail | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 383 | 1.14.29.11.1.1.6.4(Dispatch) | 206821304
FW384-Elevator Floor grill | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 384 | 1.14.29.11.1.1.6.4(Dispatch) | 206821305
FW385-Elevator M/c room & Guide | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 385 | 1.14.29.11.1.1.6.4(Dispatch) | 206821306
FW386-Inter-connecting platform to Abs | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | 386 | 1.14.29.11.1.1.6.4(Dispatch) | 206821307
FW293- Elevators and Accessories | SUP | 2024-05-05 08:00 | 2024-11-20 17:00 |  |  |  | FW293 | 1.14.29.11.1.1.6.4(Dispatch) | 206821308
Erection and commissioning | ERC | 2024-11-21 08:00 | 2025-09-16 17:00 |  |  |  |  | 1.14.29.11.1.1.6(Absorber Elevator) | 206821309
Absorber Consumables, Linings & Insulation, Casing etc. | SUP | 2023-02-24 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.29.11.1.1(Engineering and Supplies) | 206821310
FL210-FIXING COMPONENTS FOR FGD SYSTEM | SUP | 2023-11-01 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | 206821311
Engineering | ENG | 2023-11-01 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.29.11.1.1.7.1(FL210-FIXING COMPONENTS FOR FGD SYSTEM) | 206821312
Manufacturing | MFG | 2024-06-28 08:00 | 2025-04-03 17:00 |  |  |  |  | 1.14.29.11.1.1.7.1(FL210-FIXING COMPONENTS FOR FGD SYSTEM) | 206821313
Dispatch | DIS | 2025-03-05 08:00 | 2025-05-03 17:00 |  |  |  |  | 1.14.29.11.1.1.7.1(FL210-FIXING COMPONENTS FOR FGD SYSTEM) | 206821314
FL221-MINERAL WOOL FOR FGD SYSTEM-BOI | SUP | 2024-05-29 08:00 | 2025-09-29 17:00 |  |  |  |  | 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | 206821315
Ordering | ORD | 2024-05-29 08:00 | 2024-09-25 17:00 |  |  |  |  | 1.14.29.11.1.1.7.2(FL221-MINERAL WOOL FOR FGD SYSTEM-BOI) | 206821316
Engineering | ENG | 2024-07-28 08:00 | 2024-11-23 17:00 |  |  |  |  | 1.14.29.11.1.1.7.2(FL221-MINERAL WOOL FOR FGD SYSTEM-BOI) | 206821317
Manufacturing | MFG | 2024-11-24 08:00 | 2025-08-30 17:00 |  |  |  |  | 1.14.29.11.1.1.7.2(FL221-MINERAL WOOL FOR FGD SYSTEM-BOI) | 206821318
Dispatch | DIS | 2025-08-01 08:00 | 2025-09-29 17:00 |  |  |  |  | 1.14.29.11.1.1.7.2(FL221-MINERAL WOOL FOR FGD SYSTEM-BOI) | 206821319
FL700-BULKED DD COMPONENTS FOR FGD SYSTEM | SUP | 2024-04-14 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | 206821320
Ordering & Engineering | ORD | 2024-04-14 08:00 | 2024-09-10 17:00 |  |  |  |  | 1.14.29.11.1.1.7.3(FL700-BULKED DD COMPONENTS FOR FGD SYSTEM) | 206821321
Manufacturing | MFG | 2024-09-11 08:00 | 2025-07-17 17:00 |  |  |  |  | 1.14.29.11.1.1.7.3(FL700-BULKED DD COMPONENTS FOR FGD SYSTEM) | 206821322
Dispatch | DIS | 2025-06-18 08:00 | 2025-08-16 17:00 |  |  |  |  | 1.14.29.11.1.1.7.3(FL700-BULKED DD COMPONENTS FOR FGD SYSTEM) | 206821323
FL701-BPS FASTENERS FOR FGD SYSTEM | SUP | 2024-04-14 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | 206821324
Engineering | ENG | 2024-04-14 08:00 | 2024-12-09 17:00 |  |  |  |  | 1.14.29.11.1.1.7.4(FL701-BPS FASTENERS FOR FGD SYSTEM) | 206821325
Manufacturing | MFG | 2024-12-10 08:00 | 2025-09-15 17:00 |  |  |  |  | 1.14.29.11.1.1.7.4(FL701-BPS FASTENERS FOR FGD SYSTEM) | 206821326
Dispatch | DIS | 2025-08-17 08:00 | 2025-10-15 17:00 |  |  |  |  | 1.14.29.11.1.1.7.4(FL701-BPS FASTENERS FOR FGD SYSTEM) | 206821327
FL810-OUTER CASING FOR FGD SYSTEM-BOI | SUP | 2023-02-24 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | 206821328
Ordering | ORD | 2023-02-24 08:00 | 2023-06-23 17:00 |  |  |  |  | 1.14.29.11.1.1.7.5(FL810-OUTER CASING FOR FGD SYSTEM-BOI) | 206821329
Engineering | ENG | 2023-04-25 08:00 | 2023-08-22 17:00 |  |  |  |  | 1.14.29.11.1.1.7.5(FL810-OUTER CASING FOR FGD SYSTEM-BOI) | 206821330
Manufacturing | MFG | 2023-08-23 08:00 | 2024-06-27 17:00 |  |  |  |  | 1.14.29.11.1.1.7.5(FL810-OUTER CASING FOR FGD SYSTEM-BOI) | 206821331
Dispatch | DIS | 2024-05-29 08:00 | 2024-07-27 17:00 |  |  |  |  | 1.14.29.11.1.1.7.5(FL810-OUTER CASING FOR FGD SYSTEM-BOI) | 206821332
FZ990-SPECIAL WELDING ELECTRODE | SUP | 2023-02-24 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | 206821333
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.11.1.1.7.6(FZ990-SPECIAL WELDING ELECTRODE) | 206821334
Manufacturing | MFG | 2023-10-22 08:00 | 2024-03-04 17:00 |  |  |  |  | 1.14.29.11.1.1.7.6(FZ990-SPECIAL WELDING ELECTRODE) | 206821335
Dispatch | DIS | 2024-02-04 08:00 | 2024-04-03 17:00 |  |  |  |  | 1.14.29.11.1.1.7.6(FZ990-SPECIAL WELDING ELECTRODE) | 206821336
Civil Works | OTH | 2023-08-23 08:00 | 2024-12-11 17:00 |  |  |  |  | 1.14.29.11.1(Absorber) | 206821337
Absorber-Main structure | OTH | 2024-01-02 08:00 | 2024-10-22 17:00 |  |  |  |  | 1.14.29.11.1.2(Civil Works) | 206821338
RFC Civil | PE - RFC | 2024-01-02 08:00 | 2024-02-05 17:00 |  |  |  |  | 1.14.29.11.1.2.1(Absorber-Main structure) | 206821339
Excavation | CIV | 2024-02-06 08:00 | 2024-04-25 17:00 |  |  |  |  | 1.14.29.11.1.2.1(Absorber-Main structure) | 206821340
RCC | CIV | 2024-04-26 08:00 | 2024-10-22 17:00 |  |  |  |  | 1.14.29.11.1.2.1(Absorber-Main structure) | 206821341
Absorber-Supporting systems | OTH | 2024-02-21 08:00 | 2024-12-11 17:00 |  |  |  |  | 1.14.29.11.1.2(Civil Works) | 206821342
RFC of RC Pump foundation drawing | PE - RFC | 2024-02-21 08:00 | 2024-03-21 17:00 |  |  |  |  | 1.14.29.11.1.2.2(Absorber-Supporting systems) | 206821343
RCC | CIV | 2024-06-15 08:00 | 2024-07-14 17:00 |  |  |  |  | 1.14.29.11.1.2.2(Absorber-Supporting systems) | 206821344
RFC of Oxidation Blower foundation drawing | PE - RFC | 2024-02-26 08:00 | 2024-03-26 17:00 |  |  |  |  | 1.14.29.11.1.2.2(Absorber-Supporting systems) | 206821345
RCC | CIV | 2024-06-15 08:00 | 2024-12-11 17:00 |  |  |  |  | 1.14.29.11.1.2.2(Absorber-Supporting systems) | 206821346
RC PUMP Shed | CIV | 2023-08-23 08:00 | 2024-09-07 17:00 |  |  |  |  | 1.14.29.11.1.2(Civil Works) | 206821347
RFC Civil OB & RC Pump Shed Foundation drawing | PE - RFC | 2023-08-23 08:00 | 2023-10-21 17:00 |  |  |  |  | 1.14.29.11.1.2.3(RC PUMP Shed) | 206821348
RFC Civil OB & RC Pump Shed Super structure | PE - RFC | 2023-10-22 08:00 | 2023-12-20 17:00 |  |  |  |  | 1.14.29.11.1.2.3(RC PUMP Shed) | 206821349
Excavation | CIV | 2024-04-11 08:00 | 2024-06-09 17:00 |  |  |  |  | 1.14.29.11.1.2.3(RC PUMP Shed) | 206821350
RCC | CIV | 2024-06-10 08:00 | 2024-09-07 17:00 |  |  |  |  | 1.14.29.11.1.2.3(RC PUMP Shed) | 206821351
Erection | ERC | 2024-09-08 08:00 | 2025-12-28 17:00 |  |  |  |  | 1.14.29.11.1(Absorber) | 206821352
Absorber-Main structure | ERC | 2024-10-23 08:00 | 2025-08-06 17:00 |  |  |  |  | 1.14.29.11.1.3(Erection) | 206821353
Absorber Internals | ERC | 2025-05-22 08:00 | 2025-09-18 17:00 |  |  |  |  | 1.14.29.11.1.3(Erection) | 206821354
Absorber-Supporting systems | ERC | 2024-09-08 08:00 | 2025-08-08 17:00 |  |  |  |  | 1.14.29.11.1.3(Erection) | 206821355
RC Pump Shed | ERC | 2024-09-08 08:00 | 2025-02-04 17:00 |  |  |  |  | 1.14.29.11.1.3.3(Absorber-Supporting systems) | 206821356
HSFG BOLT-RC SHED-BOI | OTH | 2024-09-08 08:00 | 2024-10-22 17:00 |  |  |  |  | 1.14.29.11.1.3.3.1(RC Pump Shed) | 206821357
STRUCTURES - RC PUMP HOUSE | OTH | 2024-09-08 08:00 | 2024-12-06 17:00 |  |  |  |  | 1.14.29.11.1.3.3.1(RC Pump Shed) | 206821358
RC PUMP HOUSE CLADDING SHEETS-BOI | OTH | 2024-12-07 08:00 | 2025-02-04 17:00 |  |  |  |  | 1.14.29.11.1.3.3.1(RC Pump Shed) | 206821359
Absorbers Inter connecting Platforms | OTH | 2025-07-10 08:00 | 2025-08-08 17:00 |  |  |  |  | 1.14.29.11.1.3.3(Absorber-Supporting systems) | 206821360
FZ340-INTER-CONNECTING PLTF TO ABS | OTH | 2025-07-10 08:00 | 2025-08-08 17:00 |  |  |  |  | 1.14.29.11.1.3.3.2(Absorbers Inter connecting Platforms) | 206821361
RC Pump | OTH | 2025-04-18 08:00 | 2025-06-16 17:00 |  |  |  |  | 1.14.29.11.1.3.3(Absorber-Supporting systems) | 206821362
Oxidation blower | OTH | 2025-04-18 08:00 | 2025-06-21 17:00 |  |  |  |  | 1.14.29.11.1.3.3(Absorber-Supporting systems) | 206821363
Absorber Quenching Water Tank | OTH | 2025-05-21 08:00 | 2025-06-09 17:00 |  |  |  |  | 1.14.29.11.1.3.3(Absorber-Supporting systems) | 206821364
Absorber Piping & Valves | ERC | 2025-08-07 08:00 | 2025-12-04 17:00 |  |  |  |  | 1.14.29.11.1.3(Erection) | 206821365
Absorber Consumables, Linings & Insulation, Casing etc. | ERC | 2025-09-30 08:00 | 2025-12-28 17:00 |  |  |  |  | 1.14.29.11.1.3(Erection) | 206821366
Balance BOIs of Absorber | SUP | 2023-02-24 08:00 | 2025-04-28 17:00 |  |  |  |  | 1.14.29.11(Sub Systems) | 206821367
FW390-C276- Special welding electrode - part1 | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 390 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821368
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW390 | 1.14.29.11.2.1(FW390-C276- Special welding electrode - part1) | 206821369
Procurement | OTH | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW390 | 1.14.29.11.2.1(FW390-C276- Special welding electrode - part1) | 206821370
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW390 | 1.14.29.11.2.1(FW390-C276- Special welding electrode - part1) | 206821371
FW391-C276- Special welding electrode - part2 | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 391 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821372
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW391 | 1.14.29.11.2.2(FW391-C276- Special welding electrode - part2) | 206821373
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW391 | 1.14.29.11.2.2(FW391-C276- Special welding electrode - part2) | 206821374
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW391 | 1.14.29.11.2.2(FW391-C276- Special welding electrode - part2) | 206821375
FW392-Ti - Special welding electrode - part1 | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 392 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821376
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW392 | 1.14.29.11.2.3(FW392-Ti - Special welding electrode - part1) | 206821377
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW392 | 1.14.29.11.2.3(FW392-Ti - Special welding electrode - part1) | 206821378
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW392 | 1.14.29.11.2.3(FW392-Ti - Special welding electrode - part1) | 206821379
FW393-Ti - Special welding electrode - part2 | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 393 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821380
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW393 | 1.14.29.11.2.4(FW393-Ti - Special welding electrode - part2) | 206821381
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW393 | 1.14.29.11.2.4(FW393-Ti - Special welding electrode - part2) | 206821382
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW393 | 1.14.29.11.2.4(FW393-Ti - Special welding electrode - part2) | 206821383
FW725-Nozzle and Flanges | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 725 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821384
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW725 | 1.14.29.11.2.5(FW725-Nozzle and Flanges) | 206821385
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW725 | 1.14.29.11.2.5(FW725-Nozzle and Flanges) | 206821386
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW725 | 1.14.29.11.2.5(FW725-Nozzle and Flanges) | 206821387
FW710-MONORAIL FOR HOIST & CRANES | SUP | 2023-08-23 08:00 | 2025-04-28 17:00 |  |  |  | FW710 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821388
Engineering | ENG | 2023-08-23 08:00 | 2024-04-18 17:00 |  |  |  | FW710 | 1.14.29.11.2.6(FW710-MONORAIL FOR HOIST & CRANES) | 206821389
Manufacturing | MFG | 2024-04-19 08:00 | 2025-02-27 17:00 |  |  |  | FW710 | 1.14.29.11.2.6(FW710-MONORAIL FOR HOIST & CRANES) | 206821390
Dispatch | DIS | 2025-01-29 08:00 | 2025-04-28 17:00 |  |  |  | FW710 | 1.14.29.11.2.6(FW710-MONORAIL FOR HOIST & CRANES) | 206821391
FW717-MAN HOLE DOOR | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 717 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821392
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW717 | 1.14.29.11.2.7(FW717-MAN HOLE DOOR) | 206821393
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW717 | 1.14.29.11.2.7(FW717-MAN HOLE DOOR) | 206821394
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW717 | 1.14.29.11.2.7(FW717-MAN HOLE DOOR) | 206821395
FW718 -ROOFING SHEET | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 718 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821396
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW718 | 1.14.29.11.2.8(FW718 -ROOFING SHEET) | 206821397
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW718 | 1.14.29.11.2.8(FW718 -ROOFING SHEET) | 206821398
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW718 | 1.14.29.11.2.8(FW718 -ROOFING SHEET) | 206821399
FW992-Test Piece - C276 | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 992 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821400
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW992 | 1.14.29.11.2.9(FW992-Test Piece - C276) | 206821401
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW992 | 1.14.29.11.2.9(FW992-Test Piece - C276) | 206821402
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW992 | 1.14.29.11.2.9(FW992-Test Piece - C276) | 206821403
FW993-Test Piece - Ti | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 993 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821404
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW993 | 1.14.29.11.2.10(FW993-Test Piece - Ti) | 206821405
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW993 | 1.14.29.11.2.10(FW993-Test Piece - Ti) | 206821406
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW993 | 1.14.29.11.2.10(FW993-Test Piece - Ti) | 206821407
BOI-FW223-ABSORBER SYSTEM ACCESSORIES | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW223 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821408
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW223 | 1.14.29.11.2.11(BOI-FW223-ABSORBER SYSTEM ACCESSORIES) | 206821409
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW223 | 1.14.29.11.2.11(BOI-FW223-ABSORBER SYSTEM ACCESSORIES) | 206821410
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW223 | 1.14.29.11.2.11(BOI-FW223-ABSORBER SYSTEM ACCESSORIES) | 206821411
BOI-FW227-EMERGENCY QUENCH SYSTEM | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW227 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821412
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW227 | 1.14.29.11.2.12(BOI-FW227-EMERGENCY QUENCH SYSTEM) | 206821413
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW227 | 1.14.29.11.2.12(BOI-FW227-EMERGENCY QUENCH SYSTEM) | 206821414
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW227 | 1.14.29.11.2.12(BOI-FW227-EMERGENCY QUENCH SYSTEM) | 206821415
BOI-FW228-ABSORBER-W/D INTERFACE | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW228 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821416
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW228 | 1.14.29.11.2.13(BOI-FW228-ABSORBER-W/D INTERFACE) | 206821417
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW228 | 1.14.29.11.2.13(BOI-FW228-ABSORBER-W/D INTERFACE) | 206821418
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW228 | 1.14.29.11.2.13(BOI-FW228-ABSORBER-W/D INTERFACE) | 206821419
BOI-FW229-W/D WASH SYSTEM | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW229 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821420
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW229 | 1.14.29.11.2.14(BOI-FW229-W/D WASH SYSTEM) | 206821421
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW229 | 1.14.29.11.2.14(BOI-FW229-W/D WASH SYSTEM) | 206821422
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW229 | 1.14.29.11.2.14(BOI-FW229-W/D WASH SYSTEM) | 206821423
BOI-FW235-SPECIAL FASTENERS | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 235 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821424
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW235 | 1.14.29.11.2.15(BOI-FW235-SPECIAL FASTENERS) | 206821425
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW235 | 1.14.29.11.2.15(BOI-FW235-SPECIAL FASTENERS) | 206821426
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW235 | 1.14.29.11.2.15(BOI-FW235-SPECIAL FASTENERS) | 206821427
BOI-FW239-VIEWING PORTS | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 239 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821428
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW239 | 1.14.29.11.2.16(BOI-FW239-VIEWING PORTS) | 206821429
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW239 | 1.14.29.11.2.16(BOI-FW239-VIEWING PORTS) | 206821430
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW239 | 1.14.29.11.2.16(BOI-FW239-VIEWING PORTS) | 206821431
BOI-FW243-SLURRY DISTRIBUTION SYSTEM- RC PUMP & ABSORBER | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 243 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821432
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW243 | 1.14.29.11.2.17(BOI-FW243-SLURRY DISTRIBUTION SYSTEM- RC PUMP & ABSORBER) | 206821433
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW243 | 1.14.29.11.2.17(BOI-FW243-SLURRY DISTRIBUTION SYSTEM- RC PUMP & ABSORBER) | 206821434
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW243 | 1.14.29.11.2.17(BOI-FW243-SLURRY DISTRIBUTION SYSTEM- RC PUMP & ABSORBER) | 206821435
BOI-FW244-OXIDATION AIR DISTRIBUTION SYS | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW244 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821436
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW244 | 1.14.29.11.2.18(BOI-FW244-OXIDATION AIR DISTRIBUTION SYS) | 206821437
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW244 | 1.14.29.11.2.18(BOI-FW244-OXIDATION AIR DISTRIBUTION SYS) | 206821438
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW244 | 1.14.29.11.2.18(BOI-FW244-OXIDATION AIR DISTRIBUTION SYS) | 206821439
BOI-FW249-HANDLING EQUIPMENT - RC PUMP | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 249 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821440
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW249 | 1.14.29.11.2.19(BOI-FW249-HANDLING EQUIPMENT - RC PUMP) | 206821441
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW249 | 1.14.29.11.2.19(BOI-FW249-HANDLING EQUIPMENT - RC PUMP) | 206821442
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW249 | 1.14.29.11.2.19(BOI-FW249-HANDLING EQUIPMENT - RC PUMP) | 206821443
BOI-FW252-EXPANSION JOINT- NON METALLIC | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 252 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821444
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW252 | 1.14.29.11.2.20(BOI-FW252-EXPANSION JOINT- NON METALLIC) | 206821445
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW252 | 1.14.29.11.2.20(BOI-FW252-EXPANSION JOINT- NON METALLIC) | 206821446
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW252 | 1.14.29.11.2.20(BOI-FW252-EXPANSION JOINT- NON METALLIC) | 206821447
BOI-FW267-INSULATION MATERIALS FOR DUCT | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW267 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821448
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW267 | 1.14.29.11.2.21(BOI-FW267-INSULATION MATERIALS FOR DUCT) | 206821449
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW267 | 1.14.29.11.2.21(BOI-FW267-INSULATION MATERIALS FOR DUCT) | 206821450
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW267 | 1.14.29.11.2.21(BOI-FW267-INSULATION MATERIALS FOR DUCT) | 206821451
BOI-FW268-FIXING COMPONENTS FOR DUCT | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | FW268 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821452
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW268 | 1.14.29.11.2.22(BOI-FW268-FIXING COMPONENTS FOR DUCT) | 206821453
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW268 | 1.14.29.11.2.22(BOI-FW268-FIXING COMPONENTS FOR DUCT) | 206821454
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW268 | 1.14.29.11.2.22(BOI-FW268-FIXING COMPONENTS FOR DUCT) | 206821455
BOI-FW269-CLADDING SHEET FOR DUCT | SUP | 2023-02-24 08:00 | 2024-10-30 17:00 |  |  |  | 269 | 1.14.29.11.2(Balance BOIs of Absorber) | 206821456
Engineering | ENG | 2023-02-24 08:00 | 2023-10-21 17:00 |  |  |  | FW269 | 1.14.29.11.2.23(BOI-FW269-CLADDING SHEET FOR DUCT) | 206821457
Manufacturing | MFG | 2023-10-22 08:00 | 2024-08-31 17:00 |  |  |  | FW269 | 1.14.29.11.2.23(BOI-FW269-CLADDING SHEET FOR DUCT) | 206821458
Dispatch | DIS | 2024-08-02 08:00 | 2024-10-30 17:00 |  |  |  | FW269 | 1.14.29.11.2.23(BOI-FW269-CLADDING SHEET FOR DUCT) | 206821459
JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers | SUP | 2023-06-04 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.29(FGD ) | 206821460
Engineering | ENG | 2023-06-04 08:00 | 2023-12-30 17:00 |  |  |  |  | 1.14.29.12(JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers) | 206821461
Manufacturing & testing | MFG | 2023-10-02 08:00 | 2025-01-15 17:00 |  |  |  |  | 1.14.29.12(JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers) | 206821462
Packing, Dispatch | DIS | 2024-09-18 08:00 | 2025-02-14 17:00 |  |  |  |  | 1.14.29.12(JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers) | 206821463
Erection of Aux Transformer | ERC | 2025-03-17 08:00 | 2025-08-03 17:00 |  |  |  |  | 1.14.29.12(JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers) | 206821464
Commissioning of Aux Transformer | COM | 2025-08-04 08:00 | 2025-11-01 17:00 |  |  |  |  | 1.14.29.12(JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers) | 206821465
Testing and Commissioning | COM | 2025-12-30 08:00 | 2026-02-27 17:00 |  |  |  |  | 1.14.29(FGD ) | 206821466
PEM- Sewage Treatment Plant | OTH | 2023-12-01 08:00 | 2026-06-14 17:00 |  |  |  |  | 1.14(BOP Systems) | 206821467
STP Execution Agency | PRC | 2023-12-01 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.14.30(PEM- Sewage Treatment Plant) | 206821468
Enquiry | ENQ | 2023-12-01 08:00 | 2023-12-01 17:00 |  |  |  |  | 1.14.30.1(STP Execution Agency) | 206821469
PO Placement | ORD | 2023-12-02 08:00 | 2024-03-30 17:00 |  |  |  |  | 1.14.30.1(STP Execution Agency) | 206821470
Engineering Design/Drgs | ENG | 2024-03-31 08:00 | 2024-05-29 17:00 |  |  |  |  | 1.14.30.1(STP Execution Agency) | 206821471
Supply | SUP | 2025-05-15 08:00 | 2025-05-15 17:00 |  |  |  |  | 1.14.30(PEM- Sewage Treatment Plant) | 206821472
STP: Dispatch COMPLETION of Materials | SUP | 2025-05-15 08:00 | 2025-05-15 17:00 |  |  |  |  | 1.14.30.2(Supply) | 206821473
Civil | CIV | 2024-06-15 08:00 | 2025-12-01 17:00 |  |  |  |  | 1.14.30(PEM- Sewage Treatment Plant) | 206821474
EXCAVATION | CIV | 2024-06-15 08:00 | 2024-07-29 17:00 |  |  |  |  | 1.14.30.3(Civil) | 206821475
RCC in substructure including PCC | CIV | 2024-07-30 08:00 | 2024-12-26 17:00 |  |  |  |  | 1.14.30.3(Civil) | 206821476
RCC in superstructure including equipment foundation | CIV | 2024-12-27 08:00 | 2025-09-02 17:00 |  |  |  |  | 1.14.30.3(Civil) | 206821477
Backfilling | CIV | 2025-09-03 08:00 | 2025-10-17 17:00 |  |  |  |  | 1.14.30.3(Civil) | 206821478
Finishing works | CIV | 2025-10-18 08:00 | 2025-12-01 17:00 |  |  |  |  | 1.14.30.3(Civil) | 206821479
Execution | ERC | 2026-01-01 08:00 | 2026-06-14 17:00 |  |  |  |  | 1.14.30(PEM- Sewage Treatment Plant) | 206821480
STP:E&C of STP | COM | 2026-01-01 08:00 | 2026-06-14 17:00 |  |  |  |  | 1.14.30.4(Execution) | 206821481

## LOVSheet (hidden)
|  |  |  | 206812272 |  |  |  |  | -330 | India Standard Time
Task(Task)-->1 (Engineering) | 1(EPC Package for Talcher Thermal Power Project, Stage-III (2X660MW)) | 1801 | Documents(Documents)-->BHEL REF DOC (BHEL REF DOC) | Customer | 01(Peritus) | Consultant WF | Monthly Plan - Qty | % | Consultant WF | CIV | ACC-Air Cooled Condenser | AIR PREHEATERS | Concrete | NO | Civil | Cost | (ELEC-01) Cable tray & Support | BOI | Safety Observation | High | Boiler Erection Start | HWR | AC and Ventilation System | BPL | bap-ranipet | No | Absorber Erection | Absorber Erection | 1 | NO | APR | Agency to be finalised | BOP | BPL01BFVX01 | 39 | 001 | 16222 | 47-264 | 456-9 | PCE-00100 | PAI-01300 | IPBD | LT001 | TB901 | 001 | No | No | 001 | AG Piping Erection (Inch-Mtr.) | No | N | LTHE | Project Delivery | Construction | N | LTHE-1 | No | No | N | HL | No | BOI | Close | RFC | As Late As Possible | MDR | M/s A K Infra | BAP Ranipet | LSTK | Additional Platform | 2017
Task(Task)-->3 (Construction) | 1.2(Milestones/ as per Work Schedule) | AVINASH CHANDRA | Documents(Documents)-->CHANGE MANAGEMENT (Change Management) | Internal | 123(L&T) | Document Completion |  | Cr-INR | Document Completion | COM | ACS-Air Conditioning System | DUCT ASSEMBLY | Earthwork (Backfilling) | YES | Erection | Issue Tracker | (ELEC-02) Cabling | Civil | Unsafe act | Low | Boiler lightup | PEM | Ash Handling Plant | HERP | BRBCL FGD-SITE | Yes | AES | AES | 2 | YES | Apr | BGR | Misc | BPL01FTXX01 | 48 | 002 | 16226 | 47-284 | 460-8 | PCE-00200 | PAI-06200 | SPBD | LT002 | TB902 | 002 | Yes | Yes | 002 | AG Piping Fabrication & Erection (Inch-Dia) | Yes | Y | M/S BJCL |  | Engineering | Y | LTHE-2 | Yes | Yes | Y |  | Yes | SHO | Closed |  | As Soon As Possible | SAR | M/s Advance Ventilation Pvt Ltd | FSIP Jagdishpur (FS) | NLSTK | Associated Facilties/ ETP | 2018
Task(Task)-->4 (Schedule) | 1.3(Readiness of Major Civil Foundation) | AMIT | Documents(Documents)-->CHANGE MANAGEMENT ATTACHMENT (Change Management Attachment) | Other Unit | ADVANCE(Advance Ventilation) | Internal Engineering WF |  | CUBIC METERS | Internal Engineering WF | CUS | ACW-Auxiliary Cooling Water System | ELECTROSTATIC PRECIPITATOR | Earthwork (Excavation) |  | Overall | LLI | (ELEC-03) Panel erection | Construction | Unsafe Condition | Medium | Ceiling Girder Lifting | PMG | AUX. Boiler | HPVP | CDT-NOIDA |  | Air Coolers | Air Coolers | 3 |  | Aug | Compt | SG | BPL01MTXX01 | 50 | 003 | 16231 |  | 473-1 | PCE-00300 | PAI-06300 |  | SCR001 | TB903 | 003 |  |  | 003 | AG Piping Fabrication (Inch-Dia) |  |  | M/s ABB |  | Sub Contractor |  | Toyo-1 | [6 empty] | Disposed |  | Finish No Earlier Than |  | M/s AGIIL | HPBP Trichy |  | Bagging Building | 2019
Task(Task)-->5 (Reports) | 1.4(Readiness of Major Equipment and system) | AABHIJEET | Documents(Documents)-->CONTRACTUAL DOCUMENTS (Contractual Documents)-->LETTERS (Letters) | Vendor | ALPHA(ALPHA Power) | Internal WF 1 |  | DAYS | Internal WF 1 | CUST | AHP-Ash Handling | Steam Generators | Earthwork (Levelling and Gradi |  | Supplies | Manpower Productivity | (ELEC-04) Panel charging | Construction/Resource |  |  | Coal Firing | RPT | AUX. CW System | HWR | CFFP Haridwar |  | AUX | AUX |  |  | AUG | DWEPL | TG | BPL01REJX01 | 53 | 004 | 16235 |  | 473-10 | PCE-00400 | PAI-06500 |  |  | TB904 | 004 |  |  | 004 | Erection (MT) |  |  | M/s Bharat |  |  |  | Toyo-10 | [6 empty] | Fabrication drawing has been approved and work is starting on 19 Nov-19. Submission & Approval of balance drawings is in progess. |  | Finish No Later Than |  | M/s Airox | HPBP Trichy (A. S. T. INDUSTRIES) |  | Boiler Structure | 2020
Task(Task)-->CHANGE MANAGEMENT (Change Management) | 1.5(CUSTOMER Inputs) | ANAND | Documents(Documents)-->CONTRACTUAL DOCUMENTS (Contractual Documents)-->MOM (MOM) |  | AME(AME) | Internal Workflow review |  | GEN | Internal Workflow review | DIS | AM-Agency Mobilisation |  | Finishing |  |  | Manpower Used | (ELEC-05) SPBD Erection | Construction-Civil |  |  | Completion of Trial Operation | Trrichy | Balance ESP Passes | HYD | CFP Rudrapur |  | BES | BES |  |  | Dec | HURL |  | BPL04AFDM01 | 56 | 005 | 17505 |  | 473-2 | PCE-00410 | PAI-12900 |  |  | TB905 | 005 |  |  | 005 | Fabrication (MT) |  |  | M/s Bygging |  |  |  | Toyo-11 | [6 empty] | Issue being addressed. |  | Must Finish On |  | M/s Airox Nigen Equipments Pvt. Ltd. | HPBP Trichy (GELLILE INDUSTRIES) |  | CCR Building | 2021
Task(Task)-->COST (Cost) | 1.6(Award of Sub-Contracts by PS-Region) | AKASATI | Documents(Documents)-->IPMS MANUAL (IPMS Manual) |  | APGENCO(APGENCO (Vijaywada)) | Procurement WF |  | Inch Diameter | Procurement WF | ENG | APH-Air Pre-Heater |  | Formwork |  |  | MD GANTT Chart Image | (ELEC-06) IPBD Erection | Engineering |  |  | Condenser erection start |  | Balance Fans | JHS | CO-Delhi |  | BG | BG |  |  | DEC | HURL / PDIL |  | BPL04APHM01 | 57 | 006 | 17509 |  | 473-3 | PCE-00420 | PAI-13100 |  |  | TB906 | 006 |  |  | 006 | RCC (Cum) |  |  | M/s DL Engg. |  |  |  | Toyo-12 | [6 empty] | Manpower increased maximum to 82 on 15 Nov-19. |  | Must Start On |  | M/s Akash Techno | HPBP Trichy (GREENLAND ENGINEERING INDUSTRIES) |  | Chimney | 2022
Task(Task)-->DELAY TRACKER (Delay Tracker) | 1.6.1(Construction power package including construction lighting in plant, construction water, steel yard) | ASHA ANUPAMA TIR | Documents(Documents)-->MANUALS (Manuals)-->BULK IMPORT TEMPLATE (BULK IMPORT TEMPLATE) |  | APPDCL(APPDCL (KrishnaPatnam)) | Procurement WF 1 |  | Inch Meter | Procurement WF 1 | ENQ | BLR-Boiler & Bunker |  | Grouting |  |  | Null | (ELEC-07) Transformer erection | Fabrication |  |  | Drainable Hydro Test |  | Balance Mills Readiness | PEM/V | CSM |  | BLU | BLU |  |  | Feb | HWR |  | BPL04AWPM01 | 58 | 007 | 17510 |  | 473-4 | PCE-00430 | PAI-13300 |  |  | TB907 | 007 |  |  | 007 | UG Piping Erection (Inch-Mtr.) |  |  | M/s DTH |  |  |  | Toyo-13 | [6 empty] | Manpower increased maximum to 82 on 15 Nov-19. Current manpower is ~50. |  | Start No Earlier Than |  | M/s AKS |  |  | Conveyor & Bagging building
Task(Task)-->DPR (DPR) | 1.6.2(Enabling work) | ATUL AYACHIT | Documents(Documents)-->MANUALS (Manuals)-->CREATING A WBS (Creating a WBS) |  | ARC(Architecture) | Unguided Workflow |  | JOB | Vendor Submittal WF | ERC | C&I |  | MILESTONE CIVIL |  |  | Package Summary | (ELEC-08) Transformer charging | Mechanical |  |  | PG test |  | Chimney | RPT | EDN Bangalore |  | Boiler Drum Lifting | Boiler Drum Lifting |  |  | FEB | HYD |  | BPL04BFPM01 | 62 | 011 | 17511 |  |  | PCE-00440 | PAI-13400 |  |  | TB908 | 011 |  |  | 008 | UG Piping Fabrication (Inch-Dia) |  |  | M/s Elmatics |  |  |  | Toyo-14 | [6 empty] | NPL team is coordinating with PDIL engineering team by discussing across the table as discussed in meeting dtd. 7 Nov-19 |  | Start No Later Than |  | M/s AllCargo |  |  | Conveyor gantry
Task(Task)-->ISSUE TRACKER (Issue Tracker) | 1.6.3(Civil) | ABDUL AZIZ | Documents(Documents)-->MANUALS (Manuals)-->CREATING PROJECT (CREATING PROJECT) |  | ATG(Asia Trans Gas) | Vendor Submittal WF |  | JOINTS | Vendor WF | MFG | CHI-Chimney |  | NOT DEFINED |  |  | Package Summary Score Card | (MECH-01) Preassembly | Pre Engineering |  |  | Project |  | Coal Handling Plant | TBG | EMRP Mumbai |  | Boiler SVF Safety Valve Floating | Boiler SVF (Safety Valve Floating) |  |  | JAN | Lloyds |  | BPL04CEPM01 | 70 | 012 | 17521 |  |  | PCE-00450 | PAI-15700 |  |  | TB909 | 012 |  |  | 009 |  |  |  | M/s Hamon |  |  |  | Toyo-15 | [6 empty] | Open |  |  |  | M/s Alpha |  |  | Conveyor Gantry & Transfer Tower
Task(Task)-->MAITREE (Maitree) | 1.6.3.1(Dismantling work of above ground facility) | ABC | Documents(Documents)-->MANUALS (Manuals)-->CREATING TASK TEMPLATE (Creating Task Template) |  | BAP(Boiler Auxillaries Unit) | Vendor WF |  | Kilo Meter | Vendor WF 1 | MIL | CHP-Coal Handling |  | Pilling |  |  | Productivity Benchmark | (MECH-02) Erection | Procurement |  |  | Steam Blowing Completion |  | Cooling Tower | TRY | EPD Bangalore |  | BOXUP H | BOXUP H |  |  | Jan | LTHE |  | BPL04CPRM01 |  | 013 | 17523 |  |  | PCE-00500 | PAI-15800 |  |  | TB910 | 013 |  |  | 010 |  |  |  | M/s Hayagrev |  |  |  | Toyo-16 | [6 empty] | Pending With Unit |  |  |  | M/s Alpha Power |  |  | Conveyor System
Task(Task)-->MAITREE (Maitree)-->CIV(Civil) | 1.6.3.2(Civil- SG-1+ ESP-1+FGD-1 (Absorber+Fan+ Duct up to Chimney etc)+ BAH-1+ SCR-1 + Levelling & Grading+ Below ground dismantling work and excluding Paving work of this package) | ABDUL SAYEED | Documents(Documents)-->MANUALS (Manuals)-->ENABLE DASHBOARD (ENABLE DASHBOARD) |  | BHAWANI(M/s Bhawani Erectors Pvt Ltd.) | Vendor WF 1 |  | Kilograms |  | MNF | Cooling system |  | Reinforcement |  |  | Productivity Statistics | (MECH-03) Alignment | Quality |  |  | Synchronization |  | Cooling Tower for Steam Blowing |  | FGD BARH |  | CA | CA |  |  | Jul | M/s BKR |  | BPL04CWPM01 |  | 017 | 17524 |  |  | PCE-00600 | PAP-04300 |  |  | TB911 | 017 |  |  | 011 |  |  |  | M/s Heurtey |  |  |  | Toyo-17 | [6 empty] | Previous plan submitted was not approved by HURL/PDIL. |  |  |  | M/s Ambabhawani |  |  | CPU
Task(Task)-->MAITREE (Maitree)-->CIV(Civil)-->BOI(Boiler) | 1.6.3.3(Civil -PH-1+X-mer Yard-1+ESP/FGD Control Room+ DG building + Levelling & Grading+ Below ground dismantling work) | ABGUPTA | Documents(Documents)-->MANUALS (Manuals)-->FOLDER STRUCTURE (FOLDER STRUCTURE) |  | BHEL INT(BHEL INT) |  |  | LOT |  | MOB | CPU-Condenser Polishing Unit |  | Road Works |  |  | Quality Tracker | (MECH-04) Welding | Shop |  |  | Turbine Boxup |  | CPU |  | FGD Korba |  | CC | CBE |  |  | JUL | M/s BLPL |  | BPL04DPMX01 |  | 019 | 18001 |  |  | PCE-00700 | PAP-04400 |  |  | TB912 | 019 |  |  | 012 |  |  |  | M/s Indwell |  |  |  | Toyo-18 | [6 empty] | Previous plan submitted was not approved by HURL/PDIL. Target dates of completion for activities are being mentioned in DPR. |  |  |  | M/s Anandjiwala |  |  | CPU DM Plant RWTP
Task(Task)-->MAITREE (Maitree)-->CIV(Civil)-->NDCT(NDCT) | 1.6.3.4(Switch Yard+ 33 Kv SWGR + Levelling & Grading+ Below ground dismantling work) | ABHAYKUMAR | Documents(Documents)-->MANUALS (Manuals)-->IMPORT SUPPLY (Import Supply) |  | BHEL PSER(PSER) |  |  | LUMPSUM |  | ORD | CSS-Compressed & Service air system |  | Structure(Alignment) |  |  | S Curve 1 | (MECH-05) Hangers & Supports | Store |  |  | Turbine erection start |  | DG System |  | FGD Ramagundam |  | CES | CC |  |  | JUN | M/s CCPL |  | BPL04DWSM01 |  | 022 | 18010 |  |  | PCE-00800 | PAP-04800 |  |  | TB913 | 025 |  |  | 013 |  |  |  | M/s ISGEC |  |  |  | Toyo-2 | [10 empty] | M/s Annai Infra |  |  | DM Plant
Task(Task)-->MAITREE (Maitree)-->DIS(Dispatch) | 1.6.3.5(Civil for Coal Handling Plant (CHP)) | ABHAYK | Documents(Documents)-->MANUALS (Manuals)-->ISSUE MODULE (Issue Module) |  | BHEL ROD(BHEL ROD) |  |  | METERS |  | OTH | CST- Combined System Testing |  | Structure(Erection) |  |  | S Curve 2 | (MECH-06) Equipment erection | Sub-contractor |  |  | Turbine on Barring gear |  | DM Plant for HT |  | Ghavp Site |  | CF | CCS |  |  | Jun | M/S Driplex |  | BPL04DWTM01 |  | 023 | 18101 |  |  | PCE-00900 | PAP-04900 |  |  | TB914 | 04147 |  |  | 017 |  |  |  | M/s Jaggi |  |  |  | Toyo-3 | [10 empty] | M/s Artson |  |  | Firefighting
Task(Task)-->MAITREE (Maitree)-->ERE(Erection) | 1.6.3.6(Civil for Ash Handling Plant (AHP)) | ABHAYKUMA | Documents(Documents)-->MANUALS (Manuals)-->SCHEDULLING (Schedulling) |  | Bhopal(Bhopal) |  |  | Metric Ton |  | PE - RFC | CTR-Control Room |  | Structure(Fabrication) |  |  | S Curve 3 | C&I | Supplies |  |  |  |  | Ducting with Insulation for BLU |  | HBG |  | CGL | CES |  |  | Mar | M/s Driplex/PDIL |  | BPL04FDFM01 |  | 024 | 18111 |  |  | PCE-01000 | PAP-05300 |  |  | TB915 | 04321 |  |  | 018 |  |  |  | M/s Keller |  |  |  | Toyo-4 | [10 empty] | M/s Arun Construction |  |  | IA/PA/N2
Task(Task)-->MAITREE (Maitree)-->MAN(Manufacturing) | 1.6.3.7(NDCT cooling Tower) | ABHIJIT SAHA | Documents(Documents)-->MANUALS (Manuals)-->SEE LINKAGE (See Linkage) |  | BJCL(BJCL) |  |  | NUMBERS |  | PRC | CUST-IN-Customer Inputs |  | Structure(Supply) |  |  | S Curve 4 | Commissioning Activity | [5 empty] | Electrical and C&I for BL |  | HEEP Haridwar |  | Civil Work Completion | CF |  |  | MAR | M/s DWEPL |  | BPL04IDFM01 |  | 025 | 18235 |  |  | PCE-01100 | PAP-06000 |  |  | TB916 | 04323 |  |  | 019 |  |  |  | M/s KKSEPL |  |  |  | Toyo-5 | [10 empty] | M/s Asencius |  |  | ID Duct foundation (Boiler to ESP)
Task(Task)-->MAITREE (Maitree)-->PDE(Product Engineering) | 1.6.3.8(Balance BOPs civil) | ABHILASH REDDY | Documents(Documents)-->MILESTONE DOCUMENTS (MILESTONE DOCUMENTS) |  | Boiler Erection(Boiler Erection) |  |  | Panels |  | REC | CWS-Cooling Water system |  | SWIO- Laying of Pipelines |  |  | S Curve 5 | Fab Structure Erection | [5 empty] | ESP for LU |  | HEP Bhopal |  | CIVIL_EMB | CFOAC |  |  | MAY | M/s HURL |  | BPL04MMXX01 |  | 135 | 18901 |  |  | PCE-01200 | PAP-06100 |  |  | TB917 | 04347 |  |  | 020 |  |  |  | M/S KSL |  |  |  | Toyo-6 | [10 empty] | M/s ATLAS COPCO |  |  | Inert Gas System
Task(Task)-->MAITREE (Maitree)-->PRC(Procurement) | 1.6.3.9(Civil agency for Chimney) | ABHILASH SINGH K | Documents(Documents)-->PROJECT CL (Project Closure)-->HINDERANCE REGISTER (Hinderance Register) |  | boiler(boiler) |  |  | RM |  | SUP | DDS-Drainage & Dewatering System |  | SWIO Supply |  |  | Safety Tracker | MILSTONE E&C | [5 empty] | ETP |  | HERP Varanasi |  | COF | CGL |  |  | May | M/s JNSEPL |  | BPL04PAFM01 |  | 136 | 18910 |  |  | PCE-01300 | PAP-06400 |  |  | TB918 | 04547 |  |  | 021 |  |  |  | M/S Maxcon Global |  |  |  | Toyo-7 | [10 empty] | M/s B P Construction |  |  | Instrument Air Plant
Task(Task)-->MAITREE (Maitree)-->PRE(Project Engineering) | 1.6.3.10(Civil- FGD buildings (LHP+GHP etc) + Levelling & Grading+ Below ground dismantling work) | ABHISHEK.K | Documents(Documents)-->PROJECT CL (Project Closure)-->LL (Lessons Learned) |  | BPL(Bhopal) |  |  | RMTR |  |  | DGS-DG System |  | SWIO System |  |  |  | NOT DEFINED | [5 empty] | FANs for BLU |  | hpbp-trichy |  | Commissioning | Civil Work Completion |  |  | NOV | M/S LTHE & TFMC |  | BPL04RWIM01 |  | 138 | 30771 |  |  | PCE-01400 | PAP-06600 |  |  | TB919 | 05137 |  |  | 022 |  |  |  | M/s OCCPL |  |  |  | Toyo-8 | [10 empty] | M/s B&B Developers |  |  | Intake
Task(Task)-->MAITREE (Maitree)-->SCH(Schedule) | 1.6.4(Mechanical) | ABHISHEK SRIVAST | Documents(Documents)-->PROJECT CL (Project Closure)-->PL D (Project Closure Deliverables) |  | BROTHER(M/s Brother) |  |  | SET |  |  | DMP-DM Plant |  | SWIO-Anchor Blocks | [9 empty] | FGD |  | HPEP |  | Completion Of Basic Engineering | CIVIL_EMB |  |  | Nov | M/s Nice Pvt. Ltd |  | BPL06GTXX01 |  | 139 | 30941 |  |  | PCE-01500 | PAP-14300 |  |  | TB920 | 05147 |  |  | 023 |  |  |  | M/s Power Mech Projects Ltd |  |  |  | Toyo-9 | [10 empty] | M/s B&R |  |  | Intake PH
Task(Task)-->MAITREE (Maitree)-->SUP(Supply) | 1.6.4.1(Mechanical – Boiler, Aux Boiler & Bunker) | ABHISHEK | Documents(Documents)-->PROJECT CLOSURE (PROJECT CLOSURE)-->CONFIDENTIAL CERTIFICATES (ACCEPTANCE CERTIFICATES) |  | BYGGING(M/s BYGGING India Ltd.) |  |  | SQUARE METERS |  |  | DOS-Dosing systems | [11 empty] | Fire fighting System for BLU |  | HPEP Hyderabad |  | CST | COF |  |  | Oct | M/S Nice Pvt. Ltd. HURL / PDIL |  | BPL06NGRX01 |  | 145 | 61001 |  |  | PCE-01600 | PAP-14400 |  |  | TB921 | 05155 |  |  | 024 |  |  |  | M/s Pranam |  |  |  | TPFMC/ LTHE - 1 | [10 empty] | M/s Backbone Construction Pvt Ltd |  |  | Intake Pump House
Task(Task)-->MD GANTT CHART (MD Gantt Chart) | 1.6.4.2(Mechanical – ESP & FGD) | ABHISHEK KUMAR | Documents(Documents)-->PROJECT CLOSURE (PROJECT CLOSURE)-->HINDERANCE REGISTER(Hinderance Register) |  | C&I(C&I) | [5 empty] | DUC-Ducting | [11 empty] | Fuel oil System |  | HPVP Vizag |  | CTO | Commissioning |  |  | OCT | M/s Nice Pvt. Ltd./PDIL |  | BPL06SHRX01 |  | 149 | 61101 |  |  | PCE-01700 | PAP-15000 |  |  | TB922 | 05227 |  |  | 025 |  |  |  | M/s Reyna |  |  |  | TPFMC/ LTHE - 2 | [10 empty] | M/s BGRE |  |  | Intake System
Task(Task)-->PANKI (Panki) | 1.6.4.3( Power Cycle Piping ) | ABHISHEK TIWARI | Documents(Documents)-->PROJECT CLOSURE (PROJECT CLOSURE)-->LL(Lessons Learned) |  | CEB(Central Electricity Board, Mauritius) | [5 empty] | ELE-Electrical cabling ducts & switchgears | [11 empty] | IA & SA System |  | HYDERABAD |  | DDA | Completion Of Basic Engineering |  |  | SEP | M/s PDIL |  | BPL09GRPX01 |  | 150 | 61103 |  |  | PCE-01800 | PCI-00100 |  |  | TB923 | 05231 |  |  | 030 |  |  |  | M/S S. K. Sharma |  |  |  | TPFMC/ LTHE - 3 | [10 empty] | M/s Bhawani Erectors Pvt Ltd. |  |  | M/s Driplex/PDIL
Task(Task)-->PANKI (Panki)-->CIV(Civil) | 1.6.4.4(Steam Turbine & Generator) | ABLAKRA | Documents(Documents)-->PROJECT CLOSURE (PROJECT CLOSURE)-->PL D(Project Closure Deliverables) |  | ce-pmc(ce-pmc) | [5 empty] | ELV-Elevator | [11 empty] | MDBFP |  | Industry Sector New Delhi |  | DIS BB | CST |  |  | Sep | M/S Technip HURL / PDIL |  | BPL09HTSG01 |  | 153 | 61201 |  |  | PCE-01900 | PCI-10100 |  |  | TB924 | 05251 |  |  | 04 |  |  |  | M/s VNC |  |  |  | TPFMC-1 | [10 empty] | M/s BHEL |  |  | M/s Nice Pvt. Ltd
Task(Task)-->PANKI (Panki)-->CIV(Civil)-->BOI(Boiler) | 1.6.4.5(Structure:- Power House) | ACHIN GOYAL | Documents(Documents)-->PROJECT CLOSURE (PROJECT CLOSURE)-->POST PROJECT NOTES (POST PROJECT NOTES ANALYSIS) |  | cfp(cfp) | [5 empty] | EMU – Electric Multiple Unit | [11 empty] | Mills for Coal Firing |  | International Operations New Delhi |  | DIS BS | CTO |  |  |  | M/s Technip/ HURL / PDIL |  | BPL09HTSG02 |  | BOI | 61301 |  |  | PCE-02000 | PCI-10200 |  |  | TB925 | 05327 |  |  | 05 |  |  |  | M/sPEBS PENNAR |  |  |  | TPFMC-2 | [10 empty] | M/s BJCL |  |  | M/s Technip/ HURL / PDIL
Task(Task)-->PANKI (Panki)-->CIV(Civil)-->NDCT(NDCT) | 1.6.4.6(Structure:- CHP) | SRI AJAY DWIVEDI | Documents(Documents)-->PROJECT CLOSURE (PROJECT CLOSURE)-->PROJECT DELAY TRACKER (Project Delay tracker) |  | civil(civil) | [5 empty] | Enabling Works | [11 empty] | Power Evacuation |  | IP Jagdishpur |  | DIS EMB | DDA |  |  |  | M/S TFMC |  |  |  |  | 61302 |  |  | PCE-02100 | PCI-10300 |  |  | TB926 | 05330 |  |  | 06 |  |  |  | Toyo | [14 empty] | M/s Bluechip Technologies |  |  | M/s Thermosystems
Task(Task)-->PANKI (Panki)-->DIS(Dispatch) | 1.6.4.7(Structure:- FGD+AHP+Pipe Rack) | DEBABRATA ADAK | Documents(Documents)-->REF DOC (Ref Doc) |  | CLEAR WAT.(Clear Water) | [5 empty] | EOT-EOT Crane | [11 empty] | PT Plant |  | ISG Bangalore |  | DIS FDN | DIS BB |  |  |  | M/s Thermosystems |  |  |  |  | 61501 |  |  | PCE-02200 | PEI-01700 |  |  | TB927 | 05350 |  |  | 07 |  |  |  | TPFMC | [14 empty] | M/s Brother |  |  | M/s Wapcos
Task(Task)-->PANKI (Panki)-->ERE(Erection) | 1.6.5(Electrical & Cabling Pkg ) | ADARSH PARIDA | Documents(Documents)-->SITE PHOTOGRAPHS (Site Photographs) |  | Client(Client) | [5 empty] | ERTH-Grounding System | [11 empty] | Raw Water Sys |  | ISG Site |  | DIS GA | DIS BS |  |  |  | M/S TPFMC |  |  |  |  | HYBM001 |  |  | PCE-02300 | PEI-01800 |  |  | TB928 | 06400 |  |  | 08 |  |  |  | TPFMC / LTHE | [14 empty] | M/s BTL |  |  | M/s Wapcos/PDIL
Task(Task)-->PANKI (Panki)-->MAN(Manufacturing) | 1.6.6(C&I Pkg ) | ANBHAV DAS | Documents(Documents)-->TEST (TEST) |  | Client(Client) | [5 empty] | ESP-Electrostatic Precipitator | [11 empty] | SCR |  | isg-dg-bnglore |  | DIS MIV | DIS EMB |  |  |  | M/s Wapcos |  |  |  |  | HYBM002 |  |  | PCE-02400 | PEI-01900 |  |  | TB929 | 06401 |  |  | 09 | [18 empty] | M/s Buildtech |  |  | Main Substation
Task(Task)-->PANKI (Panki)-->PDE(Product Engineering) | 1.7(Topographical Survey and Soil Investigation) | ATANUKUMAR |  |  | cm ps(cm ps) | [5 empty] | FDF-FD Fan | [11 empty] | Start-up Power |  | IVP Goindwal |  | DIS ROT | DIS FDN |  |  |  | M/S Wapcos HURL / PDIL |  |  |  |  | HYBM003 |  |  | PCE-02500 | PEI-02000 |  |  | TB930 | 06431 |  |  | 10 | [18 empty] | M/s BYGGING India Ltd. |  |  | Mill & BUNKER Building
Task(Task)-->PANKI (Panki)-->PRC(Procurement) | 1.8(Development of Site Infrastructure) | ABHISHEK D GUPTA |  |  | cm(cm) | [5 empty] | FFS-Fire fighting system | [11 empty] | STP |  | JOY TOWER NOIDA |  | DIS RUN | DIS GA |  |  |  | M/s Wapcos/PDIL |  |  |  |  | HYBM004 |  |  | PCE-02600 | PEI-02100 |  |  | TB931 | 06434 |  |  | 11 | [18 empty] | M/s Chemin |  |  | Mills Foundation
Task(Task)-->PANKI (Panki)-->PRE(Project Engineering) | 1.8.11(Dismantling) | ADITYA KUMAR |  |  | cmd secre(CMD Secretariate) | [5 empty] | FGD-Absorber Casing Lining & Insulation | [11 empty] | TDBFP |  | NBG |  | DIS STR | DIS MIV |  |  |  | NGSL |  |  |  |  | HYBM005 |  |  | PCE-02700 | PEI-02200 |  |  | TB932 | 06437 |  |  | 12 | [18 empty] | M/s Ciscons |  |  | NDCT
Task(Task)-->PANKI (Panki)-->SCH(Schedule) | 1.9(Boiler & Auxiliaries) | ADITYA KUMAR SON |  |  | cmd sect(cmd sect) | [5 empty] | FGD-Absorber Internals | [11 empty] | TG Auxiliaries |  | NK FGD SITE |  | DIS_CM | DIS ROT |  |  |  | Order yet to be placed |  |  |  |  | HYBM006 |  |  | PCE-02800 | PEI-02300 |  |  | TB933 | 06441 |  |  | 135 | [18 empty] | M/s ClearWater |  |  | Nice
Task(Task)-->PANKI (Panki)-->SUP(Supply) | 1.9.1(Boiler Structure) | ADMIN |  |  | CMG BHOPAL(Cmg-Bhopal) | [5 empty] | FGD-Absorber Main Structure | [13 empty] | NOIDA |  | DIS_CWS | DIS RUN |  |  |  | Overall |  |  |  |  | HYBM007 |  |  | PCE-02900 | PEI-02400 |  |  | TB934 | 06444 |  |  | 136 | [18 empty] | M/s COMA COE |  |  | OSBL Piperack
Task(Task)-->PATRATU (Patratu) | 1.9.1.2(Supply (BHEL TRY)) | A G MOMIN |  |  | CMG(CMG) | [5 empty] | FGD-Absorber Supporting Systems | [13 empty] | North Karanpura -site |  | DIS_ET | DIS STR |  |  |  | PDIL |  |  |  |  | HYBM008 |  |  | PCE-03000 | PEI-02500 |  |  | TB935 | 06447 |  |  | 137 | [18 empty] | M/s Comfort Air |  |  | PDIL
Task(Task)-->PATRATU (Patratu)-->CIV(Civil) | 1.9.1.2.1(Main Boiler supporting structure (PG-35)) | AMANG |  |  | cml(cml) | [5 empty] | FGD-Absorber system | [13 empty] | NPGCL-SITE |  | DIS_GOV | DIS_CM |  |  |  | PEM |  |  |  |  | HYBM009 |  |  | PCE-03100 | PEI-02600 |  |  | TB936 | 06451 |  |  | 138 | [18 empty] | M/s Cranex |  |  | PH Building Structural works
Task(Task)-->PATRATU (Patratu)-->CIV(Civil)-->BOI(Boiler) | 1.9.1.2.1.1(FOUNDATION MATERIALS- (PGMA-35011)) | ARIF |  |  | cni(cni) | [5 empty] | FGD-Booster Fan | [13 empty] | NSPCL Bhilai |  | DIS_PROT | DIS_CWS |  |  |  | PMPL |  |  |  |  | HYBM010 |  |  | PCE-03200 | PEI-02700 |  |  | TB937 | 06452 |  |  | 139 | [18 empty] | M/s Dew Specialty |  |  | Piling
Task(Task)-->PATRATU (Patratu)-->CIV(Civil)-->NDCT(NDCT) | 1.9.1.2.1.2(MAIN COLUMNS LEFT 1ST PASS (PGMA-35111)) | ANILJAIN |  |  | COMMERCIAL - FB(Commercial- FB) | [5 empty] | FGD-Flue Gas De-sulphurization system | [13 empty] | NTPC BG |  | DIS_SEE | DIS_ET |  |  |  | PSWR |  |  |  |  | HYBM011 |  |  | PCE-03500 | PEI-02800 |  |  | TB938 | 06453 |  |  | 142 | [18 empty] | M/s Driplex |  |  | Piperack
Task(Task)-->PATRATU (Patratu)-->DIS(Dispatch) | 1.9.1.2.1.3(MAIN COLUMNS LEFT 2ND PASS (PGMA-35112)) | AJAY |  |  | COMMERCIAL - VAL(Commercial -Valves) | [5 empty] | FGD-Gates & Dampers | [13 empty] | NTPC MOUDA |  | DIS_TB | DIS_GOV |  |  |  | RPT |  |  |  |  | HYBM012 |  |  | PCE-03600 | PEI-02900 |  |  | TB939 | 06455 |  |  | 143 | [18 empty] | M/s Durga |  |  | Raw Water Intake System
Task(Task)-->PATRATU (Patratu)-->ERE(Erection) | 1.9.1.2.1.4(MAIN COLUMNS RIGHT 1ST PASS (PGMA-35121)) | AJAY_K |  |  | Commercial(Commercial) | [5 empty] | FGD-Pumps | [13 empty] | PC Chennai |  | E GGH | DIS_PROT |  |  |  | Technip |  |  |  |  | HYBM013 |  |  | PCE-03700 | PEI-03000 |  |  | TB940 | 06500 |  |  | 144 | [18 empty] | M/s Earth & water System |  |  | Raw Water Pump House
Task(Task)-->PATRATU (Patratu)-->MAN(Manufacturing) | 1.9.1.2.1.5(MAIN COLUMNS RIGHT 2ND PASS (PGMA-35122)) | AJAY KUMA |  |  | COMML(COMML) | [5 empty] | FGD-Tanks | [13 empty] | PCRI Haridwar |  | ELG Slurry Preparation | DIS_SEE |  |  |  | TRY |  |  |  |  | HYBM014 |  |  | PCE-03800 | PEI-03100 |  |  | TB941 | 06501 |  |  | 145 | [18 empty] | M/s Earth Water technoligies |  |  | Roads & Drains
Task(Task)-->PATRATU (Patratu)-->PDE(Product Engineering) | 1.9.1.2.1.6(MAIN COLUMNS MIDDLE (PGMA-35130)) | AJAYKASHYAP |  |  | const(const) | [5 empty] | FOS-Fuel Oil System | [13 empty] | PE&SD Hyderabad |  | EMB | DIS_TB |  |  |  | Umax |  |  |  |  | HYBM015 |  |  | PCE-03900 | PEI-03200 |  |  | TB942 | 06515 |  |  | 146 | [18 empty] | M/s East End |  |  | RWTP
Task(Task)-->PATRATU (Patratu)-->PRC(Procurement) | 1.9.1.2.1.7(AUXILIARY COLUMNS-LEFT SIDE (PGMA-35140)) | AJAY_KUMAR |  |  | Construction(Construction) | [5 empty] | FPS-Flood Protection System | [13 empty] | PEM Noida |  | EOT | ees |  |  |  | Umaxe |  |  |  |  | HYBM016 |  |  | PCE-04000 | PEI-03300 |  |  | TB943 | 06731 |  |  | 149 | [18 empty] | M/s ECE Industries |  |  | SS-1
Task(Task)-->PATRATU (Patratu)-->PRE(Project Engineering) | 1.9.1.2.1.8(AUXILIARY COLUMNS-RIGHT SIDE (PGMA-35150)) | AJAYNATH |  |  | Contact Mng(Contact Mng) | [5 empty] | FSS-Fire Sealing System | [13 empty] | PPEI Building |  | Er Completion of Air coolers | EMB |  |  |  | Wapcos |  |  |  |  | HYBM017 |  |  | PCE-04200 | PEI-03400 |  |  | TB944 | 06732 |  |  | 15 | [18 empty] | M/s EDAC |  |  | SS-2
Task(Task)-->PATRATU (Patratu)-->SCH(Schedule) | 1.9.1.2.1.9(GIRDER PIN CONNECTIONS (PGMA-35190)) | AJAY SINGH |  |  | CRANEX(Cranex) | [5 empty] | GDS-Gypsum Dewatering System | [13 empty] | PSER |  | Er Completion of Heat Exchanger | EOT | [8 empty] | HYBM018 |  |  | PCE-04300 | PEI-07500 |  |  | TB945 | 06734 |  |  | 150 | [18 empty] | M/s EDAC Engineering Ltd. |  |  | Substation
Task(Task)-->PATRATU (Patratu)-->SUP(Supply) | 1.9.1.2.1.10(CEILING STRUCTURE-MAIN GIRDERS 1ST PASS (PGMA-35211)) | AJIT KUMAR |  |  | CRSG(Government of Cross River State, Nigeria) | [5 empty] | GEN_H-Generator/ Motor(LIS) | [13 empty] | PSER Site |  | Er Completion of Incinerator Package | Er Completion of Air coolers | [8 empty] | HYBM019 |  |  | PCE-04400 | PEI-07600 |  |  | TB946 | 06735 |  |  | 151 | [18 empty] | M/s Elgi |  |  | Switchyard
Task(Task)-->PROG (Progress) | 1.9.1.2.1.11(CEILING STRUCTURE-MAIN GIRDERS 2ND PASS (PGMA-35212)) | AJMAL FAHAD |  |  | DIR(Director Power) | [5 empty] | GEN-Generator | [13 empty] | PSER Kolkata |  | Er Completion of Reaction Furmace Package | Er Completion of Heat Exchanger | [8 empty] | HYBM020 |  |  | PCE-04500 | PEI-07700 |  |  | TB947 | 06737 |  |  | 152 | [18 empty] | M/s Enterpriisng Engineers |  |  | TG Columns & Deck
Task(Task)-->PROG (Progress)-->CIV (Civil) | 1.9.1.2.1.12(CEIL STRUCT-CROSS WELDED BEAMS 1ST PASS (PGMA-35213)) | AK AASATI |  |  | DIS(Dispatch) | [5 empty] | GGS-Gas to Gas Heating | [13 empty] | PS-HQ |  | Er Completion of Reactors | Er Completion of Incinerator Package | [8 empty] | HYBM021 |  |  | PCE-04600 | PEI-07800 |  |  | TB948 | 06741 |  |  | 153 | [18 empty] | M/s Enton |  |  | Utility Substation
Task(Task)-->PROG (Progress)-->CIV (Civil)-->2AB CONVEYOR (2AB Conveyor) | 1.9.1.2.1.13(CEIL STRUCT-CROSS WELDED BEAMS 2ND PASS (PGMA-35214)) | ANILKAPOOR |  |  | DRIPLEX(Driplex) | [5 empty] | GHS-Gypsum Handling System | [13 empty] | PSHQ MSX |  | Erection Of Chimney | Er Completion of Reaction Furmace Package | [8 empty] | HYBM022 |  |  | PCE-04700 | PEI-07900 |  |  | TB949 | 06744 |  |  | 16 | [18 empty] | M/s EPIL |  |  | Wagon loading
Task(Task)-->PROG (Progress)-->CIV (Civil)-->3AB CONVEYOR (3AB Conveyor) | 1.9.1.2.1.14(CEILING STRUCTURE ROLLED BEAM 1ST PASS (PGMA-35221)) | AKDIXIT |  |  | DTG(DTG & PMG/CMG) | [5 empty] | GIS-GIS system | [13 empty] | PSNR |  | Erection of Fan & Ducting System | Er Completion of Reactors | [8 empty] | HYBM023 |  |  | PCE-04900 | PEI-11100 |  |  | TB950 | 06745 |  |  | 16201 | [18 empty] | M/s EPP Composites |  |  | Wagon loading platform
Task(Task)-->PROG (Progress)-->CIV (Civil)-->4AB CONVEYOR (4AB Conveyor) | 1.9.1.2.1.15(CEILING STRUCTURE ROLLED BEAM 2ND PASS (PGMA-35222)) | AKHILESH KUMAR |  |  | DVC(Damodar Valley Corporation) | [5 empty] | GOV-Governing System | [13 empty] | PSNR Noida |  | Erection of Limestone handling and Crushing System | Erection of Chimney | [8 empty] | HYBM024 |  |  | PCE-05000 | PEI-11200 |  |  | TB951 | 06747 |  |  | 16222 | [18 empty] | M/s Excel |  |  | Ware House
Task(Task)-->PROG (Progress)-->CIV (Civil)-->5AB CONVEYOR (5AB Conveyor) | 1.9.1.2.1.16(CEILING STRUCTURE HORBRACING 1ST PASS (PGMA-35231)) | ASHOK KUMAR SING |  |  | EARTH WAT.(Earth & water System) | [5 empty] | Heaters- HEATERS | [13 empty] | PSNR Site |  | FDN | Erection of Fan and Ducting System | [8 empty] | HYBM025 |  |  | PCE-05100 | PEI-11300 |  |  | TB953 | 06751 |  |  | 16226 | [18 empty] | M/s Fabco
Task(Task)-->PROG (Progress)-->CIV (Civil)-->AIR COMPRESSOR BUILDING (Air Compressor Building) | 1.9.1.2.1.17(CEILING STRUCTURE HORBRACING 2ND PASS (PGMA-35232)) | AKJAIN |  |  | EDAC(M/s EDAC Engineering Ltd.) | [5 empty] | HMW-Hydro Mechanical Works | [13 empty] | ps-pmg |  | GSL | Erection of GGH | [8 empty] | HYBM026 |  |  | PCE-05200 | PEI-11400 |  |  | TB954 | 06752 |  |  | 16231 | [18 empty] | M/s Fafco
Task(Task)-->PROG (Progress)-->CIV (Civil)-->BA OVERFLOW TREATMENT (BA overflow treatment sys alongwith tube settler) | 1.9.1.2.1.18(HORIZONTAL BRACING I PASS IMBL (PGMA-35311)) | AMITKUMARORAON |  |  | EDN(EDN Banglore) | [5 empty] | IDF-ID Fan | [13 empty] | PS-PMG New Delhi |  | GV ASSY | Erection of Gypsum De-watering System | [8 empty] | HYBM027 |  |  | PCE-05300 | PEI-11600 |  |  | TB956 | 06753 |  |  | 16235 | [18 empty] | M/s Finolex J Power
Task(Task)-->PROG (Progress)-->CIV (Civil)-->BOI (Boiler) | 1.9.1.2.1.19(HORIZ BRACING II PASS I MBL (PGMA-35312)) | AVINASH K RANJAN |  |  | ele&cni(ele&cni) | [5 empty] | ILS-Illumination System | [13 empty] | PSSR Chennai |  | Gypsum De-Watering System | Erection of Gypsum Handling System | [8 empty] | HYHE001 |  |  | PCE-05400 | PEI-11800 |  |  | TB957 | 06755 |  |  | 166 | [18 empty] | M/s Fortune Eng & Structural Pvt Ltd
Task(Task)-->PROG (Progress)-->CIV (Civil)-->BUS DUCT (BUS DUCT) | 1.9.1.2.1.20(HORIZ BRACING I PASS II MBL (PGMA-35321)) | AKRR |  |  | ELE(ELECTRICAL) | [5 empty] | IPBD-Busduct | [13 empty] | PSSR Site |  | Gypsum Handling System | Erection of Limestone Grinding Slurry preparatio | [8 empty] | HYHE002 |  |  | PCE-05500 | PEI-11900 |  |  | TB961 | 06759 |  |  | 17 | [18 empty] | M/s FSIP Jagdishpur
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CANTEEN BUILDING (CANTEEN BUILDING) | 1.9.1.2.1.21(HORIZ BRACING II PASS II MBL (PGMA-35322)) | AKSHAY KUMAR |  |  | ELEC,C&I EREC(ELEC,C&I EREC) | [5 empty] | LHS-Limestone Handling System | [13 empty] | PSWR Site |  | Heat Exchanger | Erection of Limestone handling and Crushing System | [8 empty] | HYPU001 |  |  | PCE-05600 | PEI-12000 |  |  | TB962 | 07102 |  |  | 17505 | [18 empty] | M/s G R Power
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CASCADE AERATOR/FLASH MIXER ETC (Cascade Aerator/Flash Mixer/Stiling Chamber/Parshall Flume) | 1.9.1.2.1.22(HORIZ BRACING I PASS III MBL (PGMA-35331)) | AKSINGHAL |  |  | ELGI(Elgi) | [5 empty] | LMS-Water Level & Flow Measurement System | [13 empty] | PSWR Nagpur |  | HT | FDN | [8 empty] | HYPU002 |  |  | PCE-05700 | PEI-12200 |  |  | TB963 | 07110 |  |  | 17509 | [18 empty] | M/s G&J
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CEP PIT (CEP Pit) | 1.9.1.2.1.23(HORIZ BRACING II PASS III MBL (PGMA-35332)) | A.K. TALELE |  |  | ENG - CIVIL(Engineering -Civil) | [5 empty] | LPS – Loco Propulsion System | [13 empty] | Rammam site |  | HV STR | FL | [8 empty] | HYPU003 |  |  | PCE-05800 | PEI-12400 |  |  | TB966 | 07125 |  |  | 17510 | [18 empty] | M/s Gaja Engineering
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CHEMICAL HOUSE (Chemical House) | 1.9.1.2.1.24(HORIZ BRACING I PASS IV MBL (PGMA-35341)) | ATUL THAKUR |  |  | ENG - DT(Engineering - Drive Turbine) | [5 empty] | MAIN STEAM SYSTEM- CLASS 2 ( PIPING & VALVES) | [13 empty] | Ranipet |  | I&C | GSL | [8 empty] | HYPU004 |  |  | PCE-05900 | PEI-12500 |  |  | TB968 | 07217 |  |  | 17511 | [18 empty] | M/s Gammon
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CHIMNEY (Chimney) | 1.9.1.2.1.25(HORIZ BRACING II PASS IV MBL (PGMA-35342)) | ARUN KUMAR YADAV |  |  | ENG - ELE(Engineering - Electrical) | [5 empty] | MDP-MDBFP | [13 empty] | ROD |  | Incinerator Package | GV ASSY | [8 empty] | HYPU005 |  |  | PCE-06000 | PEI-12600 |  |  | TB970 | 07223 |  |  | 17521 | [18 empty] | M/s Gammon Engineers
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CLARI FOCULATOR (CLARI FOCULATOR) | 1.9.1.2.1.26(HORIZ BRACING I PASS V MBL (PGMA-35351)) | IALBERT WILLIA |  |  | ENG - FGD(Engineering- FGD) | [5 empty] | MEMU – Mainline Electric Multiple Unit | [13 empty] | SBD-Bangalore |  | Loop test completion | Gypsum De-Watering System | [8 empty] | HYPU006 |  |  | PCE-06100 | PEI-12800 |  |  | TB971 | 07231 |  |  | 17523 | [18 empty] | M/s Gannon Dunkerley & Co. Ltd.
Task(Task)-->PROG (Progress)-->CIV (Civil)-->COMPRESSORHOUSE (CompressorHouse) | 1.9.1.2.1.27(HORIZ BRACING II PASS V MBL (PGMA-35352)) | ALFAM IQBAL |  |  | ENG - HE(Engineering - Heat Exchangers) | [5 empty] | MILL-Mills | [13 empty] | Site |  | Mechanical Completion | Gypsum Handling System | [8 empty] | HYPU007 |  |  | PCE-06200 | PII-03600 |  |  | TB974 | 07232 |  |  | 18 | [18 empty] | M/s GDC
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONCRETE VOLUTE PUMP (Concrete Volute Pump) | 1.9.1.2.1.28(HORIZ BRACING I PASS VI MBL (PGMA-35361)) | ALOKKUMAR |  |  | ENG - PUL(Engineering -Pulverizers) | [5 empty] | MIS-Miscellaneous | [13 empty] | SSBG |  | MSRE | Heat Exchanger | [8 empty] | HYPU008 |  |  | PCE-06300 | PII-03700 |  |  | TB975 | 07302 |  |  | 18001 | [18 empty] | M/s GE
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONDENSATE POLISHING UNIT (Condensate Polishing Unit Regeneration Building) | 1.9.1.2.1.29(HORIZ BRACING II PASS VI MBL (PGMA-35362)) | ALKAT |  |  | ENG - PUMP(Engineering - Pump) | [5 empty] | MIV-Main Inlet Valve/Discharge Valve | [13 empty] | Talcher |  | NHT | HT | [8 empty] | HYPU009 |  |  | PCE-06400 | PII-03800 |  |  | TB976 | 07303 |  |  | 18010 | [18 empty] | M/s GMW
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONDENSATE STORAGE TANK FOUNDAION (Condensate Storage Tank Foundaion) | 1.9.1.2.1.30(LAND & CONN PLAT TIER-1 (PGMA-35381)) | ALKAWADHWA |  |  | ENGINEERING(Engineering) | [5 empty] | MMH- Material Handling | [13 empty] | TBG Noida |  | OGA | HV STR | [8 empty] | HYPU010 |  |  | PCE-06500 | PII-03900 |  |  | TB977 | 07309 |  |  | 18111 | [18 empty] | M/s GS Geo Environs Pvt. Ltd
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONDENSER PIT (Condenser Pit) | 1.9.1.2.1.31(LAND & CONN PLAT TIER-2 (PGMA-35382)) | ALOK.BHADKAMKAR |  |  | engineering-ci(Engineering-CI) | [5 empty] | MOD-Model Testing | [13 empty] | TBG Site |  | PG | I and C | [8 empty] | HYPU011 |  |  | PCE-06600 | PII-04000 |  |  | TB978 | 07315 |  |  | 18235 | [18 empty] | M/s Gupta Engineers & Contractor
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONVEYINGAIRCOMPRESSORFOUNDATION (ConveyingAirCompressorFoundation) | 1.9.1.2.1.32(LAND & CONN PLAT TIER-3 (PGMA-35383)) | ALOKE RANJAN |  |  | engineering-mech(Engineering-Mechanical) | [5 empty] | MSR-MOISTURE SEPERATOR & REHEATER | [13 empty] | TP Jhansi |  | PGT | Incinerator Package | [8 empty] | HYPU012 |  |  | PCE-06700 | PII-04100 |  |  | TB979 | 07316 |  |  | 18236 | [18 empty] | M/s HAMON
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONVEYOR GALLERY -1A & 1B (Conveyor Gallery -1A & 1B) | 1.9.1.2.1.33(HORIL BEAMS FIRST PASS-TIER-1 (PGMA-35441)) | ALOK RANJAN |  |  | EPL(M/s J S EPL (JN Singh Engicon Pvt. Ltd.)) | [5 empty] | NPB-Non-Plant Buildings | [13 empty] | Trichy HPBP |  | Piling Work Completion | Loop test completion | [8 empty] | HYPU013 |  |  | PCE-06800 | PII-09600 |  |  | TB980 | 07317 |  |  | 18901 | [18 empty] | M/s Hardev
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONVEYOR GALLERY -6A & 6B (Conveyor Gallery -6A & 6B) | 1.9.1.2.1.34(HORIL BEAMS FIRST PASS-TIER-2 (PGMA-35442)) | AK.SINGHAL |  |  | erec-sg(Erection-SG) | [5 empty] | OFC-Optical Fiber Cable / OPGW Cable | [13 empty] | Trichy Valves |  | PRE COM | Mechanical Completion | [8 empty] | HYPU014 |  |  | PCE-06900 | PII-09700 |  |  | TB981 | 07318 |  |  | 18910 | [18 empty] | M/s Hari Construction
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CONVEYOR GALLERY -7A & 7B (Conveyor Gallery -7A & 7B) | 1.9.1.2.1.35(HORIL BEAMS FIRST PASS-TIER-3 (PGMA-35443)) | ALOK BANSAL |  |  | erection pipi(Erection-Piping) | [5 empty] | OHS-Oil Handling System | [13 empty] | Tuticorin Site |  | Reaction Furnace Package | milestone | [8 empty] | HYTC001 |  |  | PCE-07000 | PMI-00500 |  |  | TB984 | 07331 |  |  | 19 | [18 empty] | M/s Harji
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CPU BUILDING (CPU building) | 1.9.1.2.1.36(HOR BEAM-SECOND PASS- TIER-1 (PGMA-35451)) | ALOKK |  |  | erection-cvl(Erection-Civil) | [5 empty] | OZP-Ozonization plant | [15 empty] | Receipt of Reactors | MSR Erection | [8 empty] | HYTC002 |  |  | PCE-07100 | PMI-00600 |  |  | TB985 | 07360 |  |  | 20 | [18 empty] | M/s HAYAGREV
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CRUSHER HOUSE (Crusher House) | 1.9.1.2.1.37(HOR BEAM-SECOND PASS- TIER-2 (PGMA-35452)) | AMADHUSUDAN |  |  | erection-elec(Erection-Electrical) | [5 empty] | PAS-Public Address System | [15 empty] | RMU BU | NHT | [8 empty] | HYTC003 |  |  | PCE-07200 | PMI-00700 |  |  | TB986 | 07361 |  |  | 21 | [18 empty] | M/s HES Infra
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CW & ACW SUMP & FOREBAY (CW & ACW Sump & Forebay) | 1.9.1.2.1.38(HOR BEAM-SECOND PASS- TIER-3 (PGMA-35453)) | AMAN |  |  | erection-tg(Erection-TG) | [5 empty] | PHB-Power House Building | [15 empty] | RMU CIVIL | OGA | [8 empty] | HYTC004 |  |  | PCE-07300 | PMI-00800 |  |  | TB987 | 07362 |  |  | 22 | [18 empty] | M/s HNC
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CW PIPE LINE (CW Pipe Line) | 1.9.1.2.1.39(FRONT BRACING-TIER-1 (PGMA-35511)) | AMAR JHA |  |  | ESP & ROTATING(ESP & ROTATING) | [5 empty] | PLTE-Entire Plant-Engineering | [15 empty] | RMU DIS | PGT | [8 empty] | HYTC005 |  |  | PCE-07500 | PMI-00900 |  |  | TB989 | 07393 |  |  | 24 | [18 empty] | M/s HV Air conditioning
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CW PIT (CW Pit) | 1.9.1.2.1.40(FRONT BRACING-TIER-2 (PGMA-35512)) | AMIKUMAR |  |  | FEBRICATION(FEBRICATION) | [5 empty] | PLT-Entire Plant | [15 empty] | RMU ELEC | pgtc | [8 empty] | HYTC006 |  |  | PCE-07600 | PMI-01000 |  |  | TB990 | 07402 |  |  | 28 | [18 empty] | M/s HV Equipment Pvt Ltd
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CW TREATMENT BUILDING INCLUDING EQ (CW treatment Building including Equipment Foundation) | 1.9.1.2.1.41(FRONT BRACING-TIER-3 (PGMA-35513)) | AMIT K |  |  | fgd(FGD) | [5 empty] | POW-Power Cycle piping | [15 empty] | RMU GA | Piling Work Completion | [8 empty] | HYTC007 |  |  | PCE-07700 | PMI-01100 |  |  | TB991 | 07403 |  |  | 29 | [18 empty] | M/s Indure
Task(Task)-->PROG (Progress)-->CIV (Civil)-->CWPH (CWPH) | 1.9.1.2.1.42(SIDE BRACING-TIER-1 (PGMA-35521)) | AMITKUMAR |  |  | FP & CSU(FP & CSU) | [5 empty] | PPI-Plant piping | [15 empty] | RMU GOV | PRE COM | [8 empty] | HYTC008 |  |  | PCE-07800 | PMI-01200 |  |  | TB992 | 07405 |  |  | 30 | [18 empty] | M/s Indwell
Task(Task)-->PROG (Progress)-->CIV (Civil)-->DG/AIR WASHER BUILDING (DG/Air Washer Building) | 1.9.1.2.1.43(SIDE BRACING-TIER-2 (PGMA-35522)) | AMITMALHOTRA |  |  | G&J(G&J) | [5 empty] | PROT-Protection System | [15 empty] | RMU PGT | Reaction Furnace Package | [8 empty] | HYTC009 |  |  | PCE-07900 | PMI-05100 |  |  | TB993 | 07409 |  |  | 30771 | [18 empty] | M/s Ion Exchange
Task(Task)-->PROG (Progress)-->CIV (Civil)-->DM PLANT ACID ALKALI UNLOADING (DM Plant Acid alkali Unloading & storage area) | 1.9.1.2.1.44(SIDE BRACING-TIER-3 (PGMA-35523)) | AMITGARG |  |  | GANNON(M/s Gannon Dunkerley & Co. Ltd.) | [5 empty] | PRS-Pipe/Cable Rack Structure | [15 empty] | RMU REF EMP | Reactors | [8 empty] | HYTC010 |  |  | PCE-08100 | PMI-09000 |  |  | TB994 | 07423 |  |  | 30941 | [18 empty] | M/s Ion Exchange (INDIA) Ltd
Task(Task)-->PROG (Progress)-->CIV (Civil)-->DM PLANT BUILDING INCLUDING VESSEL (DM Plant Building including Vessel Foundation) | 1.9.1.2.1.45(REAR BRACING-TIER-1 (PGMA-35531)) | AMIT THAKUR |  |  | gm ytps(GM-YTPS Site) | [5 empty] | PSV-Penstock Valve | [15 empty] | RMU RTR LOW | RMU BU | [8 empty] | HYTC011 |  |  | PCE-08200 | PMI-09100 |  |  | TB996 | 07431 |  |  | 31 | [18 empty] | M/s ISC Projects
Task(Task)-->PROG (Progress)-->CIV (Civil)-->DM PLANT NEUTRALIZATION PIT (DM Plant Neutralization Pit) | 1.9.1.2.1.46(REAR BRACING-TIER-2 (PGMA-35532)) | AMIT KUMAR |  |  | Haridwar(Haridwar) | [5 empty] | PTP-PT Plant | [15 empty] | RMU SA | RMU CIVIL | [8 empty] | HYTC012 |  |  | PCE-08300 | PMI-09500 |  |  | TB997 | 07460 |  |  | 32 | [18 empty] | M/s J B Erectors
Task(Task)-->PROG (Progress)-->CIV (Civil)-->EFFLUENT TREATMENT PLANT (Effluent Treatment Plant) | 1.9.1.2.1.47(REAR BRACING-TIER-3 (PGMA-35533)) | AMITABHA |  |  | HAYAGREV(HAYAGREV) | [5 empty] | RDSO | [15 empty] | RMU SPINN | RMU DIS | [11 empty] | PCE-08400 | PNI-00200 |  |  | TB998 | 07461 |  |  | 33 | [18 empty] | M/s J S EPL (JN Singh Engicon Pvt. Ltd.)
Task(Task)-->PROG (Progress)-->CIV (Civil)-->ELEVATOR (Elevator) | 1.9.1.2.1.48(HSFG FASTENERS FOR PG 35 (PGMA-35700)) | AMITESH SAURAV |  |  | head(head) | [5 empty] | RND-Roads & Drains | [15 empty] | RMU STR HV | RMU ELEC | [11 empty] | PCE-08500 | PNI-00300 |  |  |  | 07462 |  |  | 34 | [18 empty] | M/s Janardan Nirman Pvt ltd
Task(Task)-->PROG (Progress)-->CIV (Civil)-->ESP (ESP) | 1.9.1.2.1.49(FLOOR GRILLS AND GUARD PLATE (PGMA-35811)) | AMITESH1 |  |  | hou(hou) | [5 empty] | RWS-Raw Water System | [15 empty] | RMU SYN | RMU GA | [11 empty] | PCE-08700 | PNI-00400 |  |  |  | 07502 |  |  | 35 | [18 empty] | M/s Jasmino
Task(Task)-->PROG (Progress)-->CIV (Civil)-->ESP CONTROL ROOM (ESP Control Room) | 1.9.1.2.1.50(STAIRS-LOWER (PGMA-35821)) | AMITESHSAURAV |  |  | HPVP - Vizag(HPVP - Vizag) | [5 empty] | SCADA-SCADA | [15 empty] | RMU TO | RMU GOV | [11 empty] | PCE-08800 | PNI-01500 |  |  |  | 07503 |  |  | 36 | [18 empty] | M/s JD Hoists
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FGD (FGD) | 1.9.1.2.1.51(STAIRS-MIDDLE (PGMA-35822)) | AMIT GARG |  |  | ht motors(ht motors) | [5 empty] | SCR-Selective Catalytic Reactor system | [15 empty] | RMU TUR SFT | RMU PGT | [11 empty] | PCE-08900 | PNI-05000 |  |  |  | 07505 |  |  | 37 | [18 empty] | M/s Jindal Infra
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FIRE WATER BOOSTER PUMP HOUSE (Fire Water Booster Pump House) | 1.9.1.2.1.52(STAIRS-UPPER (PGMA-35823)) | AMITKERKETTA |  |  | HURL(HURL Vendors) | [5 empty] | SDT – Static & Dynamic Testing | [15 empty] | RMU UAA | RMU REF EMP | [11 empty] | PCE-09000 | PNI-05200 |  |  |  | 07509 |  |  | 38 | [18 empty] | M/s JK Projects
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FIRST FD FAN (First FD Fan) | 1.9.1.2.1.53(HAND RAILS & POSTS (PGMA-35851)) | AMIT SHRIVASTAVA |  |  | HURL(HURL) | [5 empty] | SEE-Static Excitation Equipment | [15 empty] | ROTOR | RMU RTR LOW | [11 empty] | PCE-09100 | PNI-06700 |  |  |  | 07531 |  |  | 38208 | [18 empty] | M/s Jyothi Turbo
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FIRST ID FAN (First ID Fan) | 1.9.1.2.1.54(CONSUMABLES &Erection MATERIALS (PGMA-35993)) | AMIT MEENA |  |  | HURL/ BGR(HURL/ BGR) | [5 empty] | SFC-SFC | [15 empty] | RT | RMU SA | [11 empty] | PCE-09200 | PNI-07000 |  |  |  | 07537 |  |  | 38376 | [18 empty] | M/s Jyoti Saroop Mittal
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FIRST PA FAN (First PA Fan) | 1.9.1.2.1.55(CHUTE PIPE AND LADDERS (PGMA-35995)) | AMITPAL |  |  | HV EQUIP.(HV Equipment Pvt Ltd) | [5 empty] | SGBD COOLERS- STEM GENERATOR BLOW DOWN COOLERS | [15 empty] | RTR_ASSY | RMU SPINN | [11 empty] | PCE-09300 | PNI-07100 |  |  |  | 07560 |  |  | 38378 | [18 empty] | M/s KANWAR
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FO PRESSURIZING PUMP HOUSE (FO Pressurizing pump house) | 1.9.1.2.2(Galleries & Stairways (PG-36)) | AMIT KUMAR SHAH |  |  | HWR(Haridwar) | [5 empty] | SGBD- STEM GENERATOR BLOW DOWN | [15 empty] | SBAY | RMU STR HV | [11 empty] | PCE-09500 | PNI-08100 |  |  |  | 07991 |  |  | 38379 | [18 empty] | M/s Kanwar Enterprises
Task(Task)-->PROG (Progress)-->CIV (Civil)-->FO TRANSFER PUMP HOUSE (FO Transfer pump house) | 1.9.1.2.2.1(COLUMNS NEAR AIR PRE HEATERS (PGMA-36110)) | AMIT SINGH |  |  | HYD(Hyderabad) | [5 empty] | SRU-SRU | [15 empty] | SBC | RMU SYN | [11 empty] | PCE-09600 | PNI-08200 |  |  |  | 07992 |  |  | 38380 | [18 empty] | M/s KASHISH
Task(Task)-->PROG (Progress)-->CIV (Civil)-->GT (GT) | 1.9.1.2.2.2(MIDDLE COLUMNS IN BOILER (PGMA-36130)) | AMITVERMA |  |  | ICF(Integral Coach Factory) | [5 empty] | SSS-Security and Surveillance System | [15 empty] | SBS | RMU TO | [11 empty] | PCE-09700 | PNI-08400 |  |  |  | 07993 |  |  | 38551 | [18 empty] | M/s Kirloskar
Task(Task)-->PROG (Progress)-->CIV (Civil)-->HFO & LDO DAY TANK FOUNDATION (HFO & LDO Day Tank Foundation) | 1.9.1.2.2.3(BEAMS & BRACINGS NEAR AIR PRE HEATER (PGMA-36150)) | AMIT_KUMAR |  |  | IMS(IMS) | [5 empty] | STP-Sewage & Effluent treatment systems | [15 empty] | SDT | RMU TUR SFT | [11 empty] | PCE-09900 | PNI-08600 |  |  |  | 08001 |  |  | 38601 | [18 empty] | M/s Krishna Laxmi
Task(Task)-->PROG (Progress)-->CIV (Civil)-->ID DUCT FOUNDATION (BOILER TO ESP) (ID Duct foundation (Boiler to ESP)) | 1.9.1.2.2.4(MAIN FLOOR I MBL 1ST PASS (PGMA-36311)) | AMLAN |  |  | INDWELL(INDWELL) | [5 empty] | STR-Structure | [15 empty] | SPIN | RMU UAA | [11 empty] | PCE-10000 | PNP-08700 |  |  |  | 08003 |  |  | 38602 | [18 empty] | M/s KSL
Task(Task)-->PROG (Progress)-->CIV (Civil)-->ID DUCT FOUNDATION (ESP TO CHIMNEY (ID Duct foundation (ESP to Chimney)) | 1.9.1.2.2.5(MAIN FLOOR I MBL 2ND PASS (PGMA-36312)) | A A SONAWANE |  |  | IO(IO) | [5 empty] | SWS-Sea Water Intake System | [15 empty] | Start of Boiler Aux Supplies | ROTOR | [11 empty] | PCE-10100 | PWI-06800 |  |  |  | 08006 |  |  | 38604 | [18 empty] | M/s KUBER ENTERPRISES
Task(Task)-->PROG (Progress)-->CIV (Civil)-->IPBD PEDESTALS FOUNDATION (IPBD Pedestals Foundation) | 1.9.1.2.2.6(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36313)) | AMPANDIT |  |  | IOCL(Indian Oil Corporation Limited) | [5 empty] | SWS-Steam & Water Analysis System(SWAS) | [15 empty] | STR ASSY | RT | [11 empty] | PCE-10200 | PWI-06900 |  |  |  | 08007 |  |  | 38605 | [18 empty] | M/s Kumar Creation
Task(Task)-->PROG (Progress)-->CIV (Civil)-->LEVELLING & GRADING (Levelling & Grading) | 1.9.1.2.2.7(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36314)) | RAJA M |  |  | ISC(ISC Projects) | [5 empty] | SWS-Switchgear system | [15 empty] | STR BRL | RTR_ASSY | [11 empty] | PCE-10400 | PWI-13600 |  |  |  | 08111 |  |  | 38606 | [18 empty] | M/s Kumar Piyush
Task(Task)-->PROG (Progress)-->CIV (Civil)-->LT SWITCH GEAR ROOM (LT Switch Gear Room) | 1.9.1.2.2.8(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36315)) | AMRISH |  |  | ISG(ISG Banglore) | [5 empty] | SYD- Switchyard | [15 empty] | Supply | SBAY | [11 empty] | PCE-10500 | PWI-13800 |  |  |  | 08380 |  |  | 38607 | [18 empty] | M/s L&T
Task(Task)-->PROG (Progress)-->CIV (Civil)-->MDBFP & TDBFP FOUNDATIONS (MDBFP & TDBFP foundations) | 1.9.1.2.2.9(NON-MBL FLOOR BETWEEN MBL I&II (PGMA-36316)) | AMRIT DEVASISH |  |  | IS-PMG(Industry Sector - PMG) | [5 empty] | TCAS - Train Collision Avoidance System | [15 empty] | SYN | SBC | [11 empty] | PCE-10600 | PWI-15400 |  |  |  | 08400 |  |  | 38608 | [18 empty] | M/s L&T Geo-Structure
Task(Task)-->PROG (Progress)-->CIV (Civil)-->MILL & BUNKER BUILDING (Mill & Bunker Building) | 1.9.1.2.2.10(MAIN FLOOR II MBL IST PASS (PGMA-36321)) | AMIT KUJUR |  |  | it(it) | [5 empty] | TDP-TDBFP | [15 empty] | Synchronization | SBS | [11 empty] | PCE-10700 | PWP-04500 |  |  |  | 08501 |  |  | 38618 | [18 empty] | M/s M&S
Task(Task)-->PROG (Progress)-->CIV (Civil)-->MILLS FOUNDATION (Mills Foundation) | 1.9.1.2.2.11(MAIN FLOOR II MBL 2ND PASS (PGMA-36322)) | ANAND AMAN |  |  | JB ERECT.(M/s J B Erectors) | [5 empty] | TGA-TG Auxiliaries | [15 empty] | System Integration and Commissioning | SCCES | [11 empty] | PNI-04340 | PWP-04600 |  |  |  | 08503 |  |  | 38652 | [18 empty] | M/S Maa Kela Enterprises
Task(Task)-->PROG (Progress)-->CIV (Civil)-->MV SWITCH GEAR ROOM (MV Switch Gear Room) | 1.9.1.2.2.12(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36323)) | ANAND K T |  |  | JD HOIST(JD Hoists) | [5 empty] | TGD-TG Deck | [15 empty] | TBU | SDT | [12 empty] | PWP-04700 |  |  |  | 08901 |  |  | 38654 | [18 empty] | M/s Macawber beekay
Task(Task)-->PROG (Progress)-->CIV (Civil)-->NDCT (NDCT) | 1.9.1.2.2.13(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36324)) | ANAND TRIPATHI |  |  | JHS(JHS) | [5 empty] | Trainsets – Vande Bharat | [15 empty] | TES | SPIN | [12 empty] | PWP-05500 |  |  |  | 08910 |  |  | 38655 | [18 empty] | M/s MAHALASKMI
Task(Task)-->PROG (Progress)-->CIV (Civil)-->OZONIZATION SYSTEM (Ozonization system) | 1.9.1.2.2.14(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36325)) | CANANDA |  |  | JSMITTAL(Jyoti Saroop Mittal) | [5 empty] | Trichy | [15 empty] | TGDC | Start of Boiler and Aux Supplies | [12 empty] | PWP-05600 |  |  |  | 08911 |  |  | 38656 | [18 empty] | M/s Mangla Hoist
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PENTHOUSE 2 (Penthouse 2) | 1.9.1.2.2.15(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36326)) | ANAND DEV |  |  | KANWAR(KANWAR) | [5 empty] | TRS-Transformers | [15 empty] | TGFC | STGEM | [12 empty] | PWP-05700 |  |  |  | 08912 |  |  | 38657 | [18 empty] | M/s Maxcon Global
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PERMANANT STORAGE BUILDING (PERMANANT STORAGE BUILDING) | 1.9.1.2.2.16(NON-MBL FLOOR BETWEEN MBL II&III (PGMA-36327)) | ANANDK |  |  | KAPSCO(Kaduna State Power Supply Company) | [5 empty] | TUR_H-Turbine / Pump(LIS) | [15 empty] | TGFS | STR ASSY | [12 empty] | PWP-05800 |  |  |  | 08913 |  |  | 38658 | [18 empty] | M/s Mehrotra Buildcon
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PH BUILDING STRUCTURAL WORKS (PH Building Structural works) | 1.9.1.2.2.17(MAIN FLOOR III MBL 1ST PASS (PGMA-36331)) | ANANTH |  |  | KPMG(KPMG) | [5 empty] | TUR-Turbine | [15 empty] | TGR | STR BRL | [12 empty] | PWP-05900 |  |  |  | 09003 |  |  | 38661 | [18 empty] | M/s Mulchand
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PIPE RACK - INSIDE PLANT (Pipe Rack - Inside Plant) | 1.9.1.2.2.18(MAIN FLOOR III MBL 2ND PASS (PGMA-36332)) | ANIL VARMA |  |  | KSEBL(KSEBL) | [5 empty] | VALVES-SPECIAL PURPOSE VALVES | [15 empty] | TMT | Supply | [12 empty] | PWP-14100 |  |  |  | 09004 |  |  | 38662 | [18 empty] | M/s Narmada
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PIPE RACK- FGD (Pipe Rack- FGD) | 1.9.1.2.2.19(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36333)) | ANILJOSHI |  |  | L&T GEO(L&T Geo-Structure) | [5 empty] | WBM-Wet Ball Mill | [15 empty] | TOC | SYN | [12 empty] | PWP-14500 |  |  |  | 09005 |  |  | 38663 | [18 empty] | M/s Navrup India
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PIPEPEDESTAL (Pipepedestal) | 1.9.1.2.2.20(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36334)) | ANIL KHANDELWAL |  |  | Loco Mfg(Loco Mfg) | [5 empty] | WDS- Water Depression System | [15 empty] | TT | System Integrationa and Commissioning | [12 empty] | PWP-14700 |  |  |  | 09303 |  |  | 38664 | [18 empty] | M/s NBCC
Task(Task)-->PROG (Progress)-->CIV (Civil)-->POWER HOUSE MAIN COLUMNS (Power House Main columns) | 1.9.1.2.2.21(NON-MBL FLOOR BETWEEN MBL III & IV (PGMA-36335)) | A K YADAV |  |  | Loco PPC(Loco PPC) | [5 empty] | WPI-Water piping | [15 empty] | TUR | TBU | [12 empty] | PWP-15500 |  |  |  | 09304 |  |  | 38666 | [18 empty] | M/s NEW FIRE ENGINEERS PVT LTD
Task(Task)-->PROG (Progress)-->CIV (Civil)-->PT PLANT PUMP HOUSE (PT Plant Pump House) | 1.9.1.2.2.22(FLOOR IN II PASS (PGMA-36336)) | ANIRUDDHA |  |  | Locomotive Pro(Locomotive Pro MGMT) | [5 empty] | WSHOP-Electrical & Mechanical Workshop Equipment | [15 empty] | TUR PIT | TES | [12 empty] | PWP-15600 |  |  |  | 09503 |  |  | 38679 | [18 empty] | M/s New Fire System
Task(Task)-->PROG (Progress)-->CIV (Civil)-->RAILWAY SIDING WORK (Railway Siding Work) | 1.9.1.2.2.23(FLOOR IN I PASS (PGMA-36337)) | ANITA SHAKYA |  |  | LTHPL(LANCO TEESTA HYDRO POWER LTD) | [5 empty] | WTP- Water Treatment Plant | [15 empty] | Turbine Barring Gear | TGBU | [16 empty] | 10135 |  |  | 38682 | [18 empty] | M/s NKS
Task(Task)-->PROG (Progress)-->CIV (Civil)-->RAW WATER PUMP HOUSE (Raw Water Pump House) | 1.9.1.2.2.24(FLOOR IN II PASS (PGMA-36338)) | ANJALIRAMAN |  |  | M/s Gupta Eng.(M/s Gupta Eng. & Contractors) | [5 empty] | XLPE-XLPE Cable | [15 empty] | Turbine Oil Flushing | TGDC | [16 empty] | 10174 |  |  | 38683 | [18 empty] | M/s Noble Geo Structs
Task(Task)-->PROG (Progress)-->CIV (Civil)-->RAW WATER RESERVIOR & RWPH (Raw water Reservior & RWPH) | 1.9.1.2.2.25(MAIN FLOOR IV MBL 1ST PASS (PGMA-36341)) | SH ANJI BABU |  |  | M/s KNR(M/s KNR) | [21 empty] | UAA | TGFC | [16 empty] | 10176 |  |  | 38685 | [18 empty] | M/s Nuvotronix energy
Task(Task)-->PROG (Progress)-->CIV (Civil)-->RAW WATER RESERVIOR (Raw water Reservior) | 1.9.1.2.2.26(MAIN FLOOR IV MBL 2ND PASS (PGMA-36342)) | ANJU ARORA |  |  | M/S MEIL(M/S MEIL) | [22 empty] | TGFS | [16 empty] | 10178 |  |  | 38686 | [18 empty] | M/s OMEGA
Task(Task)-->PROG (Progress)-->CIV (Civil)-->ROADS & DRAINS (Roads & Drains) | 1.9.1.2.2.27(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36343)) | ANKIT GOYAL |  |  | M/s PE Erectors(M/s PE Erectors) | [22 empty] | TGR | [16 empty] | 10182 |  |  | 38687 | [18 empty] | M/s Otoklin Global
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SA FAN (2 NOS) (SA Fan (2 Nos)) | 1.9.1.2.2.28(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36344)) | ANKUR1 |  |  | M/s PIL(M/s PIL) | [22 empty] | TGRW | [16 empty] | 10183 |  |  | 38688 | [18 empty] | M/s P.E. Erectors
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SAT (SAT) | 1.9.1.2.2.29(NON-MBL FLOOR BETWEEN MBL IV &V (PGMA-36345)) | ANKUR AGRAWAL |  |  | MACAWBER(Macawber Beekay Pvt Ltd, Noida) | [22 empty] | TMT | [16 empty] | 10184 |  |  | 38689 | [18 empty] | M/s Paharpur Cooling Towers Ltd.
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SECOND FD FAN (Second FD Fan) | 1.9.1.2.2.30(MAIN FLOOR V MBL I ST PASS (PGMA-36351)) | ANKUR GUPTA |  |  | marketing(marketing) | [22 empty] | TOC | [16 empty] | 10185 |  |  | 38690 | [18 empty] | M/s Parkson
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SECOND ID FAN (Second ID Fan) | 1.9.1.2.2.31(MAIN FLOOR V MBL II ND PASS (PGMA-36352)) | ANKURKHARE |  |  | Mat Mng-Pur(Mat Mng-Purchase) | [22 empty] | TT | [16 empty] | 10191 |  |  | 38691 | [18 empty] | M/s PCP
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SECOND PA FAN (Second PA Fan) | 1.9.1.2.2.32(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36353)) | ANKUR GARG |  |  | MAX(MAX) | [22 empty] | TUR | [16 empty] | 10235 |  |  | 38692 | [18 empty] | M/s Perfect Engineering Corporation
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SERVICE BUILDING (Service BUILDING) | 1.9.1.2.2.33(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36354)) | ANKURKANSKAR |  |  | MCF(Modern Coach Factory) | [22 empty] | TUR PIT | [16 empty] | 10274 |  |  | 38693 | [18 empty] | M/s PMPL
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SEWAGE TREATMENT PLANT (Sewage Treatment Plant) | 1.9.1.2.2.34(NON-MBL FLOOR BETWEEN MBL V &VI (PGMA-36355)) | ANNAMALAI |  |  | Mech Engg - CHP(Mech Engg - CHP) | [22 empty] | Turbine Barring Gear | [16 empty] | 10276 |  |  | 38694 | [18 empty] | M/s Powermech Projects Pvt. Ltd
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SIDE STREAM FILTRATION FOUNDATION (Side stream Filtration Foundation) | 1.9.1.2.2.35(MAIN FLOOR VI MBL 1ST PASS (PGMA-36361)) | ANOOPJAMES |  |  | Mech Engg- AHP(Mech Engg- AHP) | [22 empty] | Turbine Oil Flushing | [16 empty] | 10278 |  |  | 38695 | [18 empty] | M/s Priya Engineering
Task(Task)-->PROG (Progress)-->CIV (Civil)-->SPBD PEDESTAL (SPBD Pedestal) | 1.9.1.2.2.36(MAIN FLOOR VI MBL 2ND PASS (PGMA-36362)) | ANURAG SHREE |  |  | MM & Planning(MM & Planning) | [22 empty] | UAA | [16 empty] | 10283 |  |  | 38696 | [18 empty] | M/s Promac
Task(Task)-->PROG (Progress)-->CIV (Civil)-->STACKER RECLAIMER INCLUDING DRIVE (Stacker Reclaimer including drive house) | 1.9.1.2.2.37(NON-MBL FLOOR ABOVE MBL VI (PGMA-36363)) | ANSHUL |  |  | mm(MM) | [22 empty] | Zero Date | [16 empty] | 10284 |  |  | 38700 | [18 empty] | M/s PRV Constructions
Task(Task)-->PROG (Progress)-->CIV (Civil)-->STATION TRANSFORMER (Station transformer) | 1.9.1.2.2.38(MISCELLANEOUS PLATFORMS-PART I (PGMA-36391)) | ANUJ.KUMAR |  |  | MNF(Manufacturing) | [39 empty] | 10285 |  |  | 38701 | [18 empty] | M/s Quality Power
Task(Task)-->PROG (Progress)-->CIV (Civil)-->STOCK YARD (Stock Yard) | 1.9.1.2.2.39(MISCELLANEOUS PLATFORMS-PART II (PGMA-36392)) | ANUJ KUMAR |  |  | MSE(MSE) | [39 empty] | 10291 |  |  | 38702 | [18 empty] | M/s R K Infra
Task(Task)-->PROG (Progress)-->CIV (Civil)-->STORAGE SHEDS LUBE OIL ETC (Storage sheds lube oil, gas cylinder etc. and Parking shed) | 1.9.1.2.2.40(MISCELLANEOUS PLATFORMS-PART III (PGMA-36393)) | ANURAJ |  |  | MSPGCL(MSPGCL) | [39 empty] | 1036 |  |  | 38709 | [18 empty] | M/s R M Engineers & Contractors
Task(Task)-->PROG (Progress)-->CIV (Civil)-->TG DECK (TG Deck) | 1.9.1.2.2.41(MISCELLANEOUS PLATFORMS-PART IV (PGMA-36394)) | ANURAG THAKUR |  |  | NALCO(NALCO) | [39 empty] | 1041 |  |  | 38719 | [18 empty] | M/s Rajeshwari
Task(Task)-->PROG (Progress)-->CIV (Civil)-->TIME OFFICE & SECURITY OFFICE (TIME OFFICE & SECURITY OFFICE) | 1.9.1.2.2.42(MISCELLANEOUS PLATFORMS-PART V (PGMA-36395)) | ANKUR |  |  | NBG(NBG) | [39 empty] | 1060 |  |  | 38720 | [18 empty] | M/S RCC infra
Task(Task)-->PROG (Progress)-->CIV (Civil)-->TRANSFORMTION YARD (Transformation Yard) | 1.9.1.2.2.43(BOILER ROOF STRUCTURE (PGMA-36610)) | KASHOK |  |  | NEW FIRE(NEW FIRE ENGINEERS PVT LTD) | [39 empty] | 1100 |  |  | 38724 | [18 empty] | M/s Reva
Task(Task)-->PROG (Progress)-->CIV (Civil)-->UAT (UAT) | 1.9.1.2.2.44(BOILER ROOF SHEETING (PGMA-36611)) | APARAJITAROY |  |  | NGG&PROP(NGG&PROP) | [39 empty] | 11074 |  |  | 38725 | [18 empty] | M/s RPP INFRA
Task(Task)-->PROG (Progress)-->CIV (Civil)-->UPS & BATTERY ROOM (UPS & Battery Room) | 1.9.1.2.2.45(RAIN WATER PIPES & GUTTER (PGMA-36613)) | ANNAPOORANI |  |  | NGSL(NGSL) | [39 empty] | 11078 |  |  | 38727 | [18 empty] | M/s RS&RC
Task(Task)-->PROG (Progress)-->CIV (Civil)-->UT (UT) | 1.9.1.2.2.46(BOILER SIDE CLADDING STRUCTURE (PGMA-36620)) | ALEKHA PRASAD |  |  | NHPC- LTHPL(NHPC- LTHPL) | [39 empty] | 1110 |  |  | 38728 | [18 empty] | M/s RVPR Constructions
Task(Task)-->PROG (Progress)-->CIV (Civil)-->WATCH TOWER (Watch Tower) | 1.9.1.2.2.47(BOILER SIDE CLADDING STRUCTURE (PGMA-36621)) | APOORVA GARG |  |  | NPCIL(Nuclear Power Corporation of India Limited) | [39 empty] | 11374 |  |  | 38729 | [18 empty] | M/s RVPR Constructions Pvt. Ltd.
Task(Task)-->PROG (Progress)-->CIV (Civil)-->WEIGH BRIDGE & CONTROL BUILDING (Weigh Bridge & Control Building) | 1.9.1.2.2.48(POSTS AND HANGERS (PGMA-36740)) | PERIYASAMY A |  |  | NSPCL(NTPC Sail Power Corporation Limited) | [39 empty] | 11378 |  |  | 38730 | [18 empty] | M/s S K Sharma
Task(Task)-->PROG (Progress)-->DIS (Dispatch) | 1.9.1.2.2.49(FLOOR GRILLS AND GUARD PLATES-LOWER (PGMA-36811)) | ASHISH RANJAN |  |  | NTPC(NTPC) | [39 empty] | 11406 |  |  | 38731 | [18 empty] | M/s S V Infratech Engineers
Task(Task)-->PROG (Progress)-->ENG (Engineering) | 1.9.1.2.2.50(FLOOR GRILLS&GUARD PLATE MIDDLE (PGMA-36812)) | SL-1.4 |  |  | NTPCBG(NTPCBG) | [39 empty] | 11408 |  |  | 38733 | [18 empty] | M/s SAIL
Task(Task)-->PROG (Progress)-->ENQ (Enquiry) | 1.9.1.2.2.51(FLOOR GRILLS&GUARD PLATES- UPPER (PGMA-36813)) | ARIF HUSSAIN |  |  | NTPL(NLC TamilNadu Power Ltd.) | [39 empty] | 11416 |  |  | 38734 | [18 empty] | M/s Samay Projects Services Pvt Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection) | 1.9.1.2.2.52(FLOOR GRILLS&GUARD PLATE MISCELLANEOUS (PGMA-36814)) | ARIF NAIYER |  |  | OHPC Ltd.(OHPC Ltd.) | [39 empty] | 11467 |  |  | 38735 | [18 empty] | M/s Sanghavi Engineering
Task(Task)-->PROG (Progress)-->ERE (Erection)-->AHP (Ash Handling Plant) | 1.9.1.2.2.53(STAIRS AND LADDERS (PGMA-36820)) | ARIJIT GHOSH |  |  | operation(operation) | [39 empty] | 11469 |  |  | 38736 | [18 empty] | M/s Santosh Infra Power Projects Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure) | 1.9.1.2.2.54(HAND RAILS &POSTS LOWER (PGMA-36851)) | ARIJITGHOSH |  |  | OTOKLIN(Otoklin) | [39 empty] | 11474 |  |  | 38737 | [18 empty] | M/s SCC Infra
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->AIR & FLUE GAS SYSTEM (Air & Flue Gas System) | 1.9.1.2.2.55(HANDRAILS & POSTS MIDDLE (PGMA-36852)) | ARJESH SHARMA |  |  | PAHARPUR(M/s Paharpur Cooling Towers Ltd.) | [39 empty] | 11478 |  |  | 38738 | [18 empty] | M/s Screnic Constructions
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->BOILER OUTER CASING (Boiler Outer Casing) | 1.9.1.2.2.56(HANDRAILS & POSTS UPPER (PGMA-36853)) | ARJUN SINGH |  |  | pcg dm(pcg dm) | [39 empty] | 11484 |  |  | 38833 | [18 empty] | M/s Shalkoot
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->BOILER SKIN CASING (Boiler Skin Casing) | 1.9.1.2.2.57(CONSUMABLES &Erection MATERIALS (PGMA-36993)) | ARJUNLAL |  |  | PCP(M/s PCP) | [39 empty] | 11487 |  |  | 38908 | [18 empty] | M/s Shalkoot Mechanique Pvt Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->COAL BUNKER BAY STRUCTURES (Coal bunker Bay Structures) | 1.9.1.2.3(Inter - Connecting Walkways (PG-38)) | ARJUN SRIVASTAVA |  |  | PEEG(Public Establishment of Electricity for Generation, Syria) | [39 empty] | 11491 |  |  | 39 | [18 empty] | M/s Shiva Infra Solution Pvt. Ltd.
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->COAL BURNER SYSTEM (Coal Burner System) | 1.9.1.2.3.1(LIFT COLUMNS (PGMA-38110)) | ARNAB GHOSH |  |  | pem pg(PEM-PG) | [39 empty] | 11494 |  |  | 39501 | [18 empty] | M/s Shree Vijaya
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->COAL FEEDERS (Coal Feeders) | 1.9.1.2.3.2(INTER CONN PLATFORMSBETN BOILER/ELEVAT (PGMA-38210)) | RAVINDER |  |  | PEM(PEM) | [39 empty] | 11606 |  |  | 39602 | [18 empty] | M/s Siddan Gowda
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->COAL VALVES & GATES (Coal Valves & Gates) | 1.9.1.2.3.3(MILL HANDLING MONORAILS (PGMA-38299)) | ARUMOY |  |  | pemse(pemse) | [39 empty] | 11608 |  |  | 39607 | [18 empty] | M/s Simar Infrastructure Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->DRAINABLE HYDRO TEST (DRAINABLE HYDRO TEST) | 1.9.1.2.3.4(CONN PLATFORMS TO MILL/DEAERATOR BAY (PGMA-38310)) | ARUNKUMARSINGH |  |  | planning hr(planning hr) | [39 empty] | 11684 |  |  | 39609 | [18 empty] | M/s SIMPLEX
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->ELECTROSTATIC PRECIPITATOR (Electrostatic Precipitator) | 1.9.1.2.3.5(ECO HANDLING STRUCTURE (PGMA-38381)) | ARUNAGULATI |  |  | PLANNING(Planning) | [39 empty] | 11694 |  |  | 39610 | [18 empty] | M/s SK Sharma
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->EXTERNAL STRUCTURES (External Structures) | 1.9.1.2.3.6(MILL MAINTANANCE PLATFORMS (PGMA-38410)) | ARUN KUMAR |  |  | planningnmon(planningnmon) | [39 empty] | 11716 |  |  | 39613 | [18 empty] | M/s SN Singh
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->FIRST ID FAN (First ID FAN) | 1.9.1.2.3.7(LIFT BEAMS & BRACINGS (PGMA-38510)) | C ARUN KARTHIK |  |  | PLANNING-YTPS(Planning-YTPS) | [39 empty] | 11718 |  |  | 39614 | [18 empty] | M/s SOLID MATERIAL CONVEYING SYSTEM
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->FIRST APH (First APH) | 1.9.1.2.3.8(PASSENGER ELEVATOR BRACINGS-MIDDLE (PGMA-38512)) | ARUN KUMAR SINGH |  |  | pm nmdc(pm nmdc) | [39 empty] | 11767 |  |  | 39625 | [18 empty] | M/s Spar Geo
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->FIRST FD FAN (First FD Fan) | 1.9.1.2.3.9(ELEVATOR CLADDING STRUCTURE (PGMA-38610)) | ARUP PAUL |  |  | PM&COM(PROJECT MANAGEMENT& COMMERCIAL) | [39 empty] | 11768 |  |  | 39626 | [18 empty] | M/s SPS Construction
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->FIRST PA FAN (First PA FAN) | 1.9.1.2.3.10(ELEVATOR CLADDING (PGMA-38611)) | ARVIND NARAYAN |  |  | PMX(PMX) | [39 empty] | 11769 |  |  | 39632 | [18 empty] | M/s Srico Projects Pvt Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->FIXING COMPONENTS (Fixing Components for Main Boiler Lining and Insulation) | 1.9.1.2.3.11(CONN PLATFORM ROOF STRUCTURE (PGMA-38612)) | ARVIND KUMAR VIS |  |  | PMX-BOP(PMX-BOP) | [39 empty] | 11787 |  |  | 41 | [18 empty] | M/s SRM
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->GALLERIES & STAIRWAYS (Galleries & Stairways) | 1.9.1.2.3.12(LIFT MACHINE ROOM DETAILS &MISC STRUCT (PGMA-38710)) | ARVIND BHARDWAJ |  |  | PMX-CIVIL(PMX-CIVIL) | [39 empty] | 11791 |  |  | 42 | [18 empty] | M/s SRR Constructions
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->IGNITOR AND SCANNER AIR SYSTEM (Ignitor and Scanner Air System) | 1.9.1.2.3.13(ELEVATOR CLADDING STRUCTURES (PGMA-38712)) | ARVIND K GUPTA |  |  | PMX-ELECT(PMX-ELECT) | [39 empty] | 11916 |  |  | 43 | [18 empty] | M/s SSEB
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->INTER - CONNECTING WALKWAYS (Inter - Connecting Walkways) | 1.9.1.2.3.14(FLOORGRILLS AND GUARD PLATE (PGMA-38810)) | ARVINDNARAYAN |  |  | POWERMECH(Powermech Projects Pvt. Ltd) | [39 empty] | 11918 |  |  | 45 | [18 empty] | M/s Star Con
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->LINING AND INSULATION MATERIALS (Lining and Insulation Materials) | 1.9.1.2.3.15(STAIRS AND LADDERS (PGMA-38820)) | ASIMSUR |  |  | PPC(PC Chennai) | [39 empty] | 11967 |  |  | 456 | [18 empty] | M/s Supernova
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->MAIN BOILER SUPPORTING STRUCTURE (Main Boiler supporting structure) | 1.9.1.2.3.16(HAND RAILS AND HAND RAIL POSTS (PGMA-38850)) | ASHISHSAXENA |  |  | PPM(Project Planning & Mgmt) | [39 empty] | 11968 |  |  | 460 | [18 empty] | M/s Swain Engineering Associate Pvt Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->MILL REJECT SYSTEM (MILL REJECT SYSTEM) | 1.9.1.2.3.17(CONSUMABLES &Erection MATERIALS (PGMA-38993)) | ANIL SINGHAL |  |  | ppmg(ppmg) | [39 empty] | 11969 |  |  | 463 | [18 empty] | M/s Techno
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->O & G BURNERS , IGNITORS & SCANNER (Oil & Gas Burners and Ignitors & Scanners) | 1.9.1.2.4(Coal bunker Bay Structures (PG-34)) | ASHEESH SAHU |  |  | proj dir(Project Director) | [39 empty] | 11987 |  |  | 467 | [18 empty] | M/s Techno Elevators
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->OIL & GAS SYSTEMS (Oil & Gas Systems) | 1.9.1.2.4.1(FOUN.MATLS FOR BUNKER COLOMNS (PGMA-34010)) | ASIM KUMAR |  |  | proj mng(project management) | [39 empty] | 11991 |  |  | 47 | [18 empty] | M/s Techno Industries
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->PULVERISED FUEL PIPING (Pulverised Fuel Piping) | 1.9.1.2.4.2(BUNKER COLUMNS (PGMA-34100)) | ASHIMKUMAR |  |  | proj planning(proj planning n monitiring) | [39 empty] | 12004 |  |  | 47-264-FSIP | [18 empty] | M/s Techno Scale
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->PULVERISED FUEL SYSTEM (Pulverised Fuel System) | 1.9.1.2.4.3(BUNKER SUPPORT FRAMES (PGMA-34200)) | ASHISH |  |  | PROMAC(PROMAC, Bengaluru) | [39 empty] | 12010 |  |  | 473 | [18 empty] | M/s Texcel
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->ROOF SKIN CASING (Roof Skin Casing) | 1.9.1.2.4.4(PLATFORMS (PGMA-34300)) | ASHISHGUPTA |  |  | PSER(Power Sector Eastern Region) | [39 empty] | 12025 |  |  | 48 | [18 empty] | M/s Thermosystems
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SA FAN (SA FAN) | 1.9.1.2.4.5(BUNKER BAY FLOOR BEAMS (PGMA-34390)) | ASHISH KUMAR |  |  | PSNR(Power Sector Northern Region) | [39 empty] | 12026 |  |  | 50 | [18 empty] | M/s ThyssenKrupp
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SCR C&I (SCR C&I) | 1.9.1.2.4.6(HORIZONTAL BEAMS BETWEEN COLUMNS (PGMA-34400)) | ASHISH ABRAHAM |  |  | PS-PMG(PS-PMG) | [39 empty] | 12027 |  |  | 52 | [18 empty] | M/s TSGENCO
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SCR DUCT (SCR Duct) | 1.9.1.2.4.7(VERTICAL BRACINGS (PGMA-34500)) | ASHISH K SINGH |  |  | PS-PMX(PS-PMX) | [39 empty] | 12037 |  |  | 55 | [18 empty] | M/s Unique Dosing Systems
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SCR FUEL SYSTEMS (SCR Fuel systems) | 1.9.1.2.4.8(FLOORGRILLS AND GUARD PLATES (PGMA-34810)) | ASHISH KUMAR SIN |  |  | PS-PSM(PS-PSM) | [39 empty] | 12038 |  |  | 56 | [18 empty] | M/s Unique Handlers
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SCR STRUCTURES (SCR Structures) | 1.9.1.2.4.9(STAIRS AND LADDERS (PGMA-34820)) | ASHOK |  |  | PSSR(Power Sector Southern Region) | [39 empty] | 12042 |  |  | 57 | [18 empty] | M/s United System
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SEAL BOXES (Seal Boxes) | 1.9.1.2.4.10(HANDRAILS & HANDRAIL POSTS (PGMA-34850)) | ASHUTOSH |  |  | PSWR(Power Sector Western Region) | [39 empty] | 12044 |  |  | 61001 | [18 empty] | M/s URC
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SECOND APH (Second APH) | 1.9.1.2.5(Manholes and Furnace Openings (PG-28)) | ASHUTOSH1 |  |  | Punatsangchhu-I(Punatsangchhu-I HEP Authority, Bhutan) | [39 empty] | 12052 |  |  | 61101 | [18 empty] | M/s Vasavi Electro Systems Pvt Ltd
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SECOND FD FAN (Second FD Fan) | 1.9.1.2.5.1(DOORS (PGMA-28220)) | ASHUTOSHK |  |  | Punatsangchhu-II(Punatsangchhu-II HEP Authority, Bhutan) | [39 empty] | 12071 |  |  | 61103 | [18 empty] | M/s Vishnu Saran
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SECOND ID FAN (Second ID Fan) | 1.9.1.2.5.2(BPS FASTENERS (PGMA-28700)) | ASHU |  |  | PVUN/NTPC(PVUN/NTPC) | [39 empty] | 12079 |  |  | 61201 | [18 empty] | M/s WIPRO ENTERPRISES (P) LTD
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->SECOND PA FAN (Second PA FAN) | 1.9.1.2.6( BOI- HT- Boiler Elevator) | ASHWANI KUMAR |  |  | QUA(Quality) | [39 empty] | 12080 |  |  | 61301 | [18 empty] | Others
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOILER STRUCTURE (Boiler Structure)-->WCS, RE-HEATERS, SUPER HEATERS (Water Circulation system, Super Heaters and Re-Heaters) | 1.9.1.2.7( BOI- FL- Quick erect scaffold) | ASHWANI GUPTA |  |  | quality(quality) | [39 empty] | 12081 |  |  | 61302 | [18 empty] | Yet to award1
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP) | 1.9.1.3(Civil) | ASHWIN BHISIKAR |  |  | r n wb(r n wb) | [39 empty] | 12087 |  |  | 61501
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->AIR COMPRESSOR SYSTEM (Air Compressor System) | 1.9.1.3.2(Boiler Foundation) | ASIF IQBAL |  |  | Raghuganga HEP(Raghuganga HEP Ltd, Nepal) | [39 empty] | 12089 |  |  | 65
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->AIR CONDITIONING SYSTEM (Air Conditioning System) | 1.9.1.3.3(Coal Bunker Bay Foundation and structure) | ASIT KUMAR BARAL |  |  | RCC INFRA(RCC INFRA) | [39 empty] | 12096 |  |  | 67
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->CONDENSATE POLISHING UNIT REGENERA (Condensate Polishing Unit Regeneration System) | 1.9.1.3.3.2(Coal BUNKER BAY FOUNDATIONS) | A.SATISH KUMAR |  |  | RCF(Rail Coach Factory) | [39 empty] | 12098 |  |  | 78663
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->CONDENSATE STORAGE TANK (Condensate Storage Tank) | 1.9.1.3.3.3(Coal Bunker Bay Floors and Roof) | ASOK |  |  | renewable(renewable) | [39 empty] | 12178 |  |  | 78724
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->CW & ACW SYSTEM (CW & ACW System) | 1.9.1.4(Erection) | ANIL SR KHANDARE |  |  | RPT(Ranipet) | [39 empty] | 12179 |  |  | 78725
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->CW TREATMENT SYSTEM (CW Treatment System) | 1.9.1.4.1(Main Boiler supporting structure (PG-35)) | ASSISTANT |  |  | RVPR(M/s RVPR Constructions Pvt. Ltd.) | [39 empty] | 12181 |  |  | 79
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->DG AND VENTILLATION SYSTEM (DG and Ventillation System) | 1.9.1.4.2(Galleries & Stairways (PG-36)) | ASURESH |  |  | SAIL(SAIL) | [39 empty] | 12184 |  |  | 79602
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->DM PLANT (DM Plant) | 1.9.1.4.3(Inter - Connecting Walkways (PG-38)) | A.K. GUPTA |  |  | SAPDC((SJVN Arun-3 Development Company Pvt Ltd)) | [39 empty] | 12187 |  |  | 79626
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->FIRE DETECTION & PROTECTION SYS (Fire Detection & Protection Sys) | 1.9.1.4.4(Coal bunker Bay Structures (PG-34)) | ATEET KUMAR |  |  | SBD(SBD) | [39 empty] | 12306 |  |  | 80
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->FUEL OIL HANDLING SYSTEM (Fuel Oil Handling system) | 1.9.1.4.5(Manholes and Furnace Openings (PG-28)) | ATHMANANDA Y K |  |  | SCS(SCS) | [39 empty] | 12314 |  |  | 80399
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->PRE-TREATMENT PLANT (Pre-treatment Plant) | 1.9.2(Water Circulation System, Super Heaters and Re-Heaters ) | AVENKATESHA |  |  | SFT(Safety) | [39 empty] | 12317 |  |  | 81
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->RAW WATER STORAGE TANK & PUMP HOUS (Raw Water Storage Tank & Pump House) | 1.9.2.1(Supply (BHEL TRY)) | AVINASH |  |  | SIMPLEX(M/s SIMPLEX) | [39 empty] | 12324 |  |  | 89
Task(Task)-->PROG (Progress)-->ERE (Erection)-->BOP (BOP)-->SIDE STREAM FILTRATION SYSTEM (Side Stream Filtration system) | 1.9.2.1.1(Water Circulation System) | AVINASHSJK |  |  | Site(Site) | [39 empty] | 12327 |  |  | 95
Task(Task)-->PROG (Progress)-->ERE (Erection)-->CHP (Coal Handling Plant) | 1.9.2.1.1.1(Separator, Storage Tanks and Supports (PG-04)) | AWADHESH PRATAP |  |  | SKSHARMA(SK SHARMA) | [39 empty] | 12328 |  |  | 96
Task(Task)-->PROG (Progress)-->ERE (Erection)-->ELECTRICAL, C&I (Electrical, C&I) | 1.9.2.1.1.1.1(SUPPORTS FOR COLLECTOR & SEPERATOR VESSEL (PGMA-4147)) | AWADHESH SINGH |  |  | SL(Skilled Labour) | [39 empty] | 12344 |  |  | 97
Task(Task)-->PROG (Progress)-->ERE (Erection)-->ESP E&C (ESP E&C) | 1.9.2.1.1.1.2(Separator Vessels with Internals & Attach (PGMA-4321)) | AWESHKUMAR |  |  | SOM(SOM) | [39 empty] | 12348 |  |  | 99
Task(Task)-->PROG (Progress)-->ERE (Erection)-->FGD (FGD) | 1.9.2.1.1.1.3(SUPP FOR COLLECTING & SEPERATOR VESSEL(DD) (PGMA-4347)) | AMITYADAV |  |  | STE(STE) | [39 empty] | 12354 |  |  | BOI
Task(Task)-->PROG (Progress)-->ERE (Erection)-->PIPING (Piping E&C) | 1.9.2.1.1.1.4(SUPP FOR COLLECTING & SEPERATOR VESSEL (PGMA-4547)) | AYANMUKHERJEE |  |  | structure(structure) | [39 empty] | 12368 |  |  | BPL01BFVX01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area) | 1.9.2.1.1.2(Waterwall Headers (PG-05)) | AYUSH |  |  | STS(STS) | [39 empty] | 12393 |  |  | BPL01FTXX01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->CONDENSER (Condenser) | 1.9.2.1.1.2.1(INLET FRONT LOWER WW HEADER (PGMA-5137)) | P AYYASAMY |  |  | SUB VENDORS(Sub Vendors) | [39 empty] | 12403 |  |  | BPL01MTXX01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->GENERATOR (Generator) | 1.9.2.1.1.2.2(INLET REAR LOWER WW HEADER (PGMA-5147)) | B EZHILMARAN |  |  | SUPPLY(Supply) | [39 empty] | 12405 |  |  | BPL01REJX01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C) | 1.9.2.1.1.2.3(INLET SIDE LOWER WW HEADER (PGMA-5155)) | B RAJASREE |  |  | SWE(SWE) | [39 empty] | 12506 |  |  | BPL04ACWM04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->EXCITATION SYSTEM (EXCITATION SYSTEM) | 1.9.2.1.1.2.4(WATERWALL REAR HANGER OUTLET HDR (PGMA-5227)) | KANTHIKIRAN |  |  | TANGEDCO(TANGEDCO) | [39 empty] | 12514 |  |  | BPL04AFDM01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->GEN GAS SYSTEM (GEN GAS SYSTEM) | 1.9.2.1.1.2.5(OUTLET FRONT UPPER WW HEADER (PGMA-5231)) | BIRANCHINAIK |  |  | TBEM,HVDC,ENGG(TBEM,HVDC,ENGG) | [39 empty] | 12515 |  |  | BPL04AHPM01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->GENERATOR (Generator) | 1.9.2.1.1.2.6(OUTLET SIDE UPPER WW HEADER (PGMA-5251)) | SATISH BACHLEY |  |  | TECHNO(Techno) | [39 empty] | 12517 |  |  | BPL04AWPM04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->HP TURBINE (HP TURBINE) | 1.9.2.1.1.2.7(Furnace Rear wall Intermediate header (PGMA-5327)) | VIKAS BAHUGUNA |  |  | THDC(THDC) | [39 empty] | 12524 |  |  | BPL04BAMM04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->IP TURBINE (IP TURBINE) | 1.9.2.1.1.2.8(FRONT INTERMEDIATE HEADER (PGMA-5330)) | BALAJIK |  |  | THDCIL(THDCIL) | [39 empty] | 12528 |  |  | BPL04BFPM01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->LP TURBINE (LP TURBINE) | 1.9.2.1.1.2.9(SIDE INTERMEDIATE HEADER (PGMA-5350)) | BALAJIRS |  |  | Transf Comm(Transf Comm) | [39 empty] | 12544 |  |  | BPL04BFPM04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->LUBE OIL SYSTEM (LUBE OIL SYSTEM) | 1.9.2.1.1.3(Waterwall Panels (PG-06)) | BALAKRISHNAN A |  |  | Transf Engg(Transf Engg) | [39 empty] | 12554 |  |  | BPL04CAMX04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->MISCELLANEOUS ACTIVITIES (MISCELLANEOUS ACTIVITIES) | 1.9.2.1.1.3.1(UNCLASSIFIED BURNER PANEL (PGMA-6400)) | BALOO |  |  | Transfor. Mfg(Transfor. Mfg) | [39 empty] | 12800 |  |  | BPL04CEPM01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->PEDESTAL RELATED WORK (PEDESTAL RELATED WORK) | 1.9.2.1.1.3.2(BURNER PNL- OS (PGMA-6401)) | BALRAJ |  |  | trc(trc) | [39 empty] | 12803 |  |  | BPL04CEPM04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->POWER CYCLE PUMPS (Power Cycle Pumps) | 1.9.2.1.1.3.3(FRONT INTERMEDIATE WW PNL -OS (PGMA-6434)) | BANIV |  |  | TRE(TRE) | [39 empty] | 12805 |  |  | BPL04CHPM01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->PW SYSTEM (PW SYSTEM) | 1.9.2.1.1.3.4(FRONT WW LOWER PANEL-OS (PGMA-6437)) | BANOTH |  |  | Trfr & Works Eng(Trfr & Works Engg) | [39 empty] | 12850 |  |  | BPL04CWPM01
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->SEAL OIL SYSTEM (SEAL OIL SYSTEM) | 1.9.2.1.1.3.5(REAR INTERMEDIATE WW PNL -OS (PGMA-6444)) | BL |  |  | Trichy(Trichy) | [39 empty] | 12852 |  |  | BPL04CWPM04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TG E&C (TG E&C)-->VALVES (VALVES) | 1.9.2.1.1.3.6(SIDE UPPER WW PNL -OS (PGMA-6451)) | S BARIK |  |  | TRY(Trichy) | [39 empty] | 12900 |  |  | BPL04DMSG04
Task(Task)-->PROG (Progress)-->ERE (Erection)-->TG (TG Area)-->TURBINE (Turbine) | 1.9.2.1.1.3.7(SIDE INTERMEDIATE WW PNL -OS (PGMA-6453)) | BHARAT ARORA |  |  | TSEGENCO(TSEGENCO) | [39 empty] | 12903 |  |  | BPL04DMTG04
Task(Task)-->PROG (Progress)-->MAN (Manufacturing) | 1.9.2.1.1.3.8(SIDE LOWER WW PNL -OS (PGMA-6455)) | BASANT KUMAR BEC |  |  | TSEGNCO(TSEGENCO) | [39 empty] | 12906 |  |  | BPL04DPMX01
Task(Task)-->PROG (Progress)-->MIL (Milestone) | 1.9.2.1.1.3.9(BURNER PANELS WITH ATTACHMENT (PGMA-6500)) | BBALU |  |  | TSGENCO(TSGENCO) | [39 empty] | 12907 |  |  | BPL04DRPM04
Task(Task)-->PROG (Progress)-->ORD (Ordering) | 1.9.2.1.1.3.10(SOFA PANELS -OS (PGMA-6501)) | BEZHILMARAN |  |  | UJVNL(Uttrakhand Jal Vidyut Nigam Limited) | [39 empty] | 12914 |  |  | BPL04FDFM01
Task(Task)-->PROG (Progress)-->PEDM (PEDM) | 1.9.2.1.1.3.11(FRONT UPPER WW PNL + ATCH (PGMA-6731)) | BHADRA |  |  | UNITED SYS.(United System) | [39 empty] | 12916 |  |  | BPL04FDFM04
Task(Task)-->PROG (Progress)-->PE-RFC (PE-RFC) | 1.9.2.1.1.3.12(Front Upper Corners Ww Panel + attachment (PGMA-6732)) | BHANUVILAS |  |  | UPRVUNL(UPRVUNL) | [39 empty] | 12917 |  |  | BPL04FGDM01
Task(Task)-->PROG (Progress)-->PRC (Procurement) | 1.9.2.1.1.3.13(FRONT INTERMEDIATE WW PNL + ATCH (PGMA-6734)) | BHASKARJIT BARUA |  |  | WBPDCL(WBPDCL) | [39 empty] | 12924 |  |  | BPL04IDFM01
Task(Task)-->PROG (Progress)-->REC (Reciept At Site) | 1.9.2.1.1.3.14(FUR LWR FRNT SPIRAL PANELS WITH I/L TERM TUBES (PGMA-6737)) | SUROJIT BHAT |  |  | WGG(Wrench Guest Group) | [39 empty] | 12927 |  |  | BPL04IDFM04
Task(Task)-->PROG (Progress)-->RESOURCE (Resource) | 1.9.2.1.1.3.15(REAR UPPER WW PNL + ATCH (PGMA-6741)) | BHEEM SAIN |  |  | WIPRO(WIPRO ENTERPRISES (P) LTD) | [39 empty] | 12928 |  |  | BPL04MMXX01
Task(Task)-->PROG (Progress)-->RESOURCE (Resource)-->RESOURCE-MANPOWER (RESOURCE-MANPOWER) | 1.9.2.1.1.3.16(FUR UPPER REAR SPIRAL PANEL (PGMA-6744)) | BHELCOM | [42 empty] | 12944 |  |  | BPL04MMXX04
Task(Task)-->PROG (Progress)-->RESOURCE (Resource)-->RESOURCE-T&P (RESOURCE-T&P) | 1.9.2.1.1.3.17(FUR LWR REAR SPIRAL PANELS WITH I/T TERM TUBES (PGMA-6747)) | BHELEDN | [42 empty] | 12948 |  |  | BPL04OBMX04
Task(Task)-->PROG (Progress)-->SUP (Supply) | 1.9.2.1.1.3.18(SIDE UPPER WW PNL + ATCH (PGMA-6751)) | BHELHDR | [42 empty] | 12954 |  |  | BPL04PAFM01
Task(Task)-->QUALITY TRACKER (Quality Tracker) | 1.9.2.1.1.3.19(Furnace vertical wall panels sides L&R (PGMA-6752)) | BHELHYD | [42 empty] | 12968 |  |  | BPL04PAFM04
Task(Task)-->RISK TRACKER (Risk Tracker) | 1.9.2.1.1.3.20(FUR UPPER SIDE SPIRAL PANELS (PGMA-6753)) | BHELPMG | [42 empty] | 12991 |  |  | BPL04RCPM04
Task(Task)-->S CURVE (S Curve) | 1.9.2.1.1.3.21(SIDE LOWER WW PNL + ATCH (PGMA-6755)) | BHELPSWR | [42 empty] | 12992 |  |  | BPL04RODM04
Task(Task)-->SAFETY MONTHLY STATISTICS (Safety Monthly Statistics) | 1.9.2.1.1.4(Circulation System Components (PG-07)) | BHELSITE | [42 empty] | 12993 |  |  | BPL04RWPM04
Task(Task)-->SAFETY TRACKER (Safety Tracker) | 1.9.2.1.1.4.1(Separator-Collecting Vessel Connecting Link (PGMA-7110)) | BHELTRY | [42 empty] | 12994 |  |  | BPL04SGM01
Task(Task)-->SCORE CARD (Score Card) | 1.9.2.1.1.4.2(Mixing Sphere (PGMA-7125)) | BHUVNESH MEENA | [42 empty] | 1318 |  |  | BPL04TGM01
Task(Task)-->TEST (TEST) | 1.9.2.1.1.4.3(FURNACE SCREEN TUBES (PGMA-7223)) | BIBHAS | [42 empty] | 1325 |  |  | BPL06GTXX01
Task(Task)-->YADADRI (Yadadri) | 1.9.2.1.1.4.4(LOWER CORNER TRANSITION TUBES (PGMA-7231)) | BIDHAN | [42 empty] | 1341 |  |  | BPL06GTXX01CD01
Task(Task)-->YADADRI (Yadadri)-->CIV(Civil) | 1.9.2.1.1.4.5(UPPER CORNER TRANSITION TUBES (PGMA-7232)) | BIDYUT | [42 empty] | 1350 |  |  | BPL06GTXX01CD02
Task(Task)-->YADADRI (Yadadri)-->CIV(Civil)-->BOI(Boiler) | 1.9.2.1.1.4.6(WW FRONT HEADER SUSPENSION-DD (PGMA-7302)) | BIKASH MISHRA | [42 empty] | 1411 |  |  | BPL06GTXX01CD03
Task(Task)-->YADADRI (Yadadri)-->CIV(Civil)-->NDCT(NDCT) | 1.9.2.1.1.4.7(WW SIDE HEADER SUSPENSION-DD (PGMA-7303)) | BIMAL | [42 empty] | 1412 |  |  | BPL06GTXX01CD04
Task(Task)-->YADADRI (Yadadri)-->DIS(Dispatch) | 1.9.2.1.1.4.8(FURNACE WALL SUPPORTS FRONT-DD (PGMA-7309)) | BINAY | [42 empty] | 1414 |  |  | BPL06GTXX01CD05
Task(Task)-->YADADRI (Yadadri)-->ERE(Erection) | 1.9.2.1.1.4.9(FUR SIDE RISERS (PGMA-7315)) | BINIT KUMAR PAND | [42 empty] | 1415 |  |  | BPL06GTXX01CD06
Task(Task)-->YADADRI (Yadadri)-->MAN(Manufacturing) | 1.9.2.1.1.4.10(FUR REAR RISERS (PGMA-7316)) | BINOD KUMAR | [42 empty] | 1416 |  |  | BPL06GTXX01CD07
Task(Task)-->YADADRI (Yadadri)-->PDE(Product Engineering) | 1.9.2.1.1.4.11(FUR FRNT RISERS (PGMA-7318)) | BIPIN KUMAR | [42 empty] | 1417 |  |  | BPL06GTXX01CD08
Task(Task)-->YADADRI (Yadadri)-->PRC(Procurement) | 1.9.2.1.1.4.12(RISER TUBE SUPPORT-DD (PGMA-7331)) | P K BISWAS | [42 empty] | 15136 |  |  | BPL06GTXX01CD09
Task(Task)-->YADADRI (Yadadri)-->PRE(Project Engineering) | 1.9.2.1.1.4.13(FURNACE SPIRAL WALL SUPPORTS-DD (PGMA-7360)) | BJCL | [42 empty] | 15177 |  |  | BPL06GTXX01CD10
Task(Task)-->YADADRI (Yadadri)-->SCH(Schedule) | 1.9.2.1.1.4.14(FURNACE WALL SUPP REAR-DD (PGMA-7361)) | BKSINGH | [42 empty] | 15178 |  |  | BPL06GTXX01CD11
Task(Task)-->YADADRI (Yadadri)-->SUP(Supply) | 1.9.2.1.1.4.15(FURNACE WALL SUPPORTS SIDES L & R-DD (PGMA-7362)) | BRIJESH KR SINGH | [42 empty] | 15236 |  |  | BPL06GTXX01CD12
| 1.9.2.1.1.4.16(CONSUMABLES &Erection MATERIALS-DD (PGMA-7393)) | BKYADAV | [42 empty] | 15278 |  |  | BPL06GTXX01CD13
| 1.9.2.1.1.4.17(COMBUSTOR OUTLET HEADER SUPPORTS (PGMA-7402)) | BANSHI LAL BEDI | [42 empty] | 15279 |  |  | BPL06GTXX01CD14
| 1.9.2.1.1.4.18(WW SIDE HEADER SUSPENSION (PGMA-7403)) | BURHANMAJHI | [42 empty] | 16079 |  |  | BPL06GTXX01CM01
| 1.9.2.1.1.4.19(WW SCREEN HEADER SUSPENSION (PGMA-7405)) | BSRINIVAS | [42 empty] | 16201 |  |  | BPL06GTXX01CM02
| 1.9.2.1.1.4.20(Furnace wall Supports front (PGMA-7409)) | BVLU | [42 empty] | 16202 |  |  | BPL06GTXX01CM03
| 1.9.2.1.1.4.21(FURNACE SCREEN TUBES-OS (PGMA-7423)) | BAIDYANATH YADAV | [42 empty] | 16203 |  |  | BPL06GTXX01CM04
| 1.9.2.1.1.4.22(RISER TUBE SUPPORT (PGMA-7431)) | C KARUNAKARAN | [42 empty] | 16222 |  |  | BPL06GTXX01CM05
| 1.9.2.1.1.4.23(Furnace Spiral Wall supports Misc. items (PGMA-7460)) | CSREERAJ | [42 empty] | 16226 |  |  | BPL06GTXX01CM06
| 1.9.2.1.1.4.24(Furnace wall Supports rear (PGMA-7461)) | P K AGARWAL | [42 empty] | 16231 |  |  | BPL06GTXX01CM07
| 1.9.2.1.1.4.25(Furnace wall Supports Sides L & R (PGMA-7462)) | SL-1.7 | [42 empty] | 16270 |  |  | BPL06GTXX01CM08
| 1.9.2.1.1.4.26(EVAPORATOR COILS (PGMA-7502)) | RAKESH SHARMA | [42 empty] | 16278 |  |  | BPL06GTXX01CM09
| 1.9.2.1.1.4.27(EVAPORATOR COILS (PGMA-7503)) | ASHISH CHAUHAN | [42 empty] | 16379 |  |  | BPL06GTXX01CM10
| 1.9.2.1.1.4.28(MODULE SUPPORT - IP (PGMA-7505)) | CHIRANJIB BISWAS | [42 empty] | 16403 |  |  | BPL06GTXX01CM12
| 1.9.2.1.1.4.29(RISER TUBE SUPPORT-SHOP (PGMA-7531)) | BIJAYKUMARCHATTA | [42 empty] | 17174 |  |  | BPL06GTXX01CM13
| 1.9.2.1.1.4.30(FURNACE SPIRAL WALL MISC ITEMS-SHOP (PGMA-7560)) | CHINMOY GAYEN | [42 empty] | 17304 |  |  | BPL06GTXX01CM14
| 1.9.2.1.1.4.31(INDEGENOUS ELECTRODE (PGMA-7991)) | CHANDRANI | [42 empty] | 17306 |  |  | BPL06GTXX01CM15
| 1.9.2.1.1.4.32(IMPORTED ELECTRODES (PGMA-7992)) | CHAKRESHKUMAR | [42 empty] | 17319 |  |  | BPL06GTXX01CM16
| 1.9.2.1.1.4.33(CONSUMABLES &Erection MATERIALS (PGMA-7993)) | CHANDAN BEHERA | [42 empty] | 17407 |  |  | BPL06GTXX01CM17
| 1.9.2.1.1.5(Buckstays and Framing (PG-08)) | CHANDANBEHRA | [42 empty] | 17476 |  |  | BPL06GTXX01CM18
| 1.9.2.1.1.5.1(FURNACE UPPER BUCKSTAYS- FRONT & REAR (PGMA-8001)) | CHANDAN KUMAR | [42 empty] | 17504 |  |  | BPL06GTXX01CM20
| 1.9.2.1.1.5.2(FURNACE UPPER BUCKSTAYS - SIDE (PGMA-8003)) | CHANDRA KETU VIS | [42 empty] | 17505 |  |  | BPL06GTXX01CM21
| 1.9.2.1.1.5.3(FURNACE INTER BUCKSTAYS (PGMA-8006)) | CHANDRAMANI | [42 empty] | 17506 |  |  | BPL06GTXX01CM22
| 1.9.2.1.1.5.4(FURNACE LOWER BUCKSTAYS (PGMA-8007)) | ACHANDRASEKHARA | [42 empty] | 17509 |  |  | BPL06GTXX01CM23
| 1.9.2.1.1.5.5(FURNACE REAR ARCH BUCKSTAYS (PGMA-8111)) | CHANDRIKA KUMAR | [42 empty] | 17510 |  |  | BPL06GTXX01CM24
| 1.9.2.1.1.5.6(UPPER BACK PASS BUCKSTAY (PGMA-8501)) | CHARAN | [42 empty] | 17511 |  |  | BPL06GTXX01CM25
| 1.9.2.1.1.5.7(FURNACE BACK PASS BUCKSTAYS -SIDE (PGMA-8503)) | CHECKER2 | [42 empty] | 17521 |  |  | BPL06SHRX01
| 1.9.2.1.1.5.8(FURNACE KEY BUCKSTAYS - UPPER (PGMA-8901)) | CHECKER2_D | [42 empty] | 17776 |  |  | BPL06STXX01
| 1.9.2.1.1.5.9(EXPN. MOVEMENT MEASUREMENT COMPONENTS (PGMA-8910)) | CHECKER1 | [42 empty] | 17807 |  |  | BPL09GRPX01
| 1.9.2.1.1.5.10(BULKED B.P.S ITEMS FOR UPPER BUCKSTAYS (PGMA-8911)) | CHECKER1_D | [42 empty] | 17900 |  |  | BPL09HTSG01
| 1.9.2.1.1.5.11(BULKED B.P.S ITEMS FOR INTERMEDIATE BUCKSTAYS (PGMA-8912)) | CHETAN PRAKAS | [42 empty] | 17903 |  |  | CWP CW 10-M
| 1.9.2.1.1.5.12(BULKED B.P.S ITEMS FOR LOWER BUCKSTAYS (PGMA-8913)) | CHINMOY MANDAL | [42 empty] | 17904 |  |  | FW
| 1.9.2.1.1.6(Economiser Headers, Coils and Components (PG-19)) | T CHIRANJEEVI | [42 empty] | 17906 |  |  | HP HEATER 6A
| 1.9.2.1.1.6.1(Economiser Supports above Roof- DD (PGMA-19304)) | C.CHITRALEKHA | [42 empty] | 17919 |  |  | HP HEATER 7A
| 1.9.2.1.1.6.2(ECO. LINES & LINKS SUPPORTS-DD (PGMA-19306)) | CHITRA MARTOLIA | [42 empty] | 17991 |  |  | HP HEATER 8A
| 1.9.2.1.1.6.3(ECO FEED PIPE SUPPORT-DD (PGMA-19307)) | CHPRASANTH | [42 empty] | 17992 |  |  | HYBM001
| 1.9.2.1.1.6.4(ECO HANGER TUBE ATTACHMENT (PGMA-19402)) | KOTRESHA C | [42 empty] | 17993 |  |  | HYBM002
| 1.9.2.1.1.6.5(ECO. LINES & LINKS SUPPORTS-SHOP (PGMA-19506)) | CKANDASAMY | [42 empty] | 18001 |  |  | HYBM003
| 1.9.2.1.1.6.6(ECO FEED PIPE SUPPORT-SHOP (PGMA-19507)) | C. KARUNAKARAN | [42 empty] | 18010 |  |  | HYBM004
| 1.9.2.1.1.6.7(ECONOMISER INLET HEADERS (PGMA-19701)) | CLIENT | [42 empty] | 18111 |  |  | HYBM005
| 1.9.2.1.1.6.8(ECONOMISER OUTLET HEADERS (PGMA-19702)) | CLIENT_D | [42 empty] | 18236 |  |  | HYBM006
| 1.9.2.1.1.6.9(ECONOMISER INTERMEDIATE HEADER - REAR (PGMA-19753)) | CLIENT1 | [42 empty] | 18701 |  |  | HYBM007
| 1.9.2.1.1.6.10(ECONOMISER INTERMEDIATE HEADER - FRONT (PGMA-19763)) | CLIENT2 | [42 empty] | 18901 |  |  | HYBM008
| 1.9.2.1.1.6.11(ECONOMISER INTERMEDIATE HEADER - INTER (PGMA-19783)) | CLMEENA | [42 empty] | 18910 |  |  | HYBM009
| 1.9.2.1.1.6.12(HEADERS OF CENTER INTER (PGMA-19793)) | AK VERMA | [42 empty] | 19092 |  |  | HYBM010
| 1.9.2.1.1.6.13(ECONOMISER HANGER TUBES (PGMA-19802)) | OP-1.1 | [42 empty] | 19304 |  |  | HYBM011
| 1.9.2.1.1.6.14(PLAIN TUBE ECONO. UPPER COIL ASSY(LEFT) (PGMA-19814)) | CHANDRA P K | [42 empty] | 19306 |  |  | HYBM012
| 1.9.2.1.1.6.15(ECO LOWER ASSY -LEFT (PGMA-19824)) | OP-1.5 | [42 empty] | 19307 |  |  | HYBM013
| 1.9.2.1.1.6.16(ECONOMISER FEED PIPE (PGMA-19850)) | TNP-CR-1 | [42 empty] | 19402 |  |  | HYBM014
| 1.9.2.1.1.6.17(LINK FROM ECO OUTLET HEADER TO ECO MIX LINE(PGMA-19851)) | CHANDANESWAR S | [42 empty] | 19506 |  |  | HYBM015
| 1.9.2.1.1.6.18(ECONOMISER-I TO ECONOMISER-II LINK (PGMA-19852)) | CSCHARY | [42 empty] | 19507 |  |  | HYBM016
| 1.9.2.1.1.6.19(ECONOMISER FEED PIPE (PGMA-19853)) | C S DEOLIKAR | [42 empty] | 19701 |  |  | HYBM017
| 1.9.2.1.1.6.20(ECO INTER ASSY - LEFT (PGMA-19884)) | CSRAJA | [42 empty] | 19702 |  |  | HYBM018
| 1.9.2.1.1.6.21(ECONOMISER MISCELLANEOUS COMPONENTS (PGMA-19903)) | CVK SINGH | [42 empty] | 19753 |  |  | HYBM019
| 1.9.2.1.1.6.22(IP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19904)) | CVKSINGH | [42 empty] | 19763 |  |  | HYHE001
| 1.9.2.1.1.6.23(ECONOMISER COIL SUPPORTS (PGMA-19905)) | CVNATHAN | [42 empty] | 19783 |  |  | HYHE002
| 1.9.2.1.1.6.24(HP ECO 4 FRONT MODULE COMPONENTS(LEFT) (PGMA-19906)) | D H SINGH | [42 empty] | 19793 |  |  | HYPU001
| 1.9.2.1.1.6.25(LP ECONOMISER SUPPORTS & SUSPENSIONS (PGMA-19907)) | D P MAJAKAR | [42 empty] | 19802 |  |  | HYPU002
| 1.9.2.1.1.6.26(HP ECONOMISER-II MODULE SUPPORTS (PGMA-19914)) | D DAS | [42 empty] | 19814 |  |  | HYPU003
| 1.9.2.1.1.6.27(PLAIN TUBE ECO. LOWER ASSY (RIGHT) (PGMA-19924)) | DALLI | [42 empty] | 19824 |  |  | HYPU004
| 1.9.2.1.1.6.28(ECO INTER ASSY - RIGHT (PGMA-19984)) | DADU | [42 empty] | 19850 |  |  | HYPU005
| 1.9.2.1.1.6.29(ECONOMISER IMPORTED ELECTRODES (PGMA-19991)) | DANESHBISEN | [42 empty] | 19851 |  |  | HYPU006
| 1.9.2.1.1.6.30(IMPORTED ELECTRODES (PGMA-19992)) | DARPAN | [42 empty] | 19852 |  |  | HYPU008
| 1.9.2.1.1.7(Boiler Integral Piping and Fittings (PG-24)) | DEBPROSAD HALDER | [42 empty] | 19853 |  |  | HYPU009
| 1.9.2.1.1.7.1(BOILER FILLING PIPING (PGMA-24350)) | DEBAJIT SINHA | [42 empty] | 19884 |  |  | HYPU010
| 1.9.2.1.1.7.2(HANGERS+SUPPORTS FOR BLR FILLING PIPING (PGMA-24351)) | DEBASHISH | [42 empty] | 19903 |  |  | HYPU011
| 1.9.2.1.1.7.3(BOILER FILL PIPING - DD (PGMA-24352)) | DEBASISA | [42 empty] | 19904 |  |  | HYPU012
| 1.9.2.1.1.7.4(HANGERS & SUPPORTS FOR BOILER FILL PIPING - OS (PGMA-24353)) | DEBORPITA GHOSH | [42 empty] | 19905 |  |  | HYPU013
| 1.9.2.1.1.7.5(BOI items for Boiler fill piping (PGMA-24354)) | DEEPA C | [42 empty] | 19906 |  |  | HYPU014
| 1.9.2.1.1.7.6(BULKED BPS COMPONENTS FOR TRIM PIPES (PGMA-24700)) | DEEPAKMAUNDEKAR | [42 empty] | 19907 |  |  | HYTC001
| 1.9.2.1.1.7.7(BOILER TRIM PIPING (PGMA-24800)) | DEEPAK.K | [42 empty] | 19914 |  |  | HYTC002
| 1.9.2.1.1.7.8(Boiler Trim Piping - Dd Items (PGMA-24803)) | DEEPAK | [42 empty] | 19924 |  |  | HYTC003
| 1.9.2.1.1.7.9(Supports - Boiler Trim Piping - Os (PGMA-24804)) | DEEPAK BORA | [42 empty] | 19984 |  |  | HYTC005
| 1.9.2.1.1.7.10(LINK TO BOILER RECIRCULATION SYSTEM (PGMA-24805)) | DEEPAKKUMAR | [42 empty] | 19991 |  |  | HYTC006
| 1.9.2.1.1.7.11(MIXING VESSEL (PGMA-24806)) | DEEPAKMAHOUR | [42 empty] | 19992 |  |  | HYTC007
| 1.9.2.1.1.7.12(RECIRCULATION PUMP SECTION LINE (PGMA-24807)) | DEEPAKNAIK | [42 empty] | 20051 |  |  | HYTC008
| 1.9.2.1.1.7.13(RECIRCULATION PUMP DISCHARGE LINE (PGMA-24808)) | DEEPAK RAJOTIA | [42 empty] | 20054 |  |  | HYTC009
| 1.9.2.1.1.7.14(BOILER RECIRCULATION LINK FROM BF LINE (PGMA-24809)) | DEVENDRA | [42 empty] | 20201 |  |  | HYTC010
| 1.9.2.1.1.7.15(HANGERS + SUPPORTS FOR STARTUP SYSTEM (PGMA-24810)) | D A GAIKWAD | [42 empty] | 20204 |  |  | IPBD
| 1.9.2.1.1.7.16(FURNACE LINK TO FLASH TAND/HWL1 TO HWL2 (PGMA-24811)) | DHARMENDRA KUMAR | [42 empty] | 20511 |  |  | LP HEATER 3
| 1.9.2.1.1.7.17(Boiler Trim Piping - Non Ht Items (PGMA-24814)) | DHARM SINGH | [42 empty] | 20794 |  |  | LP HEATER 4
| 1.9.2.1.1.7.18(DESUPERHEATER PIPES (PGMA-24815)) | DHIRENDRA KUMAR | [42 empty] | 20962 |  |  | PAI-01300
| 1.9.2.1.1.7.19(H&S For Start-Up System - Os Items (PGMA-24817)) | DHARMENDRA | [42 empty] | 20988 |  |  | PAI-01310
| 1.9.2.1.1.7.20(H&S For Start-Up System - Dd Items (PGMA-24818)) | R DILEEP | [42 empty] | 20998 |  |  | PAI-01340
| 1.9.2.1.1.7.21(EXHAUST PIPE FOR SAFETY VALVES (PGMA-24820)) | DILIP | [42 empty] | 21600 |  |  | PAI-06200
| 1.9.2.1.1.7.22(De-Superheater Pipes - Os Items (PGMA-24822)) | DINESHKUMAR | [42 empty] | 21601 |  |  | PAI-06210
| 1.9.2.1.1.7.23(De-Superheater Pipes - Dd Items (PGMA-24823)) | DINESH | [42 empty] | 21602 |  |  | PAI-06240
| 1.9.2.1.1.7.24(Exhaust Pipe For Safety Valve - Os Items (PGMA-24824)) | DINESH_KUMAR | [42 empty] | 21603 |  |  | PAI-06260
| 1.9.2.1.1.7.25(SILENCER SUPPORTS (PGMA-24825)) | DINESH CHAUHAN | [42 empty] | 21604 |  |  | PAI-06300
| 1.9.2.1.1.7.26(Silencer Support - Os Items (PGMA-24826)) | DINESHSINGH | [42 empty] | 21605 |  |  | PAI-06310
| 1.9.2.1.1.7.27(Exhaust Pipe For Safety Valve - Dd Items (PGMA-24827)) | DIPESHPALIT | [42 empty] | 21606 |  |  | PAI-06340
| 1.9.2.1.1.7.28(Exhaust Pipe For Safety Valve - BOI Item (PGMA-24828)) | DIVAKAR | [42 empty] | 21700 |  |  | PAI-06360
| 1.9.2.1.1.7.29(STARTUP VENT DIFFUSER AND SILENCER SUPPPORTS (PGMA-24835)) | DIVYA JOSHI | [42 empty] | 21800 |  |  | PAI-06500
| 1.9.2.1.1.7.30(Start-Up Vent, Diffuser, Silencer Support-Os Item (PGMA-24836)) | DIVYA | [42 empty] | 21825 |  |  | PAI-06510
| 1.9.2.1.1.7.31(Start-Up Vent, Diffuser, Silencer Support-Dd Item (PGMA-24837)) | DIVYANSHU K | [42 empty] | 21850 |  |  | PAI-06540
| 1.9.2.1.1.7.32(SAMPLE COOLER AND SUPPORTS (PGMA-24840)) | DJAWADE | [42 empty] | 21987 |  |  | PAI-06560
| 1.9.2.1.1.7.33(Sample Cooler & Supports - Os Items (PGMA-24841)) | DK.SINGH | [42 empty] | 21988 |  |  | PAP-04300
| 1.9.2.1.1.7.34(DD items for Sample Cooler and Supports (PGMA-24842)) | DEEPAK KUMARR | [42 empty] | 21992 |  |  | PAP-04320
| 1.9.2.1.1.7.35( BOI- HT- RE-CIRCULATING PUMP COMPONENTS-SD (PGMA-24855)) | DEEPAK KUMAR | [42 empty] | 22100 |  |  | PAP-04330
| 1.9.2.1.1.7.36(VALVES (PGMA-24860)) | DHANANJAY KR. MI | [42 empty] | 22101 |  |  | PAP-04340
| 1.9.2.1.1.7.37(BOI-LU-VALVES SUBDELIVERY (PGMA-24865)) | DEVENDRA KUMAR | [42 empty] | 22600 |  |  | PAP-04400
| 1.9.2.1.1.7.38(BOI-LU-VALVES FOR STARTUP RECIRCULATION SYSTEM-SD (PGMA-24867)) | DKVAISHY | [42 empty] | 22601 |  |  | PAP-04420
| 1.9.2.1.1.7.39(SAFETY VALVES (PGMA-24880)) | DHIRENDRAKUMAR | [42 empty] | 22701 |  |  | PAP-04430
| 1.9.2.1.1.7.40(SAFETY VALVES AND ERV-SD (PGMA-24881)) | DAMBARUDHAR MUND | [42 empty] | 22889 |  |  | PAP-04440
| 1.9.2.1.1.7.41(Safety Valves (BHEL) - Non Ht (PGMA-24883)) | DNARAH | [42 empty] | 22988 |  |  | PAP-04800
| 1.9.2.1.1.7.42(SILENCERS (PGMA-24885)) | DNTIWARI | [42 empty] | 24350 |  |  | PAP-04820
| 1.9.2.1.1.7.43(SPECIAL TOOLS (PGMA-24950)) | DC | [42 empty] | 24351 |  |  | PAP-04830
| 1.9.2.1.1.7.44(LAPPING TOOLS FOR SV&ERV (PGMA-24955)) | DC_D | [42 empty] | 24352 |  |  | PAP-04900
| 1.9.2.1.1.7.45(LAPPING TOOLS FOR CONVENTIONAL VALVES( (PGMA-24960)) | DSP | [42 empty] | 24353 |  |  | PAP-04920
| 1.9.2.1.1.7.46(COMMG SPARES FOR SAFETY VALVES/ERV (PGMA-24987)) | DSUBHEDAR | [42 empty] | 24354 |  |  | PAP-04930
| 1.9.2.1.1.7.47(COMMG SPARES FOR IMPORTED SUB-DELY (PGMA-24988)) | DURAIRAJ S | [42 empty] | 24700 |  |  | PAP-04950
| 1.9.2.1.1.7.48(COMMG SPARES FOR CONVENTIONAL VALVES (PGMA-24989)) | DURGESHKTHAKUR | [42 empty] | 24800 |  |  | PAP-05300
| 1.9.2.1.1.7.49(IMPORTED ELECTRODES (PGMA-24992)) | D K SRIVASTAVA | [42 empty] | 24803 |  |  | PAP-05310
| 1.9.2.1.1.7.50(CONSUMABLES &Erection MATERIALS (PGMA-24993)) | DHARMVEER KUMAR | [42 empty] | 24804 |  |  | PAP-05340
| 1.9.2.1.1.7.51(NAME PLATES (PGMA-24994)) | DWARIKA | [42 empty] | 24805 |  |  | PAP-05420
| 1.9.2.1.2(Super Heaters and Re-Heaters ) | E VENKATARAMANAN | [42 empty] | 24806 |  |  | PAP-05440
| 1.9.2.1.2.1(Superheater Headers (PG-10)) | EKS | [42 empty] | 24807 |  |  | PAP-05450
| 1.9.2.1.2.1.1(SH VERTICAL SPACED INLET HEADER (PGMA-10174)) | SL-1.13 | [42 empty] | 24808 |  |  | PAP-06100
| 1.9.2.1.2.1.2(SH.VERTICAL PLATEN SH 1NLET HEADER (PGMA-10178)) | EQUBAL | [42 empty] | 24809 |  |  | PAP-06110
| 1.9.2.1.2.1.3(REAR WALL SUPER HEATER INLET HEADER (PGMA-10182)) | EHARIKRISH | [42 empty] | 24810 |  |  | PAP-06140
| 1.9.2.1.2.1.4(FRONT WALL SUPER HEATER INLET HEADER (PGMA-10183)) | RAJESH | [42 empty] | 24811 |  |  | PAP-06160
| 1.9.2.1.2.1.5(SIDE WALL SUPER HEATER INLET HEADER (PGMA-10184)) | EVENKATARAMAN | [42 empty] | 24814 |  |  | PAP-06400
| 1.9.2.1.2.1.6(BP BOTTOM RING HDRS (PGMA-10185)) | EVENKATARAMANAN | [42 empty] | 24815 |  |  | PAP-06410
| 1.9.2.1.2.1.7(BACK PASS RING HEADER (PGMA-10191)) | SL-1.8 | [42 empty] | 24817 |  |  | PAP-06440
| 1.9.2.1.2.1.8(SH. VERTICAL SPACED OUTLET HEADER (PGMA-10274)) | FAISAL HUSSAIN | [42 empty] | 24818 |  |  | PAP-06460
| 1.9.2.1.2.1.9(SH.VERTICAL PLATEN OUTLET HEADER (PGMA-10278)) | FAIZAN | [42 empty] | 24820 |  |  | PAP-06600
| 1.9.2.1.2.1.10(SH. BACKPASS SIDE WALL FRONT OUTLET HDR. (PGMA-10283)) | FAIZMOHD | [42 empty] | 24822 |  |  | PAP-06610
| 1.9.2.1.2.1.11(SIDE WALL SUPER HEATER OUTLET HEADER (PGMA-10284)) | FARAAZ | [42 empty] | 24823 |  |  | PAP-06640
| 1.9.2.1.2.1.12(SH front wall outlet header (PGMA-10285)) | FEI | [42 empty] | 24824 |  |  | PAP-06660
| 1.9.2.1.2.1.13(SH RADIANT ROOF OUTLET HDR (PGMA-10291)) | FELIX ANTONY | [42 empty] | 24825 |  |  | PCE-00100
| 1.9.2.1.2.2(Superheater Coils and Walls (PG-11)) | FITTER | [42 empty] | 24826 |  |  | PCE-00200
| 1.9.2.1.2.2.1(FINISH SH FRNT ASSY WITH I/T TER & CROSSOVERTUBES (PGMA-11074)) | GAGAN | [42 empty] | 24827 |  |  | PCE-00300
| 1.9.2.1.2.2.2(SH PLATEN ASSY WITH TERM TUBES - LEFT (PGMA-11078)) | GANESH KUMAR | [42 empty] | 24828 |  |  | PCE-00400
| 1.9.2.1.2.2.3(FINISH SH REAR ASSY WITH O/T TER & CROSSOVERTUBES (PGMA-11374)) | GANESH YADAV | [42 empty] | 24835 |  |  | PCE-00410
| 1.9.2.1.2.2.4(SH PLATEN ASSY WITH TERM TUBES - RIGHT (PGMA-11378)) | GANESH KARAKA | [42 empty] | 24836 |  |  | PCE-00420
| 1.9.2.1.2.2.5(SH. FRONT WALL PANELS UPPER- OS (PGMA-11406)) | GANESHKUMAR | [42 empty] | 24837 |  |  | PCE-00430
| 1.9.2.1.2.2.6(SH LOWER PNL ATTACHMENT (PGMA-11408)) | P S GANESH | [42 empty] | 24840 |  |  | PCE-00440
| 1.9.2.1.2.2.7(SH REAR WALL PANELS UPPER (LEFT)-OS (PGMA-11416)) | SL-1.9 | [42 empty] | 24841 |  |  | PCE-00450
| 1.9.2.1.2.2.8(SH SW PANELS UPPER REAR (L&R)-OS (PGMA-11467)) | GAURAV | [42 empty] | 24842 |  |  | PCE-00500
| 1.9.2.1.2.2.9(SH REAR ROOF PANELS (RIGHT)-OS (PGMA-11487)) | GAUTAM SUTRADHAR | [42 empty] | 24855 |  |  | PCE-00600
| 1.9.2.1.2.2.10(SH. RADIENT ROOF TUBES -OS (PGMA-11491)) | GMAJUMDAR | [42 empty] | 24860 |  |  | PCE-00700
| 1.9.2.1.2.2.11(SH. FRONT WALL PANELS UPPER (PGMA-11606)) | BVGAUTAM | [42 empty] | 24865 |  |  | PCE-00800
| 1.9.2.1.2.2.12(SH.FRONT WALL PANELS LOWER (PGMA-11608)) | GAUTAM KUMAR | [42 empty] | 24867 |  |  | PCE-00900
| 1.9.2.1.2.2.13(SH EXTENDED SIDE WALL PANELS (PGMA-11684)) | GAJENDRA ATMARAM | [42 empty] | 24880 |  |  | PCE-01000
| 1.9.2.1.2.2.14(SH.EXTENDED BOTTOM PANELS (PGMA-11694)) | GCTHAKUR | [42 empty] | 24881 |  |  | PCE-01100
| 1.9.2.1.2.2.15(SH REAR WALL PANELS UPPER (LEFT) (PGMA-11716)) | GIRISH CHANDRA | [42 empty] | 24883 |  |  | PCE-01200
| 1.9.2.1.2.2.16(SH. REAR WALL PANELS LOWER (LEFT) (PGMA-11718)) | GIRISH BHAGC | [42 empty] | 24885 |  |  | PCE-01300
| 1.9.2.1.2.2.17(SH SIDE WALL PANELS UPPER FRONT (L&R) (PGMA-11767)) | GIRISHCHANRDA | [42 empty] | 24950 |  |  | PCE-01400
| 1.9.2.1.2.2.18(SH. SIDE WALL PANELS LOWER FRONT (L&R) (PGMA-11769)) | GAURAVJAIN | [42 empty] | 24955 |  |  | PCE-01500
| 1.9.2.1.2.2.19(SH REAR ROOF PANELS (LEFT) (PGMA-11787)) | SUMA G KANNIKAR | [42 empty] | 24960 |  |  | PCE-01600
| 1.9.2.1.2.2.20(SH. RADIENT ROOF TUBES (LEFT) (PGMA-11791)) | GULJARI | [42 empty] | 24987 |  |  | PCE-01700
| 1.9.2.1.2.2.21(SH. REAR WALL PANEL UPPER (RIGHT) (PGMA-11916)) | G MURALI | [42 empty] | 24988 |  |  | PCE-01800
| 1.9.2.1.2.2.22(SH. REAR WALL PANELS LOWER (RIGHT) (PGMA-11918)) | GOVIND J | [42 empty] | 24989 |  |  | PCE-01900
| 1.9.2.1.2.2.23(SH. SIDE WALL PANELS UPPER REAR (L&R) (PGMA-11967)) | GOPAL | [42 empty] | 24992 |  |  | PCE-02000
| 1.9.2.1.2.2.24(SH. SIDE WALL PANELS LOWER REAR ( L&R) (PGMA-11969)) | GOPALAGARWAL | [42 empty] | 24993 |  |  | PCE-02100
| 1.9.2.1.2.2.25(SH REAR ROOF PANELS (RIGHT) (PGMA-11987)) | GOPALR | [42 empty] | 24994 |  |  | PCE-02200
| 1.9.2.1.2.2.26(SH. RADIENT ROOF TUBES (RIGHT) (PGMA-11991)) | GOPALTIWARI | [42 empty] | 28220 |  |  | PCE-02300
| 1.9.2.1.2.3(Superheater Components (PG-12)) | R K GOPLANI | [42 empty] | 28700 |  |  | PCE-02400
| 1.9.2.1.2.3.1(LP SH CROSSOVERS(RIGHT) (PGMA-12178)) | GOURI SHANKAR MO | [42 empty] | 29200 |  |  | PCE-02500
| 1.9.2.1.2.3.2(SH.EXTD. SIDE WALL INLET PIPE (PGMA-12184)) | GOUTAM | [42 empty] | 30103 |  |  | PCE-02600
| 1.9.2.1.2.3.3(SH. EXTD.SIDE WALL OUTLET PIPE (PGMA-12187)) | GOWTHAMAN ASOKAN | [42 empty] | 30105 |  |  | PCE-02700
| 1.9.2.1.2.3.4(SH SUPPORT FOR LINES AND LINKS DD ITEM (PGMA-12306)) | GANESH PRASAD | [42 empty] | 30211 |  |  | PCE-02800
| 1.9.2.1.2.3.5(SUSPN OF SH RAD ROOF HDRS-DD (PGMA-12314)) | G RAMGADE | [42 empty] | 30215 |  |  | PCE-02900
| 1.9.2.1.2.3.6(SUSPN OF RADIANT ROOF-DD (PGMA-12317)) | GYANARANJAN DALE | [42 empty] | 30219 |  |  | PCE-03000
| 1.9.2.1.2.3.7(SUSPN OF BP TOP HEADERS-DD (PGMA-12324)) | P W GREGORY | [42 empty] | 30223 |  |  | PCE-03100
| 1.9.2.1.2.3.8(SUSPN OF REAR ROOF-DD (PGMA-12327)) | SL-1.11 | [42 empty] | 30224 |  |  | PCE-03200
| 1.9.2.1.2.3.9(SUSPN SH H.TUBES FT&REAR WL-DD (PGMA-12328)) | G R REDDY | [42 empty] | 30233 |  |  | PCE-03300
| 1.9.2.1.2.3.10(SUSPN OF SH PLA&SH DIVI PANTE HDR-DD (PGMA-12344)) | GOVIND S F | [42 empty] | 30234 |  |  | PCE-03400
| 1.9.2.1.2.3.11(SUSPN OF SHFL.SHSPD.CL.ASY&SH TT.SPD-DD (PGMA-12348)) | GSK | [42 empty] | 30235 |  |  | PCE-03500
| 1.9.2.1.2.3.12(SUSPN OF SH PLN &FINAL SPD. HDR-DD (PGMA-12354)) | GULSHANRAWAT | [42 empty] | 30771 |  |  | PCE-03600
| 1.9.2.1.2.3.13(SUSPN OF SH PLATEN COIL ASSY-DD (PGMA-12368)) | AMIT GUPTA | [42 empty] | 30941 |  |  | PCE-03700
| 1.9.2.1.2.3.14(ERECTION MATERIALS & CONSLE-DD (PGMA-12393)) | GURCHARAN | [42 empty] | 31010 |  |  | PCE-03800
| 1.9.2.1.2.3.15(SH. HANGER TUBES-OS (PGMA-12405)) | GURDEV SINGH | [42 empty] | 31104 |  |  | PCE-03900
| 1.9.2.1.2.3.16(SH SUPPORT FOR LINES AND LINKS SHOP ITEM (PGMA-12506)) | GURPREET SINGH | [42 empty] | 32010 |  |  | PCE-04000
| 1.9.2.1.2.3.17(SUSPEN OF SH RAD ROOF HDRS-SHOP (PGMA-12514)) | HABIBUL REHMAN | [42 empty] | 32210 |  |  | PCE-04110
| 1.9.2.1.2.3.18(BP STEAM COOLED HANGER TUBES (PGMA-12515)) | RATAN LAL | [42 empty] | 32700 |  |  | PCE-04120
| 1.9.2.1.2.3.19(Suspension Of Sh Back Pass Headers-SH (PGMA-12524)) | H J CHOKSHI | [42 empty] | 32810 |  |  | PCE-04200
| 1.9.2.1.2.3.20(SUSPN OF SH PLA&SH DIVI PANTE HDR-SHOP (PGMA-12544)) | H K YADAV | [42 empty] | 33021 |  |  | PCE-04300
| 1.9.2.1.2.3.21(SUSPN OF SH PLN &FINAL SPD. HDR-SHOP (PGMA-12554)) | HARISH KUMAR | [42 empty] | 33210 |  |  | PCE-04500
| 1.9.2.1.2.3.22(SH STEAM COOLED SPACER TUBES (PGMA-12803)) | HARPREET | [42 empty] | 33221 |  |  | PCE-04600
| 1.9.2.1.2.3.23(SH. HANGER TUBES (PGMA-12805)) | HARSH DEEP | [42 empty] | 33230 |  |  | PCE-04700
| 1.9.2.1.2.3.24(SATURATED STEAM CONNECTING PIPE (PGMA-12850)) | HARSHV | [42 empty] | 33924 |  |  | PCE-04800
| 1.9.2.1.2.3.25(SUPER HEATER DESH LINKS (PGMA-12852)) | HASEENAHMED | [42 empty] | 33970 |  |  | PCE-04900
| 1.9.2.1.2.3.26(SUPER HEATER DESH (PGMA-12900)) | HDIXIT | [42 empty] | 33971 |  |  | PCE-05000
| 1.9.2.1.2.3.27(SUPER HEATER MISCELLANEOUS COMPONENTS (PGMA-12903)) | HEMANT KUMAR | [42 empty] | 33975 |  |  | PCI-00100
| 1.9.2.1.2.3.28(SUPER HEATER LINK SUPPORTS (PGMA-12906)) | HEMA KUSHWAHA | [42 empty] | 34010 |  |  | PCI-00110
| 1.9.2.1.2.3.29(BACKPASS ROOF SUPPORTS (PGMA-12907)) | HEMANT UDUPA | [42 empty] | 34100 |  |  | PCI-00140
| 1.9.2.1.2.3.30(SUSPENSION OF SH RADIANT ROOF HEADERS (PGMA-12914)) | HEMANTAMONDAL | [42 empty] | 34200 |  |  | PCP-04641
| 1.9.2.1.2.3.31(SUSPENSION OF RADIANT ROOF (PGMA-12917)) | HEMANT K JANGID | [42 empty] | 34300 |  |  | PCP-04642
| 1.9.2.1.2.3.32(SUPER HEATER BACK PASS HEADER SUSPENSION (PGMA-12924)) | HEMANTKUMAR | [42 empty] | 34390 |  |  | PCP-04643
| 1.9.2.1.2.3.33(SUSPENSION OF REAR ROOF (PGMA-12927)) | HEMANT MEENA | [42 empty] | 34400 |  |  | PCP-04841
| 1.9.2.1.2.3.34(SUSPENSIONOFSH HAN.TUBES FT.WL.&REAR WL. (PGMA-12928)) | HIMADRI SARKAR | [42 empty] | 34500 |  |  | PCP-04842
| 1.9.2.1.2.3.35(SUSPENSION OF SH PLA.&SH DIVI.PANTE. HDR (PGMA-12944)) | HIMANI SINGLA | [42 empty] | 34721 |  |  | PCP-04843
| 1.9.2.1.2.3.36(SUSPN.OFSHFL.SHSPD.CL.ASY&LTSHTER.TE.SPD (PGMA-12948)) | HIMANSHU MARTOLI | [42 empty] | 34810 |  |  | PCP-04940
| 1.9.2.1.2.3.37(SUSPENSION OF SH PLN HDR&FINAL SPD. HDR (PGMA-12954)) | HITESH | [42 empty] | 34820 |  |  | PCP-05640
| 1.9.2.1.2.3.38(SUSPENSION OF SH PLATEN COIL ASSY (PGMA-12968)) | HKC | [42 empty] | 34850 |  |  | PCP-05740
| 1.9.2.1.2.3.39(SH. IMPORTED ELECTRODES (PGMA-12991)) | HKNIGAM | [42 empty] | 35010 |  |  | PCP-05840
| 1.9.2.1.2.3.40(IMPORTED ELECTRODES (PGMA-12992)) | HKVERMA | [42 empty] | 35011 |  |  | PCP-05940
| 1.9.2.1.2.3.41(ERECTION MATERIALS (PGMA-12993)) | HEMANT MALHOTRA | [42 empty] | 35111 |  |  | PE-04100
| 1.9.2.1.2.4(Reheater Headers (PG-15)) | HARPREET RAI | [42 empty] | 35112 |  |  | PE-04500
| 1.9.2.1.2.4.1(REHEATER-I INLET HEADER (PGMA-15136)) | HRISHI | [42 empty] | 35121 |  |  | PE-04600
| 1.9.2.1.2.4.2(FINISH RH I/L HDR (PGMA-15178)) | HRISHI AGNIVESH | [42 empty] | 35122 |  |  | PE-04700
| 1.9.2.1.2.4.3(REHEATER-I OUTLET HEADER (PGMA-15236)) | HARIKRISHNAN S P | [42 empty] | 35130 |  |  | PE-04800
| 1.9.2.1.2.4.4(REHEATER VERT PLATEN OUTLET HEADER RHH (PGMA-15278)) | OP-1.3 | [42 empty] | 35140 |  |  | PEI-01700
| 1.9.2.1.2.5(Reheater Coils and Walls (PG-16)) | SL-1.5 | [42 empty] | 35150 |  |  | PEI-01710
| 1.9.2.1.2.5.1(RH VER PLATEN FRONT COIL ASY LEFT (PGMA-16079)) | INDRAJIT | [42 empty] | 35190 |  |  | PEI-01740
| 1.9.2.1.2.5.2(LTRH UPPER ASSY (PGMA-16201)) | IM RAMALINGES | [42 empty] | 35211 |  |  | PEI-01800
| 1.9.2.1.2.5.3(LTRH INTERMEDIATE ASSY (PGMA-16202)) | INDRAJEET VERMA | [42 empty] | 35212 |  |  | PEI-01810
| 1.9.2.1.2.5.4(LTRH coils lower (PGMA-16203)) | INDRAJEET | [42 empty] | 35213 |  |  | PEI-01840
| 1.9.2.1.2.5.5(LTRH PENDANT ASSY WITH OUTLET TERM TUBES (PGMA-16270)) | INDRANILC | [42 empty] | 35214 |  |  | PEI-01900
| 1.9.2.1.2.5.6(RHVERTICAL PLATEN FRONT COIL ASSY. (RIT) (PGMA-16379)) | INDRANIL | [42 empty] | 35221 |  |  | PEI-01910
| 1.9.2.1.2.6(Reheater Components (PG-17)) | ISHWARSINGH | [42 empty] | 35222 |  |  | PEI-01940
| 1.9.2.1.2.6.1(LINK TO RH DESUPERHEATER (PGMA-17174)) | ISHA RAWAT | [42 empty] | 35231 |  |  | PEI-02000
| 1.9.2.1.2.6.2(Rh Hdr Supports & Suspensions Above Roof-DD (PGMA-17304)) | J BALU | [42 empty] | 35232 |  |  | PEI-02010
| 1.9.2.1.2.6.3(RH LINKS SUPPORTS-DD (PGMA-17306)) | J NATARAJAN | [42 empty] | 35311 |  |  | PEI-02040
| 1.9.2.1.2.6.4(RH FRONT COIL SUSPENSION-DD (PGMA-17319)) | JAYANTA GHOSH | [42 empty] | 35312 |  |  | PEI-02100
| 1.9.2.1.2.6.5(SC SPACER TUBES FOR RH. COIL-OS (PGMA-17407)) | JN SAHAY | [42 empty] | 35321 |  |  | PEI-02110
| 1.9.2.1.2.6.6(RH HEADER SUPPORTS-SHOP (PGMA-17504)) | JESSYABRAHAM | [42 empty] | 35322 |  |  | PEI-02140
| 1.9.2.1.2.6.7(RH LINKS SUPPORTS-SHOP (PGMA-17506)) | JAGJEET | [42 empty] | 35331 |  |  | PEI-02200
| 1.9.2.1.2.6.8(STEAM COOLED SPACER TUBES FOR RH. COIL (PGMA-17807)) | JAI PRAKASH SRIV | [42 empty] | 35332 |  |  | PEI-02210
| 1.9.2.1.2.6.9(REHEATER DE-SUPER HEATER (PGMA-17900)) | JAINATH | [42 empty] | 35341 |  |  | PEI-02240
| 1.9.2.1.2.6.10(RH HEADER SUPPORTS (PGMA-17904)) | JAI PRADEEP | [42 empty] | 35342 |  |  | PEI-02300
| 1.9.2.1.2.6.11(RH LINKS SUPPORTS (PGMA-17906)) | JAIPRAKASH | [42 empty] | 35351 |  |  | PEI-02310
| 1.9.2.1.2.6.12(RH FRONT COIL SUSPENSION (PGMA-17919)) | JAYESH AJAY | [42 empty] | 35352 |  |  | PEI-02340
| 1.9.2.1.2.6.13(RH IMPORTED ELECTRODES (PGMA-17991)) | JAMES JOY MATHEW | [42 empty] | 35361 |  |  | PEI-02400
| 1.9.2.1.2.6.14(RH SITE ELECTRODES IMPORTED (PGMA-17992)) | JAMESJOYMATHEW | [42 empty] | 35362 |  |  | PEI-02410
| 1.9.2.2(Erection) | JAMESPAUL | [42 empty] | 35381 |  |  | PEI-02440
| 1.9.2.2.4(Water Circulation system, Super Heaters and Re-Heaters ) | VINOD JASEJA | [42 empty] | 35382 |  |  | PEI-02500
| 1.9.2.2.4.1(BACKPASS) | JATIN AHLAWAT | [42 empty] | 35383 |  |  | PEI-02510
| 1.9.2.2.4.2( FURNACE PASS AND BP EXTENDED) | JAVEDH | [42 empty] | 35384 |  |  | PEI-02540
| 1.9.2.2.5(DRAINABLE Hydro TEST) | S J KHAN | [42 empty] | 35385 |  |  | PEI-02600
| 1.9.2.2.7(FOR CHEMICAL CLEANING AND EDTA) | JAYANTA DAS | [42 empty] | 35386 |  |  | PEI-02610
| 1.9.2.2.8(FOR STEAM BLOWING) | JAYESH PAWAR | [42 empty] | 35387 |  |  | PEI-02640
| 1.9.3(Soot Blower) | JBALU | [42 empty] | 35390 |  |  | PEI-02700
| 1.9.3.1(Supply (BHEL TRY)) | JBALA MURALI | [42 empty] | 35441 |  |  | PEI-02710
| 1.9.3.1.1(Soot Blowers (PG-20)) | OP-1.4 | [42 empty] | 35442 |  |  | PEI-02740
| 1.9.3.1.1.1(LONG RETRACTABLE SOO (PGMA-20051)) | J CHATTARJEE | [42 empty] | 35443 |  |  | PEI-02800
| 1.9.3.1.1.2(WALL BOX NON PRESSUR (PGMA-20054)) | JAIDEEP DESARKAR | [42 empty] | 35444 |  |  | PEI-02810
| 1.9.3.1.1.3(WALL DESLAGGER RW5E (PGMA-20201)) | JEETENDRA K | [42 empty] | 35445 |  |  | PEI-02840
| 1.9.3.1.1.4(WALL BOX NON PRESSUR (PGMA-20204)) | JAY BIKASH GHOSH | [42 empty] | 35446 |  |  | PEI-02900
| 1.9.3.1.1.5(DA HEAD VALVE ASSY (PGMA-20511)) | JITENDRA | [42 empty] | 35447 |  |  | PEI-02910
| 1.9.3.1.1.6(WALL BOX NON PRESSUR (PGMA-20794)) | JITEN | [42 empty] | 35451 |  |  | PEI-02940
| 1.9.3.1.1.7(TEMP PROBE DUPLEX WI (PGMA-20962)) | J KASIRAJAN | [42 empty] | 35452 |  |  | PEI-03000
| 1.9.3.1.1.8(SOOT BLOWER COMMISSIONING SPARES (PGMA-20988)) | NATARAJAN J | [42 empty] | 35453 |  |  | PEI-03010
| 1.9.3.1.1.9(SPECIAL TOOLS FOR SO (PGMA-20998)) | JOSHI | [42 empty] | 35454 |  |  | PEI-03040
| 1.9.3.1.2(Soot Blowing system (PG-21)) | MMJOSHI | [42 empty] | 35455 |  |  | PEI-03100
| 1.9.3.1.2.1(SOOT BLOWER PIPING AND FITTINGS (PGMA-21600)) | PAWAN JAISWAL | [42 empty] | 35456 |  |  | PEI-03110
| 1.9.3.1.2.2(SOOTBLOWER PIPING SUPPORTS (PGMA-21601)) | JUGDIP | [42 empty] | 35457 |  |  | PEI-03140
| 1.9.3.1.2.3(SOOT BLOWER PIPING & FITTINGS - DD (PGMA-21602)) | JYOTHISH VARGHES | [42 empty] | 35511 |  |  | PEI-03200
| 1.9.3.1.2.4(SOOT BLOWER PIPING & FITTINGS - BOI (PGMA-21603)) | K G PRASANTH RAI | [42 empty] | 35512 |  |  | PEI-03210
| 1.9.3.1.2.5(SOOT BLOWER PIPING SUPPORTS - OS (PGMA-21604)) | KMATHIYALAGAN | [42 empty] | 35513 |  |  | PEI-03240
| 1.9.3.1.2.6(Soot Blower Piping Supports - Dd (PGMA-21605)) | K P MANIMALA | [42 empty] | 35514 |  |  | PEI-03300
| 1.9.3.1.2.7(Soot Blower Piping Supports - BOI (PGMA-21606)) | PRAKASHK | [42 empty] | 35515 |  |  | PEI-03310
| 1.9.3.1.2.8(BULKED BPS COMPONENTS FOR SB PIPING (PGMA-21700)) | K T SURESH BABU | [42 empty] | 35516 |  |  | PEI-03340
| 1.9.3.1.2.9(SB VALVES (BHEL) (PGMA-21800)) | ABHIJEET KUMAR | [42 empty] | 35517 |  |  | PEI-03400
| 1.9.3.1.2.10(SB VALVES (SUB DELIVERY) (PGMA-21825)) | KABINDAR | [42 empty] | 35521 |  |  | PEI-03410
| 1.9.3.1.2.11(SOOT BLOWER SAFETY VALVE (BHEL) (PGMA-21850)) | K ADRUSTAKUMAR | [42 empty] | 35522 |  |  | PEI-03440
| 1.9.3.1.2.12(COMMG SPARES FOR SB SAFETY VALVE (PGMA-21987)) | KALIMULLA | [42 empty] | 35523 |  |  | PEI-03500
| 1.9.3.1.2.13(COMMG SPARES FOR SUB DELIVERIES (PGMA-21988)) | KALPANA | [42 empty] | 35524 |  |  | PEI-03510
| 1.9.3.1.2.14(IMPORTED ELECTRODES (PGMA-21992)) | KALYAN SARKAR | [42 empty] | 35525 |  |  | PEI-03511
| 1.9.3.2(Erection) | KALYAN | [42 empty] | 35526 |  |  | PEI-03514
| 1.9.4(Lining and Insulation System) | KAMAL SHARMA | [42 empty] | 35527 |  |  | PEI-03520
| 1.9.4.1(Supply (BHEL TRY)) | KAMALUDDIN | [42 empty] | 35531 |  |  | PEI-03521
| 1.9.4.1.1(Seal Boxes (PG-09)) | KAMLESH KUMAR | [42 empty] | 35532 |  |  | PEI-03524
| 1.9.4.1.1.1(MATERIAL FOR INSTRUMENT INSERTS (PGMA-9003)) | KANHAIYA | [42 empty] | 35533 |  |  | PEI-03530
| 1.9.4.1.1.2(Seal boxes for Furnace Openings (PGMA-9004)) | KANNAN V | [42 empty] | 35534 |  |  | PEI-03531
| 1.9.4.1.1.3(Seal boxes for Instrument Tappings (PGMA-9005)) | MKANNAN | [42 empty] | 35535 |  |  | PEI-03534
| 1.9.4.1.1.4(Material For Instrument Inserts-DD (PGMA-9303)) | KAPIL MAHESHWARI | [42 empty] | 35536 |  |  | PEI-03540
| 1.9.4.1.1.5(SEAL BOXES FOR FURNACE OPENINGS-DD (PGMA-9304)) | KARAN YADAV | [42 empty] | 35537 |  |  | PEI-03541
| 1.9.4.1.1.6(Material For Instrument Inserts-SH (PGMA-9503)) | KAUSHAL | [42 empty] | 35700 |  |  | PEI-03544
| 1.9.4.1.2(Roof Skin Casing (PG-18)) | KAUSHIK DEY | [42 empty] | 35701 |  |  | PEI-03550
| 1.9.4.1.2.1(ROOF SKIN CASING (PGMA-18001)) | KAVINDRASHEKHAR | [42 empty] | 35811 |  |  | PEI-03551
| 1.9.4.1.2.2(PR PTS ATTACHMNTS IN FURN ROOF SKN CAS (PGMA-18010)) | KAVITA GUPTA | [42 empty] | 35812 |  |  | PEI-03554
| 1.9.4.1.2.3(FURN ROO SKIN CASING - BOI (PGMA-18701)) | KAVITAGUPTA | [42 empty] | 35821 |  |  | PII-03600
| 1.9.4.1.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | KULBHUSHAN BATRA | [42 empty] | 35822 |  |  | PII-03610
| 1.9.4.1.3.1(SEAL PLATE ASSY (PGMA-30103)) | KCH | [42 empty] | 35823 |  |  | PII-03640
| 1.9.4.1.3.2(MAIN BOILER INSULATION (PGMA-30215)) | KCMAHAPATRA | [42 empty] | 35851 |  |  | PII-03700
| 1.9.4.1.3.3(VERTICAL ROOF ENCLOSURE FRAMING (PGMA-30219)) | K D CHAUHAN | [42 empty] | 35993 |  |  | PII-03710
| 1.9.4.1.3.4(GAS DISTRIBUTION BAFFLES (PGMA-30223)) | KEKA DAS | [42 empty] | 35995 |  |  | PII-03740
| 1.9.4.1.3.5(Antivibration Baffles (PGMA-30224)) | KEVRE | [42 empty] | 36110 |  |  | PII-03800
| 1.9.4.1.3.6(FIRST PASS DECK SPRT AND SEAL (PGMA-30233)) | VINOD KEVRE | [42 empty] | 36130 |  |  | PII-03810
| 1.9.4.1.3.7(SECOND PASS DECK SPRT AND SEAL (PGMA-30234)) | KGPRASHANTH | [42 empty] | 36150 |  |  | PII-03840
| 1.9.4.1.3.8(ENCLOSURE SUPPORT STEEL (PGMA-30235)) | KGUNJAN | [42 empty] | 36311 |  |  | PII-03900
| 1.9.4.1.4(Boiler Skin Casing (PG-31)) | GUNJAN | [42 empty] | 36312 |  |  | PII-03910
| 1.9.4.1.4.1(SKIN CASING COMPS WELDED TO PR. PARTS (PGMA-31010)) | NITIN KHARE | [42 empty] | 36313 |  |  | PII-03940
| 1.9.4.1.4.2(FURNACE REAR ARCH SKIN CASING (PGMA-31104)) | KHRK | [42 empty] | 36314 |  |  | PII-04000
| 1.9.4.1.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | KINGSHUK KUMAR D | [42 empty] | 36315 |  |  | PII-04010
| 1.9.4.1.5.1(FIXING COMPONENTS FOR BLR PR PARTS INSUL (PGMA-32010)) | KIRAN KUMAR | [42 empty] | 36316 |  |  | PII-04040
| 1.9.4.1.5.2(FIXING COMPONENTS FOR DUCT INSUL (PGMA-32210)) | KIRANJITHMC | [42 empty] | 36321 |  |  | PII-04100
| 1.9.4.1.5.3(BULKED BPS COMPONENT (PGMA-32700)) | KISHOR BHAGWATKA | [42 empty] | 36322 |  |  | PII-04110
| 1.9.4.1.5.4(FIXING COMPONENT FOR OUTLET DUCT (PGMA-32810)) | RKISHORE | [42 empty] | 36323 |  |  | PII-04140
| 1.9.4.1.6(Lining and Insulation Materials (PG-33)) | JAYASANKAR K | [42 empty] | 36324 |  |  | PMI-00500
| 1.9.4.1.6.1(BLR PR PARTS MINERAL WOOL (PGMA-33021)) | KAMAL JEET SINGH | [42 empty] | 36325 |  |  | PMI-00510
| 1.9.4.1.6.2(MAIN BLR CASTABLE REFRACTORY GR A (PGMA-33210)) | KK GAUTAM | [42 empty] | 36326 |  |  | PMI-00540
| 1.9.4.1.6.3(DUCT MINERAL WOOL (PGMA-33221)) | KK MAJI | [42 empty] | 36327 |  |  | PMI-00600
| 1.9.4.1.6.4(MAIN BLR POURABLE INSULATION (PGMA-33230)) | KKANT | [42 empty] | 36331 |  |  | PMI-00610
| 1.9.4.1.6.5(MISC EQPTS SEAL MATERIALS (PGMA-33924)) | KCC | [42 empty] | 36332 |  |  | PMI-00640
| 1.9.4.1.6.6(MISC EQPTS EXPANDED METAL (PGMA-33970)) | KK MISHRA | [42 empty] | 36333 |  |  | PMI-00700
| 1.9.4.1.6.7(MISC EQPTS WOVEN WIRE CLOTH (PGMA-33971)) | KKMAJI | [42 empty] | 36334 |  |  | PMI-00710
| 1.9.4.1.6.8(MISC EQPTS SEALING COMPOUND (PGMA-33975)) | KAMLESH_KUMAR | [42 empty] | 36335 |  |  | PMI-00740
| 1.9.4.1.7(Boiler Outer Casing (PG-37)) | BINOD KUMAR M | [42 empty] | 36336 |  |  | PMI-00800
| 1.9.4.1.7.1(BLR OUTER CASING COMPONENTS (PGMA-37010)) | K MANISH | [42 empty] | 36337 |  |  | PMI-00810
| 1.9.4.1.7.2(BLR OUTER CASING (PGMA-37810)) | KMATHUR | [42 empty] | 36338 |  |  | PMI-00840
| 1.9.4.2(Erection) | K MURALI | [42 empty] | 36341 |  |  | PMI-00900
| 1.9.4.2.1(Seal Boxes (PG-09)) | NAVEENCHANDRA | [42 empty] | 36342 |  |  | PMI-00910
| 1.9.4.2.2(Roof Skin Casing (PG-18)) | KSSKRISHNA | [42 empty] | 36343 |  |  | PMI-00940
| 1.9.4.2.3(Fixing Components for Main Boiler Lining and Insulation (PG-30)) | MGKOPPIKAR | [42 empty] | 36344 |  |  | PMI-01000
| 1.9.4.2.4(Boiler Skin Casing (PG-31)) | KOUSHIKACHARYA | [42 empty] | 36345 |  |  | PMI-01010
| 1.9.4.2.5(Fixing Components for Boiler Auxiliaries Insulation (PG-32)) | KPRASANT | [42 empty] | 36346 |  |  | PMI-01040
| 1.9.4.2.6(Lining and Insulation Materials (PG-33)) | KPMG ADMIN | [42 empty] | 36347 |  |  | PMI-01100
| 1.9.4.2.7(Boiler Outer Casing (PG-37)) | KRAJAY | [42 empty] | 36348 |  |  | PMI-01110
| 1.9.5(Ignition and Burning System) | B KRISHNAN | [42 empty] | 36351 |  |  | PMI-01140
| 1.9.5.1(Supply (BHEL TRY)) | KRISHNA SAH | [42 empty] | 36352 |  |  | PMI-01200
| 1.9.5.1.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | KRISHNA MOHAN P | [42 empty] | 36353 |  |  | PMI-01210
| 1.9.5.1.1.1(AIR COOLED OIL GUN ASSY, (PGMA-41350)) | K RAJITHA | [42 empty] | 36354 |  |  | PMI-01240
| 1.9.5.1.1.2(OIL GUN VICE ASSEMBLY AND RACK (PGMA-41390)) | SANJEEVKUMAR | [42 empty] | 36355 |  |  | PMI-01400
| 1.9.5.1.1.3(HIGH ENERGY ARC IGNITOR (PGMA-41500)) | KSARAVANAN | [42 empty] | 36356 |  |  | PMI-01410
| 1.9.5.1.1.4(Oil Gun Assembly - DD items (PGMA-41710)) | KANDASAMY C | [42 empty] | 36361 |  |  | PMI-01440
| 1.9.5.1.1.5(OIL&GAS BURNER COMMISSIONING SPARE (PGMA-41988)) | K SENTHI | [42 empty] | 36362 |  |  | PMI-01500
| 1.9.5.1.1.6(OIL/GAS BURNER MANDATORY SPARES (PGMA-41997)) | KSMURTHY | [42 empty] | 36363 |  |  | PMI-01510
| 1.9.5.1.2(Oil & Gas Systems (PG-42)) | KSOMESH | [42 empty] | 36364 |  |  | PMI-01540
| 1.9.5.1.2.1(PNEUMATIC FITTINGS (PGMA-42001)) | SURESHBABU | [42 empty] | 36365 |  |  | PMI-01610
| 1.9.5.1.2.2(STEAM BLOW MATERIALS (PGMA-42002)) | KULDEEP KUMAR | [42 empty] | 36366 |  |  | PMI-01640
| 1.9.5.1.2.3(INSTRUMENT FITTINGS (PGMA-42005)) | KULDEEP | [42 empty] | 36391 |  |  | PMI-01650
| 1.9.5.1.2.4(BOI-LU-LIGHT FUEL OIL PUMP SET (PGMA-42010)) | KUMAR GUNJAN | [42 empty] | 36392 |  |  | PMI-05100
| 1.9.5.1.2.5(BOI-LU-DRAIN OIL PUMP-MOTOR ASSY (PGMA-42046)) | ASHUTOSH KUMAR | [42 empty] | 36393 |  |  | PMI-05110
| 1.9.5.1.2.6(DRAIN OIL TANK (PGMA-42065)) | SANTOSHKMAHTO | [42 empty] | 36394 |  |  | PMI-05140
| 1.9.5.1.2.7(BURNER STATION SKID ASSY (PGMA-42070)) | AJAY KUMAR | [42 empty] | 36395 |  |  | PNC-04200
| 1.9.5.1.2.8(PIPING, PUMP HOUSE-FUEL OIL (PGMA-42120)) | RAJESHKUMAR | [42 empty] | 36396 |  |  | PNC-04220
| 1.9.5.1.2.9(PIPING,PUMP HOUSE STEAM - IBR (PGMA-42128)) | SARAVANA KUMAR | [42 empty] | 36610 |  |  | PNC-04230
| 1.9.5.1.2.10(PIPING,OPERATING FLOOR LIGHT FUEL OIL (PGMA-42152)) | KUNALCHAKRAVORT | [42 empty] | 36611 |  |  | PNC-04240
| 1.9.5.1.2.11(PIPING,OPRG FLOOR DRAIN OIL (PGMA-42154)) | KUNAL | [42 empty] | 36613 |  |  | PNI-00200
| 1.9.5.1.2.12(PIPING,OPERATING FLOOR ATOMIZING AIR (PGMA-42157)) | KUSH ANAND | [42 empty] | 36620 |  |  | PNI-00210
| 1.9.5.1.2.13(PIPING,OPERATING FLOOR STEAM-IBR (PGMA-42158)) | KV RAMANI | [42 empty] | 36621 |  |  | PNI-00240
| 1.9.5.1.2.14(BOI-LU-SUBDELIVERY FUEL OIL SYSTEM (PGMA-42200)) | K VIKRAM | [42 empty] | 36700 |  |  | PNI-00300
| 1.9.5.1.2.15(BHEL VALVE F.O. SYSTEM (PGMA-42300)) | KVKSV | [42 empty] | 36701 |  |  | PNI-00310
| 1.9.5.1.2.16(BHEL VALVE,OPERATING FLOOR STM-IBR (PGMA-42358)) | KVVSATYANAR | [42 empty] | 36740 |  |  | PNI-00340
| 1.9.5.1.2.17(BULKED BPS COMPONENTS (PGMA-42700)) | KYADAV | [42 empty] | 36811 |  |  | PNI-00400
| 1.9.5.1.2.18(Fuel Oil System - DD Items (PGMA-42710)) | BINDU L | [42 empty] | 36812 |  |  | PNI-00410
| 1.9.5.1.2.19(Fuel Oil System - Shop items (PGMA-42858)) | LE2 | [42 empty] | 36813 |  |  | PNI-00440
| 1.9.5.1.2.20(OIL&GAS SYSTEM COMMISSIONING SPARE (PGMA-42988)) | LE2_D | [42 empty] | 36814 |  |  | PNI-05000
| 1.9.5.1.2.21(IMPORTED ELECTRODES (PGMA-42992)) | LE1 | [42 empty] | 36820 |  |  | PNI-05010
| 1.9.5.1.2.22(OIL SYSTEM-MANDATORY SPARES (PGMA-42997)) | LE1_D | [42 empty] | 36821 |  |  | PNI-05040
| 1.9.5.1.3(Ignitor and Scanner Air System (PG-43)) | L HONEY WOOD M | [42 empty] | 36851 |  |  | PNI-05200
| 1.9.5.1.3.1(ASSY COMP SCANNER & GUN AIR SYSTEM (PGMA-43004)) | LOVEKUSH VERMA | [42 empty] | 36852 |  |  | PNI-05210
| 1.9.5.1.3.2(ASSY COMP MILL SEAL AIR SYSTEM (PGMA-43005)) | LLOYDS | [42 empty] | 36853 |  |  | PNI-05240
| 1.9.5.1.3.3(M/C COMP SCANNER & GUN AIR SYSTEM (PGMA-43104)) | LOKENDRA | [42 empty] | 36993 |  |  | PNI-06700
| 1.9.5.1.3.4(M/C COMP MILL SEAL AIR SYSTEM (PGMA-43105)) | LOKESHGHILDIYAL | [42 empty] | 37010 |  |  | PNI-06710
| 1.9.5.1.3.5(BOI-LU-SUBDEL, AIR SYSTEM (PGMA-43200)) | LRAJASEKHAR | [42 empty] | 37810 |  |  | PNI-06740
| 1.9.5.1.3.6(Seal Air & Scanner Air System - DD items (PGMA-43710)) | M C KIRANJITH | [42 empty] | 38110 |  |  | PNI-07000
| 1.9.5.1.4(Coal Burner System (PG-45)) | M K SINGH | [42 empty] | 38210 |  |  | PNI-07010
| 1.9.5.1.4.1(SA DAMPER & BURNER TILT ACTUATORS (PGMA-45200)) | MPAVAN | [42 empty] | 38299 |  |  | PNI-07040
| 1.9.5.1.4.2(Wind Box & SOFA Assembly - DD items (PGMA-45710)) | M VINOD | [42 empty] | 38310 |  |  | PNI-07100
| 1.9.5.1.4.3(Windbox assembly and SOFA tube attachment (PGMA-45801)) | MD ABU | [42 empty] | 38376 |  |  | PNI-07110
| 1.9.5.1.4.4(Windbox assembly - 32" width (PGMA-45802)) | MADHU | [42 empty] | 38379 |  |  | PNI-07140
| 1.9.5.1.4.5(Windbox assembly - SOFA (PGMA-45804)) | MADHUR N JAIN | [42 empty] | 38381 |  |  | PWI-06800
| 1.9.5.1.4.6(Windbox support and air cylinder mounting (PGMA-45805)) | MADHUSHREE PANDE | [42 empty] | 38410 |  |  | PWI-06810
| 1.9.5.1.4.7(Wind Box & SOFA Assy - Shop items (PGMA-45858)) | MAHEEP SINGH | [42 empty] | 38510 |  |  | PWI-06840
| 1.9.5.1.4.8(COAL BURNER-MANDATORY SPARES (PGMA-45997)) | MAHEN | [42 empty] | 38512 |  |  | PWI-06900
| 1.9.5.2(Erection) | MAHENDRAKUMAR | [42 empty] | 38605 |  |  | PWI-06910
| 1.9.5.2.1(Oil & Gas Burners and Ignitors & Scanners (PG-41)) | MAKHAL | [42 empty] | 38608 |  |  | PWI-06940
| 1.9.5.2.2(Oil & Gas Systems (PG-42)) | MALLEWADIKAR | [42 empty] | 38610 |  |  | PWP-04500
| 1.9.5.2.3(Ignitor and Scanner Air System (PG-43)) | MALLIK MOAZZAM | [42 empty] | 38611 |  |  | PWP-04520
| 1.9.5.2.4(Coal Burner System (PG-45)) | MALLIKMOAZZAM | [42 empty] | 38612 |  |  | PWP-04530
| 1.9.6(Air & Flue Gas System) | MANAS MANDAL | [42 empty] | 38663 |  |  | PWP-04541
| 1.9.6.3(Civil Work) | M ANANDARAJ | [42 empty] | 38679 |  |  | PWP-04542
| 1.9.6.3.1( BOF to ESP Duct Foundation) | MANAPRAKASH SAHO | [42 empty] | 38682 |  |  | PWP-04543
| 1.9.6.3.1.1(Priority (First) Pass) | SUSANTA | [42 empty] | 38683 |  |  | PWP-04544
| 1.9.6.3.1.2(Second Pass) | MANDVI GUPTA | [42 empty] | 38685 |  |  | PWP-04600
| 1.9.6.3.2( ESP Outlet to ID Fan Inlet Duct Foundation) | MANISHDWIVEDI | [42 empty] | 38686 |  |  | PWP-04620
| 1.9.6.3.2.1(Priority (First) Pass) | MANIKNAIYA | [42 empty] | 38687 |  |  | PWP-04630
| 1.9.6.3.2.2(Second Pass) | MANIKANDAN RAMKU | [42 empty] | 38691 |  |  | PWP-04700
| 1.9.6.3.3( ID Fan Outlet to Chimney Duct Foundation) | MANISH DAYA | [42 empty] | 38695 |  |  | PWP-04720
| 1.9.6.3.3.1(Priority (First) Pass) | MANISH DAYAL | [42 empty] | 38696 |  |  | PWP-04730
| 1.9.6.3.3.2(Second Pass) | MANISH JAIN | [42 empty] | 38700 |  |  | PWP-04740
| 1.9.6.4(Supply ) | MANISHA GUPTA | [42 empty] | 38709 |  |  | PWP-05500
| 1.9.6.4.1(BHEL TRY) | MANISH KUMAR | [42 empty] | 38710 |  |  | PWP-05520
| 1.9.6.4.1.1(External Structures ( Supporting Structures for Duct, PG-39 )) | MAHESH MANKER | [42 empty] | 38712 |  |  | PWP-05530
| 1.9.6.4.1.1.1(FOUNDATION MATERIALS (PGMA-39010)) | MANMOHANA | [42 empty] | 38720 |  |  | PWP-05540
| 1.9.6.4.1.1.2(FOUNDATION MATERIALS I.D.DUCT SUPPORTS (PGMA-39012)) | T MANOHARAN | [42 empty] | 38724 |  |  | PWP-05600
| 1.9.6.4.1.1.3(COLUMNS/FRAMES BEFORE ESP- LEFT (PGMA-39101)) | MANOHER SINGH | [42 empty] | 38733 |  |  | PWP-05620
| 1.9.6.4.1.1.4(COLUMNS/FRAMES BEFORE ESP- RIGHT (PGMA-39102)) | MANOJKJOSHI | [42 empty] | 38810 |  |  | PWP-05630
| 1.9.6.4.1.1.5(COLS/FRAMES NEAR I.D.FAN -LEFT (PGMA-39141)) | MANOJ SANTANI | [42 empty] | 38820 |  |  | PWP-05700
| 1.9.6.4.1.1.6(COLS/FRAMES NEAR ID FAN-RIGHT (PGMA-39142)) | MANOJ KUMAR PD | [42 empty] | 38850 |  |  | PWP-05720
| 1.9.6.4.1.1.7(COL/FRAMES BETN I.D.FAN AND Chimney (PGMA-39150)) | MANOJSANTANI | [42 empty] | 38993 |  |  | PWP-05730
| 1.9.6.4.1.1.8(PLATFORMS EXTL STRUC BOF TO ESP (PGMA-39299)) | MANOJ K MEENA | [42 empty] | 39010 |  |  | PWP-05800
| 1.9.6.4.1.1.9(PLATFORMS -EXTERNAL STRUCTURE (PGMA-39300)) | MKSINGH | [42 empty] | 39012 |  |  | PWP-05820
| 1.9.6.4.1.1.10(STRUC AND PLATFORM/FOR FANS (PGMA-39301)) | MANOJKTHAKUR | [42 empty] | 39101 |  |  | PWP-05830
| 1.9.6.4.1.1.11(STRUC FOR MOTOR HOOD/COVERING (PGMA-39302)) | MANOJSHAH | [42 empty] | 39102 |  |  | PWP-05900
| 1.9.6.4.1.1.12(FAN HANDLING STRUCTURE FOR FD FAN (PGMA-39304)) | NKMANWANI | [42 empty] | 39141 |  |  | PWP-05920
| 1.9.6.4.1.1.13(FAN HANDLING STRUCTURE FOR PA FAN (PGMA-39305)) | M A SANGEETHA | [42 empty] | 39142 |  |  | PWP-05930
| 1.9.6.4.1.1.14(FAN HANDLING STRUCTURE FOR ID FAN (PGMA-39306)) | SL-1.2 | [42 empty] | 39150 |  |  | PWP-06000
| 1.9.6.4.1.1.15(HSFG FASTENERS FOR PG 39 (PGMA-39700)) | MAUSAM KUMAR | [42 empty] | 39299 |  |  | PWP-06010
| 1.9.6.4.1.1.16(FLOOR GRILL (PGMA-39810)) | MAYANK AGARWAL | [42 empty] | 39300 |  |  | PWP-06040
| 1.9.6.4.1.1.17(STAIRS (PGMA-39820)) | MAYANK | [42 empty] | 39301 |  |  | PWP-06060
| 1.9.6.4.1.1.18(HAND RAIL AND HAND RAIL POSTS (PGMA-39850)) | MAYUR GURJAR | [42 empty] | 39302 |  |  | SC
| 1.9.6.4.1.1.19(CONSUMABLES &Erection MATERIALS (PGMA-39993)) | MD MAZHAR WAHAB | [42 empty] | 39304 |  |  | SC304
| 1.9.6.4.1.2(Duct., Dampers and Expn. Joints (PG-48)) | MUKUND CHOUDHA | [42 empty] | 39305 |  |  | SD
| 1.9.6.4.1.2.1(RECT DUCT BET F.D FAN AND AIRHEATER (PGMA-48012)) | MD AZAM | [42 empty] | 39306 |  |  | SL
| 1.9.6.4.1.2.2(EXPN PIECESBET F.D FAN AND AIRHEATER (PGMA-48014)) | MOHAMMAD HUSSAIN | [42 empty] | 39613 |  |  | SPBD
| 1.9.6.4.1.2.3(SUPPORTSETCBET F.D FAN AND AIRHEATER (PGMA-48015)) | MDZ | [42 empty] | 39614 |  |  | SR
| 1.9.6.4.1.2.4(DUCTS - SCAPH TO SAH (PGMA-48018)) | MEENA KESRI | [42 empty] | 39625 |  |  | SS
| 1.9.6.4.1.2.5(FOUNDATION MATERIALS (PGMA-48019)) | ELANGOVAN | [42 empty] | 39632
| 1.9.6.4.1.2.6(RECT DUCTS PRI FAN TO AIRHEATER PRISID (PGMA-48112)) | MG THAKAR | [42 empty] | 39700
| 1.9.6.4.1.2.7(EXPN PIECESPRI FAN TO AIRHEATER PRISID (PGMA-48114)) | MAHAVARKAR | [42 empty] | 39810
| 1.9.6.4.1.2.8(SUPPORTSETCPRI FAN TO AIRHEATER PRISID (PGMA-48115)) | M G RAMESH | [42 empty] | 39820
| 1.9.6.4.1.2.9(SEAL AIR HAG AND ID FAN OUTGATE (PGMA-48141)) | MG. THAKAR | [42 empty] | 39850
| 1.9.6.4.1.2.10(RECT DUCT COLDAIRBUS(TEMP AIR TO MILL (PGMA-48142)) | MANOJ KUMAR | [42 empty] | 39993
| 1.9.6.4.1.2.11(EXPN PIECESCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48144)) | MD INTEKHAB | [42 empty] | 41350
| 1.9.6.4.1.2.12(SUPPORTSETCCOLDAIRBUS(TEMP AIR TO MILL (PGMA-48145)) | SL-1.3 | [42 empty] | 41390
| 1.9.6.4.1.2.13(INSTRUMENT TAPPINGS ON DUCTING (PGMA-48200)) | MIHIR SARKAR | [42 empty] | 41500
| 1.9.6.4.1.2.14(RECT DUCTSAIRHEATER TO WINDBOXDUCT (PGMA-48202)) | MITHUNSONI | [42 empty] | 41710
| 1.9.6.4.1.2.15(EXPN PIECESAIRHEATER TO WINDBOXDUCT (PGMA-48204)) | MJAYAKUMARAN | [42 empty] | 41988
| 1.9.6.4.1.2.16(SUPPORTSETCAIRHEATER TO WINDBOXDUCT (PGMA-48205)) | MK | [42 empty] | 41997
| 1.9.6.4.1.2.17(CLH/VLH -HOT AIR (PGMA-48206)) | MK THAKUR | [42 empty] | 42001
| 1.9.6.4.1.2.18(FLOWMETERS FOR SECONDARY AIR FLOW (PGMA-48207)) | MAHENDRA KUMAR D | [42 empty] | 42002
| 1.9.6.4.1.2.19(DUCT-SEC.AIR TO WB (PGMA-48208)) | MAYANKKESHARWAN | [42 empty] | 42005
| 1.9.6.4.1.2.20(WIND BOX CONNECTING DUCTS - RECTANGULA (PGMA-48212)) | MUNISH | [42 empty] | 42010
| 1.9.6.4.1.2.21(EXPN PIECESWINDBOX CONNECTING DUCT (PGMA-48214)) | MUDIT KHATANA | [42 empty] | 42020
| 1.9.6.4.1.2.22(RECT DUCT-AIRHEATER PRISIDETOHOTAIR B (PGMA-48222)) | MIHIRKUMARMAJI | [42 empty] | 42030
| 1.9.6.4.1.2.23(EXPN PIECES AIRHEATER PREECEDE TO HOTAIR B (PGMA-48224)) | MAHENDRAKRMEENA | [42 empty] | 42046
| 1.9.6.4.1.2.24(SUPPORTS FOR HOT P.A (AH TO HOT BUS) (PGMA-48225)) | MUKESH KUMAR PAT | [42 empty] | 42065
| 1.9.6.4.1.2.25(RECT DUCTS HOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48232)) | MK SINHA | [42 empty] | 42070
| 1.9.6.4.1.2.26(EXPN PIECESHOT AIR BUSDUCT(HOTAIRTOMIL (PGMA-48234)) | MANOJ_KUMAR | [42 empty] | 42120
| 1.9.6.4.1.2.27(SUPPORT HOT AIR BUS (PGMA-48235)) | MKTHAKUR | [42 empty] | 42128
| 1.9.6.4.1.2.28(RECT DUCT AIRHTR TOPRINOZZLE AND SECA (PGMA-48262)) | MLAKSHMINARASI | [42 empty] | 42150
| 1.9.6.4.1.2.29(EXPN PIECESAIRHTR TOPRINOZZLE AND SECA (PGMA-48264)) | MITHILESH KUMAR | [42 empty] | 42152
| 1.9.6.4.1.2.30(SUPPORTSETCAIRHTR TOPRINOZZLE AND SECA (PGMA-48265)) | MMANI | [42 empty] | 42154
| 1.9.6.4.1.2.31(FLOW METER (PGMA-48267)) | M M MALIK | [42 empty] | 42157
| 1.9.6.4.1.2.32(RECT DUCT CASCADE EVAPORATOR TO EP (PGMA-48372)) | MNSRINIVASARAO | [42 empty] | 42158
| 1.9.6.4.1.2.33(RECT DUCT ECONOMISER TO AIRHEATER2NOP (PGMA-48382)) | MOHAMMAD FAIZAN | [42 empty] | 42200
| 1.9.6.4.1.2.34(EXPN PIECESECONOMISER TO AIRHEATER2NOP (PGMA-48384)) | MOHAMMAD DANISH | [42 empty] | 42300
| 1.9.6.4.1.2.35(SUPPORTSETCECONOMISER TO AIRHEATER2NOP (PGMA-48385)) | MOHAN SINGH | [42 empty] | 42358
| 1.9.6.4.1.2.36(DUCT BELOW DIVERTOR & SCR SYSTEM(PGMA-48386)) | MOHIT SINGH | [42 empty] | 42700
| 1.9.6.4.1.2.37(CLH/VLH-FLUE GAS (PGMA-48395)) | MOHIT KUMAR | [42 empty] | 42710
| 1.9.6.4.1.2.38(RECT DUCT AIRHEATER BOILER OUTLET-GAS (PGMA-48432)) | MOHITRANJAN | [42 empty] | 42858
| 1.9.6.4.1.2.39(EXPN PIECESAIRHEATER BOILER OUTLET-GAS (PGMA-48434)) | AS CHANDRA MOULI | [42 empty] | 42988
| 1.9.6.4.1.2.40(SUPPORTSETCAIRHEATER BOILER OUTLET-GAS (PGMA-48435)) | MITHILESH PRASAD | [42 empty] | 42992
| 1.9.6.4.1.2.41(RECT DUCT BOILER OUTLET TO ELEC PRECP (PGMA-48462)) | M PRAVIN | [42 empty] | 42997
| 1.9.6.4.1.2.42(EXPN PIECESBOILER OUTLET TO ELEC PRECP (PGMA-48464)) | MR SATISH GHATGE | [42 empty] | 43004
| 1.9.6.4.1.2.43(BOF TO EP DUCTING SUPPORTS (PGMA-48465)) | MR TEJA TARAKESH | [42 empty] | 43005
| 1.9.6.4.1.2.44(RECT DUCTS-ELEC PRPTR/M.S TO INDDRAFTF (PGMA-48482)) | MR UDAY REDDY P | [42 empty] | 43104
| 1.9.6.4.1.2.45(EXPN PIECESELEC PRPTR/M.S TO INDDRAFTF (PGMA-48484)) | MANOJ RASTOGI | [42 empty] | 43105
| 1.9.6.4.1.2.46(SUPPORTSETCELEC PRPTR/M.S TO INDDRAFTF (PGMA-48485)) | MR. DINGROCHA | [42 empty] | 43200
| 1.9.6.4.1.2.47(RECT DUCT IND DRAFT FAN TO Chimney (PGMA-48492)) | MRAVI | [42 empty] | 43710
| 1.9.6.4.1.2.48(EXPN PIECESIND DRAFT FAN TO Chimney (PGMA-48494)) | MRBHARGAV TSN | [42 empty] | 43997
| 1.9.6.4.1.2.49(I.D.SYSTEM DUCT SUPPORTS (PGMA-48495)) | MRINTYUNAJAY | [42 empty] | 45200
| 1.9.6.4.1.2.50(RECT DUCT HOT AIR BUS TO MILLS (PGMA-48662)) | MRKTHANIKACHALAM | [42 empty] | 45710
| 1.9.6.4.1.2.51(EXPN PIECESHOT AIR BUS TO MILLS (PGMA-48664)) | MOGADATI RANA PR | [42 empty] | 45801
| 1.9.6.4.1.2.52(SUPPORTS FOR HOT PA TO MILLS (PGMA-48665)) | ALPATOPPO | [42 empty] | 45802
| 1.9.6.4.1.2.53(VENTURI-PRIMARY AIR FLOW (PGMA-48667)) | MSANJALI RAMAN | [42 empty] | 45804
| 1.9.6.4.1.2.54(BULKED BPS COMPONENTS (PGMA-48700)) | MANOJIT SARKAR | [42 empty] | 45805
| 1.9.6.4.1.2.55(SLIDE BRG PLATE & PACIFIC BELLOW-BOILER (PGMA-48911)) | MSASINDHUR | [42 empty] | 45806
| 1.9.6.4.1.2.56(SLIDE BRG PLATE-ID SYSTEM (PGMA-48912)) | MUDIT DAYAL | [42 empty] | 45858
| 1.9.6.4.1.2.57(MAN HOLE DOORS (450x450) (PGMA-48915)) | MUDIT | [42 empty] | 45997
| 1.9.6.4.1.2.58(ERECTION MATERIALS (PGMA-48993)) | MUKESH KUMAR | [42 empty] | 47200
| 1.9.6.4.2(BHEL BAP) | MUKTIKANT | [42 empty] | 47261
| 1.9.6.4.2.1( GATES AND DAMPERS) | MUNAWWAR BEG | [42 empty] | 47263
| 1.9.6.4.2.1.1(BAP - GATE-ESP OUTLET(PGMA 57470)) | MUPADHYAYA | [42 empty] | 47267
| 1.9.6.4.2.1.2(BAP - GATE-ID FAN OUTLET(PGMA 57490)) | MURALIDHAR KV | [42 empty] | 47269
| 1.9.6.4.2.1.3(BAP - GATE-ID FAN INLET(PGMA 57480)) | PMUTHUKUMAR | [42 empty] | 47710
| 1.9.6.4.2.1.4(BAP - DAMPER-SCR BYPASS(PGMA 57620)) | GAUTAM MV | [42 empty] | 47858
| 1.9.6.4.2.1.5(BAP - PLATFORMS AND LADDERS– SCR GD(PGMA 57666)) | MALLAPURAM VEERA | [42 empty] | 47997
| 1.9.6.4.2.1.6(BAP - SPL MTL ELECTRODES(PGMA 57992)) | M V S SHOBANBABU | [42 empty] | 48012
| 1.9.6.4.2.1.7(BAP - GATE-FD FAN OUTLET(PGMA 57010)) | N D GAUTAM | [42 empty] | 48014
| 1.9.6.4.2.1.8(BAP - FLUE GAS AH OUT GATE(PGMA 57430)) | N DEEPA DEVARAJ | [42 empty] | 48015
| 1.9.6.4.2.1.9(BAP - GATE-ESP INLET(PGMA 57460)) | N N RAMAN | [42 empty] | 48018
| 1.9.6.4.2.1.10(BAP - DAMPER-SA SCAPH INLET(PGMA 57033)) | NARESH SINGH | [42 empty] | 48019
| 1.9.6.4.2.1.11(BAP - DAMPER-SA SCAPH OUTLET(PGMA 57063)) | NABARUN SARKAR | [42 empty] | 48022
| 1.9.6.4.2.1.12(BAP - DAMPER-SA APH OUTLET(PGMA 57203)) | RAVINDRA NAICK | [42 empty] | 48112
| 1.9.6.4.2.1.13(BAP - MTG BKT FOR CL DAMPER AIR CYL(PGMA 57209)) | NAINA SINGH | [42 empty] | 48114
| 1.9.6.4.2.1.14(BAP - PLATFORMS AND LADDERS(PGMA 57466)) | NAKUL KUMAR | [42 empty] | 48115
| 1.9.6.4.2.1.15(BAP - ACTUATORS FOR G&D(PGMA 57577)) | NANDKUMAR | [42 empty] | 48116
| 1.9.6.4.2.1.16(BAP - GATE –FGD INLET(PGMA 57560)) | JNAN | [42 empty] | 48141
| 1.9.6.4.2.1.17(BAP - GATE –FGD OUTLET(PGMA 57C70)) | VVNARASIMHA | [42 empty] | 48142
| 1.9.6.4.2.1.18(BAP - DAMPER –FGD BYPASS(PGMA 57C83)) | NARENDRA AGRAWAL | [42 empty] | 48144
| 1.9.6.4.2.1.19(BAP - PLAT FORM AND LADDER –FGD GD(PGMA 57566)) | NARENDRA AGRA | [42 empty] | 48145
| 1.9.6.4.2.1.20(BAP - GATE WITH CLADDING FOR CO2 TO METHANOL SYSTEM (PGMA 57CX0)) | NARESH GIRDHAR | [42 empty] | 48200
| 1.9.6.4.2.1.21(BAP - PLATFORMS AND LADDERS-SCR GD (PGMA 57CX0)) | NAWAZISH ALI | [42 empty] | 48202
| 1.9.6.4.2.1.22(BAP - DAMPER-PA APH INLET(PGMA 57173)) | NAVEENKUMAR | [42 empty] | 48204
| 1.9.6.4.2.1.23(BAP - DAMPER-PA APH OUTLET(PGMA 57223)) | NAVIN SAXENA | [42 empty] | 48205
| 1.9.6.4.2.1.24(BAP - DAMPER-COLD AIR TO MIL(PGMA 57143)) | NAVINS | [42 empty] | 48206
| 1.9.6.4.2.1.25(BAP - ELECTRICAL ITEMS FOR GATE,DAMP(PGMA 57578)) | NAVEEN K SADH | [42 empty] | 48207
| 1.9.6.4.2.1.26(BAP - SEAL AIR HAG AND ID FA(PGMA 57141)) | NAVNEET PATHAK | [42 empty] | 48208
| 1.9.6.4.2.1.27(BAP - DAMPER-PA FAN OUTLET(PGMA 57113)) | NCHALDER | [42 empty] | 48212
| 1.9.6.4.2.1.28(BAP - GATE-PA FAN OUTLET(PGMA 57110)) | N C NAYAK | [42 empty] | 48214
| 1.9.6.4.2.1.29(BAP - BLOWER WITH MOTOR(PGMA 57491)) | DEEPADEV | [42 empty] | 48222
| 1.9.6.4.2.1.30(BAP - GATE-COLD AIR TO MILLS(PGMA 57160)) | NDGAUTAM | [42 empty] | 48224
| 1.9.6.4.2.1.31(BAP - KNIFE GATE VALVE(PGMA 57497)) | NEEL GAGAN | [42 empty] | 48225
| 1.9.6.4.2.1.32(BAP - GATE-HOT AIR TO MILLS(PGMA 57270)) | NEELKAMAL | [42 empty] | 48232
| 1.9.6.4.2.1.33(BAP - DAMPER-HOT AIR TO MILL(PGMA 57273)) | NEERAJ MEENA | [42 empty] | 48234
| 1.9.6.4.2.1.34(BAP - DAMPER-SA SCAPH BYPASS(PGMA 57083)) | NEERAJ PAL | [42 empty] | 48235
| 1.9.6.4.2.1.35(BAP - DUCTS COMMISSIONING SPARES(PGMA 57988)) | M S NEGI | [42 empty] | 48262
| 1.9.6.5(Erection) | NIDIT KUMAR | [42 empty] | 48264
| 1.9.6.5.1(External Structures ( Supporting Structures for Duct, PG-39 )) | NIDITKUMAR | [42 empty] | 48265
| 1.9.6.5.2(Duct., Dampers and Expn. Joints) | NIKESHKUJUR | [42 empty] | 48267
| 1.9.6.5.2.1( AIR DUCTING) | NIKHILGOEL | [42 empty] | 48372
| 1.9.6.5.2.1.1( FORCED DRAFT AIR) | NILKANTH | [42 empty] | 48382
| 1.9.6.5.2.1.2( PRIMARY AIR) | NIMESH | [42 empty] | 48384
| 1.9.6.5.2.2( FLUE GAS DUCTING) | NIRAJ KUMAR | [42 empty] | 48385
| 1.9.6.5.2.2.1( ID TO COMMON DUCT TO Chimney - Priority Pass) | VNIRMALA | [42 empty] | 48386
| 1.9.6.5.2.2.2( ID to COMMON DUCT TO Chimney - Second Pass) | NISHANT | [42 empty] | 48388
| 1.9.6.5.2.2.3( ECO TO APH) | NISHANT SHEKHAR | [42 empty] | 48389
| 1.9.6.5.2.2.4( APH TO BOF) | NISHEETHKHARE | [42 empty] | 48395
| 1.9.6.5.2.2.5( BOF TO ESP - Priority Pass) | NISHTHA | [42 empty] | 48432
| 1.9.6.5.2.2.6( BOF TO ESP - Second Pass) | NITESH RANJAN | [42 empty] | 48434
| 1.9.6.5.2.2.7( ESP to ID - Priority Pass) | NITIN VIKASH | [42 empty] | 48435
| 1.9.6.5.2.2.8( ESPTO ID - Second Pass) | NITIN KUMAR | [42 empty] | 48462
| 1.9.7(Pulverised Fuel System) | NITIN K | [42 empty] | 48464
| 1.9.7.1(Civil Work) | NITIN BATRA | [42 empty] | 48465
| 1.9.7.1.1( Mills Foundation) | NITINK2 | [42 empty] | 48482
| 1.9.7.1.2(Bunker) | NITINKUMAR | [42 empty] | 48484
| 1.9.7.2(Supply) | NITIN PANDEY | [42 empty] | 48485
| 1.9.7.2.1(BHEL TRY) | NITINVIKASH | [42 empty] | 48492
| 1.9.7.2.1.1(Pulverised Fuel Piping (PG-47)) | NITISH KUMAR B | [42 empty] | 48494
| 1.9.7.2.1.1.1(Fuel Piping - Sub-delivery (PGMA-47200)) | NITISH SHAHU | [42 empty] | 48495
| 1.9.7.2.1.1.2(FUEL PIPE SUPPORTS (PGMA-47261)) | NITISH KUMAR | [42 empty] | 48496
| 1.9.7.2.1.1.3(FUEL PIPE COUPLING COLLER & ORIFICE (PGMA-47263)) | NITISH | [42 empty] | 48498
| 1.9.7.2.1.1.4(FUEL PIPE ST PIPES FOR MILL G (PGMA-47269)) | N N MISHRA | [42 empty] | 48662
| 1.9.7.2.1.1.5(Pulverised Fuel Piping - DD items (PGMA-47710)) | NIVEDITA | [42 empty] | 48664
| 1.9.7.2.1.1.6(Fuel Piping - Shop Items (PGMA-47858)) | NK.VERMA | [42 empty] | 48665
| 1.9.7.2.1.1.7(COAL PIPING MANDATORY SPARES (PGMA-47997)) | NAGENDRA KR MISH | [42 empty] | 48667
| 1.9.7.2.1.2(Coal Feeders (PG-65)) | NRIPENDRAKUMAR | [42 empty] | 48700
| 1.9.7.2.1.2.1(Coal Feeder- Sub-Delivery (PGMA-65200)) | NEETU KUMAR SING | [42 empty] | 48911
| 1.9.7.2.1.2.2(Coal Feeder - DD items (PGMA-65710)) | NNRAMAN | [42 empty] | 48912
| 1.9.7.2.1.2.3(36 INCH GRAVIMETRIC FEEDER (PGMA-65736)) | NITYA | [42 empty] | 48915
| 1.9.7.2.1.2.4(FEEDER MANDATORY SPARE (PGMA-65997)) | NPSINGH | [42 empty] | 48992
| 1.9.7.2.1.3(Coal Valves & Gates (PG-67)) | NRKRISHNA | [42 empty] | 48993
| 1.9.7.2.1.3.1(Coal Feeding System- Sub dely. (PGMA-67200)) | NARAYAN SINGH | [42 empty] | 50510
| 1.9.7.2.1.3.2(RAW COAL GATES NEEDLE TYPE (PGMA-67204)) | NAGESH | [42 empty] | 52000
| 1.9.7.2.1.3.3(COAL VALVE-36 INCH MOTOR OPERATED (PGMA-67272)) | NISHANT KUMAR | [42 empty] | 52010
| 1.9.7.2.1.3.4(RAW COAL GATE CHAIN OP 36" CIRCULAR (PGMA-67276)) | ORIGINATOR | [42 empty] | 52011
| 1.9.7.2.1.3.5(FEEDER OUTLET ISOLATION GATE (PGMA-67283)) | ORIGINATOR_D | [42 empty] | 52012
| 1.9.7.2.1.3.6(Coal Feeding System - DD items (PGMA-67710)) | OSCAR | [42 empty] | 52013
| 1.9.7.2.1.3.7(DOWN SPOUT (PGMA-67801)) | PVSHAH | [42 empty] | 52024
| 1.9.7.2.1.3.8(BUNKER EMPTYING CHUTE ARRANGEMENT (PGMA-67802)) | PEEYUSH MISHRA | [42 empty] | 52030
| 1.9.7.2.1.3.9(FEED PIPE TO MILL (PGMA-67803)) | PABITRAKUMARSAHA | [42 empty] | 52041
| 1.9.7.2.1.3.10(FDR ISOLATION GATE MAND SPARES (PGMA-67997)) | UMESH G. PADAGAT | [42 empty] | 52042
| 1.9.7.2.2(BHEL HYD) | SL-1.10 | [42 empty] | 52054
| 1.9.7.2.2.1(MILL and its Components) | PALLABI | [42 empty] | 52055
| 1.9.7.2.2.1.1(MILLS(7 NOS.)) | UKPANDA | [42 empty] | 52100
| 1.9.7.2.3( BHEL BPL) | PARITOSH PANDIT | [42 empty] | 52101
| 1.9.7.2.3.1(Mill Motor) | PANKAJ GUPTA | [42 empty] | 52211
| 1.9.7.2.4( BHEL IP ) | PANKAJ KUMAR JHA | [42 empty] | 52220
| 1.9.7.2.4.1(Ceralin Lined Pulverised Coal Piping items) | PANKAJ JAIN | [42 empty] | 52261
| 1.9.7.3(Erection) | PANKAJ KUMAR JH | [42 empty] | 52262
| 1.9.7.3.1(Mills) | PANKAJ KAPISMAY | [42 empty] | 52271
| 1.9.7.3.2(Pulverised Fuel Piping (PG-47)) | PANKAJ PARADKAR | [42 empty] | 52272
| 1.9.7.3.2.1(First 4 Nos Mills) | PARAS KUMAR LUDU | [42 empty] | 52274
| 1.9.7.3.2.2(Last 3 Nos Mills) | PARITOSH | [42 empty] | 52275
| 1.9.7.3.3(Coal Feeders (PG-65)) | PARTHA DAS | [42 empty] | 52301
| 1.9.7.3.4(Coal Valves & Gates (PG-67)) | PARUSH | [42 empty] | 52302
| 1.9.7.3.4.1( Mills/Feeders) | PAWAN KRSAXENA | [42 empty] | 52338
| 1.9.8(APH) | PAWAN KUMA | [42 empty] | 52339
| 1.9.8.1(Supply) | PAWAN KUMAR | [42 empty] | 52340
| 1.9.8.1.1(BHEL RPT) | PAYEL DUTTA | [42 empty] | 52600
| 1.9.8.1.1.1(LARG AH-ROTORHOUSING(PGMA-52030)) | PHANI BHUSHAN PR | [42 empty] | 52988
| 1.9.8.1.1.2(COLD END CONN PLATE(PGMA-52042)) | PC JHA | [42 empty] | 52997
| 1.9.8.1.1.3(HOT END CONN PLATE(PGMA-52041)) | PCHELLAPPANDIA | [42 empty] | 55000
| 1.9.8.1.1.4(LARG AH-SUPRT BEARNG(PGMA-52262)) | PERMINDER | [42 empty] | 55011
| 1.9.8.1.1.5(LARG AH-GUIDE BEARNG(PGMA-52261)) | PRATISGEE | [42 empty] | 55015
| 1.9.8.1.1.6(LARG AH-ROTOR POST(PGMA-52011)) | PANKAJGUPTA | [42 empty] | 55017
| 1.9.8.1.1.7(LARG AH-ROTOR ASSY(PGMA-52010)) | PRATISH | [42 empty] | 55021
| 1.9.8.1.1.8(LARG AH-ROTORPINRACK(PGMA-52012)) | P K ANCHURI | [42 empty] | 55024
| 1.9.8.1.1.9(SPECIAL TOOLS/CONTRA(PGMA-52000)) | PIYUSH VERMA | [42 empty] | 55025
| 1.9.8.1.1.10(LARGE AH ROTOR DRIVE(PGMA-52100)) | PIYUSHVERMA | [42 empty] | 55027
| 1.9.8.1.1.11(LARG AH-AUX ROTDRIVE(PGMA-52101)) | PJ | [42 empty] | 55031
| 1.9.8.1.1.12(LARG AH-AXIAL SEAL(PGMA-52054)) | PJAGADISWARA | [42 empty] | 55035
| 1.9.8.1.1.13(LARG AH-BY PASS SEAL(PGMA-52055)) | PK UPADHYAY | [42 empty] | 55037
| 1.9.8.1.1.14(LARG AH-ROTORSEALS(PGMA-52013)) | PANKAJ KUMAR | [42 empty] | 55091
| 1.9.8.1.1.15(OIL PIPING GUIDE BRG(PGMA-52271)) | P K GAUTAM | [42 empty] | 55216
| 1.9.8.1.1.16(OIL PIPING SUPRT BRG(PGMA-52272)) | PKM | [42 empty] | 55227
| 1.9.8.1.1.17(LARG AH-GENS DETAILS(PGMA-52220)) | RAKESKUMARYA | [42 empty] | 55327
| 1.9.8.1.1.18(LUB OIL CIRCULATION UN(PGMA-52274)) | PKSAXENA | [42 empty] | 55334
| 1.9.8.1.1.19(LARGE AIR HEATER-LUBRI(PGMA-52275)) | PKSINHA | [42 empty] | 55335
| 1.9.8.1.1.20(LARG AH-AIRSEAL PIPE(PGMA-52211)) | PKUPADHYAY | [42 empty] | 55410
| 1.9.8.1.1.21(WASH MANIFLD GAS INL(PGMA-52301)) | PKVARSHNEY | [42 empty] | 55420
| 1.9.8.1.1.22(WASH MANIFLD GAS OUT(PGMA-52302)) | PL GAJBHIYE | [42 empty] | 55430
| 1.9.8.1.1.23(CLEANING DEVICE –RETRACT TYPE (PGMA-52338)) | SL-1.14 | [42 empty] | 55510
| 1.9.8.1.1.24(LARGE AH-RETRACT CLNG DEVICE (HE)(PGMA-52339)) | P M ASWANI | [42 empty] | 55516
| 1.9.8.1.1.25(LARGE AH E,C&I COMPONENETS(PGMA-52600)) | ABHISHEK RANJAN | [42 empty] | 55520
| 1.9.8.1.1.26(LARG AH COMMISSIONING SPARES (PGMA-52988)) | ALTAMASH | [42 empty] | 55527
| 1.9.8.1.1.27(STEAM COIL APH (PGMA-50510)- BOI) | ANKIT | [42 empty] | 55530
| 1.9.8.2(Erection) | ASHUTOSH VERMA | [42 empty] | 55627
| 1.9.8.2.1( First APH) | VIVEK BECK | [42 empty] | 55635
| 1.9.8.2.2( Second APH) | CHANCHAL PATI | [42 empty] | 55716
| 1.9.9(Various Fans) | CHANDANKUNAL | [42 empty] | 55727
| 1.9.9.5(Civil Work) | DEEPAK VATS | [42 empty] | 55735
| 1.9.9.5.1(First ID Fan foundations) | PMGDIVYA | [42 empty] | 55810
| 1.9.9.5.2(Second ID Fan foundation) | ISHAN | [42 empty] | 55816
| 1.9.9.5.3(First FD Fan Foundation) | KAUSHAL PANDEY | [42 empty] | 55820
| 1.9.9.5.4(Second FD Fan Foundation) | MANISH_KUMAR | [42 empty] | 55827
| 1.9.9.5.5(First PA Fan Foundation) | MANOJKUMAR | [42 empty] | 55830
| 1.9.9.5.6(Second PA Fan Foundation) | NARENDRA | [42 empty] | 55835
| 1.9.9.5.7(SA fan Foundation) | PALLAV | [42 empty] | 55910
| 1.9.9.6(Supply) | PRABHAT | [42 empty] | 55911
| 1.9.9.6.1(Fans (PG - 55 & 56) - BHEL BAP) | RISHIPAL | [42 empty] | 55919
| 1.9.9.6.1.1(AXL IDFAN FDN MATL(PGMA-55021)) | PMGSALIL | [42 empty] | 55920
| 1.9.9.6.1.2( FD FAN FOUNDATION MATL(PGMA-55011)) | SAURABH | [42 empty] | 55930
| 1.9.9.6.1.3(PA FAN FOUNDATION MATL(PGMA-55031)) | SHADAB ALAM | [42 empty] | 55931
| 1.9.9.6.1.4(AXIAL IDFAN COUPLING(PGMA-55820)) | SUJATA SHARMA | [42 empty] | 55939
| 1.9.9.6.1.5(1 STG ID rotor(PGMA-55216)) | MATHARU | [42 empty] | 55997
| 1.9.9.6.1.6(2 STG ID ROTOR(PGMA-55327)) | VIJAYKR | [42 empty] | 55998
| 1.9.9.6.1.7(SECOND STAGE ID HOUSING(PGMA-55627)) | VIVEK KUMAR SING | [42 empty] | 56000
| 1.9.9.6.1.8(ID SEALING/COOLING FAN(PGMA-55024)) | PMISHRA | [42 empty] | 56011
| 1.9.9.6.1.9(AXIAL FDFAN COUPLING(PGMA-55810)) | P.K. NAGENDRA | [42 empty] | 56017
| 1.9.9.6.1.10(1 STG FD HOUSING (PGMA 55516)) | OP-1.2 | [42 empty] | 56075
| 1.9.9.6.1.11(FD FAN INSUL WOOL (PGMA 55919)) | ARUN PODDAR | [42 empty] | 56077
| 1.9.9.6.1.12(FD FAN COUPLING GUARD (PGMA 55015)) | POOJAAGRAWAL1 | [42 empty] | 56079
| 1.9.9.6.1.13(FD SET & INDN SHAFT (PGMA 55410)) | POOJABHARDWAJ | [42 empty] | 56113
| 1.9.9.6.1.14(FD FAN EXPN JOINTS (PGMA 55510)) | POWERMECH | [42 empty] | 56114
| 1.9.9.6.1.15(FD FAN DIFFUSER (PGMA 55816)) | PRAKASH PARIDA | [42 empty] | 56161
| 1.9.9.6.1.16(FD FAN SUCTION BOX (PGMA 55716)) | PPKASHIMALLA | [42 empty] | 56173
| 1.9.9.6.1.17(AXIAL FDFAN SILENCER(PGMA-55911)) | PPPANDHURNEKAR | [42 empty] | 56313
| 1.9.9.6.1.18(ID FAN C&I ITEMS(PGMA-55027)) | PPSAHA | [42 empty] | 56314
| 1.9.9.6.1.19(ID FAN CPLNG GUARD (PGMA 55025)) | SPRABHAKAR | [42 empty] | 56373
| 1.9.9.6.1.20(ID SET & INDN SHAFT (PGMA 55420)) | PRABHAT KATIYAR | [42 empty] | 56413
| 1.9.9.6.1.21(ID FAN EXPN JOINTS (PGMA 55520)) | PRABHUD | [42 empty] | 56414
| 1.9.9.6.1.22(ID FAN DIFFUSER (PGMA 55827)) | PRADEEP | [42 empty] | 56473
| 1.9.9.6.1.23(ID FAN SUCTION BOX (PGMA 55727)) | MRIGANG PRADEEP | [42 empty] | 56610
| 1.9.9.6.1.24(AXIAL ID FAN LUBE OIL(PGMA-55920)) | PK. MISHRA | [42 empty] | 56670
| 1.9.9.6.1.25(FD FAN C&I ITEMS(PGMA-55017)) | PRADEEPPAL | [42 empty] | 56810
| 1.9.9.6.1.26(AXIAL FD FAN LUBE OIL(PGMA-55910)) | PRADIPKMODAK | [42 empty] | 56870
| 1.9.9.6.1.27(2 STG PA ROTOR(PGMA-55335)) | PRADYUT PANJA | [42 empty] | 56911
| 1.9.9.6.1.28(2 STG PA HOUSING (PGMA 55635)) | PRAFULLA | [42 empty] | 56919
| 1.9.9.6.1.29(PA FAN INSUL WOOL (PGMA 55939)) | P P TIGGA | [42 empty] | 56997
| 1.9.9.6.1.30(PA FAN CPLNG GUARD (PGMA 55035)) | PAWANPAJAPAT | [42 empty] | 56998
| 1.9.9.6.1.31(PA SET & INDN SHAFT (PGMA 55430)) | SH PRAKASH ADME | [42 empty] | 57010
| 1.9.9.6.1.32(PA FAN EXPN JOINTS (PGMA 55530)) | PP. PANDHURNEKA | [42 empty] | 57013
| 1.9.9.6.1.33(PA FAN DIFFUSER (PGMA 55835)) | PRAMOD RAJ | [42 empty] | 57033
| 1.9.9.6.1.34(PA FAN SUCTION BOX (PGMA 55735)) | PRANIT | [42 empty] | 57063
| 1.9.9.6.1.35(RADIAL SEAL AIR FAN ROTOR(PGMA-56173)) | PRASAD SAMBARIKI | [42 empty] | 57083
| 1.9.9.6.1.36(AXL PAFAN COUPLING(PGMA-55830)) | PRASHANTAGARWAL | [42 empty] | 57110
| 1.9.9.6.1.37(PA FAN SILENCER(PGMA-55931)) | PRATAP SARKAR | [42 empty] | 57113
| 1.9.9.6.1.38(FIRST FILL LUBRICANTS(PGMA-55091)) | PRATEEK KUMAR | [42 empty] | 57141
| 1.9.9.6.1.39(RADIAL PENT HOUSE VENT(PGMA-56161)) | G PRATHEESH KUMA | [42 empty] | 57143
| 1.9.9.6.1.40(RADIAL SEAL AIR FAN BEARINGS (PGMA 56373)) | PRATHIN GUPTA | [42 empty] | 57160
| 1.9.9.6.1.41(RADIAL SEAL AIR FAN STATOR (PGMA 56473)) | PRAVEEN KUMAR | [42 empty] | 57173
| 1.9.9.6.1.42(SA FAN CPLNG GUARD (PGMA 56075)) | PRAVEENPANDEY | [42 empty] | 57203
| 1.9.9.6.1.43(SA FAN MTR CANOPY (PGMA 56079)) | PRAVEENKUMARBECK | [42 empty] | 57209
| 1.9.9.6.1.44(SEAL AIR FAN COUPLING((PGMA-56870)) | PRAVEEN DUTTA | [42 empty] | 57223
| 1.9.9.6.1.45(AXL FAN TOOL & FIXTU(PGMA-55000)) | PRAVEENKISHORE | [42 empty] | 57270
| 1.9.9.6.1.46(PA FAN C&I ITEMS(PGMA-55037)) | PRAVINSHANKAR | [42 empty] | 57273
| 1.9.9.6.1.47(SEAL AIR FAN C&I ITEMS(PGMA-56077)) | PRAWAT | [42 empty] | 57363
| 1.9.9.6.1.48(RADIAL SEAL AIR FAN MO(PGMA-56670)) | PREMPRAKASH | [42 empty] | 57370
| 1.9.9.6.1.49(AXIAL PA FAN LUBE OIL(PGMA-55930)) | PRISCILLA | [42 empty] | 57413
| 1.9.9.6.2(Fan Motor - BHEL BPL) | PRIYAKALA | [42 empty] | 57430
| 1.9.9.6.2.1(ID Fan Motor) | PRIYANKA | [42 empty] | 57460
| 1.9.9.6.2.2(FD Fan Motor) | PRAVIN R KOLI | [42 empty] | 57466
| 1.9.9.6.2.3(PA Fan Motor) | PRAKASHYADAV | [42 empty] | 57470
| 1.9.9.7(Erection) | P R MURALI | [42 empty] | 57480
| 1.9.9.7.1(First ID FAN) | PM | [42 empty] | 57490
| 1.9.9.7.2(Second ID Fan) | PM_D | [42 empty] | 57491
| 1.9.9.7.3(First FD Fan) | P R RAVI | [42 empty] | 57497
| 1.9.9.7.4(Second FD Fan) | PRASANTASAHA | [42 empty] | 57560
| 1.9.9.7.5(Second PA Fan) | PRAKASH SONIS | [42 empty] | 57566
| 1.9.9.7.6(First PA Fan) | PSOMASEKHAR | [42 empty] | 57570
| 1.9.9.7.7(SA FAN) | P.SURESH KUMAR | [42 empty] | 57577
| 1.9.10(Electrostatic Precipitator) | P SURESH | [42 empty] | 57578
| 1.9.10.2(Civil) | PTMATHESWARAN | [42 empty] | 57580
| 1.9.10.2.1( ESP Foundations) | PUKHRAJ SINGH | [42 empty] | 57583
| 1.9.10.2.1.1( ESP Foundations- First 3 Pass Foundation) | PUNEETPORWAL | [42 empty] | 57600
| 1.9.10.2.1.1.1( Excavation & PCC of Footing) | P VISHWAKARMA | [42 empty] | 57603
| 1.9.10.2.1.1.2( Footing Concreting Works) | R K SRIVASTAVA | [42 empty] | 57610
| 1.9.10.2.1.1.3( Pedestal Concreting Works) | R M JHA | [42 empty] | 57613
| 1.9.10.2.1.1.4( Backfilling Works) | RAJESH A | [42 empty] | 57620
| 1.9.10.2.1.1.5( Grade Slab Concreting Works (Paving Works)) | RACHIT GOGIA | [42 empty] | 57623
| 1.9.10.2.1.2( ESP Foundations- Balance Three Pass) | RACHIT | [42 empty] | 57666
| 1.9.10.2.1.2.1( Excavation & PCC of Footings) | RAGHURAMB | [42 empty] | 57988
| 1.9.10.2.1.2.2( Footing Concreting Works) | RAGHVENDRASINGH | [42 empty] | 57992
| 1.9.10.2.1.2.3( Pedestal Concreting Works) | RAHUL DIXIT | [42 empty] | 61001
| 1.9.10.2.1.2.4( Backfilling Works) | RAHULBHATNAGAR | [42 empty] | 61101
| 1.9.10.2.1.2.5( Grade Slab Concreting Works (Paving Works)) | RAHUL KUMAR | [42 empty] | 61103
| 1.9.10.3(Supply) | RAJ KUM | [42 empty] | 61201
| 1.9.10.3.1(BAP - Foundation Materials (PGMA 79580)) | RAJKISHORE | [42 empty] | 61301
| 1.9.10.3.2(BAP - Supporting structure for ESP (PGMA 79581)) | RAJ KUMAR | [42 empty] | 61302
| 1.9.10.3.3(BAP - ROLL/SLIDE SUPPORTS (PGMA 79501)) | DRAJABABU | [42 empty] | 61501
| 1.9.10.3.4(BAP - CASING STRUCTURE (PGMA 79548)) | SRAJAN | [42 empty] | 61911
| 1.9.10.3.5(BAP - ELECTRICAL MISC ITEMS (PGMA 79541)) | RAJARAJAN | [42 empty] | 65200
| 1.9.10.3.6(BAP - HOPPER RIDGES (PGMA 79543)) | RAJASREE | [42 empty] | 65710
| 1.9.10.3.7(BAP - CASING SHELL/PANEL (PGMA 79549)) | RAJATENDU ROY | [42 empty] | 65736
| 1.9.10.3.8(BAP - EP GALLERIES&STAIRS (PGMA 89610)) | RAJAT KUMAR GOUR | [42 empty] | 65997
| 1.9.10.3.9(BAP - FLOOR GRILL AND STEP T (PGMA 89612)) | RAJEEV KUMAR | [42 empty] | 67200
| 1.9.10.3.10(BAP - ESP ROOF BEAM (PGMA 79528)) | RAJEEV SHARMA | [42 empty] | 67204
| 1.9.10.3.11(BAP - COL ELEC SUSPENSION(PGMA 79519)) | RAJEEVSINGH | [42 empty] | 67272
| 1.9.10.3.12(BAP - EMIT SYST SUSPENSION(PGMA 79513)) | RAJESH SOY | [42 empty] | 67276
| 1.9.10.3.13(BAP - INSULATOR SUPP PANEL(PGMA 79546)) | RAJESHPRASAD | [42 empty] | 67277
| 1.9.10.3.14(BAP - EMIT SYS FRAME-TOP(PGMA 79521)) | RAJESHKM | [42 empty] | 67283
| 1.9.10.3.15(BAP - EMIT SYS FRAME-MIDLE(PGMA 79532)) | RAJESH MITRA | [42 empty] | 67411
| 1.9.10.3.16(BAP - EMIT SYS FRAME BOTOM(PGMA 79522)) | RAJIB MAZUMDAR | [42 empty] | 67511
| 1.9.10.3.17(BAP - SUPPORT INSULATORS(PGMA 79514)) | RAJIB CHAKRABORT | [42 empty] | 67710
| 1.9.10.3.18(BAP - COLLECTING ELECTRODE(PGMA 79520)) | RAJIV KUMAR | [42 empty] | 67801
| 1.9.10.3.19(BAP - GAS DIST. ASSY(PGMA 79508)) | RAJKISHOR | [42 empty] | 67802
| 1.9.10.3.20(BAP - ROOF PANEL ASSY(PGMA 79547)) | RAJNISHCHOUDHARY | [42 empty] | 67803
| 1.9.10.3.21(BAP - INLET-OUTLET FUNNEL(PGMA 79550)) | RAJNISH | [42 empty] | 67997
| 1.9.10.3.22(BAP - SPLITTER&GUIDE VANES(PGMA 79557)) | RAJUPURAM | [42 empty] | 78663
| 1.9.10.3.23(BAP - SHOCK BARS(PGMA 79524)) | RAKESH_KUMAR | [42 empty] | 79101
| 1.9.10.3.24(BAP - COLL ELECT RAPP MECH(PGMA 79525)) | RAKESH | [42 empty] | 79105
| 1.9.10.3.25(BAP - GAS SCREEN-EP(PGMA 79511)) | RAKESH K PANDEY | [42 empty] | 79106
| 1.9.10.3.26(BAP - EMITTING ELECTRODES(PGMA 79515)) | RAKESH CHANDRA | [42 empty] | 79108
| 1.9.10.3.27(BAP - OUTER ROOF-EP(PGMA 79542)) | RAKESH KHATRI | [42 empty] | 79109
| 1.9.10.3.28(BAP - HOPPER UPPER PART(PGMA 79544)) | RAKESH KUMAR | [42 empty] | 79110
| 1.9.10.3.29(BAP - HOP MLD&LOWER PART(PGMA 79545)) | RAKESH VISHNOI | [42 empty] | 79111
| 1.9.10.3.30(BAP - APP PLATFORM-HOPPER(PGMA 79565)) | RAKESKUMAR | [42 empty] | 79113
| 1.9.10.3.31(BAP - EMIT ELECT RAPP MECH(PGMA 79516)) | RAMESH_KUMAR | [42 empty] | 79114
| 1.9.10.3.32(BAP - DRIVE ARGT. FOR EMIT.(PGMA 79517)) | RAMESH KUMAR | [42 empty] | 79115
| 1.9.10.3.33(BAP - INSULATOR HOUSING AS(PGMA 79506)) | SRAMESH | [42 empty] | 79116
| 1.9.10.3.34(BAP - PENT HOUSE FOR E P(PGMA 79555)) | RAMHARI | [42 empty] | 79117
| 1.9.10.3.35(BAP - PENT HOUSE ROOFING SHE(PGMA 89614)) | MRAMAKRISHNA | [42 empty] | 79119
| 1.9.10.3.36(BAP - ESP ROOF HANDRAILS(PGMA 79526)) | GRAMMOHAN | [42 empty] | 79120
| 1.9.10.3.37(BAP - COLL ELEC RAPP DRIVE(PGMA 79526)) | RAMNIK | [42 empty] | 79121
| 1.9.10.3.38(BAP - GD-RAPPING MECHANISM(PGMA 79509)) | R N PRASAD | [42 empty] | 79122
| 1.9.10.3.39(BAP - GD_DRIVE ARRANGEMENT(PGMA 79510)) | RANJOY | [42 empty] | 79123
| 1.9.10.3.40(BAP - INSPECTION DOORS(PGMA 79523)) | RATHEEN | [42 empty] | 79124
| 1.9.10.3.41(BAP - CONTROL ROOM-INSERTS(PGMA 79559)) | RAVI_KUMAR | [42 empty] | 79125
| 1.9.10.3.42(BAP - GEARED MOTORS FOR RAPP(PGMA 79531)) | RAVI KUMAR | [42 empty] | 79126
| 1.9.10.3.43(BAP - ESP-SUB-DELIVERY COMPO(PGMA 79505)) | RAVINDER K Y | [42 empty] | 79128
| 1.9.10.3.44(BAP - HEATING ELEMENTS(PGMA 79590)) | RAVINDRA | [42 empty] | 79130
| 1.9.10.3.45(BAP - ELECTRICAL SD COMPTS(PGMA 79530)) | RAVINDRA YADAW | [42 empty] | 79131
| 1.9.10.3.46(BAP - JUNCTION BOX & PUSH BU(PGMA 79537)) | PONNA RAVIKUMAR | [42 empty] | 79132
| 1.9.10.3.47(BAP - FIXING COMP. FOR ESP I(PGMA 79568)) | RAVITEJA | [42 empty] | 79137
| 1.9.10.3.48(BAP - WATER WASHING SYSTEM(PGMA 79566)) | NARESH RAWAT | [42 empty] | 79141
| 1.9.10.3.49(BAP -SUPPORT INSULATORS(PGMA 79514)) | RAJBAHADUR | [42 empty] | 79142
| 1.9.10.3.50(BAP - BAPCON & ACCESSORIES(PGMA 79578)) | R B KARANAM | [42 empty] | 79143
| 1.9.10.3.51(BAP - IOS PANEL(PGMA 79595)) | ROHITCHAWLA | [42 empty] | 79144
| 1.9.10.3.52(BAP - INTERLOCKS(PGMA 79572)) | RELANKOVAN | [42 empty] | 79145
| 1.9.10.3.53(BAP - ELECTRICALLY OPERTD HOIST & ACCESSORIES(PGMA 79573)) | PENCHAL REDDY | [42 empty] | 79146
| 1.9.10.3.54(BAP - GUIDE VANES /GUIDE PLATES(PGMA 79589)) | REVI | [42 empty] | 79147
| 1.9.10.3.55(BAP - COMMISSIONING SPARES(PGMA 79988)) | ROHIT | [42 empty] | 79148
| 1.9.10.3.56(BAP - ESP HAND RAILS(PGMA 89611)) | RICHAB | [42 empty] | 79149
| 1.9.10.3.57(BAP - HSFG BOLTS(PGMA 89618)) | RIGGER | [42 empty] | 79150
| 1.9.10.3.58(BAP - OPACITY MONITOR & ACCE(PGMA 79574)) | RIMIL KUNKAL | [42 empty] | 79155
| 1.9.10.3.59(BAP - ASH LEVEL INDICATOR(PGMA 79563)) | RITA SAXENA | [42 empty] | 79157
| 1.9.10.3.60(BAP - EP PERF TEST EQUIPT(PGMA 79561)) | RITURAJ ARYA | [42 empty] | 79159
| 1.9.10.3.61(BAP - TOOLS & TACKLES(PGMA 79996)) | RAJEEV_KUMAR | [42 empty] | 79160
| 1.9.10.3.62(BOI Items) | R K AGRAWAL | [42 empty] | 79161
| 1.9.10.3.62.1( BAP - BOI Items: Cable Trays (79562)) | RKANT07 | [42 empty] | 79162
| 1.9.10.3.62.2( BAP - BOI Items: Floor Grills (89613)) | R.KARUNAKAR | [42 empty] | 79163
| 1.9.10.3.62.3( BAP - BOI Items: Cable (79560)) | RKK | [42 empty] | 79164
| 1.9.10.3.62.4(BAP - BOI Items: Gear Motor (79531)) | RAJ K MAJHI | [42 empty] | 79165
| 1.9.10.3.62.5(BAP - BOI Items: Inter Locks (79972)) | RAJESH PATHAK | [42 empty] | 79166
| 1.9.10.3.62.6(BAP - BOI Items: Insulation wool (79567)) | R K RAMAN | [42 empty] | 79167
| 1.9.10.3.62.7(BAP - BOI Items: Aluminium Cladding Sheet (89615)) | R.K. SAXENA | [42 empty] | 79168
| 1.9.10.3.62.8(BAP - BOI Items: PANEL TYPE HOPPER HEATERS & ACCESSORIES (79591)) | RAHUL KUMAR S | [42 empty] | 79172
| 1.9.10.3.62.9(BAP - BOI Items: LT SWITCH BOARD (79577)) | RKSRIDHARAN | [42 empty] | 79173
| 1.9.10.4(Erection) | R K VACHAK | [42 empty] | 79174
| 1.9.10.4.1( First 3 Nos Pass) | R L BHABHAR | [42 empty] | 79177
| 1.9.10.4.2( Last 3 Nos Pass) | RANI RL | [42 empty] | 79178
| 1.10(Turbo-generator & Auxiliaries) | R MAHESWARAN | [42 empty] | 79180
| 1.10.2(PH -Civil / Structural Steel Work) | RAHUL NIMESH | [42 empty] | 79181
| 1.10.2.25(STG Foundation (TG Raft & Deck)) | ROHAN KUMAR TRIP | [42 empty] | 79189
| 1.10.2.25.1(Civil Work) | ROHIT KUMAR | [42 empty] | 79190
| 1.10.2.25.1.3(COLUMN & DECK CASTING WORK WITH STAGING) | ROHIT AGARWAL | [42 empty] | 79191
| 1.10.2.26(PH AB & BC bay civil works) | ROHITH | [42 empty] | 79192
| 1.10.2.26.1(Civil Work) | OP-1.6 | [42 empty] | 79195
| 1.10.2.26.1.1(Excavation & PCC) | ROSHAN LAL SAHU | [42 empty] | 79301
| 1.10.2.26.1.2(Raft casting) | ROSHANDEWANGAN | [42 empty] | 79305
| 1.10.2.26.1.3(Pedestals (Till Bolt Lift)) | ROUNAQUE BARAI | [42 empty] | 79306
| 1.10.2.27(D, E, F bay civil Work) | ROUSHAN KUMAR | [42 empty] | 79308
| 1.10.2.27.1(Civil Work) | PADMANABHAN | [42 empty] | 79309
| 1.10.2.27.2(Foundations) | RPDAS | [42 empty] | 79310
| 1.10.2.28(PH - Structural Steel Work(Supply by Trichy)) | RAJENDRA PRASAD | [42 empty] | 79311
| 1.10.2.28.1(Civil Work) | RPRAVEEN | [42 empty] | 79313
| 1.10.2.28.1.1(Columns Fabrication works) | RAKESHRANJAN | [42 empty] | 79314
| 1.10.2.28.1.2(Column Erection works) | RRIJU BASU | [42 empty] | 79315
| 1.10.2.28.1.3(FABRICATION of floor beams(Supply-Trichy)) | RAJIBRANJAN | [42 empty] | 79316
| 1.10.2.28.1.4(Erection of Floor Beams) | RRSHARMA | [42 empty] | 79317
| 1.10.2.28.2(PH Slab Casting & Roof) | RSBALAJI | [42 empty] | 79319
| 1.10.2.28.3(Grade slab level 0.00 Mtr) | REVTI SHARAN | [42 empty] | 79320
| 1.10.2.28.4(CW pit) | R SHIBIN | [42 empty] | 79321
| 1.10.2.28.5(Oil Canal) | R S PUJARI | [42 empty] | 79322
| 1.10.3(Steam Turbine) | RAJEEV | [42 empty] | 79323
| 1.10.3.1(Civil) | RAHUL TOPPO | [42 empty] | 79324
| 1.10.3.1.2(LPBP Foundation) | RUPESH KUMAR | [42 empty] | 79325
| 1.10.3.2(Supply) | R VIJAYA GOWRI | [42 empty] | 79326
| 1.10.3.2.1(TG embedment) | RITESH YADAV | [42 empty] | 79328
| 1.10.3.2.2( Base Plate Assembly) | S GANGOPADH | [42 empty] | 79330
| 1.10.3.2.3( Bearing Pedestals (Front, HP-IP, IP-LP & LP-Gen.)) | S K BHARGAVA | [42 empty] | 79331
| 1.10.3.2.4( LP Inner Casing) | S RAHMAN | [42 empty] | 79332
| 1.10.3.2.5( LP Outer Casing) | SDGOSWAMI | [42 empty] | 79337
| 1.10.3.2.6( LP Rotor) | SANJAY GOEL | [42 empty] | 79341
| 1.10.3.2.7( HP Turbine) | SANDEEP SAXENA | [42 empty] | 79342
| 1.10.3.2.8( IP Turbine) | SABYASACHICHOWDH | [42 empty] | 79343
| 1.10.3.2.9( Cross Around Pipe) | SACHIN KUMAR | [42 empty] | 79344
| 1.10.3.2.10(ESV & CV and Overload Valve) | SACHIN | [42 empty] | 79345
| 1.10.3.2.11(BOI- LP by Pass LPBP(HWR)) | SAGALA GIRIDHAR | [42 empty] | 79346
| 1.10.3.2.12(BOI- Turbine Integral piping TIP(PC-Chennai)) | SURAJSAHA | [42 empty] | 79347
| 1.10.3.2.13(BOI- Oil Module(HWR)) | SAHILARORA | [42 empty] | 79348
| 1.10.3.2.14(IV & CV) | SAHIL | [42 empty] | 79349
| 1.10.3.2.15(Suspension of LPBP Valves) | SAIBAL | [42 empty] | 79350
| 1.10.3.2.16(Instruments & JBs) | SAIFULLAH VM | [42 empty] | 79355
| 1.10.3.2.17(TG C&I Package) | BLSAINI | [42 empty] | 79357
| 1.10.3.2.18(Compensator) | SAJAL | [42 empty] | 79359
| 1.10.3.2.19(Balance BOIs) | SAKUMAR | [42 empty] | 79360
| 1.10.3.3(Erection) | SAMARESH MANDAL | [42 empty] | 79361
| 1.10.3.3.1( PEDESTAL RELATED WORK) | SAMARESH GHOSH | [42 empty] | 79362
| 1.10.3.3.2( HP TURBINE) | SAMARTH GUPTA | [42 empty] | 79363
| 1.10.3.3.3( IP TURBINE) | SAMIR KUMAR | [42 empty] | 79365
| 1.10.3.3.4( LP TURBINE) | SAMRENDRA | [42 empty] | 79366
| 1.10.3.3.5( MISCELLANEOUS ACTIVITIES) | SAN | [42 empty] | 79367
| 1.10.3.3.6( LUBE OIL SYSTEM) | SANDEEP.KR | [42 empty] | 79368
| 1.10.3.3.7( VALVES) | SANDEEP SHARMA | [42 empty] | 79372
| 1.10.3.3.7.1( LP BYPASS VALVES) | SANDEEPKUMAR | [42 empty] | 79373
| 1.10.3.3.7.2( EMERGENCY STOP VALVES) | SANDEEP LODH | [42 empty] | 79374
| 1.10.3.3.7.3( IV CONTROL VALVES) | SANDEEP KUMAR SI | [42 empty] | 79377
| 1.10.3.3.7.4(HP BYPASS VALVES) | SANDIP_S | [42 empty] | 79378
| 1.10.4(Generator) | ASANGUGANESH | [42 empty] | 79380
| 1.10.4.1(Civil) | SANILKUMAR | [42 empty] | 79381
| 1.10.4.2(Supply) | SANJAYSAHA | [42 empty] | 79390
| 1.10.4.2.1( Foundation Accessories) | SANJAY_KR | [42 empty] | 79392
| 1.10.4.2.2( Generator Stator) | SANJAY GUHA | [42 empty] | 79401
| 1.10.4.2.3( Generator Rotor ) | SANJAYKUMAR | [42 empty] | 79405
| 1.10.4.2.4(Brushless Exciter Set & accessories) | SANJAY MEENA | [42 empty] | 79406
| 1.10.4.2.5(Gen. completing items) | SANJEEV | [42 empty] | 79408
| 1.10.4.2.6(Gen. Auxiliaries Systems) | SANJEEV K MUDALI | [42 empty] | 79409
| 1.10.4.2.7(TG Piping) | SANJEEVSRIVASTAV | [42 empty] | 79410
| 1.10.4.2.8(PW System equipments) | SANJEEV_KUMAR | [42 empty] | 79411
| 1.10.4.2.9(Loose instruments) | SANJEEV97 | [42 empty] | 79413
| 1.10.4.3(Erection) | SANJ | [42 empty] | 79414
| 1.10.4.3.1( MECHANICAL ASSEMBLY STATOR AND ROTOR) | SANJEEV KUMAR | [42 empty] | 79415
| 1.10.4.3.2( EXCITATION SYSTEM) | SANJIB KUMAR | [42 empty] | 79416
| 1.10.4.3.3( PW SYSTEM) | SANTHOSHN | [42 empty] | 79417
| 1.10.4.3.4( SEAL OIL SYSTEM) | SANTOSHKSINGH | [42 empty] | 79419
| 1.10.5(Condenser & Vacuum system) | SANTOSH MAHTO | [42 empty] | 79420
| 1.10.5.1(Civil) | S K CHAUDHARY | [42 empty] | 79421
| 1.10.5.1.1(Condenser Foundation) | SANTOSH KUMAR | [42 empty] | 79422
| 1.10.5.2(Supply) | SANTOSHNAIR | [42 empty] | 79423
| 1.10.5.2.1(Hot Well and bottom plate) | SANTOSHKP | [42 empty] | 79424
| 1.10.5.2.2(Condenser Support) | SAPNA RAO | [42 empty] | 79425
| 1.10.5.2.3(Side Walls & Internal details) | CSARAVANAN | [42 empty] | 79426
| 1.10.5.2.4(Water box & Water chamber) | SARAVANANGA | [42 empty] | 79428
| 1.10.5.2.5(Dome Walls & Dome internals) | PSHASHIKANTH | [42 empty] | 79430
| 1.10.5.2.6(LPH-1 supports & other Condenser loose items ) | SATENDERKUMAR | [42 empty] | 79431
| 1.10.5.2.7(Gland Steam Condenser & LPH-1) | SATISH | [42 empty] | 79432
| 1.10.5.2.8(Loose items of GSC & LPH-1) | SATISHKUMAR | [42 empty] | 79437
| 1.10.5.2.9(Condenser Instruments) | SATYAJIT ROY | [42 empty] | 79441
| 1.10.5.2.10(BPL - RE Joints) | SATYANC | [42 empty] | 79442
| 1.10.5.2.11(BPL - Flash Tank) | SAURABH SRIVASTA | [42 empty] | 79443
| 1.10.5.2.12(BPL - Misc. Tank) | SAURABH RUNGTA | [42 empty] | 79444
| 1.10.5.3(Erection) | SAURABH. | [42 empty] | 79445
| 1.10.6(Power Cycle Pumps) | SAURABH KUMAR | [42 empty] | 79446
| 1.10.6.1(Turbine Driven Boiler Feed Pump & Booster Pump) | SAURABH HANDA | [42 empty] | 79447
| 1.10.6.1.1(Civil) | SAURABH KHARE | [42 empty] | 79448
| 1.10.6.1.1.1(First TDBFP Foundation) | SAYAN ROY | [42 empty] | 79449
| 1.10.6.1.1.2(Second TDBFP Foundation) | SARA | [42 empty] | 79450
| 1.10.6.1.2(Supply) | SHABEER DEWAN | [42 empty] | 79455
| 1.10.6.1.2.1(HYD- TURBINE DRIVEN BOOSTER PUMP) | SIDDHARTHA B | [42 empty] | 79457
| 1.10.6.1.2.2(HYD- TURBINE DRIVEN BOILER FEED PUMP) | SB KUMAR | [42 empty] | 79459
| 1.10.6.1.2.3(HYD- BFP DRIVE TURBINE) | SBNAITHANI | [42 empty] | 79460
| 1.10.6.1.2.4(HYD- BFP DT LUB OIL SYSTEM) | SUNDARBRATA | [42 empty] | 79461
| 1.10.6.1.3(Erection) | SANDEEP SINGH BU | [42 empty] | 79462
| 1.10.6.1.3.1(First TURBINE DRIVEN BFP) | SBVERMA | [42 empty] | 79463
| 1.10.6.1.3.2(Second TURBINE DRIVEN BFP) | S C VARSHNEY | [42 empty] | 79465
| 1.10.6.2(Motor Driven Boiler Feed Pumps and Booster Pumps) | SL-1.12 | [42 empty] | 79466
| 1.10.6.2.1(Civil) | SANJAYC | [42 empty] | 79467
| 1.10.6.2.1.1(MDBFP Foundation) | SCJHA | [42 empty] | 79468
| 1.10.6.2.2(Supply) | S C VERMA | [42 empty] | 79472
| 1.10.6.2.2.1(HYD - MOTOR DRIVEN BOOSTER PUMP) | SIDDHARTHA DAS | [42 empty] | 79473
| 1.10.6.2.2.2(HYD - MOTOR DRIVEN BOILER FEED PUMP) | S D SINGH | [42 empty] | 79474
| 1.10.6.2.2.3(BPL - BFP Motor) | CHANDRA | [42 empty] | 79477
| 1.10.6.2.3(Erection) | SEMI SKILLED | [42 empty] | 79478
| 1.10.6.3(Condensate Extraction Pump) | SSETHURAM | [42 empty] | 79480
| 1.10.6.3.1(Civil) | SOMESHWARGAIKWAD | [42 empty] | 79481
| 1.10.6.3.2(Supply) | S GANGULY | [42 empty] | 79489
| 1.10.6.3.2.1(HYD -Condensate EXTRACT PUMP) | SHAHEEN EQUBAL | [42 empty] | 79490
| 1.10.6.3.2.2(HYD - DRIP PUMP) | SHAHID ANSARI | [42 empty] | 79491
| 1.10.6.3.2.3(BPL - CEP Motor) | SHALIML | [42 empty] | 79492
| 1.10.6.3.3(Erection) | SHAKILKUMAR | [42 empty] | 79495
| 1.10.7(Misc. Horizontal Pump) | SHAKTIKANT | [42 empty] | 79797
| 1.10.7.1(Civil) | SHANKAR NARAYAN | [42 empty] | 79801
| 1.10.7.1.1( Boiler Fill Pump & Hot well Make up Pump Foundation) | SHANKAR N VANKAD | [42 empty] | 79805
| 1.10.7.1.2( SG DMCW Pump foundation) | SHANKAR | [42 empty] | 79806
| 1.10.7.1.3( TG DMCW Pump foundation: EXCAVATION) | AMIT SHARMA | [42 empty] | 79808
| 1.10.7.1.4( ACW Pump foundation: EXCAVATION) | SHASHANK | [42 empty] | 79809
| 1.10.7.2(Supply (BHEL PEM)) | SHASHIBHUSHAN | [42 empty] | 79810
| 1.10.7.3(Erection) | SASHI KAPOOR RAI | [42 empty] | 79811
| 1.10.8(HP/LP Heaters & Deaerator) | R SHEKAR | [42 empty] | 79813
| 1.10.8.1(HP Heaters) | HARIHARA | [42 empty] | 79814
| 1.10.8.1.1(Civil) | SHIIVAM KUMAR | [42 empty] | 79815
| 1.10.8.1.2(Supply) | SHIV DUTT SHA | [42 empty] | 79816
| 1.10.8.1.2.1(HYD - HP Heaters) | SHIVENDRA SINGH | [42 empty] | 79817
| 1.10.8.1.3(Erection) | SHIVJYOTI M | [42 empty] | 79819
| 1.10.8.2(LP Heaters) | SHIVOM AGARWAL | [42 empty] | 79820
| 1.10.8.2.1( Civil) | SHREEDHAR T | [42 empty] | 79821
| 1.10.8.2.2(Supply) | SHSAHIL ARORA | [42 empty] | 79822
| 1.10.8.2.2.1( HYD - LP Heaters) | S TEMBHURNE | [42 empty] | 79823
| 1.10.8.2.3(Erection) | ASHISHKUMARSHUKL | [42 empty] | 79824
| 1.10.8.3(Deaerator) | PUNIT SHUKLA | [42 empty] | 79825
| 1.10.8.3.1( Civil) | SHUSHIL KUMAR | [42 empty] | 79826
| 1.10.8.3.2(Supply) | SHUVA | [42 empty] | 79828
| 1.10.8.3.2.1( HYD - Deaerator) | SHYAM BIHARI JAI | [42 empty] | 79830
| 1.10.8.3.2.2( HYD - Drain Cooler) | B SHYAM BABU | [42 empty] | 79831
| 1.10.8.3.3(Erection) | SHYAM | [42 empty] | 79832
| 1.10.9(Dosing System) | SIDDHARTHA | [42 empty] | 79837
| 1.10.9.1(Chemical Dosing System) | M SIMHACHALAM | [42 empty] | 79842
| 1.10.9.1.1(Civil) | BK SINGH | [42 empty] | 79843
| 1.10.9.1.2(Supply (BHEL PEM)) | JPSINGH | [42 empty] | 79844
| 1.10.9.1.3(Erection) | RAHULSINGH | [42 empty] | 79845
| 1.10.9.2(Oxygen Dosing System) | V SREENIVASULU | [42 empty] | 79846
| 1.10.9.2.1(Civil) | SISODIA | [42 empty] | 79847
| 1.10.9.2.2(Supply (BHEL PEM)) | SHIVAKAMASUNDARI | [42 empty] | 79848
| 1.10.9.2.3(Erection) | SIVAKRISHNABALLA | [42 empty] | 79849
| 1.10.10(PLATE HEAT EXCHANGERS) | VSIVARAM | [42 empty] | 79850
| 1.10.10.1(Civil) | R SIVA | [42 empty] | 79855
| 1.10.10.1.1( SG PHE foundation) | K S KRISHNA PRAS | [42 empty] | 79857
| 1.10.10.1.2( TG PHE foundation:) | SAURABH JOHRI | [42 empty] | 79859
| 1.10.10.2(Supply (BHEL PEM)) | SK BISWAS | [42 empty] | 79860
| 1.10.10.3(Erection) | SK GUPTA | [42 empty] | 79861
| 1.10.11(Auxiliary PRDS) | SK MAHAJAN | [42 empty] | 79862
| 1.10.11.1(Supply BOI-PEM) | SK SAXENA | [42 empty] | 79863
| 1.10.11.2(Erection) | SKAGARWAL | [42 empty] | 79865
| 1.10.12(Online Condenser Tube Cleaning System) | SKCHOUDHARY | [42 empty] | 79866
| 1.10.12.1(Supply, BHEL PEM) | SK.DAS | [42 empty] | 79867
| 1.10.12.1.1( COLTCS ) | P.SARAVANA KUMAR | [42 empty] | 79868
| 1.10.12.2(Erection) | SKANDSHIV BHARDW | [42 empty] | 79874
| 1.11(Piping & Valves) | SK BHAUMIK | [42 empty] | 79877
| 1.11.1(Supply) | SUJITK | [42 empty] | 79878
| 1.11.1.1(BHEL PC (PG 80 & 81)) | SANJAY GUPTA | [42 empty] | 79880
| 1.11.1.1.1(For Non Drainable HT) | S K GURUMUKHI | [42 empty] | 79881
| 1.11.1.1.1.3(MS FROM SUPERHEATER TO BOILER STOP VALVE (PGMA-80300)) | SANDIP | [42 empty] | 79890
| 1.11.1.1.1.4(H AND S FOR Hydro TEST - (PGMA 80920)) | SH SHAILENDRA K | [42 empty] | 79891
| 1.11.1.1.1.5(IMPORTED ELECTRODES- (PGMA -80-992)) | KODAPE SUNIL | [42 empty] | 79895
| 1.11.1.1.1.6(Misc. Erection MATLS- (PGMA -80-993)) | SKMAHATO | [42 empty] | 79897
| 1.11.1.1.2(For BLU) | SKMANDAL | [42 empty] | 79901
| 1.11.1.1.2.3(AUX STEAM HEADER- (PGMA -80-340)) | S K MANDI | [42 empty] | 79905
| 1.11.1.1.2.4(80341 AUX STEAM HEADER INTERCONN. BET UNITS) | SKMARADI | [42 empty] | 79906
| 1.11.1.1.2.5( NON DDR - FLOW NOZZLE- (PGMA -80-326)) | SURYA | [42 empty] | 79908
| 1.11.1.1.2.6(AUX STEAM TO SCAPH- (PGMA -80-342)) | SKROY | [42 empty] | 79909
| 1.11.1.1.2.7(AUX STEAM TO AH SOOT BLOWERS- (PGMA -80-343)) | SUVRAKANTISARKAR | [42 empty] | 79910
| 1.11.1.1.2.8(AUX STEAM TO DEAERATING HEATER- (PGMA -80-345)) | SHEKHAR | [42 empty] | 79911
| 1.11.1.1.2.9(AUX STEAM HEADER SV EXHAUST- (PGMA -80-373)) | SANJK | [42 empty] | 79913
| 1.11.1.1.2.10(CONDENSATE SUCTION- (PGMA -80-400)) | SKSOMANI | [42 empty] | 79914
| 1.11.1.1.2.11(CD FROM PUMP TO LPH1/DC INLET TEE AND RE- (PGMA -80-401)) | SUNILTIWARI | [42 empty] | 79915
| 1.11.1.1.2.12(CD FROM LPH1/DC INLET TEE TO TG TP- (PGMA -80-402)) | SKUMAR | [42 empty] | 79916
| 1.11.1.1.2.13(CD FROM TG TP TO DEAERATING HEATER- (PGMA -80-403)) | SANJAY K | [42 empty] | 79917
| 1.11.1.1.2.14(CONDENSATE FOR SEALING OF VACUUM- (PGMA -80-407)) | S LAKSHMI NARAYA | [42 empty] | 79919
| 1.11.1.1.2.15(CONDENSATE DUMP FROM HEADER- (PGMA -80-408)) | SNEHASIS MAN | [42 empty] | 79920
| 1.11.1.1.2.16(CONDENSATE TRANSFER- (PGMA -80-412)) | SMKRISHNA | [42 empty] | 79921
| 1.11.1.1.2.17(ERECTION MATERIALS FOR INSTRUMENTS- (PGMA -80-418)) | SMOHIT | [42 empty] | 79922
| 1.11.1.1.2.18(DEAERATOR SAFETY VALVE EXHAUST TO ATM- (PGMA -80-419)) | S M RAMANATHAN | [42 empty] | 79923
| 1.11.1.1.2.19(BOILER FEED PUMP SUCTION- (PGMA -80-420)) | SMURALI | [42 empty] | 79924
| 1.11.1.1.2.20(BOILER FEED PUMP RECIRCULATION- (PGMA -80-421)) | S MURUGAN | [42 empty] | 79925
| 1.11.1.1.2.21(BOILER FEED PUMP TO HPH INCLUDING BYPASS- (PGMA -80-423)) | SN MONDAL | [42 empty] | 79926
| 1.11.1.1.2.22(BFD BETWEEN HTRS AND GROUP PROTECTION- (PGMA -80-424)) | SUNIL_KUMAR | [42 empty] | 79928
| 1.11.1.1.2.23(BFD FROM FINAL HPH TO SG TP- (PGMA -80-425)) | S.N MONDAL | [42 empty] | 7993
| 1.11.1.1.2.24(SPRAY WATER TO HPBP- (PGMA -80-430)) | S N PRASAD | [42 empty] | 79930
| 1.11.1.1.2.25(UNLISTED SPRAY WATER - SG SCOPE- (PGMA -80-434)) | SHYAMNARAYAN | [42 empty] | 79931
| 1.11.1.1.2.26(SPRAY WATER FROM BFP INTERSTAGE- (PGMA -80-433)) | SOMNATH MISHRA | [42 empty] | 79932
| 1.11.1.1.2.27(DEAERATING HEATER OVER FLOW AND DRAIN- (PGMA -80-446)) | SONU | [42 empty] | 79937
| 1.11.1.1.2.28(BOILER INTEGRAL PIPING DRAINS- (PGMA -80-451)) | SOUGATASAHA | [42 empty] | 79941
| 1.11.1.1.2.29(HP PIPING DRAINS - SG SCOPE- (PGMA -80-452)) | SOURABH G | [42 empty] | 79942
| 1.11.1.1.2.30(LP PIPING DRAINS - SG SCOPE- (PGMA -80-453)) | SOURAJ | [42 empty] | 79943
| 1.11.1.1.2.31(SCAPH DRAINS- (PGMA -80-454)) | SPARIDA | [42 empty] | 79944
| 1.11.1.1.2.32(DRAIN FROM UNLISTED EQPT/VESSEL-SG SCOPE- (PGMA -80-455)) | SANJAY PRADHAN | [42 empty] | 79945
| 1.11.1.1.2.33(SG AUX COOLING WATER UNIT SYSTEM- (PGMA -80-460)) | SPTRPATHI | [42 empty] | 79946
| 1.11.1.1.2.34(PC - TG AUX COOLING WATER- (PGMA -80-463)) | PRAKASH YADAV | [42 empty] | 79947
| 1.11.1.1.2.35(PC - MAIN CIRCULATION WATER PIPING- (PGMA -80-468)) | SRAHMAN | [42 empty] | 79948
| 1.11.1.1.2.36(PC - MISCELLANEOUS COOLING WATER (PGMA - 80 - 469)) | SHAFIQUR | [42 empty] | 79949
| 1.11.1.1.2.37(PC - BOILER WATER WASH TO AND FROM UNIT- (PGMA -80-471)) | SRAVI | [42 empty] | 79950
| 1.11.1.1.2.38(PC - DEMINERALISED WATER SYSTEM- (PGMA -80-473)) | S RAVI | [42 empty] | 79955
| 1.11.1.1.2.39(PC - SERVICE WATER PIPING- (PGMA -80-477)) | SRIKANTH | [42 empty] | 79957
| 1.11.1.1.2.40(PC - FIRE WATER-OTHER AREAS- (PGMA -80-480)) | SREENU | [42 empty] | 79959
| 1.11.1.1.2.41(PC - CONTROL OIL PIPING (PGMA -80-484)) | SRINIVASAN S | [42 empty] | 79960
| 1.11.1.1.2.42(PC - LOW PRESSURE DOSING PIPING- (PGMA -80-601)) | PSRINIVAS | [42 empty] | 79961
| 1.11.1.1.2.43(PC - ACID CLEANING PIPING-TEMPORARY (PGMA - 80-604)) | SSRIVATSAN | [42 empty] | 79962
| 1.11.1.1.2.44(PC - SERVICE AIR-COMP SUCT AND DIS TO RECEI- (PGMA -80-610)) | S R SAHOO | [42 empty] | 79963
| 1.11.1.1.2.45(PC - SERVICE AIR FOR INDIVIDUAL UNITS- (PGMA -80-612)) | SUMITSACHDEVA | [42 empty] | 79965
| 1.11.1.1.2.46(PC - INST AIR COMP SUC AND DIS TO RECEIVER- (PGMA -80-614)) | SHYAMAL SAHA | [42 empty] | 79966
| 1.11.1.1.2.47(PC - INSTRUMENT AIR FOR INDIVIDUAL UNIT- (PGMA -80-616)) | SUMIT SAHAY | [42 empty] | 79967
| 1.11.1.1.2.48(PC - FUEL OIL Supply AND RETURN PIPING- (PGMA -80-650)) | SHIVRAJ BANSALA | [42 empty] | 79968
| 1.11.1.1.2.49(PC - H AND S FOR LP PIPING- (PGMA -80-933)) | SUBRATASEN | [42 empty] | 79972
| 1.11.1.1.2.50(PC - SUB DELIVERY VALVES FOR LIGHT UP- (PGMA -80-901)) | SCHANDRASHEKHAR | [42 empty] | 79973
| 1.11.1.1.2.51(PC - H AND S FOR LIGHT UP STEAM LINE- (PGMA -80-921)) | SSREENI | [42 empty] | 79974
| 1.11.1.1.2.52(PC - H&S FOR TEMPORARY PIPING ACID AND ALKALI (PGMA -80-926)) | SSREENIVASAN | [42 empty] | 79977
| 1.11.1.1.2.53(PC - H&S FOR TEMPORARY PIPING - STEAM BLOWING (PGMA -80-927)) | SANDEEPSRIVASTAV | [42 empty] | 79978
| 1.11.1.1.2.54(PC - H AND S FOR BOILER LIGHT UP - TG- (PGMA -80-928)) | NTPC_TALCHER | [42 empty] | 79980
| 1.11.1.1.2.55(PC - CW STORAGE TANK 16-25 CUM- (PGMA -81-036)) | SSUB | [42 empty] | 79981
| 1.11.1.1.2.56(PC - SPECIAL TANKS AND VESSELS- (PGMA -81-060)) | SANJEEV TIGGA | [42 empty] | 79988
| 1.11.1.1.2.57(PC - COOLING WATER PUMP- (PGMA -81-110)) | STORE KEEPER | [42 empty] | 79989
| 1.11.1.1.2.58(PC - FIX COM FOR MISCELLANEOUS PPG INSULATION- (PGMA -81-318)) | SUBHASCHAKRABORT | [42 empty] | 79990
| 1.11.1.1.2.59(PC - MINERAL WOOL MATTRESS- (PGMA -81-325)) | S K YADAV | [42 empty] | 79991
| 1.11.1.1.2.60(PC - SEALING COMPOUND FOR INSL- (PGMA -81-341)) | SUBRATASIT | [42 empty] | 79995
| 1.11.1.1.2.61(PC - ALUMINIUM CLADDING FOR INSULATION- (PGMA -81-350)) | SUDHANSHU KUMAR | [42 empty] | 79996
| 1.11.1.1.2.62(PC - DIRECT GAUGES FOR STEAM LINES- (PGMA -81-411)) | PSUDHIRBABU | [42 empty] | 79997
| 1.11.1.1.2.63(PC - DIRECT GAUGES FOR NON-STEAM LINES- (PGMA -81-412)) | SUDHIR KUMAR ROY | [42 empty] | 80277
| 1.11.1.1.2.64(PC - LOCAL CONTROL EQPT FOR NON-STEAM LINES- (PGMA -81-414)) | CSUGUNA | [42 empty] | 80278
| 1.11.1.1.2.65(PC - TEST THERMOWELLS- (PGMA -81-415)) | SUKANTHA BISWAS | [42 empty] | 80279
| 1.11.1.1.2.66(PC - INSTRUMENTATION FOR STARTUP SYSTEM- (PGMA -81-417)) | SUKESH MAZUMDER | [42 empty] | 80300
| 1.11.1.1.3(For SB) | SUMANMONDAL | [42 empty] | 80301
| 1.11.1.1.3.3(PC - MS FROM BOILER STOP VALVE TO ESV- (PGMA -80-301)) | SUMANTA C | [42 empty] | 80303
| 1.11.1.1.3.4(PC - MS FROM ESV TO TURBINE (PGMA - 80-302)) | SUMITCHAKRABORTY | [42 empty] | 80304
| 1.11.1.1.3.5(PC - MS HEADER TO AUX PRDS- (PGMA -80-303)) | SUMIT.T | [42 empty] | 80307
| 1.11.1.1.3.6(PC - MS HEADER TO HPBP VALVE- (PGMA -80-304)) | SUMIT AGRAWAL | [42 empty] | 80310
| 1.11.1.1.3.7(PC - HRH FROM REHEATER TO INTERCEPTOR VALVE- (PGMA -80-310)) | SUMITH B | [42 empty] | 80312
| 1.11.1.1.3.8(PC - LPBP VALVE UPSTREAM AND DOWNSTREAM- (PGMA -80-312)) | SUMIT | [42 empty] | 80320
| 1.11.1.1.3.9(PC - PERMANENT STEAM BLOWING (PGMA - 80-319)) | SUMITVERMA | [42 empty] | 80321
| 1.11.1.1.3.10(PC - CRH FROM TURBINE TO REHEATER- (PGMA -80-320)) | SUNIL | [42 empty] | 80322
| 1.11.1.1.3.11(PC - HPBP VALVE TO CRH PIPING- (PGMA -80-321)) | SUNIL KUMAR | [42 empty] | 80323
| 1.11.1.1.3.12(PC - STEAM TO BFP DRIVE TURBINE- (PGMA -80-323)) | SUNIL SHARMA | [42 empty] | 80324
| 1.11.1.1.3.13(PC - CRH HEADER TO AUX.PRDS- (PGMA -80-324)) | SUPERVISOR | [42 empty] | 80326
| 1.11.1.1.3.14(PC - H AND S FOR CRITICAL PPG(BLR & TG AREA)- (PGMA -80-830)) | SUPHAL | [42 empty] | 80329
| 1.11.1.1.3.15(PC - AUX STRUCTURE FOR CRITICAL PIPING-SG- (PGMA -80-940)) | SUPRAJIT ROY | [42 empty] | 80331
| 1.11.1.1.4(For SYN) | SURAJ | [42 empty] | 80332
| 1.11.1.1.4.3(PC - HP AND LP BYPASS WARM UP- (PGMA -80-307)) | SURENDRA PRASAD | [42 empty] | 80334
| 1.11.1.1.4.4(PC - CRH PIPING TO DEAERATING HEATER- (PGMA -80-322)) | SURESH | [42 empty] | 80335
| 1.11.1.1.4.5(PC - EXTRACTION STEAM TO BFP DRIVE TURBINE- (PGMA -80-329)) | N SURESH | [42 empty] | 80336
| 1.11.1.1.4.6(PC - EXTRACTION STEAM TO LP HEATER-2- (PGMA -80-331)) | SURESHSRIVASTAVA | [42 empty] | 80337
| 1.11.1.1.4.7(PC - EXTRACTION STEAM TO LP HEATER-3- (PGMA -80-332)) | SURESH SHARMA | [42 empty] | 80338
| 1.11.1.1.4.8(PC - EXTRACTION STEAM TO LP HEATER-4- (PGMA -80-333)) | SURVEYOR | [42 empty] | 80339
| 1.11.1.1.4.9(PC - EXTRACTION STEAM TO LP HEATER-5 (PGMA - 80334)) | SUSHANTA | [42 empty] | 80340
| 1.11.1.1.4.10(PC - EXTRACTION STEAM TO DEAERATING HEATER- (PGMA -80-335)) | SUSHANT NAYAK | [42 empty] | 80341
| 1.11.1.1.4.11(PC - EXTRACTION STEAM TO HP HEATER NO.1- (PGMA -80-336)) | SUSHANT TIWARI | [42 empty] | 80342
| 1.11.1.1.4.12(PC - EXTRACTION STEAM TO HP HEATER-2- (PGMA -80-337)) | SUSHILKRMAHATO | [42 empty] | 80343
| 1.11.1.1.4.13(PC - EXTRACTION STEAM TO HP HEATER-3- (PGMA -80-338)) | SUVANKAR SARKAR | [42 empty] | 80344
| 1.11.1.1.4.14(PC - AUX STEAM TO BFD TURBINE- (PGMA -80-339)) | SHAILENDRA KUMAR | [42 empty] | 80345
| 1.11.1.1.4.15(PC - AUX STEAM TO GLAND SEALS - TG SCOPE- (PGMA -80-349)) | SHIVKESH MEENA | [42 empty] | 80349
| 1.11.1.1.4.16(PC - AUX STEAM TO UNLISTED USERS - SG SCOPE- (PGMA -80-351)) | SVSRINIVASAN | [42 empty] | 80351
| 1.11.1.1.4.17(PC - EXHAUST STEAM FROM PRIME MOVERS-TG SCOPE- (PGMA -80-363)) | SWAMY NAIDU L | [42 empty] | 80355
| 1.11.1.1.4.18(PC - HP DRAIN FLASH TANK VENT TO ATMOSPHERE- (PGMA -80-370)) | SWAPNIL | [42 empty] | 80363
| 1.11.1.1.4.19(PC - DRAIN FLASH TANK VENT TO CONDENSER- (PGMA -80-371)) | GSYAMSUNDAR | [42 empty] | 80370
| 1.11.1.1.4.20(PC - UNLISTED SV EXHAUSTS - TG SCOPE- (PGMA -80-375)) | SYEDSAADATALI | [42 empty] | 80371
| 1.11.1.1.4.21( PC - HPH SV EXHAUST TO FLASH TANK- (PGMA -80-379)) | SL-1.6 | [42 empty] | 80373
| 1.11.1.1.4.22(PC - HP HEATER VENTS - TG SCOPE- (PGMA -80-381)) | PMGTAMAL | [42 empty] | 80375
| 1.11.1.1.4.23(PC - LP HEATER VENTS- (PGMA -80-382)) | TANMAY | [42 empty] | 80379
| 1.11.1.1.4.24(PC - VENT FROM UNLISTED PPG/EQPT TO COND- (PGMA -80-385)) | TANWER | [42 empty] | 80381
| 1.11.1.1.4.25(STEAM BLOWING PIPING-TEMPORARY (PGMA - 80-399)) | TAPAN VIKAS | [42 empty] | 80382
| 1.11.1.1.4.26(PC - UNLISTED SPRAY WATER - TG SCOPE- (PGMA -80-435)) | TAPAS NAYAK | [42 empty] | 80385
| 1.11.1.1.4.27(PC - CONTROL OIL PIPING ESV & IV- (PGMA -80-482)) | TAPISH KUMAR | [42 empty] | 80388
| 1.11.1.1.4.28(PC - GLAND STEAM COOLER DRAINS- (PGMA -80-442)) | T PRASAD | [42 empty] | 80395
| 1.11.1.1.4.29(PC - LP HEATER-1 TO CONDENSER- (PGMA -80-443)) | TARSEMLAL | [42 empty] | 80399
| 1.11.1.1.4.30(PC - LP HEATER-2/3/4/5 DRAINS AND DRIP PUMP I- (PGMA -80-444)) | TARUNARYA | [42 empty] | 80400
| 1.11.1.1.4.31(PC - HP HEATER DRAINS- (PGMA -80-447)) | TARUNG | [42 empty] | 80401
| 1.11.1.1.4.32(PC - DRAIN FROM UNLISTED EQPT/VESSEL-TG SCOPE- (PGMA -80-448)) | TARUNNIG | [42 empty] | 80402
| 1.11.1.1.4.33(PC - TG CYCLE PIPING DRAINS AND VENTS- (PGMA -80-449)) | TAUSEEF AHMED | [42 empty] | 80403
| 1.11.1.1.4.34(PC - MANIFOLDS FOR HP FLASH BOX AND CONDENS- (PGMA -80-457)) | TDUTTA | [42 empty] | 80407
| 1.11.1.1.4.35(PC - HP FLASH TANK DRAIN TO CONDENSER- (PGMA -80-459)) | T DUTTA | [42 empty] | 80408
| 1.11.1.1.4.36(PC - DRINKING WATER PIPING- (PGMA -80-478)) | SL-1.15 | [42 empty] | 80412
| 1.11.1.1.4.37(PC - HP FLASH TANK VENT TO CONDENSER- (PGMA -80-493)) | TEST USER_1905 | [42 empty] | 80418
| 1.11.1.1.4.38(PC - LP FLASH TANK VENT TO CONDENSER- (PGMA -80-494)) | TEST USER1 | [42 empty] | 80419
| 1.11.1.1.4.39(PC - LP FLASH TANK DRAIN TO COND- (PGMA -80-495)) | TEST_NTPC | [42 empty] | 80420
| 1.11.1.1.4.40(PC - LP Condensate PIPING WITHIN TG HALL FOR- (PGMA -80-545)) | SL-1.1 | [42 empty] | 80421
| 1.11.1.1.4.41(PC - LUB OIL FLUSHING & PR TESTING (PGMA - 80-673)) | THAKUR | [42 empty] | 80423
| 1.11.1.1.4.42(PC - H AND S FOR SYNCHRONISATION - TG- (PGMA -80-930)) | THOMASXA | [42 empty] | 80424
| 1.11.1.1.4.43(PC - CLEAN DRAIN FLASH TANK - DIA 1500 MM- (PGMA -81-012)) | TILAK CHAKRABO | [42 empty] | 80425
| 1.11.1.1.4.44(PC -Condensate TRANSFER PUMP- (PGMA -81-100)) | JOYS JULIUS TIRK | [42 empty] | 80430
| 1.11.1.1.4.45(PC - PERFORMANCE GUARANTEE TEST MATERIALS- (PGMA -81-416)) | TKBAGCHI | [42 empty] | 80431
| 1.11.1.1.4.46(BOI-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN ) | CHIRANJEEVI T K | [42 empty] | 80433
| 1.11.1.1.4.47(BOI-PEM - THERMAL INSULATION -ANCILLARY MATERIAL ) | TRIBHUWA | [42 empty] | 80434
| 1.11.1.1.4.48(BOI-PEM - ALUMINIUM SHEETS/COILS) | T K RAY | [42 empty] | 80435
| 1.11.1.1.4.49( BOI- PEM - AIR TRAPS ) | KRISHNA | [42 empty] | 80436
| 1.11.1.1.4.50(PEM - STEAM TRAPS ) | TOKEN ORI | [42 empty] | 80439
| 1.11.1.2(Valves) | TP SREENIVASAN | [42 empty] | 80442
| 1.11.1.2.1(Supply) | T.P.SRINIVASAN | [42 empty] | 80443
| 1.11.1.2.1.1(TRYV - Power Cycle Piping, DM. Water & Lube Oil System Valves ( PGMA - 80913)) | TRAUNNIGAM | [42 empty] | 80444
| 1.11.1.2.1.2(TRYV - Turbine Integral Piping system Valves( PGMA - 80919)) | TRINADHA | [42 empty] | 80446
| 1.11.1.2.1.3(TRYV - Extraction Line QCNRVs( PGMA - 80918)) | NAVEEN | [42 empty] | 80447
| 1.11.1.2.1.4(TRYV - HP Bypass System - Oil Supply System Valves( PGMA - 22100)) | TRIPURARI | [42 empty] | 80448
| 1.11.1.2.1.5(TRYV - HP Bypass System - HP Bypass valve ASSY valves( PGMA - 22101)) | TAJINDER SINGH | [42 empty] | 80449
| 1.11.1.2.1.6(TRYV - HP Bypass System - Oil Piping HP Bypass Valves( PGMA - 22600)) | TSKANISH | [42 empty] | 80451
| 1.11.1.2.1.7(TRYV - HP Bypass System - Common HP Oil Piping Valves( PGMA - 22601)) | TSMURALI | [42 empty] | 80452
| 1.11.1.2.1.8(TRYV - HP Bypass System - Hand Tools( PGMA - 22701)) | TEJPAL SINGH | [42 empty] | 80453
| 1.11.1.2.1.9(TRYV - HP Bypass System - Special Equipments( PGMA - 22889)) | T S VARADARAJAN | [42 empty] | 80454
| 1.11.1.2.1.10(TRYV - HP Bypass System - Common Spares( PGMA - 22988)) | TULASI RAM | [42 empty] | 80455
| 1.11.1.2.1.11(TRYV - Root Valves (Normal Measurement+PG Test) ( PGMA - 80914)) | TUSHAR SAXENA | [42 empty] | 80457
| 1.11.1.2.1.12(TRYV - SG Integral Piping Valves ( PGMA - 80905)) | TELANG | [42 empty] | 80459
| 1.11.1.2.1.13(TRYV - Low Pressure piping valves ( PGMA - 80277)) | U K PANDA | [42 empty] | 80460
| 1.11.1.2.1.14(TRYV - Heat Exchanger and Fabrication Water Expansion Relief Valves (WERV)( PGMA - 80278)) | U REVISANKARAN | [42 empty] | 80463
| 1.11.1.2.1.15(TRYV - BFP Drive Turbine Valves including SRV and QCNRV's ( PGMA - 80279)) | UDHAYA BHASKAR V | [42 empty] | 80468
| 1.11.1.2.1.16(TRYV - Acid Cleaning Valves ( PGMA - 80917)) | UJJWAL DEB | [42 empty] | 80471
| 1.11.1.2.1.17(TRYV - Steam Blowing Valves ( PGMA - 80918)) | UDYA NAIK | [42 empty] | 80473
| 1.11.1.2.1.18(BOI-PEM - BUTTERFLY VALVES (STEAM SERVICE) ) | UMESH | [42 empty] | 80477
| 1.11.1.2.1.19(BOI-PEM - BALL VALVES ) | UMESHKUMARGUPTA | [42 empty] | 80478
| 1.11.1.2.1.20(BOI-PEM - AIR RELEASE VALVES ) | UMESH MENON | [42 empty] | 80480
| 1.11.1.2.1.21(BOI-PEM - LUBE OIL TRANSFER PUMPS) | UMESH KUMAR SHAR | [42 empty] | 80493
| 1.11.1.2.1.22(BOI-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS) | UNIT USER | [42 empty] | 80494
| 1.11.1.2.1.23(BPL - Butterfly Valve) | UNSKILLED | [42 empty] | 80495
| 1.11.2(Erection) | UTTAM | [42 empty] | 80545
| 1.11.2.1( DRIP LINES AND DRAINS) | UTKARSH | [42 empty] | 80601
| 1.11.2.2( HRH PIPING) | UTTAM SINGH | [42 empty] | 80604
| 1.11.2.3( LP AND HP BYPASS PIPING) | V K VERM | [42 empty] | 80610
| 1.11.2.4(Condensate PIPING) | V M GANIGI | [42 empty] | 80612
| 1.11.2.5( BOILER FEED LINE PIPING) | V V S S SUNDAR | [42 empty] | 80614
| 1.11.2.6( MAIN STEAM PIPING) | V V SUNDAR | [42 empty] | 80616
| 1.11.2.7( EXTRACTION PIPING) | VIPULAGRAWAL | [42 empty] | 80650
| 1.11.2.8( CRH PIPING) | VAIBHAV | [42 empty] | 80673
| 1.12(Electrical) | VANAJA | [42 empty] | 80830
| 1.12.4(Civil) | VANLAL PANA VANL | [42 empty] | 80901
| 1.12.4.1(TRANSFORMER YARD) | VARRI SATHIBABU | [42 empty] | 80905
| 1.12.4.1.1(GENERATOR TRANSFORMER FOUNDATION) | NEERAJVARSHNEY | [42 empty] | 80913
| 1.12.4.1.2(STATION TRANSFORMER FOUNDATION) | VARUN GUPTA | [42 empty] | 80914
| 1.12.4.1.3(Service power transformer) | VENDOR1 | [42 empty] | 80917
| 1.12.4.1.4(Unit Aux Transformer) | VENDOR1_D | [42 empty] | 80918
| 1.12.4.1.5(Misc. Service Transformer) | VENDOR2 | [42 empty] | 80919
| 1.12.4.1.6(UNIT TRANSFORMER FOUNDATION) | VENDOR2_D | [42 empty] | 80920
| 1.12.4.1.7(STATION AUXILLARY TRANSFORMER FOUNDATION) | VENKAT AGRAWAL | [42 empty] | 80921
| 1.12.4.3(SPBD Pedestals FOUNDATION) | VENKATA | [42 empty] | 80926
| 1.12.4.4(MV SwitchGear Room) | VENKATESHWARRAO | [42 empty] | 80927
| 1.12.4.5(LT SwitchGear Room) | MUKESH VERMA | [42 empty] | 80928
| 1.12.4.6(UPS & Battery Room) | GIRISH KUMAR | [42 empty] | 80930
| 1.12.4.7(IPBD Pedestals FOUNDATION) | V G RATHOD | [42 empty] | 80933
| 1.12.4.8(ESP/FGD Control Room) | VIBHU SHARMA | [42 empty] | 80935
| 1.12.4.8.1(Up to Plinth Level) | VIDYASAGAR | [42 empty] | 80936
| 1.12.4.8.2(up to First Floor) | VIJAY KANDA | [42 empty] | 80937
| 1.12.4.8.3(Up to 2nd Floor) | VIJAYSARODE | [42 empty] | 80940
| 1.12.4.8.4(Up to Third Floor & Roof) | VIJAYSINGH.RAWAT | [42 empty] | 80941
| 1.12.5(Supply) | VIKAS GAURAV | [42 empty] | 80942
| 1.12.5.1(JHS - 25 MVA Service Power Transformer) | VIKAS PATIL | [42 empty] | 80992
| 1.12.5.2(JHS - 16 MVA Unit Aux Transformer) | VIKAS KAMAL | [42 empty] | 80993
| 1.12.5.3(JHS - 7.5 MVA Misc. Service Transformer) | VIKAS YADAV | [42 empty] | 81036
| 1.12.5.4(JHS - UNIT TRANSFORMER) | VIKAS BANSWAL | [42 empty] | 81041
| 1.12.5.5(JHS - Dry Type Transformer (DTT)) | VIKASGAURAV | [42 empty] | 81060
| 1.12.5.6(JHS - HVR) | VIKASHKUMAR | [42 empty] | 81100
| 1.12.5.7(BPL - Generator Transformer) | VIKASKUKREJA | [42 empty] | 81110
| 1.12.5.8(BPL - HT Switchgear) | VIKASPATIL | [42 empty] | 81318
| 1.12.5.9(BPL - Station Transformer) | VIKAS KUMAR SONI | [42 empty] | 81325
| 1.12.5.10( BPL - GRP) | VIMAL KUMAR | [42 empty] | 81341
| 1.12.5.11(RUDR - SPBD) | VIMAL | [42 empty] | 81350
| 1.12.5.11.1(Main Supply) | VINAY KUMA | [42 empty] | 81411
| 1.12.5.11.2(BOIs-SPBD) | VINAY KUMAR | [42 empty] | 81412
| 1.12.5.12(RUDR - IPBD) | VINAYKUMAR | [42 empty] | 81414
| 1.12.5.12.1(Main Supply) | VINAY KUMAR GUPT | [42 empty] | 81415
| 1.12.5.12.2(BOIs-IPBD) | VINEET DUBEY | [42 empty] | 81416
| 1.12.5.13(SBU - LV Switchgear & L V Bus Duct) | VINEET JAIN | [42 empty] | 81417
| 1.12.5.14(BOI- PEM - DC BATTERY CHARGER ) | VINOD KUMAR | [42 empty] | 81441
| 1.12.5.15(BOI-PEM - CABLE TRAYS & ACC. ) | VINOD_KUMAR | [42 empty] | 81444
| 1.12.5.16(BOI-PEM - ABOVE GROUND EARTHING MATERIALS EXCEPT CHP, AHP & SWITCHYARD) | VINODJACOB | [42 empty] | 87010
| 1.12.5.17(BOI-PEM - CABLE TERM.& JOINT KITS ) | VINODM | [42 empty] | 87100
| 1.12.5.18(BOI-PEM - TREFOIL CLAMPS ) | VINEET YADAV | [42 empty] | 87150
| 1.12.5.19(BOI- PEM - LT PVC CONTROL CABLE) | VIPUL | [42 empty] | 87200
| 1.12.5.20(BOI-PEM - DC Lead Acid/Nicad Battery) | VIPUL VERMA | [42 empty] | 87300
| 1.12.5.21(BOI-PEM - Electrical Lab (Calibration and diagnostics)) | ASVISHAL | [42 empty] | 87930
| 1.12.5.22(BOI-PEM - Electrical Lab (Metering and testing)) | VISHNU JYOTI GVV | [42 empty] | 87950
| 1.12.5.23(BOI-PEM - FIRE SEALING SYSTEM ) | VISHNUKUMARAGARW | [42 empty] | 87960
| 1.12.5.24(BOI-PEM - CABLE TRAY SUPPORT SYSTEM - BOLTABLE) | VIVEK KUMAR | [42 empty] | 89610
| 1.12.5.25(BOI-PEM - HT XLPE CABLES ) | VIVEK21 | [42 empty] | 89611
| 1.12.5.26(BOI- PEM - LT XLPE POWER CABLE ) | VIVEK DUDU | [42 empty] | 89612
| 1.12.5.27(BOI-PEM - SCREENED CONTROL CABLES ) | VIVEKA NAND JHA | [42 empty] | 89613
| 1.12.5.28(BOI-PEM - MS ROD FOR BELOW GROUND EARTHING ) | VIVEKSHARMA | [42 empty] | 89614
| 1.12.5.29(BOI-PEM - NEUTRAL GROUNDING RESISTOR ) | VIVEK HEMROM | [42 empty] | 89615
| 1.12.5.30(BOI-PEM - OIL FILLED SERVICE TRANSFORMER ) | VKARYA | [42 empty] | 95088
| 1.12.5.31(BOI-PEM - STATION LIGHTING SYSTEM ) | VINAY KATARIA | [42 empty] | 95089
| 1.12.5.31.1(Lighting Poles and Masts,) | VIJAY KUMAR CHUG | [42 empty] | 95091
| 1.12.5.31.2(Lighting Distribution Boards) | VKRAI | [42 empty] | 95485
| 1.12.5.31.3(Lighting Fixtures, Lamps & Misc. Items.) | V K SINGH | [42 empty] | 95487
| 1.12.5.31.4(Lighting PVC wires) | V K KUHIKAR | [42 empty] | 95488
| 1.12.5.31.5(Lighting Rigid Steel Conduits) | KVENKATESWARLU | [42 empty] | 95489
| 1.12.6(Erection) | V K VERMA | [42 empty] | 95988
| 1.12.6.1(Station Transformer, Service power transformer, Unit Transformer & Misc. Service Transformer) | VMGANIGI | [42 empty] | 96186
| 1.12.6.2(SP BUS DUCTS OF STATION BOARDS (0BA,0BB,0CC&0CB) AND RELATED TIE'S FOR UNIT BOARDS (6BA,6BB)) | VINAYNIGAM | [42 empty] | 96188
| 1.12.6.3(HT SWITCH GEARS (Station and Unit Boards)) | VASANTH RAO JAD | [42 empty] | 96193
| 1.12.6.4(SERVICE & UNIT AUXILLARY TRANSFORMERS) | M VIJAYA RAJU | [42 empty] | 96588
| 1.12.6.5(HT SWITCH GEARS (Unit Auxiliary Boards and Station Auxiliary Boards (6CA, 0CA) 3.5 M EL) | VISHWAJEET | [42 empty] | 97084
| 1.12.6.6(LT SWITCHGEAR MCC,LT Transformers and LT Bus Ducts., LT Transformers and LT Bus Ducts.) | VSAGAR | [42 empty] | 97097
| 1.12.6.7(220 V MAIN PLANT DC BATTERY SYSTEM) | VIKASSAHU | [42 empty] | 97098
| 1.12.6.10(Unit AUX Transformer) | VIJAY | [42 empty] | 97282
| 1.12.6.11(GENERATOR TRANSFORME (R/Y/B)) | VIRENDRAWAHANE | [42 empty] | 97284
| 1.12.6.12(UNIT TRANSFORMERS) | WORKERS | [42 empty] | 97285
| 1.12.6.13(STATION TRANSFORMERS) | MOHD YAMEEN | [42 empty] | 97287
| 1.12.6.14(SP BUS DUCTS OF UNIT BOARDS AND RELATED TIE'S) | YATENDER | [42 empty] | 97297
| 1.12.6.15(IP BUS DUCTS) | YATINDRA MOHAN | [42 empty] | 97298
| 1.12.6.17(ESP Charging) | YING | [42 empty] | 97407
| 1.12.6.18(HT SWITCH GEARS FOR AHP,CHP, Fire along with Associated Auxiliary Transformers.) | KESAVA RAO YARAJ | [42 empty] | 97577
| 1.13(Control & Instrumentation) | YKVERMA | [42 empty] | 97584
| 1.13.1(Civil) | YOGENDER PAL | [42 empty] | 97585
| 1.13.1.1(Main Control Room) | YOGESH GUPTA | [42 empty] | 97590
| 1.13.2(Supply) | YOGESH PATEL | [42 empty] | 97591
| 1.13.2.1(BHEL EDN) | Y PRASANNA | [42 empty] | 97592
| 1.13.2.1.1(DAVR PACKAGE) | YS. SINGH | [42 empty] | 97593
| 1.13.2.1.2(SG C&I PACKAGE ) | RYUVARAJ | [42 empty] | 97596
| 1.13.2.1.3(TG C&I PACKAGE ) | [43 empty] | 97599
| 1.13.2.1.4(HMI) | [43 empty] | 99099
| 1.13.2.1.5(Station C&I) | [43 empty] | 99100
| 1.13.2.1.6(Offsite C&I) | [43 empty] | 99300
| 1.13.2.1.7(FIELD INSTRUMENTS and erection MATERIALS) | [43 empty] | 99400
| 1.13.2.1.8(CABLES AND CABLE TRAY) | [43 empty] | 99501
| 1.13.2.1.9(CCTV) | [43 empty] | 99502
| 1.13.2.1.10(LVS) | [43 empty] | 99512
| 1.13.2.1.11(UPS & ACDB) | [43 empty] | 99514
| 1.13.2.1.12(UPS BATTERY) | [43 empty] | 99600
| 1.13.2.1.13(CHARGER FOR BATTERY) | [43 empty] | AI101
| 1.13.2.1.14(MASTER SLAVE CLOCK) | [43 empty] | AI102
| 1.13.2.1.15(HART MANAGEMENT SYSTEM) | [43 empty] | AI103
| 1.13.2.1.16(TURBINE SUPERVISORY SSTEM) | [43 empty] | AI104
| 1.13.2.1.17(ANALYZERS AND MEASURING INSTRUMENTS INCLUDING SOx , NOx ) | [43 empty] | AI105
| 1.13.2.1.18(HMI BOIs AND DIGITAL TECHNOLOGIES) | [43 empty] | AI201
| 1.13.2.2(BOI- PEM) | [43 empty] | AI202
| 1.13.2.2.1(BOI-PEM CONTROL VALVE ) | [43 empty] | AI203
| 1.13.2.2.2(BOI- PEM-FLOW ELEMENT - NOZZLE ) | [43 empty] | AI301
| 1.13.2.2.3(BOI-PEM-FLOW ELEMENT - ORIFICE ) | [43 empty] | AI303
| 1.13.2.2.4(BOI-PEM-ULTRASONIC FLOW METER) | [43 empty] | BOI
| 1.13.2.2.5(BOI-PEM-ELECTROMAGNETIC FLOW METER) | [43 empty] | BPL01FTXX01
| 1.13.2.2.6(BOI-PEM-ROTAMETER ) | [43 empty] | BPL01MTXX01
| 1.13.2.3(BHEL TRY) | [43 empty] | BPL01REJX01
| 1.13.2.3.1(Blr. Control and Instrumentation) | [43 empty] | BPL04BFPM01
| 1.13.2.3.1.1(Boiler Fuel Firing Controls (PG-95)) | [43 empty] | BPL04CEPM01
| 1.13.2.3.1.1.1(FSSS FLAME SCANNER (PGMA-95088)) | [43 empty] | BPL04CWPM01
| 1.13.2.3.1.1.2(FSSS FLAME SCANNER (PGMA-95088)) | [43 empty] | BPL04FDFM01
| 1.13.2.3.1.1.3(FSSS FIELD INTERCONNECTING EQUIPMENTS (PGMA-95091)) | [43 empty] | BPL04IDFM01
| 1.13.2.3.1.1.4(GRAVIMETRIC FEEDER REMOTE POWER CABINET (PGMA-95485)) | [43 empty] | BPL04MMXX01
| 1.13.2.3.1.1.5(UCB MOUNTED INSTS & CALIBRATION KIT (PGMA-95487)) | [43 empty] | BPL04PAFM01
| 1.13.2.3.1.1.6(FEEDER MOUNTED C&I EQUIPMENTS (PGMA-95488)) | [43 empty] | BPL06GTXX01
| 1.13.2.3.1.1.7(COAL FLOW MONITER (PGMA-95489)) | [43 empty] | BPL09GRPX01
| 1.13.2.3.1.1.8(FUEL FIRING CONTROL COMMISSIONING SPARE (PGMA-95988)) | [43 empty] | BPL09HTSG01
| 1.13.2.3.1.2(Boiler House Auxiliaries Control (PG-96)) | [43 empty] | C104
| 1.13.2.3.1.2.1(SOOT BLOWER MOTOR CONTROL CENTRE (PGMA-96186)) | [43 empty] | C112
| 1.13.2.3.1.2.2(FURNACE TEMPARATURE PROBE STARTER BOX (PGMA-96188)) | [43 empty] | C116
| 1.13.2.3.1.2.3(MISCELLANEOUS STARTER BOX (PGMA-96193)) | [43 empty] | C216
| 1.13.2.3.1.3(Boiler Instruments and Misc. Controls (PG-97)) | [43 empty] | C300
| 1.13.2.3.1.3.1(INSTRUMENTATION FIELD TRANSMITTERS (PGMA-97097)) | [43 empty] | C304
| 1.13.2.3.1.3.2(BOI-LU-FLOWMETERS (PGMA-97282)) | [43 empty] | C308
| 1.13.2.3.1.3.3(FIELD GAUGES (PGMA-97284)) | [43 empty] | C312
| 1.13.2.3.1.3.4(FIELD SWITCHES (PGMA-97285)) | [43 empty] | C316
| 1.13.2.3.1.3.5(INST & ACC IN STEAM,WATER,SB SYSTEM (PGMA-97287)) | [43 empty] | C324
| 1.13.2.3.1.3.6(MTM CLAMPS AND PADS (PGMA-97297)) | [43 empty] | CE/1276-PE1-58-01
| 1.13.2.3.1.3.7(MTM THERMO COUPLES & JUNCTION BOXES (PGMA-97298)) | [43 empty] | CE/1276-PE1-58-02
| 1.13.2.3.1.3.8(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | [43 empty] | CE/1276-PE2-58-01
| 1.13.2.3.1.3.9(ACOUSTIC STEAM LEAK DETECTOR SYTEM (PGMA-97585)) | [43 empty] | CE/1276-PE3-58-01
| 1.13.2.3.1.3.10(ERECTION MATERIALS (PGMA-97590)) | [43 empty] | CE/1276-PE3-58-02
| 1.13.2.3.1.3.11(MISCELLANEOUS ITEMS (PGMA-97591)) | [43 empty] | CE/1276-PE4-58-01
| 1.13.2.3.1.3.12(PNEUMATIC TUBINGS & FITTINGS,AIRSET (PGMA-97592)) | [43 empty] | CE/1276-PE5-58-01
| 1.13.2.3.1.3.13(CLOSED CIRCUIT TELEVISION SYSTEM (PGMA-97596)) | [43 empty] | CE/1276-PM1-58-01
| 1.13.2.3.1.3.14(PNEUMATIC ACTUATOR IN AIR&FLUE GAS SYS (PGMA-97599)) | [43 empty] | CE/1276-PM1-58-02
| 1.13.3(Erection) | [43 empty] | CE/1276-PM2-58-01
| 1.13.3.2(MAIN CONTROL ROOM) | [43 empty] | CE/1276-PM2-58-02
| 1.13.3.3(BOILER OPERATING FLOOR (AB Elevation)) | [43 empty] | CE/1276-PM3-58-01
| 1.13.3.4(SADC) | [43 empty] | CE/1276-PM3-58-02
| 1.13.3.5(FD FAN) | [43 empty] | CE/1276-PM4-58-01
| 1.13.3.5.1(First FD Fan) | [43 empty] | CE/1276-PM4-58-02
| 1.13.3.5.2(Second FD Fan) | [43 empty] | CE/1276-PM5-58-01
| 1.13.3.6(ID FAN) | [43 empty] | CE/1276-PM5-58-02
| 1.13.3.6.1(First ID Fan) | [43 empty] | CE/1276-PR1-39-01
| 1.13.3.6.2(Second ID Fan) | [43 empty] | CE/1276-PR1-56-01
| 1.13.3.7(APH) | [43 empty] | CE/1276-PR1-57-01
| 1.13.3.7.1(First APH) | [43 empty] | CE/1276-PR1-62-01
| 1.13.3.7.2(Second APH) | [43 empty] | CE/1276-PR2-39-01
| 1.13.3.8(SCANNER FAN) | [43 empty] | CE/1276-PR2-56-01
| 1.13.3.9(INSTRUMENTATION FOR BLU) | [43 empty] | CE/1276-PR2-57-01
| 1.13.3.11(BOILER OPERATING FLOOR (CD Elevation)) | [43 empty] | CE/1276-PR3-39-01
| 1.13.3.13(BOILER OPERATING FLOOR (EF Elevation)) | [43 empty] | CE/1276-PR3-56-01
| 1.13.3.14(MDBFP) | [43 empty] | CE/1276-PR3-57-01
| 1.13.3.16(Boiler C&I Required for Synchronisation) | [43 empty] | CE/1276-PR4-39-01
| 1.13.3.17(TG C&I READINESS FOR BARRING GEAR) | [43 empty] | CE/1276-PR4-56-01
| 1.13.3.18(TG C&I READINESS FOR SYNCHRONISATION) | [43 empty] | CE/1276-PR4-57-01
| 1.13.3.19(C&I READINESS FOR COAL FIRING) | [43 empty] | CE/1276-PR5-39-01
| 1.13.3.19.1(PA FAN) | [43 empty] | CE/1276-PR5-56-01
| 1.13.3.19.1.1(Second PA Fan) | [43 empty] | CE/1276-PR5-57-01
| 1.13.3.19.1.2(First PA Fan:) | [43 empty] | CE/1276-PSC-57-01
| 1.13.3.19.2(MILLS) | [43 empty] | CE/1276-PSE-58-01
| 1.13.3.19.2.1(Mills) | [43 empty] | CE/1276-SH1-39-01
| 1.13.3.19.3(SEAL AIR FAN) | [43 empty] | CE/1276-SH1-39-02
| 1.13.3.19.4(Boiler C&I Required for Coal Firing) | [43 empty] | CE/1276-SH1-48-01
| 1.13.3.19.5(TDBFP) | [43 empty] | CE/1276-SH1-50-01
| 1.14(BOP Systems) | [43 empty] | CE/1276-SH1-50-02
| 1.14.1(Chimney) | [43 empty] | CE/1276-SH1-50-03
| 1.14.1.4(Chimney- CIVIL Work) | [43 empty] | CE/1276-SH1-50-04
| 1.14.1.4.2(Chimney- Reinforcement fixing & Raft segment casting) | [43 empty] | CE/1276-SH1-50-05
| 1.14.1.4.6(Chimney- Shell Casting includes platforms & door openings) | [43 empty] | CE/1276-SH1-50-06
| 1.14.1.7(Chimney- Inner supporting structure Erection , alignment & fixing in position) | [43 empty] | CE/1276-SH1-50-07
| 1.14.1.8(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining) | [43 empty] | CE/1276-SH1-53-01
| 1.14.1.9(Chimney- Painting of Outer shell structure) | [43 empty] | CE/1276-SH1-56-01
| 1.14.2(NDCT cooling Tower) | [43 empty] | CE/1276-SH1-57-01
| 1.14.2.1( NDCT Execution Agency(Ordering by PEM)) | [43 empty] | CE/1276-SH1-58-01
| 1.14.2.2(Supply for Cooling Tower) | [43 empty] | CE/1276-SH1-58-02
| 1.14.2.3( Cooling Tower Civil Work) | [43 empty] | CE/1276-SH1-58-03
| 1.14.2.3.11( Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift)) | [43 empty] | CE/1276-SH1-58-04
| 1.14.2.3.12(Inner Grillage columns casting) | [43 empty] | CE/1276-SH1-62-01
| 1.14.2.4( Cooling Tower E&C ) | [43 empty] | CE/1276-SH2-39-01
| 1.14.3(Air Conditioning System) | [43 empty] | CE/1276-SH2-48-01
| 1.14.3.2( Air conditioning system Execution Agency) | [43 empty] | CE/1276-SH2-50-01
| 1.14.3.3( Air Conditioning System-Dispatch) | [43 empty] | CE/1276-SH2-50-04
| 1.14.3.4(E&C for AIR CONDITIONING SYSTEM) | [43 empty] | CE/1276-SH2-50-06
| 1.14.4(Air Compressor System) | [43 empty] | CE/1276-SH2-53-01
| 1.14.4.2( Air compressor system Execution Agency) | [43 empty] | CE/1276-SH2-56-01
| 1.14.4.3( Civil) | [43 empty] | CE/1276-SH2-57-01
| 1.14.4.4(Supply-PEM) | [43 empty] | CE/1276-SH2-58-01
| 1.14.4.5(Erection) | [43 empty] | CE/1276-SH2-58-02
| 1.14.5(Water Treatment system ) | [43 empty] | CE/1276-SH2-58-03
| 1.14.5.1(Raw Water Storage Reservoir & Pump house) | [43 empty] | CE/1276-SH2-58-04
| 1.14.5.1.1(Civil) | [43 empty] | CE/1276-SH2-62-01
| 1.14.5.1.1.3(RAW WATER RESERVOIR) | [43 empty] | CE/1276-SH3-39-01
| 1.14.5.1.1.4(RAW WATER CONTROL ROOM) | [43 empty] | CE/1276-SH3-48-01
| 1.14.5.1.1.5(Raw Water Pump House) | [43 empty] | CE/1276-SH3-50-01
| 1.14.5.1.2(Erection) | [43 empty] | CE/1276-SH3-50-02
| 1.14.5.2(Pre-treatment Plant) | [43 empty] | CE/1276-SH3-50-04
| 1.14.5.2.1( PT Plant Execution Agency) | [43 empty] | CE/1276-SH3-50-05
| 1.14.5.2.2(Civil Work) | [43 empty] | CE/1276-SH3-50-06
| 1.14.5.2.2.1( Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume) | [43 empty] | CE/1276-SH3-53-01
| 1.14.5.2.2.2( CLARI FOCULATOR) | [43 empty] | CE/1276-SH3-56-01
| 1.14.5.2.2.3( Chemical House) | [43 empty] | CE/1276-SH3-57-01
| 1.14.5.2.2.4( Pump House) | [43 empty] | CE/1276-SH3-58-01
| 1.14.5.2.3(Supply) | [43 empty] | CE/1276-SH3-58-02
| 1.14.5.2.4(Erection) | [43 empty] | CE/1276-SH3-58-03
| 1.14.5.3(DM Plant) | [43 empty] | CE/1276-SH3-58-04
| 1.14.5.3.4( DM Plant Execution Agency) | [43 empty] | CE/1276-SH3-62-01
| 1.14.5.3.5( Civil Works) | [43 empty] | CE/1276-SH4-39-01
| 1.14.5.3.5.1( Acid alkali Unloading & storage area) | [43 empty] | CE/1276-SH4-48-01
| 1.14.5.3.5.2( DM Plant Building including Vessel Foundation) | [43 empty] | CE/1276-SH4-50-01
| 1.14.5.3.5.3( Neutralization Pit) | [43 empty] | CE/1276-SH4-50-04
| 1.14.5.3.6(Supply for DM Plant) | [43 empty] | CE/1276-SH4-50-06
| 1.14.5.3.7(Erection) | [43 empty] | CE/1276-SH4-53-01
| 1.14.5.4(Effluent Treatment Plant with ZLD) | [43 empty] | CE/1276-SH4-56-01
| 1.14.5.4.1(ETP Execution Agency) | [43 empty] | CE/1276-SH4-57-01
| 1.14.5.4.2(Civil) | [43 empty] | CE/1276-SH4-58-01
| 1.14.5.4.3(Supply) | [43 empty] | CE/1276-SH4-58-02
| 1.14.5.4.4(Erection) | [43 empty] | CE/1276-SH4-58-03
| 1.14.6(Fuel Oil Handling system) | [43 empty] | CE/1276-SH4-58-04
| 1.14.6.4( FO system Execution Agency) | [43 empty] | CE/1276-SH4-62-01
| 1.14.6.5( Civil) | [43 empty] | CE/1276-SH5-39-01
| 1.14.6.5.1(LDO Day Tank Foundation) | [43 empty] | CE/1276-SH5-48-01
| 1.14.6.5.2( FO Pressurizing pump house & Unloading pump house) | [43 empty] | CE/1276-SH5-50-01
| 1.14.6.6(Supply) | [43 empty] | CE/1276-SH5-50-04
| 1.14.6.7(Erection) | [43 empty] | CE/1276-SH5-50-06
| 1.14.7(Site fabricated tank) | [43 empty] | CE/1276-SH5-53-01
| 1.14.7.2(Condensate Storage Tank) | [43 empty] | CE/1276-SH5-56-01
| 1.14.7.2.1(Site fabricated tank execution agency) | [43 empty] | CE/1276-SH5-56-02
| 1.14.7.2.2(Civil Work) | [43 empty] | CE/1276-SH5-57-01
| 1.14.7.2.2.1(Condensate Storage Tank Foundation) | [43 empty] | CE/1276-SH5-58-01
| 1.14.7.2.3(Erection) | [43 empty] | CE/1276-SH5-58-02
| 1.14.8(CW & ACW System) | [43 empty] | CE/1276-SH5-58-03
| 1.14.8.1(Civil Work) | [43 empty] | CE/1276-SH5-58-04
| 1.14.8.1.4( CW Pump House & ACW pump house) | [43 empty] | CE/1276-SH5-62-01
| 1.14.8.1.4.1( CW & ACW Sump & Forebay) | [43 empty] | CE/1276-SHC-56-01
| 1.14.8.1.4.2( Concrete Volute Pump) | [43 empty] | CE/1276-SHC-58-01
| 1.14.8.1.4.3( CW Pump House Building) | [43 empty] | CE/1276-SHC-58-02
| 1.14.8.1.5(CW Channel) | [43 empty] | CE/1276-SHC-58-03
| 1.14.8.2(Supply) | [43 empty] | CE/1276-SHC-58-04
| 1.14.8.2.1(BOI- PEM - MISC.PUMPS (VERTICAL) ) | [43 empty] | CE/1276-SHC-58-05
| 1.14.8.2.2(BOI-PEM - M.E. BELLOWS ) | [43 empty] | CE/1276-SHC-58-06
| 1.14.8.2.3(BOI-PEM - SELF CLEANING STRAINERS ) | [43 empty] | CE/1276-SHC-58-07
| 1.14.8.2.4(BPL - CW Pump Motor) | [43 empty] | CE/1276-SHC-58-08
| 1.14.8.2.5(COOLING WATER PUMP (CV TYPE) -2 Nos (1 No Common for Both Units)) | [43 empty] | CE/1276-SHC-58-09
| 1.14.8.3(Erection) | [43 empty] | CE/1276-SHC-58-10
| 1.14.9(EOT Cranes For PH) | [43 empty] | CE/1276-SHC-58-11
| 1.14.9.1(Supply) | [43 empty] | CE/1276-SHC-62-01
| 1.14.9.1.1(BOI-PEM - D/G EOT CRANE) | [43 empty] | CE/1416-SH6-39-01
| 1.14.9.2(Erection) | [43 empty] | CE/1416-SH6-48-01
| 1.14.10(Ventilation System) | [43 empty] | CE/1416-SH6-50-01
| 1.14.10.2( Ventilation system Execution Agency) | [43 empty] | CE/1416-SH6-50-03
| 1.14.10.3( Ventilation System) | [43 empty] | CE/1416-SH6-50-04
| 1.14.10.4(Supply) | [43 empty] | CE/1416-SH6-53-01
| 1.14.10.4.1(Ventilation System) | [43 empty] | CE/1416-SH6-56-01
| 1.14.10.5(E&C for VENTILATION SYSTEM) | [43 empty] | CE/1416-SH6-57-01
| 1.14.11(Condensate Polishing Unit ) | [43 empty] | CE/1416-SH6-58-01
| 1.14.11.2(Condensate Polishing Unit) | [43 empty] | CE/1416-SH6-58-02
| 1.14.11.3(Civil) | [43 empty] | CE/1416-SH6-58-03
| 1.14.11.4(Supply for Condensate POLISHING SYSTEM) | [43 empty] | CE/1416-SH6-58-04
| 1.14.11.5(E&C for Condensate POLISHING SYSTEM) | [43 empty] | CE/1416-SH6-58-05
| 1.14.12(CW Treatment System) | [43 empty] | CE/1416-SH6-58-06
| 1.14.12.2(Supply) | [43 empty] | CE/1416-SH6-58-07
| 1.14.12.3(Civil) | [43 empty] | CE/1416-SH6-58-08
| 1.14.12.3.1(CW treatment Building including Equipment Foundation) | [43 empty] | CE/1416-SH6-58-09
| 1.14.12.4(Erection) | [43 empty] | CE/1416-SH6-58-10
| 1.14.13(Fire Detection & Protection Sys) | [43 empty] | CE/1416-SH6-58-11
| 1.14.13.1(Supply (BHEL- PESD)) | [43 empty] | CE/1416-SH6-58-12
| 1.14.13.1.1(Hydrant Valve) | [43 empty] | CE/1428-PE1-58-01
| 1.14.13.1.2(Water Monitor & Water cum Foam monitor) | [43 empty] | CE/1428-PE1-58-02
| 1.14.13.1.3(Deluge Valve) | [43 empty] | CE/1428-PM1-58-01
| 1.14.13.1.4(Spray Nozzles) | [43 empty] | CE/1428-PM1-58-02
| 1.14.13.1.5(QBD) | [43 empty] | CE/1428-PR1-56-01
| 1.14.13.1.6(Hose Box) | [43 empty] | CE/1428-PR1-56-02
| 1.14.13.1.7(Foam Branch Pipe) | [43 empty] | CE/1428-PR1-62-01
| 1.14.13.1.8(Inline Balance Proportioner) | [43 empty] | CE/1428-SH1-39-01
| 1.14.13.1.9(Foam Chamber with Deflector) | [43 empty] | CE/1428-SH1-48-01
| 1.14.13.1.10(Fire Hose with Coupling) | [43 empty] | CE/1428-SH1-50-01
| 1.14.13.1.11(Hose Reel) | [43 empty] | CE/1428-SH1-50-02
| 1.14.13.1.12(Branch Pipe with Nozzle) | [43 empty] | CE/1428-SH1-50-03
| 1.14.13.1.13(Foam Concentrated Control Valve) | [43 empty] | CE/1428-SH1-53-01
| 1.14.13.1.14(Solenoid Valve) | [43 empty] | CE/1428-SH1-56-01
| 1.14.13.1.15(Foam Concentrate) | [43 empty] | CE/1428-SH1-57-01
| 1.14.13.1.16(Gun Metal Valve for ARV) | [43 empty] | CE/1428-SH1-58-01
| 1.14.13.1.17(Air Release Valve) | [43 empty] | CE/1428-SH1-58-02
| 1.14.13.1.18(DV LCP) | [43 empty] | CE/1428-SH1-58-03
| 1.14.13.1.19(Sprinkler system) | [43 empty] | CE/1428-SH1-58-04
| 1.14.13.1.20(Pressure Regulating Valve (Foam System)) | [43 empty] | CE/1428-SH1-58-05
| 1.14.13.1.21(Pressure Relief Valve) | [43 empty] | CE/1428-SH1-58-06
| 1.14.13.1.22(Foam Tank) | [43 empty] | CE/1428-SH1-58-07
| 1.14.13.1.23(Air Compressor) | [43 empty] | CE/1428-SH1-58-08
| 1.14.13.1.24(Hydro Pneumatic Tank) | [43 empty] | CE/1428-SH1-58-09
| 1.14.13.1.25(Foam Pump) | [43 empty] | CE/1428-SH1-58-10
| 1.14.13.1.26(Pressure Transmitters) | [43 empty] | CE/1428-SHC-56-01
| 1.14.13.1.27(Pressure Switches) | [43 empty] | CE/1535-PE5-58-01
| 1.14.13.1.28(Level Switches) | [43 empty] | CE/1535-PE5-58-02
| 1.14.13.1.29(Flow Switches) | [43 empty] | CE/1535-PM5-58-01
| 1.14.13.1.30(Pressure Gauges) | [43 empty] | CE/1535-PM5-58-02
| 1.14.13.1.31(Differential pressure Gauges) | [43 empty] | CE/1535-PR5-56-01
| 1.14.13.1.32(Radar Level Transmitters) | [43 empty] | CE/1535-PR5-57-01
| 1.14.13.1.33(IGES Package) | [43 empty] | CE/1535-PR5-62-01
| 1.14.13.1.34(Portable Fire Extinguishers) | [43 empty] | CE/1535-SH5-48-01
| 1.14.13.1.35(Fire Water Pipes) | [43 empty] | CE/1535-SH5-50-01
| 1.14.13.1.36(Fire Fighting System Conventional Valves) | [43 empty] | CE/1535-SH5-53-01
| 1.14.13.1.37(Fire Water Flanges) | [43 empty] | CE/1535-SH5-56-01
| 1.14.13.1.38(Fire Water Butt welded Fittings) | [43 empty] | CE/1535-SH5-57-01
| 1.14.13.1.39(Fire Water Flanged Fittings) | [43 empty] | CE/1535-SH5-58-01
| 1.14.13.1.40(Gaskets) | [43 empty] | CE/1535-SH5-58-02
| 1.14.13.1.41(Bolts, U Bolts, Nuts & Clamps) | [43 empty] | CE/1535-SH5-58-03
| 1.14.13.1.42(Structural Material) | [43 empty] | CE/1535-SH5-58-04
| 1.14.13.1.43(Fire Detection & Alarm System) | [43 empty] | CE/1535-SH5-62-01
| 1.14.13.1.44(Fire Alarm Cables) | [43 empty] | FW201
| 1.14.13.1.45(Fire Protection System PLC) | [43 empty] | FW202
| 1.14.13.1.46(E&C for PLC system) | [43 empty] | FW203
| 1.14.13.1.47(Spares for PLC system) | [43 empty] | FW207
| 1.14.13.1.48(Cable Trays & Accessories) | [43 empty] | FW209
| 1.14.13.1.49(Fire Water Pumps & Auxiliaries) | [43 empty] | FW212
| 1.14.13.1.50(Fire Water Storage Tank) | [43 empty] | FW213
| 1.14.13.1.51(Paint & Primer) | [43 empty] | FW214
| 1.14.13.1.52(Wrapping & Coating for Underground Piping) | [43 empty] | FW215
| 1.14.13.2(Civil ) | [43 empty] | FW216
| 1.14.13.3(Erection) | [43 empty] | FW217
| 1.14.13.3.9(HYDRANT SYSTEM) | [43 empty] | FW218
| 1.14.13.3.10(SPRAY SYSTEM) | [43 empty] | FW219
| 1.14.13.3.11(HVWS SYSTEM FOR TRANSFORMERS) | [43 empty] | FW220
| 1.14.13.3.13(HVWS SYSTEM FOR OIL EQUIPMENTS) | [43 empty] | FW221
| 1.14.13.3.14(HVWS SYSTEM FOR BOILER BURNER FRONT) | [43 empty] | FW222
| 1.14.13.3.15(MVWS - SYSTEM -- ESP 0.0 MTR ELEVATION) | [43 empty] | FW223
| 1.14.13.3.16(MVWS SYSTEM - TG BUILDING CABLE GALLERIES) | [43 empty] | FW224
| 1.14.13.3.17(MVWS SYSTEM FOR DIESEL TANK IN DG HOUSE) | [43 empty] | FW225
| 1.14.13.3.18(FIRE DETECTION SYSTEM) | [43 empty] | FW226
| 1.14.14(Coal Handling Plant) | [43 empty] | FW227
| 1.14.14.1( Civil Works) | [43 empty] | FW228
| 1.14.14.1.10( Track Hopper) | [43 empty] | FW229
| 1.14.14.1.11( CHP Main Control cum MCC Room) | [43 empty] | FW230
| 1.14.14.1.12( CHP MCC Room) | [43 empty] | FW231
| 1.14.14.1.13(Common CHP, LHP & GHP Pump House) | [43 empty] | FW232
| 1.14.14.1.14(CHP Workshop cum office Building ) | [43 empty] | FW233
| 1.14.14.1.15(CHP Dozer Shed) | [43 empty] | FW234
| 1.14.14.1.16(CHP Coal Settling Pond ( CSSP)) | [43 empty] | FW235
| 1.14.14.1.17( Stacker Reclaimer ) | [43 empty] | FW236
| 1.14.14.1.18( Stock Yard) | [43 empty] | FW237
| 1.14.14.1.19( Crusher House) | [43 empty] | FW238
| 1.14.14.1.19.6( Transfer Points) | [43 empty] | FW239
| 1.14.14.1.19.6.1(CHP Transfer Point-1) | [43 empty] | FW240
| 1.14.14.1.19.6.2(CHP Transfer Point-2) | [43 empty] | FW243
| 1.14.14.1.19.6.3(CHP Transfer Point-3 & any additional TPs) | [43 empty] | FW244
| 1.14.14.1.19.6.4(Drive House) | [43 empty] | FW249
| 1.14.14.1.19.7( Conveyor Tunnel) | [43 empty] | FW250
| 1.14.14.1.19.8( Conveyor Galleries with Trestles) | [43 empty] | FW251
| 1.14.14.1.19.8.1( Conveyor Gallery -1A & 1B) | [43 empty] | FW252
| 1.14.14.1.19.8.2( Conveyor Gallery -2A & 2B) | [43 empty] | FW253
| 1.14.14.1.19.8.3( Conveyor Gallery -3A & 3B) | [43 empty] | FW254
| 1.14.14.1.19.8.4( Conveyor Gallery -4A & 4B) | [43 empty] | FW255
| 1.14.14.1.19.8.5( Conveyor Gallery -5A & 5B) | [43 empty] | FW256
| 1.14.14.1.19.8.6( Reversible Yard Conveyor Gallery -6) | [43 empty] | FW257
| 1.14.14.1.19.8.6.7(Cable Trestle/Cable Gallery) | [43 empty] | FW258
| 1.14.14.2(Engineering, Supply &Erection) | [43 empty] | FW259
| 1.14.14.2.3( Track Hopper (Paddle Feeder)) | [43 empty] | FW260
| 1.14.14.2.4( Stacker Reclaimer (Reversible)) | [43 empty] | FW261
| 1.14.14.2.5( Conveyor System for CHP, LHP & GHP (incl. Conv, CR, ACVS, DE & Boiler tripper)) | [43 empty] | FW262
| 1.14.14.2.6( Crusher House (Part of Conv. System)) | [43 empty] | FW263
| 1.14.14.2.7( DS & Water System + BOBR) | [43 empty] | FW264
| 1.14.14.2.8(JHS - 16MVA, 11/3.45 KV CHP AUX Transformer ) | [43 empty] | FW265
| 1.14.15(Ash Handling Plant) | [43 empty] | FW267
| 1.14.15.1( Civil Works) | [43 empty] | FW268
| 1.14.15.1.7( Bottom Ash Hopper) | [43 empty] | FW269
| 1.14.15.1.8(ASH SLURRY PUMP HOUSE) | [43 empty] | FW280
| 1.14.15.1.9(ASH WATER PUMP HOUSE) | [43 empty] | FW281
| 1.14.15.1.10(Compressor House) | [43 empty] | FW282
| 1.14.15.1.11(Fly Ash Silo) | [43 empty] | FW283
| 1.14.15.1.12(Intermediate Silo) | [43 empty] | FW285
| 1.14.15.1.13(Silo Utility Building) | [43 empty] | FW292
| 1.14.15.1.14(Classifier Silo) | [43 empty] | FW293
| 1.14.15.1.15( Pipe Rack (Inside Plant)) | [43 empty] | FW294
| 1.14.15.1.16( Pipe pedestal) | [43 empty] | FW295
| 1.14.15.1.16.6( AHP Main Control cum MCC Room & LHS MCC Room) | [43 empty] | FW296
| 1.14.15.1.16.7( AHP MCC Room) | [43 empty] | FW297
| 1.14.15.2(Engineering, Supply &Erection) | [43 empty] | FW298
| 1.14.15.2.1(Bottom Ash Handling & Coarse Ash Handling System) | [43 empty] | FW299
| 1.14.15.2.1.3(Bottom Ash Hopper, Coarse Ash System, Equipment & Piping from Boiler area to BA Slurry PH) | [43 empty] | FW300
| 1.14.15.2.1.3.4( Equipment Erection) | [43 empty] | FW301
| 1.14.15.2.1.4(Ash water PH, Ash Slurry PH & piping upto plant Boundary) | [43 empty] | FW302
| 1.14.15.2.1.4.4( and RECEIPT) | [43 empty] | FW303
| 1.14.15.2.2( Fly Ash Conveying System) | [43 empty] | FW304
| 1.14.15.2.2.3(Compressor house) | [43 empty] | FW305
| 1.14.15.2.2.3.4( and RECEIPT) | [43 empty] | FW306
| 1.14.15.2.2.4(ESP area) | [43 empty] | FW307
| 1.14.15.2.2.4.4( and RECEIPT) | [43 empty] | FW314
| 1.14.15.2.2.5(Intermediate Silo & Fly Ash Silo Equipment) | [43 empty] | FW322
| 1.14.15.2.2.5.4( and RECEIPT) | [43 empty] | FW371
| 1.14.15.2.3(Fly ash Classifier) | [43 empty] | FW372
| 1.14.15.2.3.4( and RECEIPT) | [43 empty] | FW373
| 1.14.15.2.4(Fly ash Bagging System) | [43 empty] | FW381
| 1.14.15.2.5(JHS - 12.5MVA, 11/3.45 KV AHP AUX Transformer) | [43 empty] | FW382
| 1.14.16(Illumination Package for CHP, AHP, LHP & GHP) | [43 empty] | FW383
| 1.14.17(Electrical: E&C for CHP, AHP, LHP & GHP) | [43 empty] | FW384
| 1.14.18(DG) | [43 empty] | FW386
| 1.14.18.2(Supply) | [43 empty] | FW610
| 1.14.18.2.1(DG Set) | [43 empty] | FW611
| 1.14.18.3(E&C DG SET) | [43 empty] | FW612
| 1.14.19(MILL REJECT SYSTEM) | [43 empty] | FW613
| 1.14.19.1(Supply) | [43 empty] | FW614
| 1.14.19.1.1(MILL REJECT SYSTEM ) | [43 empty] | FW701
| 1.14.19.2(Civil) | [43 empty] | FW702
| 1.14.19.2.1(Conveying Air Compressor Foundation) | [43 empty] | FW705
| 1.14.19.2.2(Silo Structure Foundation) | [43 empty] | FW709
| 1.14.19.3(Erection) | [43 empty] | FW710
| 1.14.20(400kV Switchyard) | [43 empty] | FW711
| 1.14.20.1(Engineering Activities) | [43 empty] | FW712
| 1.14.20.2(Ordering of BOIs - 400 kV Switchyard) | [43 empty] | FW713
| 1.14.20.3(Detailed Engineering for 400 kV Switchyard) | [43 empty] | FW714
| 1.14.20.4(Manufacturing, Testing and Dispatch) | [43 empty] | FW715
| 1.14.20.4.1(400 kV Gas Insulated Switchgear) | [43 empty] | FW716
| 1.14.20.4.2(400 kV CVT) | [43 empty] | FW717
| 1.14.20.4.3(400 kV BPI) | [43 empty] | FW718
| 1.14.20.4.4(336 kV LA) | [43 empty] | FW720
| 1.14.20.4.5(400 kV WT) | [43 empty] | FW721
| 1.14.20.4.6(400 kV Control & Relay Panels and SAS) | [43 empty] | FW722
| 1.14.20.4.7(FOTE) | [43 empty] | FW723
| 1.14.20.4.8(Control & Power Cable) | [43 empty] | FW724
| 1.14.20.4.9(125 MVAr Reactor) | [43 empty] | FW725
| 1.14.20.4.10(Composite Long Rod Insulator) | [43 empty] | FW729
| 1.14.20.4.11(LT Switchgear) | [43 empty] | FW730
| 1.14.20.4.12(Marshalling Kiosk & JBs) | [43 empty] | FW731
| 1.14.20.4.13(Earthing Material) | [43 empty] | FW732
| 1.14.20.4.14(Shield Wire) | [43 empty] | FW733
| 1.14.20.4.15(ACSR Conductor) | [43 empty] | FW734
| 1.14.20.4.16(Al tube) | [43 empty] | FW735
| 1.14.20.4.17(Cable Trench Material) | [43 empty] | FW736
| 1.14.20.4.18(Structures & Hardwares) | [43 empty] | FW737
| 1.14.20.4.19(Battery & Battery Chargers) | [43 empty] | FW738
| 1.14.20.4.20(Auxiliary Transformer) | [43 empty] | FW740
| 1.14.20.4.21(Illumination System) | [43 empty] | FW741
| 1.14.20.4.22(Fire Protection System) | [43 empty] | FW742
| 1.14.20.4.23(Air Conditioning and Ventilation System) | [43 empty] | FW743
| 1.14.20.4.24(EOT Crane) | [43 empty] | FW744
| 1.14.20.4.25(Self Power Hydraulic Aerial Working Platform) | [43 empty] | FW745
| 1.14.20.5(Civil) | [43 empty] | FW746
| 1.14.20.5.2(GIS Building) | [43 empty] | FW747
| 1.14.20.5.3(Control Room) | [43 empty] | FW748
| 1.14.20.5.4(AHU Building) | [43 empty] | FW749
| 1.14.20.6(and Dispatch) | [43 empty] | FW750
| 1.14.21(Station C&I) | [43 empty] | FW751
| 1.14.22(Chlorine Dioxide dosing system) | [43 empty] | FW752
| 1.14.22.2(Award of Execution Agency) | [43 empty] | FW753
| 1.14.22.3( Civil) | [43 empty] | FW754
| 1.14.22.4(Supply) | [43 empty] | FW755
| 1.14.22.5(Erection) | [43 empty] | FW758
| 1.14.23(Pipe Rack and Cable Trestle, Station Piping) | [43 empty] | FW760
| 1.14.23.2(Award of Execution Agency) | [43 empty] | FW761
| 1.14.23.3( Civil) | [43 empty] | FW762
| 1.14.23.4(Supply) | [43 empty] | FW763
| 1.14.23.5(Erection) | [43 empty] | FW765
| 1.14.24(Misc. Elevators) | [43 empty] | FW766
| 1.14.24.1(Supply) | [43 empty] | FW767
| 1.14.24.1.1(Elevator) | [43 empty] | FW768
| 1.14.24.1.2(Civil) | [43 empty] | FW769
| 1.14.24.1.3(Erection) | [43 empty] | FW774
| 1.14.25(Lifting Equipments) | [43 empty] | FW775
| 1.14.25.1(Supply) | [43 empty] | FW776
| 1.14.25.1.1(Lifting Tackles (PG-99)) | [43 empty] | FW779
| 1.14.25.1.1.1(MISC CHAIN PULLEY BLOCKS (PGMA-99099)) | [43 empty] | FW781
| 1.14.25.1.1.2(FAN HANDLING EQUIPMENT (PGMA-99100)) | [43 empty] | FW784
| 1.14.25.1.1.3(CIR PUMP / FEED PUMP HANDLING EQUIPMENT (PGMA-99300)) | [43 empty] | FW785
| 1.14.25.1.1.4(AIRHEATER,STEAMCOIL AIRHEATER HANDLG E (PGMA-99400)) | [43 empty] | FW786
| 1.14.25.1.1.5(FURNACE CRADLE -WALL COVERAGE ELECTR (PGMA-99512)) | [43 empty] | FW787
| 1.14.25.1.1.6(FO SYSTEM HANDLING EQUIPMENT (PGMA-99600)) | [43 empty] | FW789
| 1.14.25.1.1.7(BOI-PEM - CHAIN PULLEY BLOCK ) | [43 empty] | FW790
| 1.14.25.1.1.8(BOI-PEM - ELECTRIC HOIST ) | [43 empty] | FW793
| 1.14.25.1.1.9(BOI-PEM - D/G EOT CRANE (UPTO 100 T) ) | [43 empty] | FW798
| 1.14.25.1.1.10(BOI-PEM - Single Girder EOT / HOT Misc. Cranes ) | [43 empty] | FW800
| 1.14.25.1.2(Erection) | [43 empty] | FW802
| 1.14.26(Misc. Building) | [43 empty] | FW803
| 1.14.26.1(NON PLANT Building) | [43 empty] | FW804
| 1.14.26.1.9(Gate Complex along with CISF Building) | [43 empty] | FW805
| 1.14.26.1.10(Construction office) | [43 empty] | FW806
| 1.14.26.1.11( CANTEEN BUILDING) | [43 empty] | FW807
| 1.14.26.1.12(Fire Station building and Drill Tower) | [43 empty] | FW808
| 1.14.26.1.13(FQA Lab building) | [43 empty] | FW809
| 1.14.26.1.14(CHP office cum Workshop Building) | [43 empty] | FW814
| 1.14.26.1.15(Administration Building) | [43 empty] | FW815
| 1.14.26.1.16(O&M Workshop Building) | [43 empty] | FW816
| 1.14.27(1.4 MWp Solar Rooftop Pkg) | [43 empty] | FW817
| 1.14.27.1(Engineering) | [43 empty] | FW818
| 1.14.27.2(Procurement, Manufacturing & Dispatch) | [43 empty] | FW819
| 1.14.27.4(Erection & Commissioning) | [43 empty] | FW820
| 1.14.28(Aux Boiler) | [43 empty] | FW821
| 1.14.28.2(Foundation Materials and Structure) | [43 empty] | FW822
| 1.14.28.3(Boiler Drums, PG 04) | [43 empty] | FW823
| 1.14.28.4(Pressure Parts, PG 06,07,08,09,10,11,12,19) | [43 empty] | FW824
| 1.14.28.5(Soot Blowers Valves & Fittings, PG 20,21) | [43 empty] | FW825
| 1.14.28.6(Fuel Firing System, PG 41, 42) | [43 empty] | FW826
| 1.14.28.7(Ducts, PG 48) | [43 empty] | FW827
| 1.14.28.8(BAP - Damper FD fan outlet (PGMA 57013)) | [43 empty] | FW828
| 1.14.28.9(BAP - Aux fan (PG 56)) | [43 empty] | FW829
| 1.14.28.10(BAP - CYLINDRICAL Chimney (SELF SUPPORTED)- H-35 M (PG- 87)) | [43 empty] | FW830
| 1.14.28.11(Lining & Insulation, PG 33) | [43 empty] | FW834
| 1.14.28.12(Electrical and C&I, PG 95, 97) | [43 empty] | FW840
| 1.14.29(FGD ) | [43 empty] | FW841
| 1.14.29.1(Engineering) | [43 empty] | FW842
| 1.14.29.2(Gypsum Dewatering building) | [43 empty] | FW845
| 1.14.29.2.1(Engineering &Supply) | [43 empty] | FW848
| 1.14.29.2.1.1(FOUNDATION MATERIALS) | [43 empty] | FW851
| 1.14.29.2.1.2(COLUMNS) | [43 empty] | FW854
| 1.14.29.2.1.3(BEAMS & BRACING) | [43 empty] | FW897
| 1.14.29.2.1.4(FLOOR & PLATFORMS) | [43 empty] | FW988
| 1.14.29.2.1.5(WALL BEAMS) | [43 empty] | FW991
| 1.14.29.2.1.6(STAIRS) | [43 empty] | FW996
| 1.14.29.2.1.7(MISC STRUCTURES) | [43 empty] | FW997
| 1.14.29.2.1.8(Equipments (Sub-Assembly)) | [43 empty] | FW999
| 1.14.29.2.1.9(LIME FEEDING/DOSING SYSTEM) | [43 empty] | HYBM001
| 1.14.29.2.1.10(BOI-PEM- ELEVATORS) | [43 empty] | HYBM002
| 1.14.29.2.2(Civil Works) | [43 empty] | HYBM003
| 1.14.29.2.3(Erection of Structure) | [43 empty] | HYBM005
| 1.14.29.2.4(Erection of Equipment) | [43 empty] | HYBM006
| 1.14.29.2.5(Commissioning of Equipments) | [43 empty] | HYBM007
| 1.14.29.3(Ball Mill Building and Ball Mills) | [43 empty] | HYBM008
| 1.14.29.3.1(Engineering &Supply) | [43 empty] | HYBM009
| 1.14.29.3.1.1(HYD - Wet Ball Mill) | [43 empty] | HYBM010
| 1.14.29.3.1.2(BPL - Ball Mill Motor) | [43 empty] | HYBM011
| 1.14.29.3.1.3(FOUNDATION MATERIALS FOR BALL MILL BLDG) | [43 empty] | HYBM012
| 1.14.29.3.1.4( BALL MILL BLDG COLUMNS) | [43 empty] | HYBM013
| 1.14.29.3.1.5(BALL MILL BUILDING BEAMS & BRACING) | [43 empty] | HYBM014
| 1.14.29.3.1.6(BALL MILL BUILDING FLOOR & PLATFORMS) | [43 empty] | HYBM015
| 1.14.29.3.1.7(BALL MILL BUILDING WALL BEAMS) | [43 empty] | HYBM016
| 1.14.29.3.2(Civil Works) | [43 empty] | HYBM017
| 1.14.29.3.3(Erection) | [43 empty] | HYBM018
| 1.14.29.4(Day Silo) | [43 empty] | HYBM019
| 1.14.29.4.1(Engineering &Supply) | [43 empty] | HYHE001
| 1.14.29.4.1.1( FOUNDATION MATERIALS) | [43 empty] | HYPU001
| 1.14.29.4.1.2(COLUMNS) | [43 empty] | HYPU002
| 1.14.29.4.1.3(BEAMS & BRACING) | [43 empty] | HYPU003
| 1.14.29.4.1.4(FLOOR & PLATFORMS) | [43 empty] | HYPU004
| 1.14.29.4.1.5(WALL BEAMS) | [43 empty] | HYPU005
| 1.14.29.4.1.6(STAIRS) | [43 empty] | HYPU006
| 1.14.29.4.1.7(MISC STRUCTURES) | [43 empty] | HYPU008
| 1.14.29.4.1.8( HYD- LIMESTONE DAY SILO AND ACCESSORIES) | [43 empty] | HYPU009
| 1.14.29.4.2( Civil Works) | [43 empty] | HYPU010
| 1.14.29.4.3(Erection) | [43 empty] | HYPU011
| 1.14.29.5(LHS & GHS System) | [43 empty] | HYPU012
| 1.14.29.5.1(Ordering & Engineering of LHS & GHS) | [43 empty] | HYPU013
| 1.14.29.5.2(Limestone Transfer Point-1) | [43 empty] | HYTC001
| 1.14.29.5.2.1(Equipment Dispatch) | [43 empty] | HYTC002
| 1.14.29.5.2.2(Engineering &Supply of Structure) | [43 empty] | HYTC003
| 1.14.29.5.2.2.1( FOUNDATION MATERIALS LTP1) | [43 empty] | HYTC005
| 1.14.29.5.2.2.2(LTP1 COLUMNS) | [43 empty] | HYTC006
| 1.14.29.5.2.2.3(LTP1 BEAMS & BRACING) | [43 empty] | HYTC007
| 1.14.29.5.2.2.4(LTP1 FLOOR & PLATFORMS) | [43 empty] | HYTC008
| 1.14.29.5.2.2.5( LTP1 WALL BEAMS) | [43 empty] | HYTC009
| 1.14.29.5.2.2.6( LTP1 FASTENERS) | [43 empty] | HYTC010
| 1.14.29.5.2.2.7( LTP1 STAIRS & LADDERS) | [43 empty] | PAI-01310
| 1.14.29.5.2.2.8(LTP1 MISC STRUCTURES) | [43 empty] | PAI-06260
| 1.14.29.5.2.3(Civil Works) | [43 empty] | PAI-06310
| 1.14.29.5.2.4(Erection) | [43 empty] | PAI-06360
| 1.14.29.5.3(ISG- Limestone Truck Tippler ) | [43 empty] | PAI-06510
| 1.14.29.5.3.1(Equipment Dispatch) | [43 empty] | PAI-06560
| 1.14.29.5.3.2(Civil Works) | [43 empty] | PAP-05310
| 1.14.29.5.4(ISG- Surface Feeder) | [43 empty] | PAP-05340
| 1.14.29.5.4.1(Equipment Dispatch) | [43 empty] | PAP-05450
| 1.14.29.5.4.2(Civil Works) | [43 empty] | PAP-06160
| 1.14.29.5.5( Belt Conveyor-1A/B) | [43 empty] | PAP-06460
| 1.14.29.5.5.1(Equipment Dispatch) | [43 empty] | PAP-06660
| 1.14.29.5.5.2(Engineering &Supply of Structure) | [43 empty] | PCE-00100
| 1.14.29.5.5.2.1(FOUNDATION MATERIALS CONVEYOR-LC-1A/B) | [43 empty] | PCE-03000
| 1.14.29.5.5.2.2(CONVEYOR-LC-1A/B COLUMNS - TRESTLES) | [43 empty] | PCE-03300
| 1.14.29.5.5.2.3( CONVEYOR-LC-1A/B BEAMS & BRACING) | [43 empty] | PCE-03400
| 1.14.29.5.5.2.4(CONVEYOR-LC-1A/B FLOOR & PLATFORMS) | [43 empty] | PCI-00110
| 1.14.29.5.5.2.5(CONVEYOR-LC-1A/B STAIRS & LADDERS) | [43 empty] | PEI-01710
| 1.14.29.5.5.2.6(CONVEYOR-LC-1A/B MISC STRUCTURES) | [43 empty] | PEI-01810
| 1.14.29.5.5.3(Civil Works) | [43 empty] | PEI-01910
| 1.14.29.5.5.4(Erection) | [43 empty] | PEI-02010
| 1.14.29.5.6(Limestone Crusher House) | [43 empty] | PEI-02110
| 1.14.29.5.6.1(Equipment Dispatch) | [43 empty] | PEI-02210
| 1.14.29.5.6.2(Engineering &Supply of Structure) | [43 empty] | PEI-02310
| 1.14.29.5.6.2.1( FOUNDATION MATERIALS) | [43 empty] | PEI-02410
| 1.14.29.5.6.2.2(COLUMNS) | [43 empty] | PEI-02510
| 1.14.29.5.6.2.3(BEAMS & BRACING) | [43 empty] | PEI-02610
| 1.14.29.5.6.2.4(FLOOR & PLATFORMS) | [43 empty] | PEI-02710
| 1.14.29.5.6.2.5(WALL BEAMS) | [43 empty] | PEI-02810
| 1.14.29.5.6.2.6(STAIRS & LADDERS) | [43 empty] | PEI-02910
| 1.14.29.5.6.2.7(MISC STRUCTURES) | [43 empty] | PEI-03010
| 1.14.29.5.6.3(Civil Works) | [43 empty] | PEI-03110
| 1.14.29.5.7(Limestone Belt Feeder) | [43 empty] | PEI-03210
| 1.14.29.5.7.1(Equipment Dispatch) | [43 empty] | PEI-03310
| 1.14.29.5.8(Limestone Bulk Storage Silo and Bucket Elevator) | [43 empty] | PEI-03410
| 1.14.29.5.8.1(Engineering &Supply) | [43 empty] | PEI-03510
| 1.14.29.5.8.1.1(FOUNDATION MATERIALS SILO STR) | [43 empty] | PEI-03511
| 1.14.29.5.8.1.2(SILO STR COLUMNS) | [43 empty] | PEI-03520
| 1.14.29.5.8.1.3(SILO STR BEAMS & BRACING) | [43 empty] | PEI-03521
| 1.14.29.5.8.1.4(SILO STR FLOOR & PLATFORMS) | [43 empty] | PEI-03530
| 1.14.29.5.8.1.5(SILO STR WALL BEAMS) | [43 empty] | PEI-03531
| 1.14.29.5.8.1.6(SILO STR STAIRS & LADDERS) | [43 empty] | PEI-03540
| 1.14.29.5.8.1.7(SILO STR MISC STRUCTURES) | [43 empty] | PEI-03541
| 1.14.29.5.8.1.8(SILO SHELL) | [43 empty] | PEI-03550
| 1.14.29.5.8.1.9(Equipments) | [43 empty] | PEI-03551
| 1.14.29.5.8.2(Civil Works) | [43 empty] | PII-03610
| 1.14.29.5.8.3(Erection) | [43 empty] | PII-03710
| 1.14.29.5.9(Limestone Bucket Elevator and Reversible Belt Feeder) | [43 empty] | PII-03810
| 1.14.29.5.9.1(Equipment Dispatch) | [43 empty] | PII-03910
| 1.14.29.5.10(Gypsum Conveyor-1A/B) | [43 empty] | PII-04010
| 1.14.29.5.10.1(Equipment Dispatch) | [43 empty] | PII-04110
| 1.14.29.5.10.2(Engineering &Supply of Structure) | [43 empty] | PMI-00510
| 1.14.29.5.10.2.1(FOUNDATION MATERIALSCONVEYOR-GC-1A/B) | [43 empty] | PMI-00610
| 1.14.29.5.10.2.2(FX110 - CONVEYOR-GC-1A/B COLUMNS - TRESTLES) | [43 empty] | PMI-00710
| 1.14.29.5.10.2.3(FX210 - CONVEYOR-GC-1A/B BEAMS & BRACING) | [43 empty] | PMI-00810
| 1.14.29.5.10.2.4(FX310 - CONVEYOR-GC-1A/B FLOOR & PLATFORMS) | [43 empty] | PMI-00910
| 1.14.29.5.10.2.5(FX710 - CONVEYOR-GC-1A/B FASTENERS) | [43 empty] | PMI-01010
| 1.14.29.5.10.2.6(FX810 - CONVEYOR-GC-1A/B STAIRS & LADDERS) | [43 empty] | PMI-01110
| 1.14.29.5.10.2.7(FX910 - CONVEYOR-GC-1A/B MISC STRUCTURES) | [43 empty] | PMI-01210
| 1.14.29.5.10.3(Civil Works) | [43 empty] | PMI-01410
| 1.14.29.5.11(Gypsum Travelling Tripper/Gypsum Storage Shed) | [43 empty] | PMI-01510
| 1.14.29.5.11.1(Equipment Dispatch) | [43 empty] | PMI-01610
| 1.14.29.5.11.2(Engineering &Supply of Structure) | [43 empty] | PMI-01640
| 1.14.29.5.11.2.1(FX014 - FOUNDATION MATERIALSGYPSUM SHED) | [43 empty] | PMI-01650
| 1.14.29.5.11.2.2(FX140 - GYPSUM SHED COLUMNS) | [43 empty] | PMI-05110
| 1.14.29.5.11.2.3(FX240 - GYPSUM SHED BEAMS & BRACING) | [43 empty] | PMI-05140
| 1.14.29.5.11.2.4(FX340 - GYPSUM SHED FLOOR & PLATFORMS) | [43 empty] | PNI-00210
| 1.14.29.5.11.2.5(FX640 - GYPSUM SHED WALL BEAMS) | [43 empty] | PNI-00310
| 1.14.29.5.11.2.6(FX740 - GYPSUM SHED FASTENERS) | [43 empty] | PNI-00410
| 1.14.29.5.11.2.7(FX840 - GYPSUM SHED STAIRS & LADDERS) | [43 empty] | PNI-05010
| 1.14.29.5.11.2.8(FX940 - GYPSUM SHED MISC STRUCTURES) | [43 empty] | PNI-05040
| 1.14.29.5.11.3(Civil Works) | [43 empty] | PNI-05210
| 1.14.29.5.12(Pump House for LHP/ GHP) | [43 empty] | PNI-05240
| 1.14.29.5.12.1(Equipment Dispatch) | [43 empty] | PNI-06710
| 1.14.29.5.12.2(Civil Works ) | [43 empty] | PNI-07010
| 1.14.29.5.13(Weigh Bridge) | [43 empty] | PNI-07110
| 1.14.29.5.13.1(Equipment Dispatch) | [43 empty] | PWI-06810
| 1.14.29.5.13.2(Civil Works of Weigh Bridge GHP) | [43 empty] | PWI-06910
| 1.14.29.5.13.3(Civil Works of Weigh Bridge LHP) | [43 empty] | PWP-06060
| 1.14.29.5.14(Electrical and C&I Items) | [43 empty] | SC104
| 1.14.29.5.14.1(Equipment Dispatch) | [43 empty] | SC112
| 1.14.29.5.15(Misc./Auxiliary Systems) | [43 empty] | SC116
| 1.14.29.5.15.1(Equipment Dispatch) | [43 empty] | SC216
| 1.14.29.5.16(MCC building) | [43 empty] | SC300
| 1.14.29.5.16.1(Civil Works) | [43 empty] | SC304
| 1.14.29.5.16.2(Erection of Panels) | [43 empty] | SC308
| 1.14.29.6(Pumps) | [43 empty] | SC312
| 1.14.29.6.1(Engineering &Supply) | [43 empty] | SC316
| 1.14.29.6.1.1(BOI-FW701 SLURRY PUMPS & ACCESSORIES(A,B,C&D)) | [43 empty] | SC324
| 1.14.29.6.1.2(BOI- FW702 -WATER PUMPS & ACCESSORIES) | [43 empty] | SD307
| 1.14.29.6.2(Civil Works) | [43 empty] | SD342
| 1.14.29.6.3(Erection of Equipment) | [43 empty] | SD344
| 1.14.29.7(BOI-Tanks-PEM) | [43 empty] | SD345
| 1.14.29.7.1(Engineering &Supply) | [43 empty] | SD352
| 1.14.29.7.2(Civil) | [43 empty] | SD354
| 1.14.29.7.3(Erection / Assembly) | [43 empty] | SD355
| 1.14.29.8(Electrical Items) | [43 empty] | SD362
| 1.14.29.8.1(Engineering &Supply) | [43 empty] | SD364
| 1.14.29.8.1.1(FW806 - CONTROL JUNCTION BOX) | [43 empty] | SD365
| 1.14.29.8.1.2(FW807 - POWER JUNCTION BOX) | [43 empty] | SD386
| 1.14.29.8.1.3(FW779 - SUPPORTS FOR CABLE TRAYS/CONTR) | [43 empty] | SD407
| 1.14.29.8.1.4(FW841 - CONTROL VALVES) | [43 empty] | SD911
| 1.14.29.8.1.5(Electrical - Balance BOIs) | [43 empty] | SD915
| 1.14.29.8.2( Balance BOIs- HOIST, VALVES, CHAIN PULLEY, COMMISSIONING SPARES etc.) | [43 empty] | SD993
| 1.14.29.8.3(Electrical and C&I Erection works (Cable Tray, Cabling, termination, Earthing etc) & Pre-Commissioning) | [43 empty] | SL021
| 1.14.29.9( HT Motors) | [43 empty] | SL210
| 1.14.29.9.1(Engineering and Supply) | [43 empty] | SL700
| 1.14.29.9.1.1(RC PUMP MOTOR) | [43 empty] | SL701
| 1.14.29.9.1.2(OXIDATION BLOWER MOTOR) | [43 empty] | SL810
| 1.14.29.9.2(Erection) | [43 empty] | SR010
| 1.14.29.10(Earthing) | [43 empty] | SR020
| 1.14.29.11(Sub Systems) | [43 empty] | SR050
| 1.14.29.11.1(Absorber) | [43 empty] | SR100
| 1.14.29.11.1.1(Engineering and Supplies) | [43 empty] | SR103
| 1.14.29.11.1.1.1(Absorber-Structure) | [43 empty] | SR106
| 1.14.29.11.1.1.1.1(FW226 - EQWT) | [43 empty] | SR121
| 1.14.29.11.1.1.1.2(FW281 - FOUNDATION MATL FOR ABSORBER) | [43 empty] | SR122
| 1.14.29.11.1.1.1.3(FW285 - SUPRTING STR FOR EMERGENCY QWT) | [43 empty] | SR128
| 1.14.29.11.1.1.1.4(FW300 - ABSORBER COLUMN) | [43 empty] | SR150
| 1.14.29.11.1.1.1.5(FW301 - ABSORBER BEAM AND BRACINGS) | [43 empty] | SR151
| 1.14.29.11.1.1.1.6(FW302 - ABSORBER LOWER FLOORS) | [43 empty] | SR152
| 1.14.29.11.1.1.1.7(FW303 - ABSORBER UPPER FLOORS) | [43 empty] | SR158
| 1.14.29.11.1.1.1.8(FW304 - ABSORBER FLOOR GRILLS) | [43 empty] | SR171
| 1.14.29.11.1.1.1.9(FW305 - ABSORBER STAIR & HANDRAILS) | [43 empty] | SR172
| 1.14.29.11.1.1.1.10(FW306 - ABSORBER HSFG FASTNERS) | [43 empty] | SR178
| 1.14.29.11.1.1.1.11(FW307 - ABSORBER MISCELLANEOUS) | [43 empty] | SR180
| 1.14.29.11.1.1.2( Absorber Casing) | [43 empty] | SR181
| 1.14.29.11.1.1.2.1(FW201-ABSORBER RC PUMP NOZZLE) | [43 empty] | SR182
| 1.14.29.11.1.1.2.2(FW202-ABS NOZZLE NB300 & ABOVE) | [43 empty] | SR188
| 1.14.29.11.1.1.2.3(FW203-ABS NOZZLE NB 25 TO NB250) | [43 empty] | SR191
| 1.14.29.11.1.1.2.4(FW209-MANHOLE DOOR FOR ABSORBER) | [43 empty] | SR192
| 1.14.29.11.1.1.2.5(FW216-ABSORBER BAFFLE GRATING SUPPORT) | [43 empty] | SR198
| 1.14.29.11.1.1.2.6(FW217-ABSORBER ME SUPPORT) | [43 empty] | SR200
| 1.14.29.11.1.1.2.7(FW218-ABSORBER SPRAY PIPE SUPPORT) | [43 empty] | SR203
| 1.14.29.11.1.1.2.8(FW219-ABSORBER SYSTEM-BASE) | [43 empty] | SR206
| 1.14.29.11.1.1.2.9(FW221-ABSORBER SYSTEM-CASING BOTTOM) | [43 empty] | SR207
| 1.14.29.11.1.1.2.10(FW222-ABSORBER SYSTEM-CASING TOP) | [43 empty] | SR251
| 1.14.29.11.1.1.2.11(FW224-ABSORBER LINING - C276) | [43 empty] | SR252
| 1.14.29.11.1.1.2.12(FW228-ABSORBER-W/D INTERFACE- C276 zone) | [43 empty] | SR258
| 1.14.29.11.1.1.2.13(FW328-ABSORBER-W/D INTERFACE- CS zone) | [43 empty] | SR270
| 1.14.29.11.1.1.2.14(FW231-ABSORBER SHEAR PLATE) | [43 empty] | SR281
| 1.14.29.11.1.1.2.15(FW322-ABSORBER SYSTEM-CASING INTERMEDIATE) | [43 empty] | SR282
| 1.14.29.11.1.1.2.16(FW324-HOOD OVER ABSORBER) | [43 empty] | SR288
| 1.14.29.11.1.1.2.17(FW227-EMERGENCY QUENCHING SYSTEM) | [43 empty] | SR300
| 1.14.29.11.1.1.2.18(FW229-W/D WASH SYSTEM) | [43 empty] | SR301
| 1.14.29.11.1.1.3(Absorber Internals) | [43 empty] | SR303
| 1.14.29.11.1.1.3.1(FW 215-SUBDELIVERY - MIST ELIMINATOR) | [43 empty] | SR306
| 1.14.29.11.1.1.3.2( FW213- Absorber system ) | [43 empty] | SR307
| 1.14.29.11.1.1.3.3(FW720-ABSORBER AGITATOR- BOI) | [43 empty] | SR308
| 1.14.29.11.1.1.4(Absorber-Supporting systems) | [43 empty] | SR311
| 1.14.29.11.1.1.4.1(RC Pump Shed) | [43 empty] | SR312
| 1.14.29.11.1.1.4.1.1(Engineering &Supply) | [43 empty] | SR318
| 1.14.29.11.1.1.4.1.1.1(FW371 - HSFG BOLT-RC SHED-BOI) | [43 empty] | SR330
| 1.14.29.11.1.1.4.1.1.2(FW283 FOUNDATION MATERIAL & FW236 -STRUCTURES ) | [43 empty] | SR400
| 1.14.29.11.1.1.4.1.1.3(FW208- RC PUMP OXIDATION BLOWER SUPPORT) | [43 empty] | SR490
| 1.14.29.11.1.1.4.1.1.4(FW236- STRUCTURE FOR RC PUMP HOUSE) | [43 empty] | SR500
| 1.14.29.11.1.1.4.2(Absorbers Duct, Duct Structure & Duct support) | [43 empty] | SR503
| 1.14.29.11.1.1.4.2.1(FW207-OUTLET GUIDE VANE) | [43 empty] | SR506
| 1.14.29.11.1.1.4.2.2(FW232-DUCT SUPPORT BTW BYPASS DUCT & BUF/GGH) | [43 empty] | SR507
| 1.14.29.11.1.1.4.2.3(FW234-DUCT SUPPORT B/T ABSORBER & STACK/BYPASS) | [43 empty] | SR511
| 1.14.29.11.1.1.4.2.4(FW251-EXPANSION JOINT - METALLIC) | [43 empty] | SR512
| 1.14.29.11.1.1.4.2.5(FW252-EXPANSION JOINT - NON-METALLIC) | [43 empty] | SR518
| 1.14.29.11.1.1.4.2.6(FW255-DUCT BETWEEN BYPASS AND BUF) | [43 empty] | SR580
| 1.14.29.11.1.1.4.2.7(FW257-DUCT BETWEEN ABSORBER AND BYPASS/STACK) | [43 empty] | SR590
| 1.14.29.11.1.1.4.2.8(FW267-INSULATION MATERIALS FOR DUCT) | [43 empty] | SR900
| 1.14.29.11.1.1.4.2.9(FW268-FIXING COMPONENTS FOR DUCT) | [43 empty] | SR988
| 1.14.29.11.1.1.4.2.10(FW269-CLADDING SHEET FOR DUCT) | [43 empty] | SR990
| 1.14.29.11.1.1.4.2.11(FW260-DUCT STRUCTURE BETWEEN BYPASS AND BUF) | [43 empty] | SR992
| 1.14.29.11.1.1.4.2.12(FW262-DUCT STRUCTURE B/T ABSORBER&STACK) | [43 empty] | SR998
| 1.14.29.11.1.1.4.2.13(FW280-FOUNDATION MATL FOR DUCT STRUCTURE) | [43 empty] | SS010
| 1.14.29.11.1.1.4.2.14(FW297-PLATFORM FOR DUCT) | [43 empty] | SS011
| 1.14.29.11.1.1.4.2.15(FW298-PLATFORM FOR G&D) | [43 empty] | SS012
| 1.14.29.11.1.1.4.2.16(FW612-GALLERIES AND RAILINGS FOR DAMPERS) | [43 empty] | SS100
| 1.14.29.11.1.1.4.2.17(FW 613-GALLERIES AND RAILINGS FOR DUCTS) | [43 empty] | SS101
| 1.14.29.11.1.1.4.2.18(FW373-HSFG Bolt–Duct Struct) | [43 empty] | SS102
| 1.14.29.11.1.1.4.3(HYD- ABSORBER SLURRY RECIRCULATION PUMP) | [43 empty] | SS103
| 1.14.29.11.1.1.4.3.1(RC Pump-4 NOS) | [43 empty] | SS110
| 1.14.29.11.1.1.4.4(HYD-Oxidation blower) | [43 empty] | SS111
| 1.14.29.11.1.1.4.4.1(Oxidation Blower-A(100% Capacity, 1 Standby)) | [43 empty] | SS112
| 1.14.29.11.1.1.4.5(Absorber Handling System) | [43 empty] | SS113
| 1.14.29.11.1.1.4.5.1(FH990-ABSORBER ISLAND-HANDLING SYSTEM-BOI) | [43 empty] | SS191
| 1.14.29.11.1.1.5(Absorber Piping &Valves) | [43 empty] | SS192
| 1.14.29.11.1.1.5.1(FW860-FRP PIPING (LS,GS)) | [43 empty] | SS210
| 1.14.29.11.1.1.5.2(FW861-CSRL PIPE-1 (GS,LS)) | [43 empty] | SS215
| 1.14.29.11.1.1.5.3(FW862-CSRL PIPE-2 (GS,LS)) | [43 empty] | SS291
| 1.14.29.11.1.1.5.4(FW863-CS PIPING (PW,CW,SW)) | [43 empty] | SS292
| 1.14.29.11.1.1.5.5(FW864-SS PIPING (W/D)) | [43 empty] | SS311
| 1.14.29.11.1.1.5.6(FW865-GI PIPING (IA, DW)) | [43 empty] | SS321
| 1.14.29.11.1.1.5.7(FW866-FASTENERS CS & SS) | [43 empty] | SS331
| 1.14.29.11.1.1.5.8(FW867-RUBBER GASKET, SHEET) | [43 empty] | SS341
| 1.14.29.11.1.1.5.9(FW868-U-BOLTS) | [43 empty] | SS361
| 1.14.29.11.1.1.5.10(FW869-RUBBER EXP. BELLOWS) | [43 empty] | SS362
| 1.14.29.11.1.1.5.11(FW870-PIPING ACC.) | [43 empty] | SS363
| 1.14.29.11.1.1.5.12(FW871-PIPING SUPPORT STRUCTURES) | [43 empty] | SS364
| 1.14.29.11.1.1.5.13(FW875-FRP PIPING (LOT-2)) | [43 empty] | SS391
| 1.14.29.11.1.1.5.14(FW876-CSRL PIPIE-1 (LOT-2)) | [43 empty] | SS392
| 1.14.29.11.1.1.5.15(FW877-CS PIPING (LOT-2)) | [43 empty] | SS393
| 1.14.29.11.1.1.5.16(FW878-SS PIPING (LOT-2)) | [43 empty] | SS394
| 1.14.29.11.1.1.5.17(FW- Balance Valves & Commissioning spares) | [43 empty] | SS395
| 1.14.29.11.1.1.5.18(FW879-GI PIPING (LOT-2)) | [43 empty] | SS396
| 1.14.29.11.1.1.5.19(FW880-PIPING ACC (LOT-2)) | [43 empty] | SS400
| 1.14.29.11.1.1.6(Absorber Elevator) | [43 empty] | SS401
| 1.14.29.11.1.1.6.4(Dispatch) | [43 empty] | SS402
| 1.14.29.11.1.1.7(Absorber Consumables, Linings & Insulation, Casing etc.) | [43 empty] | SS403
| 1.14.29.11.1.1.7.1(FL210-FIXING COMPONENTS FOR FGD SYSTEM) | [43 empty] | SS440
| 1.14.29.11.1.1.7.2(FL221-MINERAL WOOL FOR FGD SYSTEM-BOI) | [43 empty] | SS441
| 1.14.29.11.1.1.7.3(FL700-BULKED DD COMPONENTS FOR FGD SYSTEM) | [43 empty] | SS442
| 1.14.29.11.1.1.7.4(FL701-BPS FASTENERS FOR FGD SYSTEM) | [43 empty] | SS443
| 1.14.29.11.1.1.7.5(FL810-OUTER CASING FOR FGD SYSTEM-BOI) | [43 empty] | SS491
| 1.14.29.11.1.1.7.6(FZ990-SPECIAL WELDING ELECTRODE) | [43 empty] | SS492
| 1.14.29.11.1.2(Civil Works) | [43 empty] | SS500
| 1.14.29.11.1.2.1(Absorber-Main structure) | [43 empty] | SS501
| 1.14.29.11.1.2.2(Absorber-Supporting systems) | [43 empty] | SS502
| 1.14.29.11.1.2.3(RC PUMP Shed) | [43 empty] | SS503
| 1.14.29.11.1.3(Erection) | [43 empty] | SS550
| 1.14.29.11.1.3.3(Absorber-Supporting systems) | [43 empty] | SS551
| 1.14.29.11.1.3.3.1(RC Pump Shed) | [43 empty] | SS552
| 1.14.29.11.1.3.3.2(Absorbers Inter connecting Platforms) | [43 empty] | SS553
| 1.14.29.11.2(Balance BOIs of Absorber) | [43 empty] | SS591
| 1.14.29.11.2.1(FW390-C276- Special welding electrode - part1) | [43 empty] | SS592
| 1.14.29.11.2.2(FW391-C276- Special welding electrode - part2) | [43 empty] | SS610
| 1.14.29.11.2.3(FW392-Ti - Special welding electrode - part1) | [43 empty] | SS611
| 1.14.29.11.2.4(FW393-Ti - Special welding electrode - part2) | [43 empty] | SS620
| 1.14.29.11.2.5(FW725-Nozzle and Flanges) | [43 empty] | SS621
| 1.14.29.11.2.6(FW710-MONORAIL FOR HOIST & CRANES) | [43 empty] | SS700
| 1.14.29.11.2.7(FW717-MAN HOLE DOOR) | [43 empty] | SS701
| 1.14.29.11.2.8(FW718 -ROOFING SHEET) | [43 empty] | SS810
| 1.14.29.11.2.9(FW992-Test Piece - C276) | [43 empty] | SS811
| 1.14.29.11.2.10(FW993-Test Piece - Ti) | [43 empty] | SS820
| 1.14.29.11.2.11(BOI-FW223-ABSORBER SYSTEM ACCESSORIES) | [43 empty] | SS850
| 1.14.29.11.2.12(BOI-FW227-EMERGENCY QUENCH SYSTEM) | [43 empty] | SS901
| 1.14.29.11.2.13(BOI-FW228-ABSORBER-W/D INTERFACE) | [43 empty] | SS906
| 1.14.29.11.2.14(BOI-FW229-W/D WASH SYSTEM) | [43 empty] | SS907
| 1.14.29.11.2.15(BOI-FW235-SPECIAL FASTENERS) | [43 empty] | SS908
| 1.14.29.11.2.16(BOI-FW239-VIEWING PORTS) | [43 empty] | SS915
| 1.14.29.11.2.17(BOI-FW243-SLURRY DISTRIBUTION SYSTEM- RC PUMP & ABSORBER) | [43 empty] | SS916
| 1.14.29.11.2.18(BOI-FW244-OXIDATION AIR DISTRIBUTION SYS) | [43 empty] | SS917
| 1.14.29.11.2.19(BOI-FW249-HANDLING EQUIPMENT - RC PUMP) | [43 empty] | SS918
| 1.14.29.11.2.20(BOI-FW252-EXPANSION JOINT- NON METALLIC) | [43 empty] | SS925
| 1.14.29.11.2.21(BOI-FW267-INSULATION MATERIALS FOR DUCT) | [43 empty] | SS926
| 1.14.29.11.2.22(BOI-FW268-FIXING COMPONENTS FOR DUCT) | [43 empty] | SS927
| 1.14.29.11.2.23(BOI-FW269-CLADDING SHEET FOR DUCT) | [43 empty] | SS928
| 1.14.29.12(JHS - 10 MVA, 11/3.45 KV FGD AUX Transformers) | [43 empty] | SS935
| 1.14.30(PEM- Sewage Treatment Plant) | [43 empty] | SS936
| 1.14.30.1(STP Execution Agency) | [43 empty] | SS937
| 1.14.30.2(Supply) | [43 empty] | SS938
| 1.14.30.3(Civil) | [43 empty] | SS945
| 1.14.30.4(Execution) | [43 empty] | SS946
| TAL-DEL(Deliverables) | [43 empty] | SS947
| TAL-DEL-SUP(Supplies) | [43 empty] | SS948
| TAL-DEL-SUP1(TRY) | [43 empty] | SS955
| TAL-DEL-SUP2(HWR) | [43 empty] | SS965
| TAL-DEL-SUP3(HYD) | [43 empty] | SS975
| TAL-DEL-SUP4(RPT) | [43 empty] | SS981
| TAL-DEL-SUP5(PEM) | [43 empty] | SS982
| TAL-DEL-SUP6(ISG) | [43 empty] | SS983
| TAL-DEL-SUP7(BPL) | [43 empty] | SS996
| TAL-DEL-SUP8(JHS) | [43 empty] | SS997
| TAL-DEL-SUP9(RUDR) | [43 empty] | SS998
| TAL-DEL-SUP10(PESD) | [43 empty] | SS999
| TAL-DEL-SUP11(SBD) | [43 empty] | WT001
| TAL-DEL-SUP12(EDN) | [43 empty] | WT002
| TAL-DEL-SUP13(PC) | [43 empty] | WT003
| TAL-DEL-SUP14(TBG) | [43 empty] | WT004
| TAL-DEL-SUP15(PSWR) | [43 empty] | WT022
| TAL-DEL.2(Civil - Site Activities) | [43 empty] | WT023
| TAL-DEL.3(Erection & Commissioning) | [43 empty] | WT024
| 56000-RPT(56000-FAN TOOLS & FIXTURES) | [43 empty] | WT025
| 56011-RPT(56011-FD FAN FIX MATLS) | [43 empty] | WT030
| 56015-RPT(56015- FD FAN CPLNG GUARD) | [43 empty] | WT040
| 56017-RPT(56017-FD FAN C&I ITEMS) | [43 empty] | WT055
| 56091-RPT(56091-FIRST FILL LUBRICANT) | [43 empty] | WT060
| 56114-RPT(56114-FD FAN ROTOR) | [43 empty] | WT070
| 56310-RPT(56310-FD BEARING HSG & ACC) | [43 empty] | WT080
| 56414-RPT(56414-RADIAL FD FAN STATOR) | [43 empty] | WT100
| 56810-RPT(56810-RADL FDFAN COUPLING) | [43 empty] | WT101
| 56919-RPT(56919-RADIAL FD FAN INSULATION) | [43 empty] | WT150
| 56997-RPT(56997-RADFAN-MANDTRY SPARE) | [43 empty] | WT153
| 56998-RPT(56998-MANDATORY SPARE ELECT C AND I) | [43 empty] | WT165
| 57013-RPT(57013-DAMPER-FD FAN OUTLET) | [43 empty] | WT210
| 57141-RPT(57141-SEAL AIR PIPING) | [43 empty] | WT220
| 57209-RPT(57209-MOUNTING BRACKET) | [43 empty] | WT222
| 57491-RPT(57491-BLOWER WITH MOTOR) | [43 empty] | WT223
| 57497-RPT(57497-KGV & CHECK VALVE) | [43 empty] | WT225
| 57560-RPT(57560-GATE-FGD INLET) | [43 empty] | WT226
| 57566-RPT(57566-PLATFORMS AND LADDERS-FGD GD) | [43 empty] | WT230
| 57577-RPT(57577-ELECT ACTUATOR FOR GATE,DAMPER) | [43 empty] | WT231
| 57578-RPT(57578-ELECTRICAL ITEMS FOR GATE,DAMP) | [43 empty] | WT235
| 57988-RPT(57988-COMMISSIONING SPARES) | [43 empty] | WT240
| 57992-RPT(57992-SPL MATL ELECTRODES) | [43 empty] | WT242
| 57C70-RPT(57C70-GATE-FGD OUTLET) | [43 empty] | WT244
| 57C83-RPT(57C83-DMPR-FGD BYPASS) | [43 empty] | WT245
| 87010-RPT(87010-CHIMNEY FDN MATERIAL) | [43 empty] | WT246
| 87100-RPT(87100-CHIMNEY SHELL) | [43 empty] | WT247
| 87150-RPT(87150-CHIMNEY STRAKES) | [43 empty] | WT248
| 87200-RPT(87200-PAINTER TROLLEY) | [43 empty] | WT250
| 87300-RPT(87300-PLATFORMS & LADDERS) | [43 empty] | WT253
| 87930-RPT(87930-AVIATION LAMPS) | [43 empty] | WT305
| 87950-RPT(87950-CHIMNEY INSULATION) | [43 empty] | WT320
| 87960-RPT(87960-CHIMN INS FIX COMP) | [43 empty] | WT323
| FW201-RPT(FW201-ABSORB. RC PUMP NOZZLE) | [43 empty] | WT324
| FW202-RPT(FW202-ABS NOZL NB 300 & ABOVE) | [43 empty] | WT330
| FW203-RPT(FW203-NOZZLE NB25 TO NB250) | [43 empty] | WT331
| FW207-RPT(FW207-OUTLET GUIDE VANE) | [43 empty] | WT332
| FW208-RPT(FW208-RC PUMP OB SUPPORT) | [43 empty] | WT333
| FW209-RPT(FW209-MAN HOLE DOOR FOR ABSORBER) | [43 empty] | WT334
| FW213-RPT(FW213-ABSORBER SYSTEM INTERNALS) | [43 empty] | WT335
| FW214-RPT(FW214-ABS BAFFLE GRATING) | [43 empty] | WT336
| FW215-RPT(FW215-MIST ELIMINATOR & ACCESSORIES) | [43 empty] | WT337
| FW216-RPT(FW216-ABS BAFFLE GRATING SUPP) | [43 empty] | WT338
| FW217-RPT(FW217-ABS ME SUPPORT) | [43 empty] | WT339
| FW218-RPT(FW218-ABS SPRAY PIPE SUPP) | [43 empty] | WT340
| FW219-RPT(FW219-ABSORBER SYSTEM-BASE) | [43 empty] | WT500
| FW221-RPT(FW221-ABSORBER SYSTEM-CASING BOTTOM) | [43 empty] | WT550
| FW222-RPT(FW222-ABSORBER SYSTEM-CASING TOP) | [43 empty] | WT551
| FW223-RPT(FW223-ABSORBER SYSTEM ACCESSORIES) | [43 empty] | WT552
| FW224-RPT(FW224-ABSORBER SYSTEM-LINING-C276) | [43 empty] | WT555
| FW226-RPT(FW226-EMERGENCY QUENCH WATER TANK) | [43 empty] | WT556
| FW227-RPT(FW227-EMERGENCY QUENCH SYSTEM) | [43 empty] | WT988
| FW228-RPT(FW228-ABSORBER-W/D INTERFACE) | [43 empty] | WT997
FW229-RPT(FW229-W/D WASH SYSTEM)
FW231-RPT(FW231-ABSORBER SHEAR PLATE)
FW232-RPT(FW232-DUCT SUP BYP & BUF/GGH)
FW234-RPT(FW234-DUCT SUP ABS & STACK/BYP)
FW235-RPT(FW235-SPECIAL FASTNERS)
FW236-RPT(FW236-STRUCTURES FOR RC PUMP HOUSE)
FW239-RPT(FW239-VIEWING PORTS)
FW249-RPT(FW249-HANDLING EQUIP- RC PUMP)
FW251-RPT(FW251-EXPNSN JNT METALLIC)
FW252-RPT(FW252-EXPNSN JNT NON METALLIC)
FW255-RPT(FW255-DUCT BYP & BUF/GGH/ABS)
FW257-RPT(FW257-DUCT ABS & BYP/STACK)
FW260-RPT(FW260-DUCT STR BYP & BUF/GGH/ABS)
FW262-RPT(FW262-DUCT STR ABS & BYP/STACK)
FW267-RPT(FW267-INSULATION MATERIALS FOR DUCT)
FW268-RPT(FW268-FIXING COMP FOR DUCT)
FW269-RPT(FW269-CLADDING SHEET FOR DUCT)
FW280-RPT(FW280-FOUNDATION MATL FOR DUCT STRUC)
FW281-RPT(FW281-FOUNDATION MATL FOR ABS)
FW282-RPT(FW282-FOUNDATION MATL FOR ELEVATOR)
FW283-RPT(FW283-FOUNDATION MATL RC PUMP SHED)
FW285-RPT(FW285-SUPRTING STR FOR EMERGENCY QWT)
FW293-RPT(FW293-ELEVATOR AND ACCESSORIES)
FW297-RPT(FW297-PLATFORM FOR DUCT)
FW298-RPT(FW298-PLATFORM FOR G&D)
FW300-RPT(FW300-ABSORBER COLUMNS)
FW301-RPT(FW301-ABSORBER BEAMS AND BRACINGS)
FW302-RPT(FW302-ABSORBER LOWER FLOORS)
FW303-RPT(FW303-ABSORBER UPPER FLOORS)
FW304-RPT(FW304-ABSORBER FLOOR GRILLS)
FW305-RPT(FW305-ABSORBER STAIRS & HANDRAILS)
FW306-RPT(FW306-ABSORBER HSFG FASTNERS)
FW307-RPT(FW307-ABSORBER MISCELLANEOUS)
FW322-RPT(FW322-ABSORBER SYSTEM-CASING INTERM)
FW324-RPT(FW324-HOOD OVER ABSORBER)
FW328-RPT(FW328-W/D INTERFACE (CARBON STEEL))
FW371-RPT(FW371-HSFG BOLT-RC SHED)
FW372-RPT(FW372-HSFG BOLT-ELEV STRUC)
FW373-RPT(FW373-HSFG BOLT-DUCT STRU)
FW380-RPT(FW380-ELEVATOR COLUMN)
FW381-RPT(FW381-ELEVATOR BEAM AND BRACING)
FW382-RPT(FW382-ELEVATOR FLOORS)
FW383-RPT(FW383-ELEVATOR STAIR AND HAND RAIL)
FW384-RPT(FW384-ELEVATOR FLOOR GRILL)
FW385-RPT(FW385-ELEVATOR M/C ROOM & GUIDE ,)
FW386-RPT(FW386-INTER-CONNECTING PLTF TO ABS)
FW390-RPT(FW390-C276- SPL WELD ELECTRODE P-1)
FW391-RPT(FW391-C276- SPL- WELD ELECTRODE P-2)
FW392-RPT(FW392-TI- SPL WELD ELECTRODE P-1)
FW393-RPT(FW393-TI- SPL WELD ELECTRODES P-2)
FW612-RPT(FW612-GALLARIES AND RAILINGS FOR DAM)
FW613-RPT(FW613-GALLARIES AND RAILINGS FOR DUC)
FW701-RPT(FW701-SLURRY PUMPS & ACCESSORIES)
FW702-RPT(FW702-WATER PUMPS & ACCESSORIES)
FW710-RPT(FW710-MONORAIL FOR HOIST & CRANES)
FW713-RPT(FW713-CHAIN PULLEYS)
FW714-RPT(FW714-HOISTS)
FW717-RPT(FW717-MAN HOLE DOOR)
FW718-RPT(FW718-ROOF SHEETING)
FW720-RPT(FW720-AGITATORS)
FW725-RPT(FW725-NOZZLES & FLANGES)
FW779-RPT(FW779-SUPPORTS FOR CABLE TRAYS/CONTR)
FW798-RPT(FW798-AIR RECEIVERS)
FW804-RPT(FW804-POWER CABLE)
FW806-RPT(FW806-CONTROL JUNCTION BOX)
FW807-RPT(FW807-POWER JUNCTION BOX)
FW815-RPT(FW815-RC PUMP INLT & OUTLT VALVE)
FW816-RPT(FW816-MANL BTRFLY VALV- UTLTY)
FW817-RPT(FW817-MOTOR BTRFL VALV-UTLTY)
FW818-RPT(FW818-PNEM BTRFLY VALV-UTLTY)
FW819-RPT(FW819-MAN BTRFLY VALV-LS SLRY)
FW820-RPT(FW820-MOTOR BTRFLY VALV-LS SLRY)
FW821-RPT(FW821-PNEUM BTRFLY VALV-LS SLRY)
FW822-RPT(FW822-MAN BTRFLY VALV-GYP SLRY)
FW823-RPT(FW823-MOTOR BTRFLY VALV -GYP SLRY)
FW824-RPT(FW824-PNEUM BTRFLY VALV-GYP SLRY)
FW828-RPT(FW828-MAN GATE VALV-UTLTY)
FW829-RPT(FW829-MOTOR GATE VALV-UTLTY)
FW830-RPT(FW830-PNEUM GATE VALVE-UTLTY)
FW834-RPT(FW834-MAIN GLOBE VALV-UTLTY)
FW840-RPT(FW840-CERAMIV VALVES)
FW841-RPT(FW841-CONTROL VALVES)
FW842-RPT(FW842-MAN PINCH VALV-GYP SLRY)
FW845-RPT(FW845-BALL VALVES- WATER)
FW848-RPT(FW848-CHECK VALVES- WATER)
FW851-RPT(FW851-DIAPHRAGM VALV-SLURRY)
FW860-RPT(FW860-FRP PIPING (LS,GS))
FW861-RPT(FW861-CSRL PIPE-1 (GS,LS))
FW862-RPT(FW862-CSRL PIPE-2 (GS,LS))
FW863-RPT(FW863-CS PIPING (PW,CW,SW))
FW864-RPT(FW864-SS PIPING (W/D))
FW865-RPT(FW865-GI PIPING (IA, DW))
FW866-RPT(FW866-FASTENERS CS & SS)
FW867-RPT(FW867-RUBBER GASKET, SHEET)
FW868-RPT(FW868-U-BOLTS)
FW869-RPT(FW869-RUBBER EXP. BELLOWS)
FW870-RPT(FW870-PIPING ACC.)
FW871-RPT(FW871-PIPING SUPPORT STR.)
FW875-RPT(FW875-FRP PIPING (LOT-2))
FW876-RPT(FW876-CSRL PIPIE-1 (LOT-2))
FW877-RPT(FW877-CS PIPING (LOT-2))
FW878-RPT(FW878-SS PIPING (LOT-2))
FW879-RPT(FW879-GI PIPING (LOT-2))
FW880-RPT(FW880-PIPING ACC (LOT-2))
FW988-RPT(FW988-COMMISSIONING SPARES)
FW992-RPT(FW992-TEST PIECE-C276)
FW993-RPT(FW993-TEST PIECE-TI)
FW996-RPT(FW996-TOOLS & TACKLES)
001-HWR(001-H P TURBINE [PRGR-001])
002-HWR(002-I P TURBINE [PRGR-002])
003-HWR(003-L P ROTOR [PRGR-003])
004-HWR(004-L P INNER CASING [PRGR-004])
005-HWR(005-L P OUTER CASING [PRGR-005])
006-HWR(006-CROSS AROUND PIPE [PRGR-006])
007-HWR(007-FRONT BEARING PEDESTAL [PRGR-007])
008-HWR(008-H P BEARING PEDESTAL [PRGR-008])
009-HWR(009-I P PEDESTAL [PRGR-009])
010-HWR(010-L P PEDESTAL [PRGR-010])
011-HWR(011-ESV/CV CASING [PRGR-011])
012-HWR(012-IV/CV CASING [PRGR-012])
013-HWR(013-LP BYPASS VALVE [PRGR-013])
017-HWR(017-INSTRUMENTS & RACK [PRGR-017])
018-HWR(018-TOOLS & TACKLES [PRGR-018])
019-HWR(019-EMBEDDED PARTS [PRGR-019])
020-HWR(020-OIL EQUIPMENTS [PRGR-020])
021-HWR(021-TURBINE PIPING ACCESSORIES [PRGR-021])
022-HWR(022-CONDENSER [PRGR-022])
023-HWR(023-L P HEATERS [PRGR-023])
024-HWR(024-MOUNTING ACCESSORIES [PRGR-024])
025-HWR(025-COMPONANT FOR BASE PLATE [PRGR-025])
135-HWR(135-STATOR [PRGR-135])
136-HWR(136-ROTOR [PRGR-136])
137-HWR(137-EXCITER FOUNDATION [PRGR-137])
138-HWR(138-EMBEDED PARTS & FOUND. PARTS [PRGR-138])
139-HWR(139-COMPLETING ITEMS [PRGR-139])
144-HWR(144-EXCITER COVERS [PRGR-144])
145-HWR(145-EXCITER COMPLETING ITEMS [PRGR-145])
149-HWR(149-H2 & SEAL OIL EQIPMENT [PRGR-149])
150-HWR(150-TG PIPING [PRGR-150])
152-HWR(152-PANELS [PRGR-152])
153-HWR(153-STATOR WATER COOLING ITEMS [PRGR-153])
BG005-HWR(BG005-MOISTURE MEASURING SYSTEM [PRGR-BG005])
BG008-HWR(BG008-MOTORISED TEMPERATURE CONTROL VALVE FOR COLD GAS [PRGR-BG008])
BG009-HWR(BG009-H2 GAS ANALYSER CABINET [PRGR-BG009])
BG018-HWR(BG018-STARTING RESISTOR FOR DC S.O MOTOR [PRGR-BG018])
BG021-HWR(BG021-GROUNDING BRUSH MONITOR [PRGR-BG021])
BG022-HWR(BG022-FIBRE OPTIC END WINDING VIBRATION MONITORING SYSTEM [PRGR-BG022])
BG092-HWR(BG092-MOTORISED TEMPERATURE CONTROL VALVE FOR PRIMARY WATER [PRGR-BG092])
BH010-HWR(BH010-CONDENSOR AIR EVACUATION PACKAGE (VACUUM PUMP) [PRGR-BH010])
BH012-HWR(BH012-AIR EXHAUSTER WITH MOTOR (GSC AIR EXHAUSTER) [PRGR-BH012])
BH023-HWR(BH023-WELDED AUSTENITIC S.S. TUBES GR.316 L (FOR CONDENSER) [PRGR-BH023])
BH028-HWR(BH028-PTFE BEARING SUPPORT [PRGR-BH028])
BH037-HWR(BH037-TURBINE OIL COOLER ( PHE) [PRGR-BH037])
BT001-HWR(BT001-LIFTING BEAM [PRGR-BT001])
BT006-HWR(BT006-BUTTERFLY VALVES [PRGR-BT006])
BT008-HWR(BT008-DOUBLE THREE WAY VALVES [PRGR-BT008])
BT009-HWR(BT009-NRV WITH ALUMINIUM FLAP [PRGR-BT009])
BT011-HWR(BT011-OIL PURIFICATION UNIT (OIL CENTRIFUGE) [PRGR-BT011])
BT014-HWR(BT014-SPRAY NOZZLES [PRGR-BT014])
BT015-HWR(BT015-DIRT CATCHERS [PRGR-BT015])
BT016-HWR(BT016-DAMPER [PRGR-BT016])
BT017-HWR(BT017-VARIABLE LOAD SPRING CAGES [PRGR-BT017])
BT020-HWR(BT020-THERMAL INSULATION OF TURBINE [PRGR-BT020])
BT021-HWR(BT021-THERMAL INSULATION OF TIP [PRGR-BT021])
BT023-HWR(BT023-TURBINE OIL [PRGR-BT023])
BT024-HWR(BT024-DRY AIR PRESERVATION SYSTEM [PRGR-BT024])
BT025-HWR(BT025-OIL PURIFICATION SYSTEM (CENTRAL) [PRGR-BT025])
BT028-HWR(BT028-H & S FOR TURBINE INTEGRAL PIPING [PRGR-BT028])
BT029-HWR(BT029-CALIBRATED FLOW NOZZLE ASSLY. [PRGR-BT029])
BT043-HWR(BT043-CONTROL FLUID (FRF) [PRGR-BT043])
BT046-HWR(BT046-LP BYPASS STOP & CONTROL VALVE WITH EHA AND WATER INJECTION VALVE [PRGR-BT046])
BT054-HWR(BT054-STEAM TRAP [PRGR-BT054])
BT065-HWR(BT065-GEAR PUMP (LUB. OIL RECIRCULATION) [PRGR-BT065])
BT071-HWR(BT071-LEVEL INDICATORS FOR OIL TANKS [PRGR-BT071])
BT074-HWR(BT074-VACUUM BREAKER VALVE WITH PNEUMATIC ACTUATOR [PRGR-BT074])
BT081-HWR(BT081-HPT STEAM EVACUATION VALVE [PRGR-BT081])
BT094-HWR(BT094-DC STARTERS & INSTRUMENTATION CABINET [PRGR-BT094])
BT096-HWR(BT096-OIL MODULE [PRGR-BT096])
BT097-HWR(BT097-OIL THROTTLE VALVES [PRGR-BT097])
BT104-HWR(BT104-SEAL STEAM CONTROL VALVE WITH ACTUATOR [PRGR-BT104])
BT105-HWR(BT105-LEAK STEAM CONTROL VALVE WITH ACTUATOR [PRGR-BT105])
BT106-HWR(BT106-TURBINE INSTRUMENT RACKS [PRGR-BT106])
BT107-HWR(BT107-PNEUMATIC GLOBE VALVE [PRGR-BT107])
BT110-HWR(BT110-HYDRAULIC POWER SUPPLY UNIT FOR TURBINE VALVES [PRGR-BT110])
BT111-HWR(BT111-ELECTRO-HYDRAULIC ACTUATORS FOR TURBINE VALVES [PRGR-BT111])
BT125-HWR(BT125-BOROSCOPIC VIDEO IMAGE KIT [PRGR-BT125])
BT142-HWR(BT142-PRESSURE TRANSMITTERS FOR STEAM TURBINE [PRGR-BT142])
BT147-HWR(BT147-PRESSURE GAUGES FOR TG SET [PRGR-BT147])
BT149-HWR(BT149-BAR PROBE WITH AMPLIFIER [PRGR-BT149])
BT150-HWR(BT150-CALIBRATION JIG [PRGR-BT150])
BT153-HWR(BT153-BLADE VIBRATION MONITORING SYSTEM (BVMS) [PRGR-BT153])
BT155-HWR(BT155-CONSTANT LOAD SPRING CAGES [PRGR-BT155])
TAL-DEL.4(Milestones)
PAI-01300-PEM(PAI-01300-PEM - LUBE OIL TRANSFER PUMPS)
PAI-06200-PEM(PAI-06200-PEM - CHAIN PULLEY BLOCK)
PAI-06300-PEM(PAI-06300-PEM - ELECTRIC HOIST)
PAI-06500-PEM(PAI-06500-PEM - Single Girder EOT / HOT Misc. Cranes)
PAI-13100-PEM(PAI-13100-PEM - MOBILE PICK UP & CARRY CRANE)
PAI-13300-PEM(PAI-13300-PEM - WORKSHOP EQUIPMENTS)
PAI-13400-PEM(PAI-13400-PEM - FQA Lab-Mechanical)
PAP-04300-PEM(PAP-04300-PEM - AIRCONDITIONING SYSTEM)
PAP-04400-PEM(PAP-04400-PEM - COMPRESSED AIR SYSTEM)
PAP-04800-PEM(PAP-04800-PEM - FUEL OIL HANDLING AND STORAGE SYSTEM)
PAP-04900-PEM(PAP-04900-PEM - MISC. TANKS(SITE FABRICATED))
PAP-05300-PEM(PAP-05300-PEM - D/G EOT CRANES ABOVE 100T)
PAP-06100-PEM(PAP-06100-PEM - ELEVATORS)
PAP-06400-PEM(PAP-06400-PEM - D/G EOT CRANES UP TO 100T)
PAP-14300-PEM(PAP-14300-PEM - MILL REJECT SYSTEM ( CONVEYOR TYPE))
PAP-15000-PEM(PAP-15000-PEM - VENTILATION SYSTEM)
PCI-10200-PEM(PCI-10200-PEM- Wind Tunnel Test for Chimney)
PEI-01700-PEM(PEI-01700-PEM - DC BATTERY CHARGER)
PEI-01900-PEM(PEI-01900-PEM - CABLE TRAYS & ACC.)
PEI-02100-PEM(PEI-02100-PEM - ABOVE GROUND EARTHING MATERIALS)
PEI-02200-PEM(PEI-02200-PEM - CABLE TERM.& JOINT KITS)
PEI-02300-PEM(PEI-02300-PEM - TREFOIL CLAMPS)
PEI-02600-PEM(PEI-02600-PEM - FIRE SEALING SYSTEM)
PEI-02700-PEM(PEI-02700-PEM - HT XLPE CABLES)
PEI-02900-PEM(PEI-02900-PEM - LT XLPE POWER CABLE)
PEI-03100-PEM(PEI-03100-PEM - SCREENED CONTROL CABLES)
PEI-03200-PEM(PEI-03200-PEM - MS ROD FOR BELOW GROUND EARTHING)
PEI-03300-PEM(PEI-03300-PEM - NEUTRAL GROUNDING RESISTOR)
PEI-03400-PEM(PEI-03400-PEM - OIL FILLED SERVICE TRANSFORMER)
PEI-07500-PEM(PEI-07500-PEM - STN. LIGHTING - POLES & MAST)
PEI-07600-PEM(PEI-07600-STN. LIGHTING - DISTRIBUTION BOARDS)
PEI-07700-PEM(PEI-07700-STN. LIGHTING - LIGHTING FIXTURES,LAMPS & MISC. ITEMS)
PEI-07800-PEM(PEI-07800-PEM - STN. LIGHTING - PVC WIRES)
PEI-07900-PEM(PEI-07900-PEM - STN. LIGHTING - RIGID STEEL CONDUITS)
PEI-11300-PEM(PEI-11300-PEM - LT PVC CONTROL CABLE)
PEI-11400-PEM(PEI-11400-PEM - CABLE TRAY SUPPORT SYSTEM -BOLTABLE)
PEI-12000-PEM(PEI-12000-PEM - DC Lead Acid / Ni-Cd Batteries)
PEI-12500-PEM(PEI-12500-PEM - ELECTRIC LAB EQUIPMENT)
PEI-12600-PEM(PEI-12600-PEM - PA SYSTEM)
PEI-12800-PEM(PEI-12800-PEM - FQA Lab-Electrical)
PII-03600-PEM(PII-03600-PEM - ANUBAR ( DELTA TUBE))
PII-03700-PEM(PII-03700-PEM - CONTROL VALVE)
PII-03800-PEM(PII-03800-PEM- FLOW ELEMENT - NOZZLE)
PII-03900-PEM(PII-03900-PEM - FLOW ELEMENT - ORIFICE)
PII-04000-PEM(PII-04000-PEM- ROTAMETER)
PII-04100-PEM(PII-04100-PEM- ULTRASONIC FLOW METERS)
PII-09700-PEM(PII-09700-PEM - ELECTROMAGNETIC FLOW METER)
PMI-00500-PEM(PMI-00500-PEM - THERMAL INSULATION - R-MATTRESSES/P-SECN)
PMI-00600-PEM(PMI-00600-PEM - THERMAL INSULATION -ANCILLARY MATERIAL)
PMI-00700-PEM(PMI-00700-PEM - ALUMINIUM SHEETS/COILS)
PMI-00800-PEM(PMI-00800-PEM - AIR TRAPS)
PMI-00900-PEM(PMI-00900-PEM - STEAM TRAPS)
PMI-01000-PEM(PMI-01000-PEM - BUTTERFLY VALVES(STEAM SERVICE))
PMI-01100-PEM(PMI-01100-PEM - BALL VALVES)
PMI-01200-PEM(PMI-01200-PEM - AIR RELEASE VALVES)
PMI-05100-PEM(PMI-05100-PEM - M.E. BELLOWS)
PMI-09500-PEM(PMI-09500-PEM - THERMAL INSULATION-Ceramic Fibre Blanket)
PNI-00200-PEM(PNI-00200-PEM - COLTCS)
PNI-01500-PEM(PNI-01500-PEM - SUMP PUMPS/SUBMERSIBLE PUMPS)
PNI-05000-PEM(PNI-05000-PEM - MISC.PUMPS (VERTICAL))
PNI-05200-PEM(PNI-05200-PEM - SELF CLEANING STRAINERS)
PNI-06700-PEM(PNI-06700-PEM - MISC.PUMPS (HORIZONTAL))
PNI-07000-PEM(PNI-07000-PEM - HEAT EXCHANGERS(PLATE TYPE))
PNI-07100-PEM(PNI-07100-PEM - AUX PRDS)
PNI-08800-PEM(PNI-08800-COOLING TOWERS)
PWI-06800-PEM(PWI-06800-PEM - CHEMICAL DOSING SYSTEM)
PWI-06900-PEM(PWI-06900-PEM - OXYGEN DOSING SYSTEM)
PWI-13600-PEM(PWI-13600-PEM - AGITATORS/STIRRERS)
PWI-13800-PEM(PWI-13800-PEM - LIME FEEDING/DOSING SYSTEM)
PWI-15400-PEM(PWI-15400-PEM - Gypsum Dewatering System)
PWP-04500-PEM(PWP-04500-PEM - PRETREATMENT PLANT)
PWP-04600-PEM(PWP-04600-PEM - D.M. PLANT)
PWP-04700-PEM(PWP-04700-PEM - EFFLUENT TREATMENT PLANT)
PWP-05500-PEM(PWP-05500-PEM - CONDENSATE POLISHING UNIT)
PWP-05700-PEM(PWP-05700-PEM - CW TREATMENT PLANT)
PWP-05900-PEM(PWP-05900-PEM - Sewage Treatment Plant)
PWP-14100-PEM(PWP-14100-PEM - CHLORINE DIOXIDE DOSING SYSTEM)
PWP-14500-PEM(PWP-14500-PEM - H2 GEN. PLANT)
PWP-15500-PEM(PWP-15500-PEM - Effluent/Sewage Transfer System)
16226-HYD(16226-LP HEATERS-3)
16231-HYD(16231-LP HEATERS-4)
16235-HYD(16235-LP HEATERS-5)
17509-HYD(17509-HP HEATERS -7)
17510-HYD(17510-HP HEATER -7B)
17511-HYD(17511-HP HEATERS -8)
17512-HYD(17512-HP HEATER 8B)
17523-HYD(17523-HP HEATERS -9)
17524-HYD(17524-HP HEATER -9B)
18001-HYD(18001-MOTOR DRIVEN BOILER FEED PUMP (MDBFP))
18101-HYD(18101-DRIP PUMP (DP))
18111-HYD(18111-CONDENSATE EXTRACTION PUMP (CEP))
18901-HYD(18901-MD BOOSTER PUMP (MDBP))
30771-HYD(30771-BFP DRIVE TURBINE)
61001-HYD(61001-JOURNAL SHAFT ASSEMBLY)
61101-HYD(61101-GEARBOX ASSEMBLY)
61103-HYD(61103-BOWL & BOWL HUB ASSEMBLY)
61201-HYD(61201-MILL SIDE ASSEMBLY)
61301-HYD(61301-SEPARATOR BODY ASSEMBLY)
61302-HYD(61302-SEPARATOR TOP ASSEMBLY)
61501-HYD(61501-250 LPM MILL LUBE OIL SYSTEM)
HYBM008-HYD(HYBM008-BULL RING SEGMENT)
HYBM009-HYD(HYBM009-KNIFE GATE VALVE)
HYBM010-HYD(HYBM010-MILL MOTOR COUPLING)
HYHE001-HYD(HYHE001-FEED STORAGE TANKS & DEARATOR HEATER)
HYHE002-HYD(HYHE002-DRAIN COOLERS)
HYPU001-HYD(HYPU001-BFP HYDRAULIC COUPLING)
HYPU002-HYD(HYPU002-R.C VALVES)
HYTC001-HYD(HYTC001-GEAR BOX)
50510-RPT(50510-STEAM COIL A P H)
52000-RPT(52000-SPECIAL TOOLS/CONTRA)
52010-RPT(52010-LARG AH-ROTOR ASSY)
52011-RPT(52011-LARG AH-ROTOR POST)
52012-RPT(52012-LARG AH-ROTORPINRACK)
52013-RPT(52013-LARG AH-ROTORSEALS)
52030-RPT(52030-LARG AH-ROTORHOUSING)
52041-RPT(52041-HOT END CONN PLATE)
52042-RPT(52042-COLD END CONN PLATE)
52054-RPT(52054-LARG AH-AXIAL SEAL)
52055-RPT(52055-LARG AH-BY PASS SEAL)
52100-RPT(52100-LARGE AH ROTOR DRIVE)
52101-RPT(52101-LARG AH-AUX ROTDRIVE)
52211-RPT(52211-LARG AH-AIRSEAL PIPE)
52220-RPT(52220-LARG AH-GENS DETAILS)
52261-RPT(52261-LARG AH-GUIDE BEARNG)
52262-RPT(52262-LARG AH-SUPRT BEARNG)
52271-RPT(52271-OIL PIPING GUIDE BRG)
52272-RPT(52272-OIL PIPING SUPRT BRG)
52274-RPT(52274-LUB OIL CIRCULATION UNIT)
52275-RPT(52275-LARGE AIR HEATER-LUBRICANTS)
52301-RPT(52301-WASH MANIFLD GAS INL)
52302-RPT(52302-WASH MANIFLD GAS OUT)
52338-RPT(52338-LARGE AH-MULTIMEDI CLNG DEV-CE)
52339-RPT(52339-LARGE AH-RETRACT CLNG DEV (HE))
52600-RPT(52600-LARGE AH E,C&I COMPONENETS)
52988-RPT(52988-LARG AH COMMISSIONING SPARE)
55000-RPT(55000- FAN TOOL & FIXTURE)
55011-RPT(55011-FAN FIX MATERIAL)
55015-RPT(55015-FD FAN COUPLING GUARD)
55017-RPT(55017-FD FAN C&I ITEMS)
55021-RPT(55021-ID FAN FIX MATERIAL)
55024-RPT(55024-ID FAN C & S AIR FAN)
55025-RPT(55025-ID FAN CPLNG GUARD)
55027-RPT(55027-ID FAN C&I ITEMS)
55031-RPT(55031-PA FAN FIX MATERIAL)
55035-RPT(55035-PA FAN CPLNG GUARD)
55037-RPT(55037-PA FAN C&I ITEMS)
55091-RPT(55091-FIRST FILL LUBRICANT)
55216-RPT(55216-1 STG FD ROTOR)
55327-RPT(55327-2 STG ID ROTOR)
55335-RPT(55335-2 STG PA ROTOR)
55410-RPT(55410-FD SET & INDN SHAFT)
55420-RPT(55420-ID SET & INDN SHAFT)
55430-RPT(55430-PA SET & INDN SHAFT)
55510-RPT(55510-FD FAN EXPN JOINTS)
55516-RPT(55516-1 STG FD HOUSING)
55520-RPT(55520-ID FAN EXPN JOINTS)
55530-RPT(55530-PA FAN EXPN JOINTS)
55627-RPT(55627-2 STG ID HOUSING)
55635-RPT(55635-2 STG PA HOUSING)
55716-RPT(55716-FD FAN SUCTION BOX)
55727-RPT(55727-ID FAN SUCTION BOX)
55735-RPT(55735-PA FAN SUCTION BOX)
55810-RPT(55810- FD FAN COUPLING)
55816-RPT(55816- FD FAN DIFFUSER)
55820-RPT(55820-ID FAN COUPLING)
55827-RPT(55827-ID FAN DIFFUSER)
55830-RPT(55830-PA FAN COUPLING)
55835-RPT(55835-PA FAN DIFFUSER)
55910-RPT(55910-FD FAN LUBE OIL SYS)
55911-RPT(55911-FD FAN SILENCER)
55919-RPT(55919-FD FAN INSUL WOOL)
55920-RPT(55920-ID FAN LUBE OIL SYS)
55930-RPT(55930-PA FAN LUBE OIL SYS)
55931-RPT(55931-PA FAN SILENCER)
55939-RPT(55939-PA FAN INSUL WOOL)
56075-RPT(56075- SA FAN CPLNG GUARD)
56077-RPT(56077-SA FAN C&I ITEMS)
56079-RPT(56079-SA FAN MTR CANOPY)
56161-RPT(56161-PENT HOUSE FAN)
56173-RPT(56173-SA FAN ROTOR)
56373-RPT(56373-RADIAL SEAL AIR FAN BEARINGS)
56473-RPT(56473-RADIAL SEAL AIR FAN STATOR)
56670-RPT(56670-RADIAL SEAL AIR FAN MOTOR)
56870-RPT(56870-SEAL AIR FAN COUPLING(RADIAL))
57010-RPT(57010-GATE-FD FAN OUTLET)
57033-RPT(57033-DAMPER-SA SCAPH INLET)
57063-RPT(57063-DAMPER-SA SCAPH OUTLET)
57083-RPT(57083-DAMPER-SA SCAPH BYPASS)
57110-RPT(57110-GATE-PA FAN OUTLET)
57113-RPT(57113-DAMPER-PA FAN OUTLET)
57143-RPT(57143-DAMPER-COLD AIR TO MILL)
57160-RPT(57160-GATE-COLD AIR TO MILLS)
57173-RPT(57173-DAMPER-PA APH INLET)
57203-RPT(57203-DAMPER-SA APH OUTLET)
57223-RPT(57223-DAMPER-PA APH OUTLET)
57270-RPT(57270-GATE-HOT AIR TO MILLS)
57273-RPT(57273-DAMPER-HOT AIR TO MILL)
57430-RPT(57430-FLUE GAS AH OUT GATE)
57460-RPT(57460-GATE-ESP INLET)
57466-RPT(57466-PLATFORMS AND LADDERS)
57470-RPT(57470-GATE-ESP OUTLET)
57480-RPT(57480-GATE-ID FAN INLET)
57490-RPT(57490-GATE-ID FAN OUTLET)
57620-RPT(57620-GATE-SCR BYPASS)
57666-RPT(57666-PLATFORMS AND LADDERS-SCR GD)
57897-RPT(57897-MANDATORY SPAR ELECTRICAL ITEM)
57997-RPT(57997-MANDATORY SPAR MECHANICAL ITEM)
57CX0-RPT(57CX0-GATE-WITH CLADDING)
79501-RPT(79501-ROLL/SLIDE SUPPORTS)
79505-RPT(79505-ESP-SUB-DELIVERY COMPONENTS)
79506-RPT(79506-INSULATOR HOUSING AS)
79508-RPT(79508-GAS DIST. ASSY)
79509-RPT(79509-GD-RAPPING MECHANISM)
79510-RPT(79510-GD_DRIVE ARRANGEMENT)
79511-RPT(79511-GAS SCREEN-EP)
79513-RPT(79513-EMIT SYST SUSPENSION)
79514-RPT(79514-SUPPORT INSULATORS)
79515-RPT(79515-EMITTING ELECTRODES)
79516-RPT(79516-EMIT ELECT RAPP MECH)
79517-RPT(79517-DRIVE ARGT. FOR EMIT. SYS)
79519-RPT(79519-COL ELEC SUSPENSION)
79520-RPT(79520-COLLECTING ELECTRODE)
79521-RPT(79521-EMIT SYS FRAME-TOP)
79522-RPT(79522-EMIT SYS FRAME BOTOM)
79523-RPT(79523-INSPECTION DOORS)
79524-RPT(79524-SHOCK BARS)
79525-RPT(79525-COLL ELECT RAPP MECH)
79526-RPT(79526-COLL ELEC RAPP DRIVE)
79528-RPT(79528-ESP ROOF BEAM)
79530-RPT(79530-ELECTRICAL SD COMPTS)
79531-RPT(79531-GEARED MOTORS FOR RAPPING MECH)
79532-RPT(79532-EMIT SYS FRAME-MIDLE)
79537-RPT(79537-JUNCTION BOX & PUSH BUTTON STA)
79541-RPT(79541-ELECTRICAL MISCELLANEOUS ITEMS)
79542-RPT(79542-OUTER ROOF-EP)
79543-RPT(79543-HOPPER RIDGES)
79544-RPT(79544-HOPPER UPPER PART)
79545-RPT(79545-HOP MLD&LOWER PART)
79546-RPT(79546-INSULATOR SUPP PANEL)
79547-RPT(79547-ROOF PANEL ASSY)
79548-RPT(79548-CASING STRUCTURE)
79549-RPT(79549-CASING SHELL/PANEL)
79550-RPT(79550-INLET-OUTLET FUNNEL)
79555-RPT(79555-PENT HOUSE FOR E P)
79557-RPT(79557-SPLITTER&GUIDE VANES)
79559-RPT(79559-SUPPORTS FOR ELECTRICAL ITEMS)
79560-RPT(79560-CABLE-CABLE RACKS)
79561-RPT(79561-EP PERF TEST EQUIPT)
79562-RPT(79562-CABLE TRAY AND FLEXIBLE SUPPTS)
79563-RPT(79563-ASH LEVEL INDICATOR)
79565-RPT(79565-APP PLATFORM-HOPPER)
79566-RPT(79566-WATER WASHING SYSTEM)
79567-RPT(79567-MIN WOOL FOR ESP INSULATION)
79568-RPT(79568-FIXING COMP. FOR ESP INSULATIN)
79572-RPT(79572-INTERLOCKS-EP)
79573-RPT(79573-ELECTRICALLY OPERTD HOIST&ACCE)
79574-RPT(79574-OPACITY MONITOR & ACCESSORIES)
79578-RPT(79578-BAPCON & ACCESSORIES)
79580-RPT(79580-FOUNDATION MATLS FOR ESP)
79581-RPT(79581-SUPPOTING STRUCTURES FOR ESP)
79589-RPT(79589-GUIDE PLATE/VANE EP INLET DUCT)
79590-RPT(79590-HEATING ELEMENTS)
79591-RPT(79591-PANEL TYPE HOPPER HEATERS & AC)
79595-RPT(79595-IOS PANEL)
79797-RPT(79797-E-SHOP MANDATORY SPARES)
79897-RPT(79897-MANDATORY SPARES ELECTRICAL)
79988-RPT(79988-COMMISSIONING SPARES)
79996-RPT(79996-TOOLS & TACKLES)
79997-RPT(79997-MANDATORY SPARES)
89610-RPT(89610-EP GALLERIES&STAIRS)
89611-RPT(89611-ESP ROOF HANDRAILS)
89612-RPT(89612-FLOOR GRILL AND STEP TREAD)
89613-RPT(89613-FLOOR GRILL AND MOBILE LADDER)
89614-RPT(89614-PENT HOUSE ROOFING SHEETS)
89615-RPT(89615-INSULATION CLADDING SH FOR ESP)
89618-RPT(89618-HSFG BOLTS FOR ESP STRUT)
BG001-HWR(BG001-EMPTY H2 CYLINDER [PRGR-BG001])
BG002-HWR(BG002-EMPTY CO2 CYLINDER [PRGR-BG002])
BG003-HWR(BG003-EMPTY N2 CYLINDER [PRGR-BG003])
BG004-HWR(BG004-PORTABLE GAS ANALYSER [PRGR-BG004])
BG007-HWR(BG007-VAPOUR EXHAUSTER [PRGR-BG007])
BG011-HWR(BG011-REFRIGERATION GAS DRYER [PRGR-BG011])
BG080-HWR(BG080-STROBOSCOPE [PRGR-BG080])
BG082-HWR(BG082-HYDRAULIC UNIT ASSEMBLY [PRGR-BG082])
BG098-HWR(BG098-EXCITER COVER COMPLETE WITH FABRICATION AND LINING [PRGR-BG098])
BG107-HWR(BG107-PRIMARY WATER PUMP & MOTOR SET [PRGR-BG107])
BG113-HWR(BG113-ELECTROMAGNETIC CORE IMPERFECTION DETECTOR (ELCID) [PRGR-BG113])
BG114-HWR(BG114-RECURRENT SURGE OSCILLOSCOPE (RSO) [PRGR-BG114])
BT027-HWR(BT027-TURBINE INTEGRAL PIPING [PRGR-BT027])
ProjectEngg(Project Engineering)
PEM(PEM)
ProjectEngg.2(Ranipet)
ProjectEngg.3(Haridwar)
ProjectEngg.4(Hyderabad)
ProjectEngg.5(Jhansi)
ProjectEngg.6(Bhopal)
ProjectEngg.8(RUDR)
ProjectEngg.10(PESD)
ProjectEngg.12(IP)
ProjectEngg.14(SBD)
ProjectEngg.15(TRY)
ProjectEngg.16(EDN)
ProjectEngg.17(ISG)
04147-TRY(04147-Supprts for Collectr & Separatr Vessel)
04321-TRY(04321-VERTICAL SEPARATOR)
04323-TRY(04323-STORAGE TANK)
04347-TRY(04347-Seperator/Collecting Vessel Supp DD)
05137-TRY(05137-EVAPORATOR INLET HDR - FRNT)
05147-TRY(05147-FUR LWR REAR INLET HDR)
05155-TRY(05155-FUR LWR SIDE INLET HDRS)
05227-TRY(05227-FUR UPPER REAR OUTLET HDR)
05231-TRY(05231-FUR UPPER FRNT OUTLET HDR)
05251-TRY(05251-FUR UPPER SIDE OUTLET HDRS)
05327-TRY(05327-FUR INTERMEDIATE REAR HDR)
05330-TRY(05330-FUR INTERMEDIATE FRNT HDR)
05350-TRY(05350-FUR INTERMEDIATE SIDE HDRS)
06400-TRY(06400-FUR BURNER PANELS)
06401-TRY(06401-Burner Panel- OS)
06431-TRY(06431-Front Upper Ww Panel Attachment)
06434-TRY(06434-Front Intermediate WW Panel -OS)
06437-TRY(06437-Front WW Lower Panel-OS)
06441-TRY(06441-Rear Upper WW Panel -OS)
06444-TRY(06444-Rear Intermediate WW Panel -OS)
06447-TRY(06447-Rear Lower WW Panel -OS)
06451-TRY(06451-Side Upper Ww Panel Attachment)
06453-TRY(06453-Side Intermediate WW Panel -OS)
06455-TRY(06455-Side Lower WW Panel -OS)
06500-TRY(06500-FUR SOFA PANELS)
06501-TRY(06501-Sofa Panels -OS)
06731-TRY(06731-FUR VERTICAL WALL PANELS - FRNT)
06732-TRY(06732-FRONT WW PNL + ATT)
06734-TRY(06734-FUR UPPER FRNT SPIRAL PANEL)
06735-TRY(06735-FUR FRNT SPIRAL TO VERTICAL TRANS. PANEL)
06737-TRY(06737-FUR LWR FRNT SPRL PNL WITH I/T TERM TUBE)
06741-TRY(06741-FUR REAR ARCH PANELS)
06744-TRY(06744-FUR UPPER REAR SPIRAL PANEL)
06745-TRY(06745-FUR REAR SPIRAL TO vert TRANSITION PANEL)
06747-TRY(06747-FUR LWR RR SPRL PNL WITH I/T TERM TUBES)
06751-TRY(06751-FUR VERTICAL WALL PANELS - SIDE)
06752-TRY(06752-FUR LWR VERTICAL WALL PANELS - SIDE)
06753-TRY(06753-FUR UPPER SIDE SPIRAL PANELS)
06755-TRY(06755-FUR LWR SIDE SPIRAL PANELS)
06759-TRY(06759-FUR SIDE SPIRAL TO VERT TRANSITION PANEL)
07102-TRY(07102-LINKS FROM SEPARATOR TO STORAGE TANK)
07110-TRY(07110-DOWNCOMER TO CONNECTING SPHERE)
07125-TRY(07125-Connecting Sphere)
07217-TRY(07217-SCREEN RELIFE TUBES)
07223-TRY(07223-FUR SCREEN AND HANGER ASSEMBLY)
07231-TRY(07231-FUR SPIRAL WALL OUTLET TERM TUBES)
07232-TRY(07232-FUR VERTICAL WALL INLET TERM TUBES)
07309-TRY(07309-Furnace Wall Supports Front-DD)
07315-TRY(07315-FUR SIDE RISERS)
07316-TRY(07316-FUR REAR RISERS)
07318-TRY(07318-FUR FRNT RISERS)
07331-TRY(07331-Riser Tube Support DD Item)
07360-TRY(07360-Furnace Spiral Wall Support DD Item)
07361-TRY(07361-Furnace Wall¿ Support Rear DD Item)
07362-TRY(07362-Furnace Wall¿ Support Side L&R DD Item)
07393-TRY(07393-Consumables & Erection Materials-DD)
07402-TRY(07402-WW FRT HDR SUSPN)
07403-TRY(07403-WW SIDE HDR SUSPN)
07405-TRY(07405-WW SCR.HDR SUSPN.)
07409-TRY(07409-Furnace wall Supports front)
07423-TRY(07423-Furnace Screen Tubes Attachment)
07431-TRY(07431-RISER TUBE SUPPORT)
07460-TRY(07460-Furnace Spiral Wall supports Misc items)
07461-TRY(07461-Furnace wall Supports rear)
07462-TRY(07462-Furnace wall Supports Sides L & R)
07502-TRY(07502-Ww Front Header Suspn Shop Item)
07503-TRY(07503-Ww Side Header Suspension Shop Item)
07505-TRY(07505-Ww Screen Header Suspn Shop Item)
07509-TRY(07509-MISC PR.PART COMPNTS)
07531-TRY(07531-Riser Tube Support Shop Item)
07560-TRY(07560-Furnace Spiral Wall Support Shop Item)
07991-TRY(07991-Welding Electrodes-Part-1)
07992-TRY(07992-Welding Electrodes)
07993-TRY(07993-EREC MATLS, CONSUMES)
08001-TRY(08001-FURN UPR BKSTYS-F&R)
08003-TRY(08003-FURN UPR BKSTYS-SIDE)
08006-TRY(08006-FURN INT BKSTYS)
08007-TRY(08007-FURN LWR BKSTYS)
08111-TRY(08111-FURN REAR ARCH BKSTYS)
08380-TRY(08380-FURN BOT SUPRTS)
08400-TRY(08400-FURN GUIDES)
08501-TRY(08501-FURN B P BKSTYS-F&R)
08503-TRY(08503-FURN B P BKSTYS-SIDE)
08901-TRY(08901-FURN KEY BKSTYS-UPR)
08910-TRY(08910-EX.MOVT MEAS COMP)
08911-TRY(08911-Bulk Bps Items-Upper)
08912-TRY(08912-Bulk Bps Items-Inter)
08913-TRY(08913-Bulk Bps Items-Lower)
09003-TRY(09003-MATL FOR INST TAPPG)
09004-TRY(09004-SEAL BOX FURN OPENG)
09005-TRY(09005-SEAL BOX INST OPENG)
09304-TRY(09304-Seal Boxes For Furnace Openings-DD)
10135-TRY(10135-FUR ARCH SUPPPORT INLET HDR)
10174-TRY(10174-FINISH SH INLET HDR)
10176-TRY(10176-SH PLATEN FRONT INLET HEADER(S-26))
10178-TRY(10178-SH PLATEN INLET HDR)
10182-TRY(10182-BP LWR REAR HDR)
10183-TRY(10183-BP UPPER SIDE INLET HDR)
10184-TRY(10184-BP EXTENDED SIDE INLET HDR)
10185-TRY(10185-BP LWR FRNT HDR)
10191-TRY(10191-SH FUR ROOF INLET HDR)
10235-TRY(10235-FUR ARCH SUPPPORT OUTLET HDR)
10274-TRY(10274-FINISH SH OUTLET HDR)
10276-TRY(10276-SH PLATEN FRONT OUTLET HEADER(S-28))
10278-TRY(10278-SH PLATEN OUTLET HDR)
10283-TRY(10283-BP LWR SIDE HDRS)
10284-TRY(10284-BP EXT FLOOR OUTLET HDR WITH TERM TUBES)
10285-TRY(10285-BP FRNT OUTLET HDR)
10291-TRY(10291-SH FUR ROOF OUTLET HDR)
11074-TRY(11074-FINISH SH FRNT ASSY WITH I/T TERM & COT)
11078-TRY(11078-SH PLATEN ASSY WITH TERM TUBES - LEFT)
11374-TRY(11374-FINISH SH REAR ASSY WITH O/T TERM & COT)
11378-TRY(11378-SH PLATEN ASSY WITH TERM TUBES - RIGHT)
11406-TRY(11406-SH Frnt Upper Pnl Attachment)
11467-TRY(11467-SH Sc Side Pnl Upper Left Attachment)
11469-TRY(11469-SH Sw Panels Lower Front (L&R)-OS)
11474-TRY(11474-SH Vertical Spaced Coil Attachment)
11487-TRY(11487-BP LTRH Hanger Tube Attchment)
11491-TRY(11491-SH Radient Roof Tubes (Left)-OS)
11494-TRY(11494-SH Extended Bottom Panels-OS)
11606-TRY(11606-BP FRNT WALL PANELS)
11608-TRY(11608-BP FRNT WALL PANEL - LWR)
11684-TRY(11684-BP EXTENDED SIDE FIN WELDED PANEL)
11694-TRY(11694-BP EXTENDED SIDE FLOOR FIN WELDED PANEL)
11716-TRY(11716-BP UPPER REAR PANEL)
11718-TRY(11718-BP LWR REAR PANEL)
11767-TRY(11767-BP UPPER SIDE PANEL-LEFT)
11768-TRY(11768-SH SIDE WALL PANELS INTER (FRONT))
11769-TRY(11769-BP LWR SIDE PANEL - LEFT)
11787-TRY(11787-BP REAR ROOF PANELS)
11791-TRY(11791-SH FUR ROOF FIN WELDED PANEL)
11916-TRY(11916-SH REAR WALL PANELS UPPER (RIGHT))
11918-TRY(11918-SHSC RR WL PNL LR RT)
11967-TRY(11967-BP UPPER SIDE PANEL-RIGHT)
11968-TRY(11968-SH SIDE WALL PANELS INTER (REAR))
11969-TRY(11969-BP LWR SIDE PANEL - RIGHT)
11987-TRY(11987-SHSC RR ROOF PNL RT)
11991-TRY(11991-SH FUR ROOF TUBES)
12178-TRY(12178-LINK TO SH DESUPERHEATER)
12179-TRY(12179-LINK TO FINISH SH INLET HDR)
12181-TRY(12181-FUR ARCH SUPPORT LINKS)
12184-TRY(12184-BP EXTENDED SIDE CONNECTION LINK)
12187-TRY(12187-SH BYPASS PIPES)
12306-TRY(12306-SH Spprt For Lines And Links DD Item)
12314-TRY(12314-Suspn of SH R.Roof Headers DD Item)
12317-TRY(12317-Suspn of R.Roof Headers DD Item)
12324-TRY(12324-Suspension of SH Rear Wall DD Items)
12327-TRY(12327-Suspension of SH Rear Wall DD Items)
12328-TRY(12328-Suspension of SH Rear Wall DD Items)
12344-TRY(12344-Suspn of Vert. Spaced Assy DD Item)
12348-TRY(12348-Suspn of Vert. Spaced Assy DD Item)
12354-TRY(12354-Suspn of Vert. Spaced Assy DD Item)
12368-TRY(12368-RH Vert Platen Frnt Coil Left DD Item)
12393-TRY(12393-SH Misc Components DD Item)
12405-TRY(12405-SH Hanger Tube Attachment)
12506-TRY(12506-SH Spprt For Lines And Links Shop Item)
12514-TRY(12514-Suspn of SH R.Roof Hdrs Shop Item)
12517-TRY(12517-Suspn of R.Roof Headers Shop Item)
12524-TRY(12524-Suspension of SH Rear Wall Shop Item)
12528-TRY(12528-Suspension of SH Rear Wall Shop Item)
12554-TRY(12554-Suspn of Vert. Spaced Assy Shop Item)
12800-TRY(12800-SH DESUP-STAGE II)
12803-TRY(12803-SH STEAM COOLED SPACER TUBES)
12805-TRY(12805-BP FRNT WALL SCREEN TUBES)
12850-TRY(12850-SH CONNECTING PIPE)
12852-TRY(12852-LINKS TO SH PLATEN INLET HDR)
12900-TRY(12900-SH DESUPERHEATER)
12903-TRY(12903-SH MISCL COMPONENTS)
12906-TRY(12906-SH LINK SUPPORTS)
12907-TRY(12907-RAD&RR ROOF SUPPORTS)
12914-TRY(12914-EXPN-SH RAD ROOF HDR)
12917-TRY(12917-SUSPN OF RADINT ROOF)
12924-TRY(12924-SUSPN-SH BAKPASS HDR)
12927-TRY(12927-SUSPN OF REAR ROOF)
12928-TRY(12928-SUSPN - SH REAR WALL)
12944-TRY(12944-SUSPN-SH PLATEN HDRS)
12948-TRY(12948-SUSP-VERT SPACD ASSY)
12954-TRY(12954-SUSP-VERT SPACD HDRS)
12968-TRY(12968-SUSPN OF PLATEN ASSY)
12991-TRY(12991-Welding Electrodes-Part-1)
12992-TRY(12992-Welding Electrodes)
12993-TRY(12993-EREC MATLS, CONSUMES)
12994-TRY(12994-PORT IN FOR THK MSMT)
15136-TRY(15136-LTRH INLET HDR)
15178-TRY(15178-FINISH RH INLET HDR)
15236-TRY(15236-LTRH OUTLET HDR)
15278-TRY(15278-FINISH RH OUTLET HDR)
16201-TRY(16201-LTRH UPPER ASSEMBLY)
16202-TRY(16202-LTRH INTERMEDIATE ASSEMBLY)
16203-TRY(16203-LTRH LWR ASSEMBLY WITH INLET TERM TUBES)
16270-TRY(16270-LTRH PENDANT ASSY WITH O/T TERM TUBES)
16278-TRY(16278-FINISH RH ASSEMBLY WITH TERMINAL TUBES)
16379-TRY(16379-RH VERPLN FR COIL RT)
17174-TRY(17174-LINK TO RH DESUPERHEATER)
17304-TRY(17304-RH Spprts For Lines And Links DD Item)
17306-TRY(17306-RH Suprt For Lines And Links DD Item)
17319-TRY(17319-RH Frnt Suspension DD Item)
17407-TRY(17407-RH Sc Spacer Tube Attchment)
17476-TRY(17476-RH V.S. CENTRE CROSS OVER TUBE ATTCHMT)
17504-TRY(17504-RH Suprts For Lines And Links Shop Item)
17506-TRY(17506-RH Suprt For Lines And Links Shop Item)
17807-TRY(17807-RH STM COOL SPACERS)
17900-TRY(17900-RH DESUPERHEATER)
17903-TRY(17903-RH MISCL COMPONENTS)
17904-TRY(17904-RH HDR SUPRT AB ROOF)
17906-TRY(17906-RH SUPRT LINES & LIN)
17919-TRY(17919-RH FRONT SUSPENSION)
17991-TRY(17991-Welding Electrodes-Part-1)
17992-TRY(17992-Welding Electrodes)
18001-TRY(18001-FUR ROOF SKIN CASING)
18002-TRY(18002-1 PASS ROOF SKINCASG)
18010-TRY(18010-PR PARTS ATTACH-CASG)
18701-TRY(18701-Furnace Roof Skin Casing BOI Item)
19092-TRY(19092-ECO OUTLET TERM TUBES)
19306-TRY(19306-Eco Supports For Line & Links DD Item)
19307-TRY(19307-Eco Feed Pipe Suspn DD Item)
19402-TRY(19402-Eco Hanger Tube Attachment)
19506-TRY(19506-Eco Supports For Line & Links Shop Item)
19507-TRY(19507-Eco Feed Pipe Suspn Shop Item)
19701-TRY(19701-ECO INLET HDR)
19702-TRY(19702-ECO OUTLET HDR)
19704-TRY(19704-ECO II INLET HEADER)
19753-TRY(19753-ECO JUNCTION HDR)
19763-TRY(19763-ECO JUNCTION HDR)
19783-TRY(19783-ECO JUNCTION HDR)
19793-TRY(19793-ECO JUNCTION HDR)
19802-TRY(19802-ECO LWR HANGER TUBES)
19804-TRY(19804-ECO UPPER HANGER TERMINAL TUBES)
19814-TRY(19814-ECO UPPER ASSY - LEFT)
19824-TRY(19824-ECO LWR ASSY -LEFT)
19850-TRY(19850-ECO INLET LINKS)
19851-TRY(19851-LINKS FROM ECO OUT. HDR TO ECO MIX LINE)
19852-TRY(19852-ECO MIXING LINE)
19853-TRY(19853-LINKS FROM ECO MIX LINE TO FURN I/T HDRS)
19884-TRY(19884-ECO INTER ASSY - LEFT)
19903-TRY(19903-ECO.MISCL COMP)
19904-TRY(19904-ECO HDR SUPT AB ROOF)
19905-TRY(19905-ECO HDR SUPT BL ROOF)
19906-TRY(19906-ECO LINE&LINK SUPORT)
19907-TRY(19907-ECO,FEEDPIPE SUPPORT)
19914-TRY(19914-ECO UPPER ASSY - RIGHT)
19924-TRY(19924-ECO LWR ASSY-RIGHT)
19984-TRY(19984-ECO INTER ASSY - RIGHT)
19991-TRY(19991-Welding Electrodes-Part-1)
19992-TRY(19992-Welding Electrodes)
20051-TRY(20051-LONG RETRACT SB M11E)
20054-TRY(20054-WALL BOX NPR LRSB MI)
20201-TRY(20201-WALL DESLAGGER RW5E)
20204-TRY(20204-WALL BOX NPR-RW5E)
20511-TRY(20511-DA HEAD VALVE ASSY)
20794-TRY(20794-WALL BOX NPR FOR TP)
20962-TRY(20962-TR PROBE DUP PT&AC)
20998-TRY(20998-SPL TOOLS FOR SB)
21600-TRY(21600-S.B. PPG & FITTINGS)
21601-TRY(21601-S.B PIPING SUPPORTS)
21602-TRY(21602-Sb Piping - DD Items)
21603-TRY(21603-Sb Piping - BOI Items)
21604-TRY(21604-SB Piping Supports - OS items)
21605-TRY(21605-SB Piping Supports - DD Items)
21606-TRY(21606-SB Piping Supports - BOI Items)
21700-TRY(21700-BULKED BPS COMP)
21800-TRY(21800-SB VALVES (BHEL))
21825-TRY(21825-SB VALVES (SUBDELY))
21850-TRY(21850-SB SAFETY VALVE BHEL)
21992-TRY(21992-WELDING ELECTRODES)
24350-TRY(24350-BLR FILLING PIPING)
24351-TRY(24351-H&S BLR FILLING PPG)
24352-TRY(24352-Boiler Fill Piping - DD Items)
24353-TRY(24353-H&S For Boiler Fill Piping - OS Items)
24354-TRY(24354-BOI Items for Blr Trim Piping)
24700-TRY(24700-BULKED BPS COMP)
24800-TRY(24800-BOILER TRIM PIPING)
24801-TRY(24801-SUPPORTS-TRIM PIPING)
24803-TRY(24803-Boiler Trim Piping - DD Items)
24804-TRY(24804-Supports - Blr Trim Piping - OS Items)
24805-TRY(24805-LINK TO BOILER RECIRCU SYSTEM)
24806-TRY(24806-MIXING VESSEL)
24807-TRY(24807-RECIRCU PUMP SUCTION LINE)
24808-TRY(24808-RECIRCU PUMP DISCHARGE LINE)
24809-TRY(24809-BOILR RECIR LINK FROM BF LINE)
24810-TRY(24810-H and S FOR STARTUP SYSTEM)
24811-TRY(24811-Fur Link to Flash tank HWL1&2)
24815-TRY(24815-SPRAY WATER SYSTEM)
24817-TRY(24817-H&S For Start-Up System - OS Items)
24818-TRY(24818-H&S For Start-Up System - DD Items)
24820-TRY(24820-EXHAUS PIPE SAFETY VLV)
24822-TRY(24822-De-Superheater Pipes - OS Items)
24823-TRY(24823-De-Superheater Pipes - DD Items)
24824-TRY(24824-Exhaust Pipe For Sv - OS Items)
24825-TRY(24825-SILENCER SUPPORTS)
24826-TRY(24826-Silencer Supp - OS Items)
24827-TRY(24827-Exhaust Pipe For Sv - DD Items)
24828-TRY(24828-Exhaust Pipe For Sv - BOI Items)
24835-TRY(24835-STARTUP VENT DIFFUSER SILEN SUP)
24836-TRY(24836-Start-Up Vent, Diffuser, Sil Supp-OS)
24837-TRY(24837-Start-Up Vent, Diffuser, Sil Supp-DD)
24840-TRY(24840-SAMPLE COOLER AND SUPPORTS)
24841-TRY(24841-Sample Cooler & Supports - OS Items)
24842-TRY(24842-Sample Cooler and Suprts-DD items)
24855-TRY(24855-RECIRCULATING PUMB COMP)
24860-TRY(24860-VALVES (BHEL))
24865-TRY(24865-CTL VALVES FOR SPRAY PIPING SD)
24867-TRY(24867-CTL VAL FOR STARTUP RECIRCU SYS)
24880-TRY(24880-SAFETY VALVES)
24881-TRY(24881-SAFETY VALVES AND ERV(BHEL) SD)
24883-TRY(24883-Safety Valves (Bhel) - Non HT)
24885-TRY(24885-SILENCERS(BHEL))
24950-TRY(24950-SPECIAL TOOLS)
24955-TRY(24955-LAP TOOL SV&ERV)
24960-TRY(24960-LAP TOOL-CON VAL(BHEL))
24966-TRY(24966-NITROGEN BLANKETING SYSTEM PIPING)
24967-TRY(24967-NITROGEN BLANKETING SYSTEM PIPING OS)
24968-TRY(24968-NITROGEN BLANKETING SYSTEM PIPING DD)
24969-TRY(24969-NITROGEN BLANKETING SYSTEM PIPING SD)
24992-TRY(24992-WELDING ELECTRODES-TRIM PPG)
24993-TRY(24993-CONSUME & EREC MATLS)
24994-TRY(24994-NAME PLATES)
28220-TRY(28220-DOORS)
28700-TRY(28700-BPS FASTENERS)
30103-TRY(30103-SEAL PLATE ASSY)
30105-TRY(30105-FUR BOTTOM ENCL FRAM)
30211-TRY(30211-FUR REAR ARCH ENCL)
30215-TRY(30215-MAIN BOILER ENCL)
30219-TRY(30219-VERT ROOF ENCL)
30223-TRY(30223-GAS DIST BAFFLES)
30224-TRY(30224-Antivibration Baffles)
30233-TRY(30233-IST PASS DECK SPRT)
30234-TRY(30234-2ND PASS DECK SPRT)
30235-TRY(30235-ENCL SUPPORT STEEL)
31010-TRY(31010-COMPS WELDED TO PR)
31104-TRY(31104-FUR REAR ARCH SKIN)
32010-TRY(32010-FICOM BLR PP INSUL)
32210-TRY(32210-FIX COMP-DUCT INSULN)
32700-TRY(32700-BULKED DD COMPONENT)
32810-TRY(32810-EQUIPMENT OUTER CASING)
33021-TRY(33021-BLR PP MINRL WOOL)
33210-TRY(33210-MAIN BLR CAST REF GR)
33221-TRY(33221-DUCT MINERAL WOOL)
33230-TRY(33230-MAIN BLR POUR INSUL)
33924-TRY(33924-MISC EQPTS PCK MATLS)
33970-TRY(33970-MISC EQPTS EXP METAL)
33971-TRY(33971-MISC EQPTS WW CLOTH)
33975-TRY(33975-MISC EQPTS SEAL COMP)
34101-TRY(34101-Bunker Columns 1st Tier)
34102-TRY(34102-Bunker Columns 2nd Tier)
34103-TRY(34103-Bunker Columns 3rd Tier)
34104-TRY(34104-Bunker Columns 4th Tier)
34105-TRY(34105-COLM-Q ROW LOWE TIER)
34200-TRY(34200-BUNKER SUPPORT BEAMS)
34300-TRY(34300-BUNKER BAY HORIZONTAL BRACINGS¿)
34390-TRY(34390-Misc.Structures)
34441-TRY(34441-Bunker Horizontal Beams Tier 1)
34442-TRY(34442-Bunker Horizontal Beams Tier 2)
34443-TRY(34443-Bunker Horizontal Beams Tier 3)
34444-TRY(34444-Bunker Horizontal Beams Tier 4)
34445-TRY(34445-Bunker Horizontal Beams Tier 5)
34511-TRY(34511-Bunker Vertical Bracings Tier 1)
34512-TRY(34512-Bunker Vertical Bracings Tier 2)
34513-TRY(34513-Bunker Vertical Bracings Tier 3)
34514-TRY(34514-Bunker Vertical Bracings Tier 4)
34515-TRY(34515-Bunker Vertical Bracings Tier 5)
34721-TRY(34721-HSFG FASTENERS FOR 34PG - TIER 1)
34722-TRY(34722-HSFG FASTENERS FOR 34PG - TIER 2)
34723-TRY(34723-HSFG FASTENERS FOR 34PG - TIER 3)
34724-TRY(34724-HSFG FASTENERS FOR 34PG - TIER 4)
34725-TRY(34725-HSFG FASTENERS FOR 34PG - TIER 5)
34730-TRY(34730-HSFG FASTENERS - BUNKER SUPPORT BEAMS)
34731-TRY(34731-FASTENERS)
34732-TRY(34732-FASTENERS)
34733-TRY(34733-FASTENERS)
34810-TRY(34810-FLOOR GRILLS)
34820-TRY(34820-STAIRS)
34850-TRY(34850-HAND RAILS)
35010-TRY(35010-FOUNDATION MATERIALS)
35131-TRY(35131-Middle Columns RHS 1st Tier)
35132-TRY(35132-Middle Columns RHS 2nd Tier)
35133-TRY(35133-Middle Columns RHS 3rd Tier)
35134-TRY(35134-Middle Columns RHS 4th Tier)
35135-TRY(35135-Middle Columns RHS 5th Tier)
35136-TRY(35136-Middle Columns RHS 6th Tier)
35137-TRY(35137-Middle Columns RHS 7th Tier)
35138-TRY(35138-MIDDLE COLUMNS 8TH TIER)
35141-TRY(35141-Auxiliary Columns LHS 1st Tier)
35142-TRY(35142-Auxiliary Columns LHS 2nd Tier)
35143-TRY(35143-Auxiliary Columns LHS 3rd Tier)
35144-TRY(35144-Auxiliary Columns LHS 4th Tier)
35145-TRY(35145-Auxiliary Columns LHS 5th Tier)
35146-TRY(35146-Auxiliary Columns LHS 6th Tier)
35147-TRY(35147-Auxiliary Columns LHS 7th Tier)
35148-TRY(35148-AUXILIARY COLUMNS LHS 8TH TIER)
35151-TRY(35151-AUXCOL LHSLWR 1&2PAS)
35152-TRY(35152-AUXCOL RHSMID 1&2PAS)
35153-TRY(35153-AUXCOL RHSUPR 1&2PAS)
35154-TRY(35154-Auxiliary Columns RHS 4th Tier)
35155-TRY(35155-Auxiliary Columns LHS 7th Tier)
35156-TRY(35156-Auxiliary Columns RHS 6th Tier)
35157-TRY(35157-Auxiliary Columns RHS 7th Tier)
35158-TRY(35158-AUXILIARY COLUMNS RHS 8TH TIER)
35181-TRY(35181-Main Columns 1st Tier)
35182-TRY(35182-Main Columns 2nd Tier)
35183-TRY(35183-Main Columns 3rd Tier)
35184-TRY(35184-Main Columns 4th Tier)
35185-TRY(35185-Main Columns 5th Tier)
35186-TRY(35186-Main Columns 6th Tier)
35187-TRY(35187-Main Columns 7th Tier)
35188-TRY(35188-MAIN COLUMNS 8TH TIER)
35190-TRY(35190-GIRDER PIN CONNECTIO)
35211-TRY(35211-CEILING STRUCTUREMAI)
35212-TRY(35212-CEILING STRUCTUREMAI)
35213-TRY(35213-CEIL STRUCT -CROSS W)
35214-TRY(35214-CEIL STRUCT -CROSS W)
35221-TRY(35221-CEILING STRUCTURE RO)
35222-TRY(35222-CEILING STRUCTURE RO)
35231-TRY(35231-CEILING STRUCTURE HO)
35232-TRY(35232-CEILING STRUCTURE HO)
35311-TRY(35311-HORIZONTAL BRACING I)
35312-TRY(35312-HORIZ BRACING II PAS)
35321-TRY(35321-HORIZ BRACING I PASS)
35322-TRY(35322-HORIZ BRACING II PAS)
35331-TRY(35331-HORIZ BRACING I PASS)
35332-TRY(35332-HORIZ BRACING II PAS)
35341-TRY(35341-HORIZ BRACING I PASS)
35342-TRY(35342-HORIZ BRACING II PAS)
35351-TRY(35351-HORIZ BRACING I PASS)
35352-TRY(35352-HORIZ BRACING II PAS)
35361-TRY(35361-HORIZ BRACING I PASS)
35362-TRY(35362-HORIZ BRACING II PAS)
35371-TRY(35371-Horizontal Bracing@79100 (MBL-7)1st Pass)
35372-TRY(35372-Horizontal Bracing @79100(MBL-7)2nd Pass)
35374-TRY(35374-Horizontal Bracing@87500(MBL-8) 1st Pass)
35375-TRY(35375-Horizontal Bracing@87500(MBL-8) 2nd Pass)
35381-TRY(35381-Landing & Connecting Platforms Tier-1)
35382-TRY(35382-Landing & Connecting Platforms Tier-2)
35383-TRY(35383-Landing & Connecting Platforms Tier-3)
35384-TRY(35384-Landing & Connecting Platforms Tier-4)
35385-TRY(35385-Landing & Connecting Platforms Tier-5)
35386-TRY(35386-Landing & Connecting Platforms Tier-6)
35387-TRY(35387-Landing & Connecting Platforms Tier-7)
35388-TRY(35388-Landing & Connecting Platforms Tier-8)
35390-TRY(35390-MISC STRUCTURES)
35442-TRY(35442-Horil Beams First Pass-Tier-2)
35443-TRY(35443-Horil Beams First Pass-Tier-3)
35444-TRY(35444-Horil Beams First Pass-Tier-4)
35445-TRY(35445-Horil Beams First Pass-Tier-5)
35446-TRY(35446-Horil Beams First Pass-Tier-6)
35447-TRY(35447-Horil Beams First Pass-Tier-7)
35448-TRY(35448-Horil Beams First Pass-Tier-8)
35451-TRY(35451-Hor Beam-Second Pass- Tier-1)
35452-TRY(35452-Hor Beam-Second Pass- Tier-2)
35453-TRY(35453-Hor Beam-Second Pass- Tier-3)
35454-TRY(35454-Hor Beam-Second Pass- Tier-4)
35455-TRY(35455-Hor Beam-Second Pass- Tier-5)
35456-TRY(35456-Hor Beam-Second Pass- Tier-6)
35457-TRY(35457-Hor Beam-Second Pass- Tier-7)
35458-TRY(35458-Hor Beam-Second Pass- Tier-8)
35511-TRY(35511-Front Bracing-Tier-1)
35512-TRY(35512-Front Bracing-Tier-2)
35513-TRY(35513-Front Bracing-Tier-3)
35514-TRY(35514-Front Bracing-Tier-4)
35515-TRY(35515-Front Bracing-Tier-5)
35516-TRY(35516-Front Bracing-Tier-6)
35517-TRY(35517-Front Bracing-Tier-7)
35518-TRY(35518-Front Bracing-Tier-8)
35521-TRY(35521-Side Bracing-Tier-1)
35522-TRY(35522-Side Bracing-Tier-2)
35523-TRY(35523-Side Bracing-Tier-3)
35524-TRY(35524-Side Bracing-Tier-4)
35525-TRY(35525-Side Bracing-Tier-5)
35526-TRY(35526-Side Bracing-Tier-6)
35527-TRY(35527-Side Bracing-Tier-7)
35528-TRY(35528-Side Bracing-Tier-8)
35531-TRY(35531-Rear Bracing-Tier-1)
35532-TRY(35532-Rear Bracing-Tier-2)
35533-TRY(35533-Rear Bracing-Tier-3)
35534-TRY(35534-Rear Bracing-Tier-4)
35535-TRY(35535-Rear Bracing-Tier-5)
35536-TRY(35536-Rear Bracing-Tier-6)
35537-TRY(35537-Rear Bracing-Tier-7)
35538-TRY(35538-Rear Bracing-Tier-8)
35721-TRY(35721-HSFG FASTENERS FOR 35PG - TIER 1)
35722-TRY(35722-HSFG FASTENERS FOR 35PG - TIER 2)
35723-TRY(35723-HSFG FASTENERS FOR 35PG - TIER 3)
35724-TRY(35724-HSFG FASTENERS FOR 35PG - TIER 4)
35725-TRY(35725-HSFG FASTENERS FOR 35PG - TIER 5)
35726-TRY(35726-HSFG FASTENERS FOR 35PG - TIER 6)
35727-TRY(35727-HSFG FASTENERS FOR 35PG - TIER 7)
35728-TRY(35728-HSFG FASTENERS FOR 35PG - TIER 8)
35730-TRY(35730-HSFG FASTENERS - CEILING)
35811-TRY(35811-FLOOR GRILLS AND GUARD PLATE)
35812-TRY(35812-Edge Strip And Guard Plate)
35821-TRY(35821-STAIRS - LOWER)
35822-TRY(35822-STAIRS - MIDDLE)
35823-TRY(35823-STAIRS - UPPER)
35851-TRY(35851-HAND RAILS AND POSTS)
35993-TRY(35993-CONSUMABLESANDERECTI)
35995-TRY(35995-CHUTE PIPE AND LADDE)
36111-TRY(36111-COLUMNS NEAR APH Tier 1)
36112-TRY(36112-COLUMNS NEAR APH Tier 2)
36113-TRY(36113-COLUMNS NEAR APH Tier 3)
36114-TRY(36114-COLUMNS NEAR AIR PRE HEATERS/SCR Tier4)
36115-TRY(36115-COLUMNS NEAR AIR PRE HEATERS/SCR Tier5)
36151-TRY(36151-BEAMS AND BRACINGS NEAR APH Tier 1)
36152-TRY(36152-BEAMS AND BRACINGS NEAR APH Tier 2)
36153-TRY(36153-BEAMS AND BRACINGS NEAR APH Tier 3)
36154-TRY(36154-BEAMS AND BRACINGS NEAR AIR PREHEATER/SC)
36155-TRY(36155-BEAMS AND BRACINGS NEAR AIR PREHEATER/SC)
36311-TRY(36311-MAIN FLOOR I MBL 1ST)
36313-TRY(36313-NON-MBL FLOOR BETWEE)
36314-TRY(36314-NON-MBL FLOOR BETWEE)
36315-TRY(36315-NON-MBL FLOOR BETWEE)
36316-TRY(36316-NON-MBL FLOOR BETWEE)
36321-TRY(36321-MAIN FLOOR II MBL IST)
36322-TRY(36322-MAIN FLOOR II MBL 2ND)
36323-TRY(36323-NON-MBL FLOOR BETWEE)
36324-TRY(36324-NON-MBL FLOOR BETWEE)
36325-TRY(36325-NON-MBL FLOOR BETWEE)
36326-TRY(36326-NON-MBL FLOOR BETWEE)
36331-TRY(36331-MAIN FLOOR III MBL 1)
36332-TRY(36332-MAIN FLOOR III MBL 2)
36333-TRY(36333-NON-MBL FLOOR BETWEE)
36334-TRY(36334-NON-MBL FLOOR BETWEE)
36335-TRY(36335-NON-MBL FLOOR BETWEE)
36336-TRY(36336-NON-MBL FLOOR BETWEE)
36341-TRY(36341-MAIN FLOOR IV MBL 1ST)
36342-TRY(36342-MAIN FLOOR IV MBL 2ND)
36343-TRY(36343-NON-MBL FLOOR BETWEE)
36344-TRY(36344-NON-MBL FLOOR BETWEE)
36345-TRY(36345-NON-MBL FLOOR BETWEE)
36351-TRY(36351-MAIN FLOOR V MBL IST)
36352-TRY(36352-MAIN FLOOR V MBL II ND)
36353-TRY(36353-NON-MBL FLOOR BETWEE)
36354-TRY(36354-NON-MBL FLOOR BETWEE)
36355-TRY(36355-NON-MBL FLOOR BETWEE)
36361-TRY(36361-MAIN FLOOR VI MBL 1ST)
36362-TRY(36362-MAIN FLOOR VI MBL 2ND)
36363-TRY(36363-NON_MBL FLOOR ABOVE)
36364-TRY(36364-NON MBL FLOOR ABOVE MBL VI)
36365-TRY(36365-NON MBL FLOOR ABOVE MBL VI)
36371-TRY(36371-Floor Beams @ 79100 (MBL-7) 1st Pass)
36372-TRY(36372-Floor Beams @ 79100 (MBL-7) 2nd Pass)
36373-TRY(36373-Floor Beams @ 83400 (Tier-8))
36374-TRY(36374-Floor Beams @ 87500 (MBL-8) 1st Pass)
36375-TRY(36375-Floor Beams @ 87500 (MBL-8) 2nd Pass)
36376-TRY(36376-Floor Beams @ 90500 (Tier-8)2nd Pass)
36391-TRY(36391-MISCELLANEOUS PLATFO)
36392-TRY(36392-MISCELLANEOUS PLATFO)
36393-TRY(36393-APH, SCAPH, HANDLING)
36394-TRY(36394-MISCELLANEOUS PLATFO)
36395-TRY(36395-MISCELLANEOUS PLATFO)
36396-TRY(36396-Slide Bearing Plates)
36610-TRY(36610-BOILER ROOF STRUCTUR)
36611-TRY(36611-BOILER ROOF SHEETING)
36613-TRY(36613-RAIN WATER PIPES and)
36620-TRY(36620-BOILER SIDE CLADDING)
36621-TRY(36621-BOILER SIDE CLADDING)
36721-TRY(36721-HSFG FASTENERS FOR 36PG - TIER 1)
36722-TRY(36722-HSFG FASTENERS FOR 36PG - TIER 2)
36723-TRY(36723-HSFG FASTENERS FOR 36PG - TIER 3)
36724-TRY(36724-HSFG FASTENERS FOR 36PG - TIER 4)
36725-TRY(36725-HSFG FASTENERS FOR 36PG - TIER 5)
36726-TRY(36726-HSFG FASTENERS FOR 36PG - TIER 6)
36727-TRY(36727-HSFG FASTENERS FOR 36PG - TIER 7)
36728-TRY(36728-HSFG FASTENERS FOR 36PG - TIER 8)
36731-TRY(36731-FASTENERS)
36732-TRY(36732-FASTENERS)
36733-TRY(36733-FASTENERS)
36740-TRY(36740-POSTS AND HANGERS)
36811-TRY(36811-FLOORGRILLSANDGUARDP)
36812-TRY(36812-FLOORGRILLSANDGUARDP)
36813-TRY(36813-FLOORGRILLSANDGUARDP)
36814-TRY(36814-FLOORGRILLSANDGUARDP)
36821-TRY(36821-STAIRS AND LADDERS)
36822-TRY(36822-STAIRS AND LADDERS)
36823-TRY(36823-STAIRS AND LADDERS)
36851-TRY(36851-HANDRAILS AND POSTS)
36852-TRY(36852-HANDRAILS AND POSTS)
36853-TRY(36853-HANDRAILS AND POSTS)
37010-TRY(37010-BLR OUTER CSG COMPS)
37810-TRY(37810-BLR OUTER CASING)
38210-TRY(38210-INTER CONN PLATFORMS)
38299-TRY(38299-MILL HANDLING MONORA)
38310-TRY(38310-CONN PLATFORMS TO MI)
38410-TRY(38410-MILL MAINTANANCE PLA)
38510-TRY(38510-LIFT BEAMS AND BRACI)
38610-TRY(38610-ELEVATOR CLADDING ST)
38611-TRY(38611-ELEVATOR CLADDING SH)
38710-TRY(38710-LIFT MACHINE ROOM DE)
38810-TRY(38810-FLOORGRILLS AND GUAR)
38820-TRY(38820-STAIRS AND LADDERS)
38850-TRY(38850-HAND RAILS AND HAND)
38993-TRY(38993-CONSUMABLES AND EREC)
39012-TRY(39012-FOUNDATION MATERIALS)
39101-TRY(39101-COLUMNS FRAMES BEFOR)
39102-TRY(39102-COLUMNS FRAMES BEFOR)
39141-TRY(39141-COLS FRAMES NEAR ID)
39142-TRY(39142-COLS FRAMES NEAR ID)
39150-TRY(39150-COL FRAMES BETN I.D.)
39299-TRY(39299-Platforms - Before ESP)
39300-TRY(39300-PLATFORMS - AFTER ESP)
39301-TRY(39301-STRUC AND PLATFORM F)
39302-TRY(39302-STRUC FOR MOTOR HOOD)
39304-TRY(39304-FAN HANDLING STRUCTU)
39305-TRY(39305-FAN HANDLING STRUCTU)
39306-TRY(39306-FAN HANDLING STRUCTU)
39700-TRY(39700-HSFG FASTENERS FOR P)
39810-TRY(39810-FLOOR GRILL)
39820-TRY(39820-STAIRS)
39850-TRY(39850-HAND RAIL AND HAND R)
39993-TRY(39993-CONSUMABLES AND EREC)
41350-TRY(41350-ACOIL GUN ASSY)
41390-TRY(41390-OIL GUN VICE&RACK)
41500-TRY(41500-HEA IGNITOR)
41710-TRY(41710-Oil Gun Assembly - DD items)
42001-TRY(42001-PNEUMATIC FITTINGS)
42002-TRY(42002-STEAM BLOW MATERIALS)
42005-TRY(42005-INSTRUMENT FITTINGS)
42010-TRY(42010-LFO PUMP SET)
42046-TRY(42046-DO PUMP-MOTOR ASSY)
42065-TRY(42065-DRAIN OIL TANK)
42070-TRY(42070-BURNER STN SKID ASLY)
42120-TRY(42120-PIPING,PH FUEL OIL)
42152-TRY(42152-PIPING,OP.FLR LFO)
42154-TRY(42154-PIPING,OP.FLR DO)
42157-TRY(42157-PIPING,OP.FLR AIR)
42200-TRY(42200-SUB.DEL FO SYSTEM)
42300-TRY(42300-BHEL VALVE F.O. SYS)
42700-TRY(42700-BULKED BPS COMPONENT)
42710-TRY(42710-Fuel Oil System - DD Items)
42858-TRY(42858-Fuel Oil System - Shop items)
42992-TRY(42992-IMPORTED ELECTRODES)
43004-TRY(43004-ASSY SCNR&GUN AIR SY)
43005-TRY(43005-ASSY MILL AIR SYSTEM)
43104-TRY(43104-M/C SCNR&GUN AIR SYS)
43105-TRY(43105-M/C MILL AIR SYSTEM)
43200-TRY(43200-SUBDEL,IGNR,SCNR AIR)
43710-TRY(43710-Seal Air & Scanner Air System - DD items)
45200-TRY(45200-Windbox - Sub Delivery)
45710-TRY(45710-Wind Box & SOFA Assembly - DD items)
45801-TRY(45801-WINDBOX AND SOFA TUBE ATTACH)
45802-TRY(45802-WINDBOX ASSEMBLY - 32" WIDTH)
45804-TRY(45804-WINDBOX - SOFA ASSEMBLY)
45805-TRY(45805-WINDBOX SUPPT AIR CYL MOUNTG)
45858-TRY(45858-Wind Box & SOFA Assy - Shop items)
47200-TRY(47200-Fuel Piping - Sub-delivery)
47261-TRY(47261-Fuel Pipe Supports)
47263-TRY(47263-Fuel Pipe Couplng , Collar,Gate Misc Ite)
47269-TRY(47269-St Pipes & Shop Bends For Rest Of Mills)
47710-TRY(47710-Pulverised Fuel Piping - DD items)
47858-TRY(47858-Fuel Piping - Shop items)
48012-TRY(48012-DUCT - -FDFAN TO A.H)
48014-TRY(48014-EXP.JT - -FDFAN TO A.H)
48015-TRY(48015-SUPPORT-FDFAN TO A.H)
48018-TRY(48018-MISC. DUCT&SPRT MATL)
48019-TRY(48019-AIRDUCT SUP FDN MATL)
48112-TRY(48112-DUCT - -PAFAN-PRI-AH)
48114-TRY(48114-EXP.JT - -PAFAN-PRI-AH)
48115-TRY(48115-SUPPORT-PAFAN-PRI-AH)
48141-TRY(48141-SEAL AIR HAG&ID GATE)
48142-TRY(48142-DUCT - -COLDAIRBUS)
48144-TRY(48144-EXP.JT - -COLDAIRBUS)
48145-TRY(48145-SUPPORT-COLDAIRBUS)
48200-TRY(48200-INS TAPPINGS ON DUCT)
48202-TRY(48202-DUCT - AH-WIND BOX)
48204-TRY(48204-EXPJT - AH-WIND BOX)
48205-TRY(48205-SUPORT AH-WIND BOX)
48206-TRY(48206-CLH/VLH -Hot Air)
48207-TRY(48207-FLOWMTR-SEC AIRFLOW)
48208-TRY(48208-DUCT-SEC.AIR TO WB)
48212-TRY(48212-DUCT - WIND BOX CONN)
48214-TRY(48214-EXPJT - WIND BOX CONN)
48222-TRY(48222-SQ DUCT AH-HOT AIR BUS)
48224-TRY(48224-EXPN PCS AH-HOT AIR BUS)
48225-TRY(48225-SUPPORT AH-HOT AIR BUS)
48232-TRY(48232-DUCT - HOT AIR BUS)
48234-TRY(48234-EXPJT - HOT AIR BUS)
48235-TRY(48235-SUPORT HOT AIR BUS)
48262-TRY(48262-Rect Duct Aihtr Toprinozzle And Seca)
48264-TRY(48264-Expn Piece Aihtr Toprinozzle and Seca)
48265-TRY(48265-Supports Aihtr Toprinozzle And Seca)
48267-TRY(48267-FLOW METER- SOFA)
48372-TRY(48372-DUCT - ECO HOPPER TO AH)
48382-TRY(48382-DUCT - ECO-HOPPER)
48384-TRY(48384-EXPNJT - ECO-HOPPER)
48385-TRY(48385-SUPPORT - ECO-HOPPER)
48388-TRY(48388-DUCT - ,ECO-PRI AH)
48395-TRY(48395-CLH/VLH-FLUE GAS)
48432-TRY(48432-DUCT - AH-BLROUTFL)
48434-TRY(48434-EXPJT - AH-BLROUTFL)
48435-TRY(48435-SUPORT AH-BLROUTFL)
48462-TRY(48462-DUCT - BLROUTFL-EP)
48464-TRY(48464-EXPJT - BLROUTFL-EP)
48465-TRY(48465-SUPORT BLR OUTFL-EP)
48482-TRY(48482-DUCT - ESP TO ID FAN)
48484-TRY(48484-EXPNJT - ESP TO ID FAN)
48485-TRY(48485-SUPPORT - ESP TO ID FAN)
48492-TRY(48492-DUCT - IDFAN-CHIMNY)
48494-TRY(48494-EXPNJT - IDFAN-CHIMNY)
48495-TRY(48495-SUPORT IDFAN-CHIMNEY)
48498-TRY(48498-DUCT - ,ID FAN-CHIM,)
48662-TRY(48662-CIRCULAR DUCT HOT BUS MILLS)
48664-TRY(48664-EXPN PCS HOT BUS MILLS)
48665-TRY(48665-SUPPORTS HOT BUS MILLS)
48667-TRY(48667-FLOW METER)
48700-TRY(48700-BULKED BPS COMPONENT)
48911-TRY(48911-Slide Brg Pl & Pac Bellow-Blr)
48912-TRY(48912-Slide Brg Pl-Id Sys)
48915-TRY(48915-Man Hole Doors (450X450))
48993-TRY(48993-ERECTON-MATERIALS)
65200-TRY(65200-Coal Feeder- Sub-Delivey)
65710-TRY(65710-Coal Feeder - DD items)
65736-TRY(65736-36GRAVIMETRIC FEEDER)
67200-TRY(67200-Coal Feeding System- Sub dely.)
67204-TRY(67204-RAW COAL GATES)
67272-TRY(67272-BUNKER OUTLET GATE -36" MOTOR)
67276-TRY(67276-FEEDER INLET GATE- 36" CHAIN)
67283-TRY(67283-FEEDER OUTLET ISOLATION GATE)
67710-TRY(67710-Coal Feeding System - DD items)
67801-TRY(67801-DOWN SPOUT)
67802-TRY(67802-BUNKER EMPTYINGCHUTE)
67803-TRY(67803-FEED PIPE TO MILL)
95088-TRY(95088-FSSS FLAME SCANNER)
95091-TRY(95091-FSSS INT.CON.EQPTS)
95485-TRY(95485-GRAVI.FDR.REMOTE.CAB)
95487-TRY(95487-GRA.FDR.ELEC.PACKAGE)
95488-TRY(95488-FEEDER MOUNTED C&IEQ)
95489-TRY(95489-COAL FLOW MONITER)
95988-TRY(95988-FF CONT COMMG SPARE)
96186-TRY(96186-SB MOTOR CONT CENTRE)
96188-TRY(96188-TEMP.PROBE START BOX)
96193-TRY(96193-MISC STARTER BOX)
96588-TRY(96588-ELECT.ACTUATOR-A&FG)
97097-TRY(97097-Instrumentation Field Transmitters)
97098-TRY(97098-INST.PANEL&MOUN.INST)
97282-TRY(97282-FLOWMETERS)
97284-TRY(97284-FIELD GAUGES)
97285-TRY(97285-FIELD SWITCHES)
97287-TRY(97287-INST-STM,WTR,SB SYS)
97297-TRY(97297-MTM CLAMPS & PADS)
97298-TRY(97298-MTM Thermocouples & Junction Boxes)
97407-TRY(97407-Instrumentation Field Transmitters)
97584-TRY(97584-ACOUSTIC PYROMETER S)
97585-TRY(97585-ACO STM LEAK DET SYS)
97590-TRY(97590-ERECTION MATERIALS)
97591-TRY(97591-BURNER TILT SHEAR PIN FAILURE SYS.)
97592-TRY(97592-PNEU TUB&FIT,AIRSET)
97593-TRY(97593-ELEVATOR & ACCESSORI)
97596-TRY(97596-CC TV SYSTEM)
97599-TRY(97599-PNEU.ACTUR A&FG SYS)
99099-TRY(99099-MISC CHAIN PULLY BLO)
99100-TRY(99100-FAN HANDLING EQUIPT)
99300-TRY(99300-PUMP HANDLING EQUIPT)
99400-TRY(99400-SCAPH,RAPH HANDLG EQ)
99501-TRY(99501-QUICK ERECT SCAFFOLD)
99502-TRY(99502-Pre.Parts Handling Equipmens)
99514-TRY(99514-FURN CRADL-4WALC)
99600-TRY(99600-FO SYSTEM HANDLG EQU)
CE/1895-SH1-48-01-EDN(CE/1895-SH1-48-01-NTPC TALCHER EPC (2X660 MW) DAVR UNIT1)
CE/1895-SH1-50-01-EDN(CE/1895-SH1-50-01-NTPC TALCHER EPC (2X660 MW) SG UNIT1)
CE/1895-SH1-56-01-EDN(CE/1895-SH1-56-01-NTPC TALCHER EPC (2X660 MW) HMI UNIT1)
CE/1895-SH1-57-01-EDN(CE/1895-SH1-57-01-NTPC TALCHER EPC (2X660 MW) TG UNIT1)
CE/1895-SH1-58-01-EDN(CE/1895-SH1-58-01-NTPC TALCHER EPC (2X660 MW) BOP UNIT1)
80300-PC(80300-MS FROM SUPERHEATER TO BOILER STOP VALVE)
80301-PC(80301-MS FROM BOILER STOP VALVE TO ESV)
80303-PC(80303-MS HEADER TO AUX PRDS)
80304-PC(80304-MS HEADER TO HPBP VALVE)
80307-PC(80307-HP AND LP BYPASS WARM UP)
80310-PC(80310-HRH FROM REHEATER TO INTERCEPTOR VALVE)
80312-PC(80312-LPBP VALVE UPSTREAM AND DOWNSTREAM)
80319-PC(80319-PERMANENT STEAM BLOWING PIPING)
80320-PC(80320-CRH FROM TURBINE TO REHEATER)
80321-PC(80321-HPBP VALVE TO CRH PIPING)
80322-PC(80322-CRH PIPING TO DEAERATING HEATER)
80323-PC(80323-STEAM TO BFP DRIVE TURBINE)
80324-PC(80324-CRH HEADER TO AUX.PRDS)
80326-PC(80326-PIPES FOR FLOW NOZZLE - MFC ACTIVITY ONL)
80329-PC(80329-EXTRACTION STEAM TO BFP DRIVE TURBINE)
80331-PC(80331-EXTRACTION STEAM TO LP HEATER-2)
80332-PC(80332-EXTRACTION STEAM TO LP HEATER-3)
80334-PC(80334-EXTRACTION STEAM TO LP HEATER-5)
80335-PC(80335-EXTRACTION STEAM TO DEAERATING HEATER)
80336-PC(80336-EXTRACTION STEAM TO HP HEATER NO.1)
80337-PC(80337-EXTRACTION STEAM TO HP HEATER-2)
80338-PC(80338-EXTRACTION STEAM TO HP HEATER-3)
80339-PC(80339-AUX STEAM TO BFD TURBINE)
80340-PC(80340-AUX STEAM HEADER)
80341-PC(80341-AUX STEAM HEADER INTERCONN BETWEEN UNITS)
80342-PC(80342-AUX STEAM TO SCAPH)
80343-PC(80343-AUX STEAM TO AH SOOT BLOWERS)
80345-PC(80345-AUX STEAM TO DEAERATING HEATER)
80349-PC(80349-AUX STEAM TO GLAND SEALS - TG SCOPE)
80351-PC(80351-AUX STEAM TO UNLISTED USERS - SG SCOPE)
80363-PC(80363-EXHAUST STEAM FROM PRIME MOVERS-TG SCOPE)
80370-PC(80370-HP DRAIN FLASH TANK VENT TO ATMOSPHERE)
80371-PC(80371-DRAIN FLASH TANK VENT TO CONDENSER)
80373-PC(80373-AUX STEAM HEADER SV EXHAUST)
80375-PC(80375-UNLISTED SV EXHAUSTS - TG SCOPE)
80379-PC(80379-HPH SV EXHAUST TO FLASH TANK)
80381-PC(80381-HP HEATER VENTS - TG SCOPE)
80382-PC(80382-LP HEATER VENTS)
80385-PC(80385-VENT FROM UNLISTED PPG/EQPT TO COND)
80399-PC(80399-STEAM BLOWING PIPING-TEMPORARY)
80400-PC(80400-CONDENSATE SUCTION)
80401-PC(80401-CD FROM PUMP TO LPH1/DC INLET TEE AND RE)
80402-PC(80402-CD FROM LPH1/DC INLET TEE TO TG TP)
80403-PC(80403-CD FROM TG TP TO DEAERATING HEATER)
80407-PC(80407-CONDENSATE FOR SEALING OF VACUUM)
80408-PC(80408-CONDENSATE DUMP FROM HEADER)
80412-PC(80412-CONDENSATE TRANSFER)
80418-PC(80418-ERECTION MATERIALS FOR INSTRUMENTS)
80419-PC(80419-DEAERATOR SAFETY VALVE EXHAUST TO ATM)
80420-PC(80420-BOILER FEED PUMP SUCTION)
80421-PC(80421-BOILER FEED PUMP RECIRCULATION)
80423-PC(80423-BOILER FEED PUMP TO HPH INCLUDING BYPASS)
80424-PC(80424-BFD BETWEEN HTRS AND GROUP PROTECTION)
80425-PC(80425-BFD FROM FINAL HPH TO SG TP)
80430-PC(80430-SPRAY WATER TO HPBP)
80433-PC(80433-SPRAY WATER FROM BFP INTERSTAGE)
80434-PC(80434-UNLISTED SPRAY WATER - SG SCOPE)
80435-PC(80435-UNLISTED SPRAY WATER - TG SCOPE)
80442-PC(80442-GLAND STEAM COOLER DRAINS)
80443-PC(80443-LP HEATER-1 TO CONDENSER)
80444-PC(80444-LP HEATER-2/3/4/5 DRAINS AND DRIP PUMP I)
80446-PC(80446-DEAERATING HEATER OVER FLOW AND DRAIN)
80447-PC(80447-HP HEATER DRAINS)
80448-PC(80448-DRAIN FROM UNLISTED EQPT/VESSEL-TG SCOPE)
80449-PC(80449-TG CYCLE PIPING DRAINS AND VENTS)
80451-PC(80451-BOILER INTEGRAL PIPING DRAINS)
80452-PC(80452-HP PIPING DRAINS - SG SCOPE)
80453-PC(80453-LP PIPING DRAINS - SG SCOPE)
80454-PC(80454-SCAPH DRAINS)
80455-PC(80455-DRAIN FROM UNLISTED EQPT/VESSEL-SG SCOPE)
80457-PC(80457-MANIFOLDS FOR HP FLASH BOX AND CONDENS)
80459-PC(80459-HP FLASH TANK DRAIN TO CONDENSER)
80460-PC(80460-SG AUX COOLING WATER UNIT SYSTEM)
80463-PC(80463-TG AUX COOLING WATER)
80468-PC(80468-MAIN CIRCULATION WATER PIPING)
80471-PC(80471-BOILER WATER WASH TO AND FROM UNIT)
80473-PC(80473-DEMINERALISED WATER SYSTEM)
80477-PC(80477-SERVICE WATER PIPING)
80478-PC(80478-DRINKING WATER PIPING)
80480-PC(80480-FIRE WATER-OTHER AREAS)
80493-PC(80493-HP FLASH TANK VENT TO CONDENSER)
80494-PC(80494-LP FLASH TANK VENT TO CONDENSER)
80495-PC(80495-LP FLASH TANK DRAIN TO COND)
80545-PC(80545-"LP CONDENSATE PIPING WITHIN TG HALL FOR)
80601-PC(80601-LOW PRESSURE DOSING PIPING)
80604-PC(80604-ACID CLEANING PIPING-TEMPORARY)
80610-PC(80610-SERVICE AIR-COMP SUCT AND DIS TO RECEI)
80612-PC(80612-SERVICE AIR FOR INDIVIDUAL UNITS)
80614-PC(80614-INST AIR COMP SUC AND DIS TO RECEIVER)
80616-PC(80616-INSTRUMENT AIR FOR INDIVIDUAL UNIT)
80650-PC(80650-FUEL OIL SUPPLY AND RETURN PIPING)
80673-PC(80673-LUBE OIL PIPING SYSTEM)
80830-PC(80830-H AND S FOR CRITICAL PIPING - STEAM LINE)
80901-PC(80901-SUB DELIVERY VALVES FOR LIGHT UP)
80920-PC(80920-H AND S FOR HYDRO TEST)
80921-PC(80921-H AND S FOR LIGHT UP STEAM LINE)
80926-PC(80926-H AND S FOR TEMPORARY PIPING ACID AND AL)
80927-PC(80927-H AND S FOR TEMPORARY PIPING - STEAM BLO)
80928-PC(80928-H AND S FOR BOILER LIGHT UP - TG)
80930-PC(80930-H AND S FOR SYNCHRONISATION - TG)
80933-PC(80933-H AND S FOR LP PIPING)
80940-PC(80940-AUX STRUCTURE FOR CRITICAL PPG AND CD B)
80992-PC(80992-WELDING ELECTRODES-1)
80993-PC(80993-MISC ERECTION MATLS)
81012-PC(81012-CLEAN DRAIN FLASH TANK - DIA 1500 MM)
81036-PC(81036-CW STORAGE TANK 16-25 CUM)
81060-PC(81060-SPECIAL TANKS AND VESSELS)
81100-PC(81100-CONDENSATE PUMP)
81110-PC(81110-COOLING WATER PUMP)
81318-PC(81318-FIX COM FOR MISCELLANEOUS PPG INSULATION)
81325-PC(81325-MINERAL WOOL MATTRESS)
81341-PC(81341-SEALING COMPOUND FOR INSL)
81350-PC(81350-ALUMINIUM CLADDING FOR INSULATION)
81411-PC(81411-DIRECT GAUGES FOR STEAM LINES)
81412-PC(81412-DIRECT GAUGES FOR NON-STEAM LINES)
81414-PC(81414-LOCAL CONTROL EQPT FOR NON-STEAM LINES)
81415-PC(81415-TEST THERMOWELLS)
81416-PC(81416-PERFORMANCE GUARANTEE TEST MATERIALS)
81417-PC(81417-"INSTRUMENTATION FOR STARTUP SYSTEM ")
AHP-1-ISG(AHP-1-DRY FLY ASH HANDLING SYSTEM PACKAGE)
AHP-2-ISG(AHP-2-BOTTOM ASH AND SLURRY SYSTEM PACKAGE)
CHP-10-ISG(CHP-10-PADDLE FEEDERS)
CHP-11-ISG(CHP-11-DS & WATER SYSTEM)
CHP-1-ISG(CHP-1-CHP, LHP & GHP MAIN CONVEYOR PKG INCLUDING CRUSHERS ,VIBRATING FEEDER, ACVS, DE SYSTEM)
CHP-5-ISG(CHP-5)
Civil1312(Civil)
Geotechnical Survey(Geotechnical Survey)
Site Development Works(Site Development Works)
Construction Power(Construction Power)
Storage Area Development(Storage Area Development)
Civil Work including foundation of storage shed(Civil Work including foundation of storage shed)
Illumination(Illumination)
Weigh Bridge(Weigh Bridge)
Land Development(Land Development)
Earthwork in open storage yard(Earthwork in open storage yard)
WBM Road(WBM Road)
Mess Building(Mess Building)
PEB Shed(PEB Shed)
Boiler & Auxiliaries(Boiler & Auxiliaries)
Power House(Power House)
Chimney(Chimney)
Cooling Tower(Cooling Tower)
Raw Water(Raw Water)
Balance of Plants(Balance of Plants)
DM Plant(DM Plant)
PT Plant(PT Plant)
Fire Protection System(Fire Protection System)
Mill Reject System(Mill Reject System)
AC and Ventilation System(AC and Ventilation System)
Compressed Air System(Compressed Air System)
Fuel Oil Handling System(Fuel Oil Handling System)
Condensate polishing unit(Condensate polishing unit)
CW Pump House(CW Pump House)
CW Piping(CW Piping)
Ash Handling Plant(Ash Handling Plant)
Coal Handling Plant(Coal Handling Plant)
FGD(FGD)
FGD Building(FGD Building)
LHS(LHS)
GHS(GHS)
ETP and STP(ETP and STP)
Non Plant Building(Non Plant Building)
Plant Road & Drain(Plant Road & Drain)
Miscellaneous Works(Miscellaneous Works)
Owners Office(Owners Office)
Safety Park(Safety Park)
Dismantling of Existing facilities(Dismantling of Existing facilities)
Construction of labour colony(Construction of labour colony)
Supply(Supply)
Supply of PPC Cement(Supply of PPC Cement)
Supply of OPC Cement(Supply of OPC Cement)
Supply of TMT(Supply of TMT)
Supply of Chimney Borosilicate Lining(Supply of Chimney Borosilicate Lining)
Structure(Structure)
Pipe Rack(Pipe Rack)
Structure.2(Power House)
Structure.3(Ash Handling Plant)
Structure.4(Coal Handling Plant)
Structure.5(FGD)
FGD Building.1(Gypsum Dewatering System)
TAL-DEL.3.7(Mechanical Works)
TAL-DEL.3.7.3(Boiler & Auxiliaries)
TAL-DEL.3.7.4(TG & Auxiliaries)
TAL-DEL.3.7.5(Chimney)
TAL-DEL.3.7.6(Cooling Tower)
TAL-DEL.3.7.7(Raw Water)
TAL-DEL.3.7.8(Balance of Plants)
TAL-DEL.3.7.9(Ash Handling Plant)
TAL-DEL.3.7.10(Coal Handling Plant)
TAL-DEL.3.7.11(FGD)
TAL-DEL.3.7.12(ETP and STP)
TAL-DEL.3.7.13(Non Plant Building)
TAL-DEL.3.7.14(Plant Road & Drain)
TAL-DEL.3.7.15(Miscellaneous Works)
TAL-DEL.3.7.16(Supply)
TAL-DEL.3.7.16.1(Supply of PPC Cement)
TAL-DEL.3.7.16.2(Supply of OPC Cement)
TAL-DEL.3.7.16.3(Supply of TMT)
TAL-DEL.3.7.16.4(Supply of Chimney Borosilicate Lining)
TAL-DEL.3.7.15.1(Owners Office)
TAL-DEL.3.7.15.2(Safety Park)
TAL-DEL.3.7.15.3(Dismantling of Existing facilities)
TAL-DEL.3.7.15.4(Construction of labour colony)
TAL-DEL.3.7.11.1(FGD Building)
TAL-DEL.3.7.11.2(LHS)
TAL-DEL.3.7.11.3(GHS)
TAL-DEL.3.7.8.1(DM Plant)
TAL-DEL.3.7.8.2(PT Plant)
TAL-DEL.3.7.8.3(Fire Protection System)
TAL-DEL.3.7.8.4(Mill Reject System)
TAL-DEL.3.7.8.5(AC and Ventilation System)
TAL-DEL.3.7.8.6(Compressed Air System)
TAL-DEL.3.7.8.7(Fuel Oil Handling System)
TAL-DEL.3.7.8.8(Condensate polishing unit)
TAL-DEL.3.7.8.9(CW Pump House)
TAL-DEL.3.7.8.10(CW Piping)
TAL-DEL.3.7.11.1.1(Gypsum Dewatering System)
04547-TRY(04547-Seperator/Collecting Vessel Supp Shop)
12544-TRY(12544-Suspn of Vert. Spaced Assy Shop Item)
35441-TRY(35441-Horil Beams First Pass-Tier-1)
36312-TRY(36312-MAIN FLOOR I MBL 2ND)
TAL-DEL.2.9(Award Of Packages)
Boiler & Auxiliaries.1(Boiler Foundation)
Boiler & Auxiliaries.2(Coal BUNKER BAY FOUNDATIONS)
Boiler & Auxiliaries.3(Coal Bunker Bay Floors and Roof)
Boiler & Auxiliaries.4(BOF to ESP Duct Foundation- Priority (First) Pass)
Boiler & Auxiliaries.5(BOF to ESP Duct Foundation- Second Pass)
Boiler & Auxiliaries.6(ESP Outlet to ID Fan Inlet Duct Foundation)
Boiler & Auxiliaries.7(Priority (First) Pass)
Boiler & Auxiliaries.8(Second Pass)
Boiler & Auxiliaries.9(ID Fan Outlet to Chimney Duct Foundation)
Boiler & Auxiliaries.10(Priority (First) Pass)
Boiler & Auxiliaries.11(Second Pass)
Boiler & Auxiliaries.12(Mills Foundation)
Boiler & Auxiliaries.13(First ID Fan foundations)
Boiler & Auxiliaries.14(Second ID Fan foundation)
Boiler & Auxiliaries.15(First FD Fan Foundation)
Boiler & Auxiliaries.16(Second FD Fan Foundation)
Boiler & Auxiliaries.17(First PA Fan Foundation)
Boiler & Auxiliaries.18(Second PA Fan Foundation)
Boiler & Auxiliaries.19(ESP Foundations- First 3 Pass Foundation)
Boiler & Auxiliaries.20(Excavation & PCC of Footing)
Boiler & Auxiliaries.21(Pedestal Concreting Works)
Boiler & Auxiliaries.22(Backfilling Works)
Boiler & Auxiliaries.23(Grade Slab Concreting Works (Paving Works))
Boiler & Auxiliaries.24(ESP Foundations- Balance Three Pass)
Boiler & Auxiliaries.25(Excavation & PCC of Footings)
Boiler & Auxiliaries.26(Footing Concreting Works)
Boiler & Auxiliaries.27(Pedestal Concreting Works)
Boiler & Auxiliaries.28(Backfilling Works)
Boiler & Auxiliaries.29(Grade Slab Concreting Works (Paving Works))
Boiler & Auxiliaries.30(ESP/FGD Control Room)
Boiler & Auxiliaries.31(Up to Plinth Level)
Boiler & Auxiliaries.32(up to First Floor)
Boiler & Auxiliaries.33(Up to 2nd Floor)
Boiler & Auxiliaries.34(Up to Third Floor & Roof)
Boiler & Auxiliaries.35(SA fan Foundation)
Boiler & Auxiliaries.36(ESP Foundations)
Boiler & Auxiliaries.37(Footing Concreting Works)
TAL-DEL-ORD1(Package Ordering)
TAL-DEL-ORD2(Geo-Technical Survey)
TAL-DEL-ORD3(Construction Power package Including construction lighting work in plant, construction water, steel yard)
TAL-DEL-ORD4(Enabling works)
TAL-DEL-ORD5(Civil)
TAL-DEL-ORD6(Dismantling work of above ground facility)
TAL-DEL-ORD7(Civil -PH-1+X-mer Yard-1+ESP/FGD Control Room+ DG building + Levelling & Grading+ Below ground dismantling work)
TAL-DEL-ORD8(Switch Yard+ 33 Kv SWGR + Levelling & Grading+ Below ground dismantling work)
TAL-DEL-ORD9(Civil for Coal Handling Plant (CHP))
TAL-DEL-ORD10(Civil for Ash Handling Plant (AHP))
TAL-DEL-ORD11(NDCT cooling Tower)
TAL-DEL-ORD12(Chimney-Civil)
TAL-DEL-ORD13(Balance BOPs Civil)
TAL-DEL-ORD14(Civil- FGD buildings (LHP+GHP etc) + Levelling & Grading+ Below ground dismantling work)
TAL-DEL-ORD15(Mechanical)
TAL-DEL-ORD16(Mechanical – Boiler, Aux Boiler & Bunker)
TAL-DEL-ORD17(Mechanical – ESP & FGD)
TAL-DEL-ORD18(Power Cycle Piping)
TAL-DEL-ORD19(Steam Turbine & Generator)
TAL-DEL-ORD20(Structure:- Power House)
TAL-DEL-ORD21(Structure:- CHP)
TAL-DEL-ORD22(Structure:- FGD+AHP+Pipe Rack)
TAL-DEL-ORD23(Electrical and C&I)
TAL-DEL-ORD24(Electrical-1(Equipments erection, testing & commissioning))
TAL-DEL-ORD25(Electrical-2 (Cabling))
TAL-DEL-ORD26(Electrical-3 (illumination))
TAL-DEL-ORD27(C&I Pkg)
Power House.1(PH -Civil / Structural Steel Work)
Power House.4(PH AB & BC bay civil works)
Power House.5(Civil Work)
Power House.6(Excavation & PCC)
Power House.7(Raft casting)
Power House.8(Pedestals (Till Bolt Lift))
Power House.9(D, E, F bay civil Work)
Power House.10(Civil Work)
Power House.11(Foundations)
Power House.12(PH Slab Casting & Roof)
Power House.13(Grade slab level 0.00 Mtr)
Power House.14(CW pit)
Power House.15(Oil Canal)
Power House.16(Steam Turbine)
Power House.17(LPBP Foundation)
Power House.18(Generator)
Power House.19(Condenser & Vacuum system)
Power House.20(Condenser Foundation)
Power House.21(Power Cycle Pumps)
Power House.22(Turbine Driven Boiler Feed Pump & Booster Pump)
Power House.23(First TDBFP Foundation)
Power House.24(Second TDBFP Foundation)
Power House.25(Motor Driven Boiler Feed Pumps and Booster Pumps)
Power House.26(MDBFP Foundation)
Power House.27(Condensate Extraction Pump)
Power House.28(Misc. Horizontal Pump)
Power House.29(Boiler Fill Pump & Hot well Make up Pump Foundation)
Power House.30(SG DMCW Pump foundation)
Power House.31(TG DMCW Pump foundation: EXCAVATION)
Power House.32(ACW Pump foundation: EXCAVATION)
Power House.33(HP Heater)
Power House.34(LP Heater)
Power House.35(Deaerator)
Power House.36(Chemical dosing system)
Power House.37(Oxygen dosing system)
Power House.38(PLATE HEAT EXCHANGERS)
Power House.39(SG PHE foundation)
Power House.40(TG PHE foundation:)
Power House.41(TRANSFORMER YARD)
Power House.42(GENERATOR TRANSFORMER FOUNDATION)
Power House.43(STATION TRANSFORMER FOUNDATION)
Power House.44(Service power transformer)
Power House.45(Unit Aux Transformer)
Power House.46(Misc. Service Transformer)
Power House.47(UNIT TRANSFORMER FOUNDATION)
Power House.48(STATION AUXILLARY TRANSFORMER FOUNDATION)
Power House.49(SPBD Pedestals FOUNDATION)
Power House.50(MV SwitchGear Room)
Power House.51(LT SwitchGear Room)
Power House.52(UPS & Battery Room)
Power House.53(IPBD Pedestals FOUNDATION)
Power House.54(Main Control Room)
Power House.55(STG Foundation (TG Raft & Deck))
Power House.56(Civil Work)
Chimney.1(Chimney- CIVIL Work)
Chimney.1.2(Chimney- Reinforcement fixing & Raft segment casting)
Chimney.1.6(Chimney- Shell Casting includes platforms & door openings)
Chimney.4(Chimney- Inner supporting structure Erection , alignment & fixing in position)
Chimney.5(Chimney-Flue Erection with borosilicate/Titanium/C276 Alloy lining)
Chimney.6(Chimney- Painting of Outer shell structure)
Cooling Tower.1(Cooling Tower Civil Work)
Cooling Tower.1.11(Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift))
Cooling Tower.1.12(Inner Grillage columns casting)
Cooling Tower.2(Cooling Tower Civil : Shell Casting including top platform (Approx 100 Lift))
Cooling Tower.3(Inner Grillage columns casting)
Raw Water.1(RAW WATER RESERVOIR)
Raw Water.2(RAW WATER CONTROL ROOM)
Raw Water.3(Raw Water Pump House)
DM Plant.1(Civil Works)
DM Plant.1.1(Acid alkali Unloading & storage area)
DM Plant.1.2(DM Plant Building including Vessel Foundation)
DM Plant.1.3(Neutralization Pit)
PT Plant.1(Cascade Aerator/Flash Mixer/Stilting Chamber/Parshall Flume)
PT Plant.2(CLARI FOCULATOR)
PT Plant.3(Chemical House)
PT Plant.4(Pump House)
Mill Reject System.1(Conveying Air Compressor Foundation)
Mill Reject System.2(Silo Structure Foundation)
AC and Ventilation System.1(Ventilation System)
Compressed Air System.1(Civil)
Fuel Oil Handling System.1(LDO Day Tank Foundation)
Fuel Oil Handling System.2(FO Pressurizing pump house & Unloading pump house)
Condensate polishing unit.1(Civil)
CW Pump House.1(CW & ACW Sump & Forebay)
CW Pump House.2(Concrete Volute Pump)
CW Pump House.3(CW Pump House Building)
CW Pump House.4(CW Channel)
Ash Handling Plant.1(Bottom Ash Hopper)
Ash Handling Plant.2(ASH SLURRY PUMP HOUSE)
Ash Handling Plant.3(ASH WATER PUMP HOUSE)
Ash Handling Plant.4(Compressor House)
Ash Handling Plant.5(Fly Ash Silo)
Ash Handling Plant.6(Intermediate Silo)
Ash Handling Plant.7(Silo Utility Building)
Ash Handling Plant.8(Classifier Silo)
Ash Handling Plant.9(Pipe Rack (Inside Plant))
Ash Handling Plant.10(Pipe pedestal)
Ash Handling Plant.10.6(AHP Main Control cum MCC Room & LHS MCC Room)
Ash Handling Plant.10.7(AHP MCC Room)
Coal Handling Plant.1(Track Hopper)
Coal Handling Plant.2(CHP Main Control cum MCC Room)
Coal Handling Plant.3(CHP MCC Room)
Coal Handling Plant.4(Common CHP, LHP & GHP Pump House)
Coal Handling Plant.5(CHP Workshop cum office Building)
Coal Handling Plant.6(CHP Dozer Shed)
Coal Handling Plant.7(CHP Coal Settling Pond ( CSSP))
Coal Handling Plant.8(Stacker Reclaimer)
Coal Handling Plant.9(Stock Yard)
Coal Handling Plant.10(Crusher House)
Coal Handling Plant.10.6(Transfer Points)
Coal Handling Plant.10.7(Conveyor Tunnel)
Coal Handling Plant.10.8(Conveyor Galleries with Trestles)
Coal Handling Plant.10.8.1(Conveyor Gallery -1A & 1B)
Coal Handling Plant.10.8.2(Conveyor Gallery -2A & 2B)
Coal Handling Plant.10.8.3(Conveyor Gallery -3A & 3B)
Coal Handling Plant.10.8.4(Conveyor Gallery -4A & 4B)
Coal Handling Plant.10.8.5(Conveyor Gallery -5A & 5B)
Coal Handling Plant.10.8.6(Reversible Yard Conveyor Gallery -6)
Coal Handling Plant.10.6.1(CHP Transfer Point-1)
Coal Handling Plant.10.6.2(CHP Transfer Point-2)
Coal Handling Plant.10.6.3(CHP Transfer Point-3 & any additional TPs)
Coal Handling Plant.10.6.4(Drive House)
Coal Handling Plant.10.8.6.7(Cable Trestle/Cable Gallery)
FGD.4(Gypsum Dewatering building)
FGD.5(Ball Mill Building and Ball Mills)
FGD.5.1(Wet ball Mill)
FGD.6(Limestone Transfer Point-1)
FGD.7(Limestone Truck Tippler)
FGD.8(Surface Feeder)
FGD.9(Belt Conveyor-1A/B)
FGD.10(Limestone Crusher House)
FGD.11(Limestone Bulk Storage Silo and Bucket Elevator)
FGD.12(Gypsum Conveyor-1A/B)
FGD.13(Gypsum Travelling Tripper/Gypsum Storage Shed)
FGD.14(Pump House for LHP/ GHP)
FGD.15(Weigh Bridge)
FGD.16(MCC building)
FGD.17(Pumps)
FGD.18(Absorber)
FGD.18.1(Absorber-Main structure)
FGD.18.2(Absorber-Supporting systems)
FGD.18.3(RC PUMP Shed)
Non Plant Building.1(Gate Complex along with CISF Building)
Non Plant Building.2(Construction office)
Non Plant Building.3(CANTEEN BUILDING)
Non Plant Building.4(Fire Station building and Drill Tower)
Non Plant Building.5(FQA Lab building)
Non Plant Building.6(CHP office cum Workshop Building)
Non Plant Building.7(Administration Building)
Non Plant Building.8(O&M Workshop Building)
TBG-CIV-7770(Piping)
PSWR-CIV-7772(Pipe Rack)
PSWR-Ciu-6753(Switchyard)
TBG-CIV-7777(GIS Building)
PSWR-CIV-7782(Control Room)
PSWR-CIV-7790(AHU Building)
PSWR-CIV-8527(Water Treatment Plant)
PSWR-CIV-8438(Effluent Treatment Plant with ZLD)
PSWR-CIV-8545(Chlorine dioxide dosing system)
PSWR-CIV-8537(Sewage Treatment Plant)
PSWR-CIV-9068(ETP)
PSWR-CIV-9069(STP)
PSWR-CIV-9072(CW treatment)
PSWR-CIV-9078(CW treatment Building including Equipment Foundation)
PSWR-CIV-8584(Condensate Storage Tank)
PSWR-CIV-8564(Condensate Storage Tank Foundation)
Boiler Structure-12344(Boiler Structure)
Boiler Supporting Structure-09876(Boiler Drum)
Galleries and Stairways-0987645(Water Walls Headers)
Water Wall Panel2012(Water Wall Panel)
Circulation System Components(Circulation System Components)
Buckstays and Framing(Buckstays and Framing)
Seal Boxes(Seal Boxes)
Superheater Headers(Superheater Headers)
Superheater Coils and Walls(Superheater Coils and Walls)
Superheater Components(Superheater Components)
Reheater headers(Reheater headers)
Reheater coil and walls(Reheater coil and walls)
Reheater Components(Reheater Components)
Economiser Headers, Coils and components(Economiser Headers, Coils and components)
Boiler Supporting Structure(Boiler Supporting Structure)
Gallaries and Stairways(Gallaries and Stairways)
Inter Connecting Walkways(Inter Connecting Walkways)
External Structures(External Structures)
Lining & Insulation System(Lining & Insulation System)
Roof Skin Casing(Roof Skin Casing)
Fixing Components for Main Boiler Lining(Fixing Components for Main Boiler Lining)
Boiler Skin Casing(Boiler Skin Casing)
Fixing Components for Boiler Auxiliaries(Fixing Components for Boiler Auxiliaries)
Lining & Insulation Materials(Lining & Insulation Materials)
Boiler Outer Casing(Boiler Outer Casing)
Ignition System(Ignition System)
Oil & Gas Burners(Oil & Gas Burners)
Oil & Gas System(Oil & Gas System)
Ignitor & Scanner Air System(Ignitor & Scanner Air System)
Soot Blower-1234(Coal Burner System)
Air & Flue Gas-19122(Boiler Fuel Firing Control)
Boiler House Auxiliaries Control(Boiler House Auxiliaries Control)
Boiler Instruments(Boiler Instruments)
Coal System(Coal System)
Coal Bunker Structures(Coal Bunker Structures)
Pulverised Fuel Piping(Pulverised Fuel Piping)
Coal Feeders(Coal Feeders)
Mill Plant Auxiliaries(Mill Plant Auxiliaries)
Soot Blower(Soot Blower)
Soot Blowes(Soot Blowes)
Soot Blowers and Soot Blowing System(Soot Blowers and Soot Blowing System)
Piping(Piping)
Boiler Integral Piping & Fittings(Boiler Integral Piping & Fittings)
Air & Flue Gas System(Air & Flue Gas System)
Duct Dampers & Expansion Joints(Duct Dampers & Expansion Joints)
Miscellaneous(Miscellaneous)
Lifting Tackles(Lifting Tackles)
Auxiliaries(Auxiliaries)
APH2112(APH)
PA Fan2112(PA FAN)
FD Fan2112(FD Fan)
ID Fan2112(ID Fan)
SA Fan2112(SA Fan)
Ducts and Dampers2112(Ducts and Dampers)
ESP2112(ESP)
FGD (wet)2112(FGD (wet))
FGD Chimney2112(FGD Chimney)
Fan Miscellaneous2112(Fan Miscellaneous)
poipidnaf21234(Piping)
hangeser 212(Hangers and Supports)
MS POjadhdf2121(MS Piping)
HRH pipi22121(HRH Piping)
CRH Piping 2212(CRH Piping)
Re-circualtion2212(Re-circulation Lines)
Extraction lines22121(Extraction lines and Aux. steam)
Valves & Valve lIne(Valves & Valve lines)
Echauset drain vent(Exhaust, Vent & Drain lines)
Condensate Lining22123(Condensate lines)
Aux coolin 2345112(Aux. Cooling water)
Main circulation2212(Main circulation water)
Pumps221345(Pumps)
Tanks&Vessesl2121(Tanks & Vessels)
Oil Piping2212(Oil Piping)
Insulation2212(Insulation)
C&I2212(C&I)
Miscellaneous2212(Miscellaneous)
Condenser [PRGR-022](Condenser [PRGR-022])
L P Heaters [PRGR-023](L P Heaters [PRGR-023])
Hydrogen Cooler [PRGR-139](Hydrogen Cooler [PRGR-139])
Exciter [PRGR-0144](Exciter [PRGR-0144])
BOI212132(BOI)
L P Turbine [PRGR-004](LP Turbine)
HP Turbine [PRGR-001](HP Turbine [PRGR-001])
L P Turbine - PRGR 004(L P Turbine - PRGR 004)
CROSS AROUND PIPE [PRGR-006](CROSS AROUND PIPE [PRGR-006])
Pedestals21221(Pedestals)
C&I21212678(C&I)
Vlaves214315(Valves)
toolsand tackles212131(TOOLS & TACKLES [PRGR-018])
EMbeddedparts049(Embedded Parts[PRGR-019])
Oil Equipmentshdfkaj(Oil Equipments)
Miscellaneuoos2143546(Miscellaneous)
dksjflfjkadhshc2134676(Generator)
exciter68234(Exciter)
embeddedpartsfdgsajf(Embedded Parts and Found)
tgbdsaahfdkal(TG Piping [PRGR-0150])
TAL-DEL.3.7.3.1(Boiler)
TAL-DEL.3.7.3.1.1(Boiler Pressure Parts)
TAL-DEL.3.9(Electrical and C&I)
TAL-DEL-ORD5.10(Civil- SG-1+ ESP-1+FGD-1 (Absorber+Fan+ Duct up to Chimney etc)+ BAH-1+ SCR-1 + Levelling & Grading+ Below ground dismantling work and excluding Paving work of this package)